## Issues
# | Status | Date opened | Workstream | Priority | Issue description | Impact | Assigned to | Next Review Date | Due date | Running log (Date - update) | Date closed

## Risks
# | Status | Date identified | Impact | Probability | Description | Workstream | Risk owner | Next Review date | Date to Activate Contingency / Mitigation Plan | Risk response | Contingency plan | Mitigation plan | Risk resolution | Running Log (Date - Update) | Risk resolution date

## Assumptions
# | Current | Workstream | Assumption (brief description) | Potential impact if assumption proves to be false | Comments

## Decisions
# | Decision date | Decision makers | Category | Decision | Comments
1 | 2012-06-07 | Chris Martin | Infrastructure | Mobile is not included in ATF POCs
2 | 2012-06-07 | Chris Martin |  | Tasks/Issues will be SP out of box
3 | 2012-06-07 | Chris Martin |  | Shared Calendars – Lotus Notes is out of scope.
4 | 2012-06-07 | Chris Martin |  | Shared Calendars – Outlook calendaring only
5 | 2012-06-07 | Chris Martin | Group Management | Group management software will not be include in the scope
6 | 2012-06-07 | Chris Martin | CMS | ATF will need the RSS feeds (and potentially additional feeds). This will be an out of the box function.
7 | 2012-06-07 | Chris Martin | Infrastructure | SharePoint Office Web Apps – This is a requirement for the ATF pilot.
8 | 2012-06-07 | Chris Martin | Search | SEARCH – This is a requirement for the ATF pilot
9 | 2012-06-07 | Chris Martin | Search | Will need to search across farms (due to multi-country requirements)
10 | 2012-06-08 | Chris Martin | Language Support | User Interface Languages needing to be supported are - English, Japanese, Korean, Traditional Chinese, Simplified Chinese, French (Canadian), Spanish (Mexican), Russian
11 | 2012-06-08 | Chris Martin | Language Support | Content Language Support - English, Japanese, Korean, Traditional & Mandarin Chinese, Taiwanese, French (Canadian), Spanish (Mexican), Danish, Hebrew, Norwegian (Bokmår), German and Russian.
04-Oct-11: R Bouji: A Mickleson confirmed agreement by FSG in Washington
04-Oct-11: R Bouji: A Mickleson confirmed this decision was made by FSG in Washington
04-Oct-11: Added by R Bouji

## Actions
# | Action Need By | Status | Owner | Category | Item
1 | 2012-06-16 | Open | Chris Martin |  | Provide NFRS to the M&C team
2 | 2012-06-08 | Complete | Michelle Edmonds |  | Provide list of SP services to the FAS&T team
3 | 16 June 2012` | Open | Chris Martin |  | Provide list of SP services needed to the M&C team
4
5
6
7
8
9
10
11