## Slide 1
2. Overall assessment of Program health
PMO Narrative
Budget
Schedule – Overall status RED
Resource.
RAIDs. The clean-up of risks and issues (as a result of template change) continues. We have at present 37 risks/issues missing at least one piece of information. Summaries of missing data (by workstream) are distributed and displayed twice a week in London, with detailed information sent to all RAID attendees on Mondays. Additional individual workstream calls continue to be scheduled. There are 131 decisions and 15 assumptions to be reviewed and revalidated in light of the cloud decision. 72 of these decisions are owned by the Tech Foundation workstream; doc out per Al for team to commence review as of 23-Feb. Last week we closed nine issues, reducing those overdue by four. Six new issues were opened this week.
Commercial/Vendor.
General .
 |  | RAG Trend |  |  |  |  | 
Program | This week | Last week | Week -2 | Week -3 | Week -4 | Week -5 | Week -6
SharePoint |  |  |  |  |  |  | 
App & Data |  |  |  |  |  |  | 
Infrastructure |  |  |  |  |  |  | 
Change Management |  |  |  |  |  |  | 
Tech Foundation |  |  |  |  |  |  | 
Unified Communications |  |  |  |  |  |  | 
IT Transition Management |  |  |  |  |  |  | 
Business Deployment |  |  |  |  |  |  | 
Release Management |  |  |  |  |  |  | 
Weekly Ratings |  |  |  |  |  |  |  |  | 
 | Program Assessment (Per PM Tool) |  |  |  | PMO Assessment |  |  |  | 
Program | Overall | Scope | Time | Cost | RAID | Resource | Financial | Schedule | Vendor
SharePoint |  |  |  |  |  |  |  |  | 
App & Data |  |  |  |  |  |  |  |  | 
Change Management |  |  |  |  |  |  |  |  | 
Unified Communications |  |  |  |  |  |  |  |  | 
Tech Foundation |  |  |  |  |  |  |  |  | 
IT Transition Management |  |  |  |  |  |  |  |  | 
Business Deployment |  |  |  |  |  |  |  |  | 
Release Management |  |  |  |  |  |  |  |  | 
Overall |  |  |  |  |  |  |  |  | 
Notes: Cost
GREEN - Estimate at Completion (EAC) = + 0 - 5% of approved spend (cost baseline + approved change requests)
AMBER - Estimate at Completion (EAC) = + 6 - 10% of approved spend (cost baseline + approved changes) and/or pending spend
RED – Estimate at Completion (EAC) exceeds + 10% or $100,000 of approved spend (cost baseline + approved changes) and/or pending spend or no project budget defined
Schedule
GREEN - The project schedule supports the end date of the project (with some elapsed time contingency).
AMBER - The project schedule supports the end date, but issues, risks and/or changes exist that may put the date in jeopardy.
RED – The project schedule does not exist and/or the project schedule does not support the end of the project.
Scope
GREEN - Scope defined and approved (scope baseline) with no pending change requests.
AMBER - Scope defined and approved (scope baseline) with pending change requests – known and not raised and raised but not agreed.
RED – Scope undefined or unapproved (no scope baseline) and/or multiple pending change requests.
Risk
GREEN – Low amount of risks with negligible impact
AMBER – Medium amount of risks. High or medium impact but with mitigation actions in place. Time left to put in place mitigation plans.
RED – High number of risks. High score risks which impact in the near term. No mitigation in place for High risks.
Issue
GREEN – No or low impact issues. Medium impact issues with resolution plans agreed and in place.
AMBER – Large amount of issues and/or Medium impact issues with no resolution plans.
RED – High impact issues present. No resolution plans in place for Medium of High level issues
Commercial
GREEN - TBD
AMBER - TBD
RED – TBD
Resource
GREEN – No resource issue or constraints
AMBER – Resource issues exist but plans are in place to resolve.
RED – Resource issues exist with no plans in place to resolve.