## Instructions
Worksheet name | How to use
General | 1. For each worksheet, enter the project name and last updated date in the header 2. Project leads and managers will raise items from their individual project RAIDs to the program level RAID if it cannot be resolved within the project and/or if it has an impact at the overall program level (scope, quality, cost and schedule). 3. The person identifying and raising the item to the log must follow the instructions outlined below to properly define the item. It is critical for this person to: a. Clearly describe the item, including its potential effect or impact on the program b. Assess each impact category (quality, scope, cost and schedule) with your workstream lead c, Talk to potential item owner or assigned party and agree ownership. If nobody is identified, assign to item identifier. 4. The person assigned to the item is responsible to: a. Manage until action plan completed. b. Create an action plan. c. Manage changes and tasks d. Keep workstream lead informed e. Update working notes, review notes and other fields as described below.
Risks
Risk Log | 1. Enter a unique # for the Risk; this number serves as the item reference number. Proceed in numerical order such that first risk added to the log has # R1, the second R2, etc. 2. Enter the Date Captured. The Date Captured is the date on which the risk is discovered. 3. Enter the name of the person who raised the risk to the log in the Identified by column. 4. Select the Status from the dropdown list. The risk can be 01. Open, 02. Open & Assigned, 03. Action/Mitigation Plan Defined, 04. Action Plan Complete, 05. Risk Closed, 06. Deferred, 07. Risk has become an Issue, 08. Blank 5. Enter information in the Cause column. A Cause describes what may have created the risk and may be a requirement, assumption, constraint or condition that creates the possibility of negative or positive outcomes. 6. Enter description in the Risk column. A Risk is a threat (bad event) or an opportunity (good event) that may positively or negatively impact a project. Risks may be unknown factors. 7. Enter information in the Effect column. Describe to what the risk could/would/may lead. 8. Select the Workstream/Project/Program which owns the risk. It can be App and Data Migration, Change Management, IAM, M&C Program, SharePoint, Technology Foundation or Unified Communications. 9. Enter the name of the person who is the Risk Owner. The risk owner is someone from within the current program assigned to monitor the risk. 10. Enter the person Assigned to manage the risk. 11. Select the Priority from the dropdown list. It can be Critical, High, Moderate, Minor or Negligible. See chart in Ratings tab. 12. Select the Proximity. Proximity is, from a time perspective, how close the risk is to occurring Can be Impact < 4 weeks, Impact > 4 weeks, Impact > 3 months. 13. Select the Risk probability from the dropdown list. It is the likelihood that the risk will occur. It can be 01. Unsure, 02. Slight, 03. Doubtful, 04. Possible, 05. Probable, or 06. Certain. See the Probability chart in Ratings tab for further definition. 14. Select the impact factor this risk will have on the project Scope from the dropdown list. It is the effect on the project's scope if the risk occurs. See Impact table in Ratings tab for further clarification. 15. Select the impact factor this risk will have on the project Quality from the dropdown list. It is the effect on the project's quality if the risk occurs. See Impact table in Ratings tab for further clarification.
16. Select the impact factor this risk will have on the project Schedule from the dropdown list. It is the effect on the project's schedule if the risk occurs. See Impact table in Ratings tab for further clarification. 17. Select the impact factor this risk will have on the project Cost from the dropdown list. It is the effect on the project's cost if the risk occurs. See Impact table in Ratings tab for further clarification. 18. Enter the Trigger description for the identified risk. It is the risk symptoms or warning signs that a potential risk might happen 19. Select the Risk response. It describes how the project team is going to respond to the risk event. Choose a value from the dropdown list. It can be: Undecided, Acceptance, Avoidance , Mitigation. a. Risk Acceptance - A risk response planning technique that indicates that the project team has decided not to change the PMP to deal with a risk or is unable to identify any other suitable response strategy. b. Risk Avoidance - A risk response planning technique for a threat that creates changes to the project management plan that are meant to either eliminate the risk or to protect the project management objectives from its impact. c. Risk Mitigation - A risk response planning technique associated with threats that seeks to reduce the probability of occurrence or impact of a risk. 20. Enter description of the Contingency plan. It is the fallback plan should the risk occur. 21. Enter the description of the Mitigation plan. It is the plan to mitigate the risk. 22. Enter the date and updates, changes and actions taken/planned in the Update Log (Progress). Be sure to include justification for any alterations made to the Required Risk Resolution Date. 23. Enter the Next Review Date, the date of the next meeting during which the risk should be reviewed. 24. Choose the Escalation level from a dropdown list. It can be Project Manager, Program Manager, Program Director, Managing Sponsor, Executive Sponsor, or Other. 25. Enter the Risk resolution description. 26. Enter the Required Risk Resolution Date. This is the date by which actions need to be taken to be able to close the risk. Any changes to this field must be documented and justified in the Update Log (Progress) column. 27. Enter the Actual Risk Resolution Date. This is the date that the risk is closed. 28. If the risk becomes an Issue or Change Request, document the reference number of the new item in Output Reference.
Issues
Issue Definition | 1. Enter a unique # for the issue; this number serves as the item reference number. Proceed in numerical order such that first issue added to the log has # I1, the second I2, etc. 2. Enter the date the issue was discovered in the Date captured field. 3. Enter the name of the person who identified the issue in the Identified by field. 4. Select the Status for the issue in the Issue definition section as Active or Closed. 5. Enter the Input Reference # from the Risk log. When a risk is realized / occurs, it becomes an issue and should be tracked in the Issues log. This field will help to maintain an audit trail of the lifecycle of a risk to an issue. 6. Enter a description of the issue in the Issue description field. Include brief definition of the issue, along with details of the impact to the project/program. 7. Select the impact factor this issue will have on the project Scope from the dropdown list. Can be Undecided, Low, Medium, High, Critical. See Impact table in Ratings tab for further clarification. 8. Select the impact factor this issue will have on the project Quality from the dropdown list. Can be Undecided, Low, Medium, High, Critical. See Impact table in Ratings tab for further clarification. 9. Select the impact factor this issue will have on the project Schedule from the dropdown list. Can be Undecided, Low, Medium, High, Critical. See Impact table in Ratings tab for further clarification. 10. Select the impact factor this issue will have on the project Cost from the dropdown list. Can be Undecided, Low, Medium, High, Critical. See Impact table in Ratings tab for further clarification. 11. Select the Priority from a dropdown list. It can be Critical, High, Moderate, Minor or Negligible. This value will reflect the highest impact value from the impact-related columns.Therefore, by definition, if any of the Impacts are rated High or Critical, the Priority must rated High or Critical, as well.
Issue Assignment | 1. Enter the name of the person who is the Issue Owner. The Issue Owner is a person within the current program assigned to monitor the Issue. 2. Enter the person the issue is Assigned to. This is the person assigned to manage the issue. 3. Select the Workstream/Project/Program which owns the issue. It can be App & Data Migration, Change Management, IAM, M&C Program, SharePoint, Technology Foundation or Unified Communications.
Issue Resolution | 1. Enter the planned resolution option for the issue in the Planned Resolution field. 2. Enter the Next review date. This is the date of the next meeting on which the item should be reviewed. 3. Provide the Required Resolution Date for complete resolution of the issue. This is the due date. 4. Enter the date and updates, changes and actions taken/planned in the Update Log. Be sure to include justification for any alterations made to the Required Resolution Date. 5. Select the Escalation level from a dropdown list. It can be Project Manager, Program Manager, Program Director, Managing Sponsor, Executive Sponsor, or Other. 6. Enter the Actual resolution details available for this issue. 7. Enter the Actual Resolution date for the issue. 8. If the output is a Change Request, please enter the Output Reference #.
Assumptions
Assumptions Log | 1. Enter a unique # for the assumption; this number serves as the item reference number. Proceed in numerical order such that first assumption added to the log has # A1, the second A2, etc. 2. Enter the name of the person who raised the Assumption to the log in the Identified by column. 3. Select the Workstream/Project/Program which owns the assumption. It can be App & Data Migration, Change Management, M&C Program, SharePoint, Technology Foundation or Unified Communications. 4. Enter an Assumption, with a brief description. 5. Enter the Potential impact if assumption proves to be false. 6. Enter the Forum/Individual that will be responsible for validating the assumption. 7. Enter details of the person who validated the assumption in the Validated by column. 8. Enter the date the assumption was last reviewed on in the Last review date column. 9. Enter the date for the next review of the assumption in the Next review date column. 10. Enter the date by which the Assumption must be validated in the Due Date column. 11. Select the Status of the item. It can be Validated, Not yet validated, Output to Risk/Issue or Obsolete. 12. Enter the Risk or Issue # as the Output Reference # if the Assumption has become one of these. 13. Enter any Comments you may have on the assumption.
Decisions
Decisions Log | 1. Enter a unique # for the decision; this number serves as the item reference number. Proceed in numerical order such that first decision added to the log has # D1, the second D2, etc. 2. Enter the name of the person who raised the Assumption to the log in the Identified by column. 3. Select the Workstream/Project/Program which owns the assumption. It can be App & Data Migration, Change Management, M&C Program, SharePoint, Technology Foundation or Unified Communications. 4. Select the Status of the Decision. It can be Pending, Closed, Obsolete. 5. Enter the Target Date for the decision; that is, the date by which the decision must be made. 6. Enter the Decision date when this decision was made. When this date is entered, the Status of the item should be changed from Pending to Closed. 7. Enter the details of all Decision makers involved in making the decision. 8. Enter Decision Description and Impact of the decision. 9. Enter any Comments you may have about the Decision.

## Ratings
Impact: Risks and Issues
Area | 00. Undecided | 01. Low | 02. Medium | 03. High | 04. Critical
Time | Priority to be determine | Impact on Critical Path is less than 5% | Impact on Critical Path is between 5% and 25% | Impact on Critical path is between 25% and 50% | Impact on Critical Path is greater than 50%
Cost | Priority to be determine | Impact on cost baseline is less than 5% | Impact on cost baseline is between 5% and 25% | Impact on cost baseline is between 25% and 50% | Impact on cost baseline is greater than 50%
Scope | Priority to be determine | Scope change which impacts Time or Cost greater than 5% | Scope change which impacts Time or Cost between 5% and 25% | Scope change which impacts Time or Cost between 25% and 50% | Scope change which impacts Time or Cost between more than 50%
Quality | Priority to be determine | Minimal quality deliverable issues | Small amount of quality deliverable issues which require remediation | Large amount of quality deliverable issues which require remediation at program level | Large amount of quality deliverable issues which impact Time and Cost and which require remediation at senior level
Risk Priority Definitions:
Critical | If the risk event occurs, the program/project will fail. Minimum acceptable requirements will not be met.
High | If the risk event occurs, the program/project will encounter major cost/schedule increases. Minimum acceptable requirements will be met. Secondary requirements may not be met.
Moderate | If the risk event occurs, the program/project will encounter moderate cost/schedule increases. Minimum acceptable requirements will be met; some secondary requirements may not be met.
Minor | If the risk event occurs, the program/project will encounter small cost/schedule increases. Minimum acceptable requirements will be met. Most secondary requirements will be met.
Negligible | If the risk event occurs, it will have no effect on the program/project. All requirements will be met.
Issue Priority Definitions:
Critical | The issue will cause the program/project to fail. Minimum acceptable requirements will not be met.
High | The issue will cause the program/project to encounter major cost/schedule increases. Minimum acceptable requirements will be met. Secondary requirements may not be met.
Moderate | The issue will cause the program/project to encounter moderate cost/schedule increases. Minimum acceptable requirements will be met; some secondary requirements may not be met.
Minor | The issue will cause the program/project to encounter small cost/schedule increases. Minimum acceptable requirements will be met. Most secondary requirements will be met.
Negligible | The issue will have no effect on the program/project. All requirements will be met.
Probability
05. Certain | 91-100%: very likely the risk will occur
04. Probable | 61-90%: likely the risk will occur
03. Possible | 41-60%: even likelihood the risk will occur
02. Doubtful | 11-40%: unlikely the risk will occur
01. Slight | 0-10%: very unlikely the risk will occur
00. Unsure | Investigation required
Proximity
01. Impact less than 4 weeks
02. Impact greater than 4 weeks
03. Impact greater than 3 months

## Risk Log
# | Date Captured | Identified by | Status | Cause As a result of (cause) | Risk (uncertain event) may occur | Effect which could/would/may lead to (effect / impact) | Program / Workstream | Project / Workstream | Risk Owner | Assigned to | Priority | Proximity | Risk probability | Impact: Scope | Impact: Quality | Impact: Schedule | Impact: Cost | Risk Trigger | Risk response | Contingency Plan | Mitigation plan | Update Log (Progress) | Next Review Date | Escalation level | Risk resolution | Required Risk Resolution Date | Actual Risk Resolution Date | Input/Output Refernce | 2012-03-22 | Status | Today > Res. Date | 30-90 days | 91-180 days | 180+ days | Critical or High | Days until Due | Due in the next week | Critical, High or Moderate
R102A | 2012-02-08 | Neil Sahdev | 07. Risk has become an Issue | Delays confirming future state of each application - in-turn this will delay the A&DM Program Archiving, Decommmisioning and Replatforming applications. | IT Service Delivery Leads are flagging that their teams do not have both the bandwidth and a charge code to review / validate the Rediscovery reports | No response received from IT Service Delivery leads | App and Data Migration |  | Neil Sahdev | TBC | Critical | 01. Impact < 4 weeks | 04. Probable | 01. Low | 01. Low | 04. Critical | 03. High | No responses received from IT Service Delivery Leads | Mitigation | None - the decision on the future state of each application needs to be confirmed by the IT Service Delivery Leads on behalf of the business | Host briefing sessions to provide support to the IT Service Delivery teams - in progress | 07-Mar: Risk now closed as item has been raised as an issue (#140) 22-Feb: inc. in man. Pack again; waiting on Operating Model decision. 15-Feb: include in management pack. 8-Feb: Risk raised; Neil reqd this item go into the mng pack. Will impact when the team can do the work and thus has financial implications, as well. | 2012-02-29 | Program Director |  | 2012-03-02 |  |  |  | FALSE | TRUE
R106A | 2012-02-28 | Neil Sahdev | 02. Open & Assigned | If RFP lead time > 4 months | Based on the time is has taken to finalise other M&C RFPs the lead time to procure vendor(s) required for the A&DM Portfolio Teams may not be sufficient for work commence 1st Jul'12. If this was the case then the delivery date of the target application would be impacted. | The deployment of the first application replatforms from the portfolio teams would be delayed | App and Data Migration |  | Neil Sahdev | Neil Sahdev | High | 02. Impact > 4 Weeks < 3 Months | 04. Probable | 01. Low | 01. Low | 03. High | 03. High | If RFP lead time > 4 months | Mitigation | Defer start-dates of the Portfolio teams however this will defer the business benefits (i.e. decommissioning legacy apps) | Gain agreement to the A&DM Operating Model (Issue 141) then work with Procurement to initiate the RFP process | 16-Mar: Neil said there are a few actions remaining before closure (from his call with Alan). 06 Mar: The preferred approach to mitigating the risk is initiate the RFP process now however this is dependant on agreeing both the Operating Model and Resourcing Strategy for A&DM (issue 141) | 2012-03-23 | Program Director |  | 2012-03-30 |  |  |  | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 8 | FALSE | TRUE
R23 | 2011-05-11 |  | 05. Risk Closed |  | Relative scope of Application Migration (AM) and Solution Portfolio Asset Rationalisation (SPAR) unclear |  | App and Data Migration |  | Neil Sahdev |  |  |  | 03. Possible | 02. Medium | [7 empty] | 30/08- SPAR program now disbanded. Close. | 2011-08-17 |  | Discussing emerging scope with SPAR program team. Updating AM charter accordingly. Will seek approval of same from SPAR. |  | 2011-08-30 |  | 316 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R24 | 2011-05-11 |  | 05. Risk Closed |  | Process of identifying "as is" applications, business and technical classification, and decision making not well defined. |  | App and Data Migration |  | Neil Sahdev |  |  |  | 03. Possible | 02. Medium | [7 empty] | 12/10 - Manually reaching out to the business on these applications. | 2011-10-05 |  | Define processes as part of AM program. Seek approval from SPAR, DCC, and other programs with common interest. |  | ? |  | 316 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R25 | 2011-05-11 | unknown | 07. Risk has become an Issue | timeline provided by Msft | Timeline for conversion of 15 applications by Microsoft shows 20+ week schedule which if extrapolated for remainder of the applications would indicate Program would not complete by mid-2013. | wouldn't complete by mid-2013, would still have aplpications running when the licensing expires | App and Data Migration |  | Neil Sahdev | Neil Sahdev | Moderate | 01. Impact < 4 weeks | 05. Certain | 01. Low | 01. Low | 04. Critical | 03. High |  |  |  |  | 10-Jan: Neil confirmed that this is really an issue. Made I91. 12/10 - 'Top Down' Program plan based on current known data; Neil and Martin to rebaseline plan in Q1'12 once data has been enriched through the Rediscovery project | 2012-01-25 | Program Director | Became issue 10-Jan-2012 | 2012-01-31 | 10-Jan-2012 (became an issue) | I91 | 316 | FALSE | TRUE | FALSE | FALSE | TRUE | FALSE | -51 | FALSE | TRUE
R26 | 2011-05-11 | unknown | 05. Risk Closed | Lack of business SME availability | Phase 1 plan completion data is dependant on availability of business users and IT service delivery resources to support required activities, i.e. acceptance testing, requirements workshops, etc. | If can't meet the date, will delay completion of Phase 1. | App and Data Migration |  | Neil Sahdev | Nicola Cooper | Critical | 01. Impact < 4 weeks | 04. Probable | 01. Low | 01. Low | 03. High | 03. High | If the business and/or IT service delivery resources cannot confirm that they can support required activities, then will occur. | Mitigation | None - Business and IT Service Delivery resources are needed for Phase 1 | Send to the business and IT services resources a list of activities they are expected to support to gain their commitment - in progress | 06-Mar: Risk closed as scope of Phase 1 has been restructured to take into account the availability of the business SMEs 29/Feb :action pending planning meeting shed for Monday 5th March. 22/Feb: inc. in man. pack; still waiting to hear back on Operating Model. 15-Feb: Neil reqd we include in man. pack again. 08-Feb: Neil reqd we include this in the management pack. 07-Feb: The A&DM Operating Model needs to be agreed by the CLT to determine exactly which activities will be performed by the A&DM and IT SD teams 10-Jan: updated with new column data; added a required risk res date (prev blank) of 31-Jan. 02/11 - Candidate applications for Phase 1 being received from the Assurance organisation; currently being reviewed against entry criteria 18/05 - Deferred. Lower priority. 11/05 - No applications identified yet, thus no users. Leave as is until identify the 15 apps (SOW was updated to specify the identification of 15 apps that already have requirements). 22/11 - Phase 1 project team are defining a 'calendar of events' to be sent to the business which will outline the support required over the coming months (incl. UAT) 14/12 - 1st draft 'calendar of events' sent to business reps for first few applications - awaiting confirmation to understand if they can meet the demands | 2012-02-29 | Program Director |  | 2012-02-08 |  |  | 316 | FALSE | TRUE | FALSE | FALSE | TRUE | TRUE | -43 | FALSE | TRUE
R27 | 2011-05-11 | unknown | 05. Risk Closed | Msft delivery approach unclear to EY. In addition, SOW has insufficient detail. | Microsoft development effort estimating method unclear, and estimates appear to be nominal. | The timelines within the project plans for Phase 1 may be invalid. | App and Data Migration |  | Neil Sahdev | Nicola Cooper | Moderate | 01. Impact < 4 weeks | 04. Probable | 02. Medium | 02. Medium | 02. Medium | 02. Medium | When Msft starts delivering, if they are unable to meet required timelines and quality standards, this will occur. | Mitigation | None - To avoid numerous issues during delivery it is critical that we have a clear and unambiguous SoW between MS and EY | Update the SOW to clarify the points needing clarification | 14-Feb: Decision made to stand-down MSFT development team until key inbound dependancy dates are known (i.e. design of sharepoint components). Risk can be closed. 07-Feb: EY Phase 1 PM has documented all areas that need updating in the SoW (namely testing approach, environment provisioning, timelines, location of resources and roles and responsibililities) 18-Jan: Agreement reached with MS to document areas in the contract that need clarifying which will be discussed later in Jan'12 10-Jan: updated, filling in new columns. Added a req res date of 31-Jan. 30/08 - Engaged with MS to better understand their approach/timelines, etc. 18/05 - Deferred. Lower priority. 11/05 - Will clear this up one MS gets in and can answer our questions. 22/05 - Following a series of calls the MS delivery method for App Transformation and Data Migration is now known and understood. | 2012-02-15 | Program Director | MSFT team stood down | 2012-02-02 | 2012-02-15 |  | 316 | FALSE | TRUE | FALSE | FALSE | TRUE | FALSE | -49 | FALSE | TRUE
R50A | 2011-07-07 |  | 05. Risk Closed |  | Impact of 'Discovery & Assessment' program unknown. If treated as a prerequisite, will impact schedule significantly. |  | App and Data Migration |  | Neil Sahdev |  |  |  | 04. Probable | 03. High | [7 empty] | 05/10 - Close. 07/09 - Neil: have Discovery and Assessment team identifying apps among Lotus and Lotus Notes. Working to make sure we don't duplicate effort. Neil has long list of actions taking in next couple weeks to mitigate. Follow-up in 2 weeks. | 2011-10-05 |  | Align approaches between A&DM and D&A Programs. |  | 2011-10-05 |  | 259 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R51A | 2011-07-07 |  | 05. Risk Closed |  | Impact of Data Centre Consolidation Program and associated "Application Remediation" activity is unknown. |  | App and Data Migration |  | Neil Sahdev |  |  |  | 04. Probable | 03. High | [7 empty] | 05/10 - Close. | 2011-10-05 |  | Align approaches between A&DM and DCC Programs. |  | 2011-10-05 |  | 259 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R52A | 2011-07-07 | unknown | 05. Risk Closed |  | Program is continuing without stakeholder engagement and consequently no agreed charter. |  | App and Data Migration |  | Neil Sahdev |  | Moderate |  | 03. Possible | 02. Medium | [7 empty] | 10-Jan: This is included in R26. Updated wording in R26 to be clearly inclusive and closed this item (Neil and Laura). 02/11 - Program has varying level of engagement from >80% of Service Lines / CBS functions - plans in place to fully engage with remaining areas 05/10 - Monitor this item; push out date one month to November. 22/11 - Engagement with Service Lines / CBS functions continues to mature; team are now working on specific comms to be published to the teams outlining the support required from them over the coming months | 2012-01-11 |  | Included in R26 (10-Jan) |  | 2012-01-10 | R26 | 259 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | TRUE
R53 | 2011-07-07 |  | 05. Risk Closed |  | Program is being treated as a technical migration program, with no reference back to business process and/or EY's strategic objectives. |  | App and Data Migration |  | Neil Sahdev |  |  |  | 04. Probable | 03. High | [7 empty] | 05/10 - Neil confirmed this has been resolved. Close. | 2011-10-05 |  | Build approach to include business interlock, the BCFs and Solution Roadmaps. |  | 2011-10-05 |  | 259 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R54 | 2011-08-30 |  | 05. Risk Closed |  | Most applications do not have existing documentation (technical, business, testing, etc.) so A&DM program will need to factor into future plans. |  | App and Data Migration |  | Neil Sahdev |  |  |  | 04. Probable | 02. Medium | [7 empty] | 12/10 - Risk closed, documentation is know to be poor or non-existent. Planning assumption. | 2011-10-05 |  | Make allowances in the detailed plans progressing through Sept '11. |  | 2011-10-12 |  | 205 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R55 | 2011-08-30 |  | 05. Risk Closed |  | Most applications have not undergone a security review so this will need to be factored in future plans (est. 10->20 days / application) |  | App and Data Migration |  | Neil Sahdev |  |  |  | 04. Probable | 02. Medium | [7 empty] | 12/10 - Risk closed, captured as an activity. | 2011-10-05 |  | Make allowances in the detailed plans progressing through Sept '11. |  | 2011-10-12 |  | 205 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R66 | 2011-10-26 |  | 07. Risk has become an Issue |  | Lack of space in the Becket House, London office is preventing team from working in a co-located environment. | 2011-10-28 | App and Data Migration |  | TBC |  |  |  | 03. Possible | 02. Medium |  |  |  |  | Mitigation |  | Seek necessary approvals to procure space for the team | 22/11/11 - Escalated to an Issue (# I64) | 2011-10-26 |  |  |  | 2011-11-22 | I64 | 148 | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | -40990 | FALSE | FALSE
R67 | 2011-10-26 | unknown | 05. Risk Closed | Significant number of resources required to deliver program. | Approval is required to onboard required resources (as per the resource forecast) to prevent delays to delivery. In addition agreement is needed on the resourcing strategy (i.e. blend of ITS, contractors and CBS / Markets resources) | Delays in gaining approval to onboard project resources will impact project timelines. | App and Data Migration |  | Neil Sahdev / Martin Stutchbury | Neil Sahdev | Critical | 01. Impact < 4 weeks | 04. Probable | 01. Low | 01. Low | 04. Critical | 02. Medium | Not getting necessary approvals in time to procure resources. | Mitigation | None - Agreement needs to be reached between the IT SD teams and Cross-Org on where the resources required for the A&DM Program will be sourced from | 1) Ensure all resource requests are in the Resource Request DB and align to project plans - complete 2) Meeting to be scheduled with Margaret Walsh and Christopher Hall to determine percentage of permanent employees to recruit and utilise in the Program - in progress; meetings held, agreement yet to be reached. 3) Agree resourcing strategy / mix with Markets and CBS - in progress (meetings set-up with People and Assurance IT Service Delivery Leaders) 4) Agree Operating Model between x-org and IT SD teams - in progress (proposed A&DM operating model sent to Chris, Margaret and Alan for review / discussion at next CLT meeting scheduled 24/01/12) | 06-Mar: Risk closed as decision (D75B) raised to track agreement to both the A&DM Operating Model and Resourcing Strategy 22-Feb: inc. in man. pack; still waiting to hear on Operating Model. 15-Feb: Neil reqd we include in man. pack again; need decision. 08-Feb: This corresponds with above (R26); need agreement on operating model. Neil would like this raised in mng. pack as well. 07-Feb: Awaiting decision 25-Jan: Awaiting decision from CLT ref preferred resourcing strategy for the Program. Neil sent Mike Laci latest deck (Mike involved on Operating Model team). Neil requested this go to the weekly Management Pack for Guy/Alan. 18-Jan: Portfolio 1 and 2 start dates 1-July; plan has been updated accordingly. Alan working with Mo to determine where the resolution will come from. Review next week. 10-Jan: updated all columns, added risk res date of 31-Jan. | 2012-02-29 | Managing Sponsor |  | 2012-02-15 |  |  | 148 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | -36 | FALSE | TRUE
R74 | 2011-11-01 | unknown | 05. Risk Closed |  | To maintain the Program schedule it is important that the Business and IT Service Delivery teams nominate empowered decision makers for each Service Line / CBS function who can readily review / approve Program deliverables and work products. This includes having one decision maker in cases where there are multiple stakeholders (i.e. where an application is owned by one organisation yet consumed by multiple organisations). |  | App and Data Migration |  | Neil Sahdev |  | High |  | 03. Possible | 03. High |  |  |  |  | Mitigation |  | 7/21/11 - Meetings held with Assurance, People, Knowledge, Markets, Comms & Marketing. Scheduled time with Margaret Walsh for 7/12/11 to outline resource requirement and sourcing strategy. Provide the business (Assurance initially for Phase 1) with a clear calendar of events outlining what support is needed (i.e. workshop participation, document reviews, decisions required....) from them over the coming months. | 10-Jan: Closed this risk; this is included in R26. 14/12 - Meetings held with Margaret and Chris to agree A&DM Operating Model - agreement reached for Decomm, Archive and Data Migration; operating model for App Transformation to be finalised 07/12 - Meeting with Margaret today; review next week. 30/11 - Neil and Martin have conversation planned with Assurance for Monday. Thereafter Neil will update this item accordingly. 09/11 - date out end of month. 02/11 - Neil will pick up offline with Michelle for update here. | 2011-12-21 |  | Included in R26 (10-Jan) |  | 2012-01-10 | R26 | 142 | FALSE | FALSE | FALSE | TRUE | FALSE | TRUE | -40990 | FALSE | TRUE
R78A | 2011-11-22 | unknown | 05. Risk Closed | Large number of applications needed to be assessed for Phase 1. | To-date the Phase 1 BA team have had to analyse nearly 40 applications to identify 5 which can be progressed. Based on this the team would need to analyse another 80 applications to identify the remaining 10 applications required for Phase 1. | Analysing such large quantities of applications was never planned for and as a result the Phase 1 project plan has been updated to reflect this for the remaining applications that need to be identified. If this ratio of 8 canditates : 1 identied application increases then the project plans will need to be further updated. | App and Data Migration |  | Neil Sahdev | Nicola Cooper | Moderate | 01. Impact < 4 weeks | 03. Possible | 02. Medium | 01. Low | 02. Medium | 02. Medium | If Phase 1 BA team is unable to identify and baseline 15 required applications for Phase 1, will occur. | Mitigation | None - Need to ensure sufficient analysis time is allowed for in the plans | 1, Update Phase 1 project plans to take analysis effort into account - complete 2. Monitor the effort expended vs. Planned for the remaining 10 applications - in progress (team are heavily dependant on knowing exactly what the Sharepoint Program will deliver and when) | 07/03 - Risk closed as replanning being managed as a BAU activity 29/02 - Replanning underway following decision to offboard 2 Phase 1 BA resources 22/02 - Since two members of the Phase 1 BA team are being offboarded due to budget reasons the delivery dates are being impacted. It is therefore likely that candidate applications will be descoped from Phase 1 as they can no longer be delivered within the timelines requested by the business. 14/02 - Same status as 07/02/12 07/02 - Phase 1 BA team are heavily dependant on knowing exactly what the Sharepoint Program will deliver and when to baseline the 15 applications 23/11 - Push out 1 month for next review. | 2012-03-07 | Program Director |  | 2012-02-15 |  |  | 121 | FALSE | TRUE | FALSE | TRUE | FALSE | FALSE | -36 | FALSE | TRUE
R87 | 2012-01-10 | Neil Sahdev | 07. Risk has become an Issue | Currently discovery team largely staffed with IT advisory resources for a finite period of time. | As the Rediscovery project is now expected to complete June 2012, there is a need to extend the resources of the team. If the resources can't be extended, we will lose them. | We will have to identify and onboard new resources, therefore affecting the timelines. | App and Data Migration |  | Neil Sahdev | Akos Rabi | High | 01. Impact < 4 weeks | 05. Certain | 01. Low | 01. Low | 03. High | 03. High | Team can't be extended. | Mitigation |  | Extend resources | 25-Jan: 3 x ITA resources expected to leave end-Jan'12/early-Feb'12. 2 x resources (1 PM and 1 data analyst) required to backfill however no suitable candidates identified so far. 18-Jan: Approval received from Alan to extend team; Martin now engaging with ITA to agree revised end-dates for each of the resources (which is dependant on start date of their next engagement) 11-Jan: Neil is meeting with Lindsey tomorrow on this topic; should have more information for next week's call. 10-Jan - opened by Neil. | 2012-01-25 | Program Director | This is no longer a risk, but an issue. 25-Jan made issue #I104. | 2012-01-31 | 2012-01-25 | I104 | 72 | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | -51 | FALSE | TRUE
R88 | 2012-01-10 | Neil Sahdev | 02. Open & Assigned | The Rediscovery project team need access to Lotus applications to perform analysis | The Rediscovery team does not have the required level of access and therefore can't perform analysis. | Team cannot complete analysis. | App and Data Migration |  | Neil Sahdev | Christian Driver | Moderate | 01. Impact < 4 weeks | 05. Certain | 01. Low | 01. Low | 03. High | 01. Low | Team can't get necessary access | Mitigation | None - Team require access to perform analysis | Gain necessary approval from Q&RM and security and operations to grant team required access | 06-Mar: Recently onboarded Rediscovery PM now working with Operations and Q&RM to agree accesses required to these applications 22-Feb: Confirmation received from Q&RM ref gaining access to applications without sensitive data or not in the 'red box' countries; process to be defined for accessing these types of applications 15-Feb: Steve - Susan was documenting her statement around what will be in and out of scope for access. Neil will update further. 18-Jan: This was due to be addressed at the Q&RM Steering Group scheduled 26th Jan'12 however it has now been cancelled. Steve provided update that he spoke with Susan yesterday and this is being moved forward outside of the Steering Group. Should gain clarity by the end of the week. 11-Jan: Operations agreed which data they need in order to get the access. Review in two weeks (for probable ability to close). 10-Jan - opened by Neil. 30 Jan - QRM meeting to make decision cancelled, chasing up outside of normal channels but no decision made yet. | 2012-03-23 | Program Director |  | 2012-03-30 |  |  | 72 | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | 8 | FALSE | TRUE
R99 | 2012-02-01 | Neil Sahdev | 05. Risk Closed | Testing environments may not be available on time | Turn around time for environment provisioning is currently 90 days. To intiate the process requires significant detailed design about the application so that the appropriate environment can be provisioned. This information is not available until the SDD/SAD and TDD have been completed. The development timeframe is short for MSFT, so the codeset will be provided back to us with no environment to put it into. | Testing cannot start of the MSFT deliverables | App and Data Migration |  | Martin Stutchbury | Nicola Cooper | Moderate | 01. Impact < 4 weeks | 04. Probable | 01. Low | 01. Low | 03. High | 02. Medium | Unclear process for initial environment provisioning | Mitigation | None - Without environements the delivery schedule will be impacted | Escalate within the Soln architects for Phase 1, and prioritise effort to complete (as best as known) environment requirements | 06/03 - Risk closed as replanning is being managed as a BAU activity 29/02 - Replanning underway since understanding many inbound depenencies will not be delivered many months later than planned 22/02: The dates which the environments are needed by may change depending on the current Phase 1 replan 07-Feb: Phase 1 solution and infrastructure architect teams are working with TF to better understand what information they need to provision environments | 2012-03-07 | Program Director |  | 2012-02-17 |  |  | 50 | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | -34 | FALSE | TRUE
R58 | 2011-07-19 |  | 05. Risk Closed |  | The engagement of all key stakeholders across the business will prevent progress being made but there is an expectation that this must be done. |  | Change Management |  | Sophie Boiron |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation |  | Identify key stakeholders with managing Sponsors Agree plan of engagement through Managing Sponsors Suugest we close that issue now Claire is on board and developing a plan moving forward | 04-Jan: Jackie reqd we review this next week. 19/10 - Jackie had added this, but it is to be removed since it is being managed from a project RAID level. | 2012-01-11 |  |  |  | 2011-10-19 |  | 247 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R59 | 2011-08-31 | unknown | 05. Risk Closed | Insufficient engagement with senior executives on M&C | There will be insufficient leadership focus from senior executives to drive this major transformation in EY | Realization benefits will be slower than required. | Change Management |  | Bob Reiner | Bob Reiner | Moderate | 01. Impact < 4 weeks | 03. Possible | 01. Low | 03. High | 03. High | 02. Medium | not a specific event, see Cause | Avoidance | Roll-out as a technology replacement | Identify the role of the leadership team and the expectations of them - discuss and engage with them. Formalise the briefing mechanism through key sytakeholder engagement Develop a story for Lync and Outlook with a story to engage with the business Engagement by Bob Reiner with John Murphy - also confirmed as Exec Sponsor | 07-Feb: Closed due to mitigating actions including comms manager taking responsibility for SAS deck. 10-Jan: Comms manager is taking over responsibility for developing the final version of the SAS deck. First draft due this week. 19/12 - Final version of SAS deck has gone out to Alan and Bob. Engagement has begun with Amerca's CFO, Asia Pac operations committee and ITS relations managers. Means of engaging with EMEIA still to be identified. Engagement with service lines will make use of the blue print. 9/11 SAS initial draft of M&C story will be presented at FSG for feedback. Jeremy establishing what else needs to be done to develop the story - by service line etc. Jackie Knight is working with Jeremy to establish a plan for engagement with Senior Area leadership. 3/11 - Discussion with leadership is dependent upon the SAS storry and agreement on the messages going forward. Awaiting SAS material. 19/10 - Reduce priority to Moderate. | 2012-02-01 | Executive Sponsor | 75% towards resolution | 2011-12-31 |  |  | 204 | FALSE | TRUE | FALSE | FALSE | TRUE | FALSE | -82 | FALSE | TRUE
R60 | 2011-07-19 |  | 05. Risk Closed |  | There will be insufficient Business Change Management resource (at central team and 'local' level ie Change network) for a change of this magnitude in EY to meet current expectations of key stakeholder |  | Change Management |  | Sophie Boiron |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation |  | Identify the Change approach and socialise 25/10 Resource plan agreed. Now required to resource to that plan Identify costs and resource requirements including Change network Identify potential sources of resource or where responsibilities will lie - working with Transition Identify where budget will come from work with relationship managers (areas) to evaluate change support and engage on next steps | 02/11 - have confirmation that this can be closed (per Jackie). 24/10 Immediate Resource plan agreed now seeking to resource 19/10 - Opened in Program RAID. Set review date out two weeks. | 2011-11-02 |  |  |  | 2011-11-02 |  | 247 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R61 | 2011-07-19 |  | 05. Risk Closed |  | We will replace tools without making a step change in collaboration and realising one of the envisaged benefits of M&C |  | Change Management |  | Jeremy Brown / Sophie Boiron |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation | Roll out as technology replacemnet and do not reap the full benefits. | Confirm a step change is required Development of the story on what we want to achieve - and benefits behind. To establish the degree og step change required. Assess of behavioural change required Ensure Training and Communications strategy and plans reflect step change requirement. Business Impact assessment must address step change Review behavioural changes that need to occur to address step change. | 29/11 - Now have clarity that we will be making a step change 08/11 - Will be confirmed with validation of the SAS story for M&C. Will be able to descibe the step change and behavioural change. 01/11 - benefits case will identify if step changed required. Story to John Murphy and senior team will help identify what step change they are looking for (if any) 19/10 - Opened in Program RAID. Review next week when Jeremy is present on call. | 2011-11-07 |  |  |  | 2011-11-07 |  | 247 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R62 | 2011-08-31 |  | 05. Risk Closed |  | There is misalignment across the program, both at senior level and lower down, of the potential benefits and key messages for M&C causing confusion amongst the business/users, mixed managed expectation causing reputational issues, delaying communications. |  | Change Management |  | Jeremy Brown |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation |  | Agreement of high level key messages of managing Sponsor group and Exec. M&C story being developed to clarifyvision and objectives of the program Clear communicated business case - the case for change | 02/11 - Working to get SAS story corrent and to John Murphy for approval. Benefits person; sits with Jeremy. Review beginning December. 24/10 SAS brought on to develop a story for M&C. This will be used to engage with senior executives | 2011-12-07 |  | Combined with R61 |  | 2011-11-03 |  | 204 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R63A | 2011-07-19 |  | 05. Risk Closed |  | We will offer training to non-EY employees which will compromise the legal position with respect to our contract with them |  | Change Management |  | Catherine Graham |  |  |  | 03. Possible | 02. Medium |  |  |  |  | Acceptance |  | Global Legal Counsel (Gillian Haselden) has confirmed that non-EY employees may be trained to support EY's transition to M&C | [5 empty] | 2011-07-25 |  | 247 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R63B | 2011-10-11 |  | 07. Risk has become an Issue |  | The Lync & Outlook Change network will not be in place soon enough to accommodate the roll-out schedule. |  | Change Management |  | Jackie Knight |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation |  | Raise with Business sponsors the necessity for Area representation Work with Lync & Outlook PM re. Seeking alternative area reps | 3/11 - Closed as now an issue 02/11 - Jackie will update; this is same as some others. | 2011-11-09 |  | Not resolved. Now an issue |  | 2011-11-03 | Issue I49 | 163 | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | -40990 | FALSE | FALSE
R64A | 2011-07-19 |  | 05. Risk Closed |  | The changing staffing model may lead to wide variances with respect to Training requirements and we sign a contract that is too big for our needs |  | Change Management |  | Scott Greengold |  |  |  | 04. Probable | 02. Medium |  |  |  |  | Mitigation |  | RFP designed to reflect changing scale | [7 empty] | 247 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R64B | 2011-07-19 | Sophie Boiron | 03. Action/Mitigation Plan Defined | History of EY portfolio management and business and IT engagement | The individual programs will forge ahead without consideration in the wider sense of the end user community's capacity for change. | Users unable to take on board change in the time scales anticipated | Change Management |  | Sophie Boiron / Alan Guthrie | Sophie Boiron / Alan Guthrie | Moderate | 03. Impact > 3 Months | 04. Probable | 02. Medium | 02. Medium | 03. High | 02. Medium | Could be major implementation/change in another area of the business at the same time as that in M&C. | Undecided | NA | Understand of change picture and revise change plan accordingly Use Change networks to asessess change volumes in their area and highlight where too much change is occuring and respond as and when | 13/03/12: RB: Interim approach to communicate to business owners via ITSDLs under discussion with M Walsh. This will only address communication with application owners via IT, however, and not overall end-user impact of multiple changes being deployed. This still needs to be worked through by Business Change once re-baselined plan is delivered at the end of March. Date moved out to mid-April 8/3: Downgraded as a business/IT model is now in place for the program. To be updated based on outcome of I139 29/Feb :action pending planning meeting shed for Monday 5th March. 22-Feb: Sophie has a meeting today on how the programs will work together; Alan to work out how IT and the business with coordinate at cross-program level. Review in 1 month. 15-Feb: Sophie talking to business to build a picture. Sophie will follow-up. 19-Dec: The change deployment team will engage with the business and build a picture of current and future change at area level. 07-Dec: changed from Sophie to Ian since global PMO is looking at this. Review next week. 24/11 Business Deployment manager will be in place in Q1 2012 (calendar) and working closely with change management (sophie) on overall approach for business deployment (overall M&C deployment) There is a plan to build a enterprise view of the change across EY. Work to start in Dec. 09/11 There will be a workshop to identify programme of change for End Users as a whole. Will take place before end of December. Sophie organising. 03/11 Blaine Pardoe and John Pritchett are raising this issue from a capacity of IT to deliver the volume of Chnage itself. 02/11 - Sophie will provide update next week. 26/10 - This is around capacity of end user change. Looking at workshop for end user perspective. Previously the aim has been to coordinate M&C Change plan and integrate and work closely with Enterprise plan however there is no Change Management happening on the other programs to coordinate with. | 2012-03-23 | Executive Sponsor |  | 2012-04-13 |  |  | 247 | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | 22 | FALSE | TRUE
R65A | 2011-07-19 |  | 05. Risk Closed |  | All the other IT changes happening outside M&C will impact end users & IT and Knowledge professionals as well and may limit their capacity to take on the changes M&C wish to deliver. New IT Service Management tool (ServiceNow) planned implementation for December 2011. |  | Change Management |  | Alan G / Sophie Boiron |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation |  | Work through EPO to establish timing and impact of M&C changes against overall Change plans. Service Delivery Leaders to understand change in their area of the organisation and reflect back to the M&C program. | 19/10 - Opened in Program RAID, but this is being managed at Project Level. Close here. | 2011-10-19 |  |  |  | 2011-10-19 |  | 247 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R68 | 2011-08-03 |  | 05. Risk Closed |  | The risk is that the current Silverlight distribution time frame will not result in Silverlight being installed on all IT Services machines in time for use on Outlook, Exchange, Lync and SharePoint e-Learning. |  | Change Management |  | Scott Greengold |  |  |  | 03. Possible | 02. Medium | [6 empty] | the Training requirement will be 1. For IT training - potentially this can be managed by the IT person going through Service desk to install Silverlight(?) if it gets highlighted in Training material that they need to do this? (your call if appropriate) SCOTT G response: I agree that adding text stating Silverlight may need to be installed is acceptable. Silverlight will ask a user to download and install itself automatically through Microsoft if the need is encountered (i.e. a WBL requiring Silverlight is launched and Silverlight is not present). No one will require Helpdesk / Service Desk assistance to install Silverlight - it's a standard plug-in type of install. However, a machine accepting the install from Microsoft will result in a non-Firm standard version of Silverlight being present on that machine. That is where the risk potential exists. 2.Training development and test - can this be done by requested download or automated? SCOTT G response:We are probably fine to use the automated download as needed on a case-by-case basis if necessary. 3.For End User. That would be for training for any pilot and then for roll-out. SCOTT G response:It seems Lync is scheduled to be the first rollout of all the M&C topics. As long as Silverlight is deployed to the user population targeted by each Lync deployment two to four weeks prior to each rollout date we should be fine. (i.e. Silverlight should go out 2-Jan-2012 to meet the Lync pilot time frame (Feb 2012) learning need. Silverlight should be distributed mid-February to everyone on the Full Rollout list scheduled for March 2012 etc..) Daren Wilks provided dates for Silverlight 'silent roll-out' which will be in time for bluk of learning. Individuals in IT can download silverlight as required before silent roll-out. | [7 empty] | 232 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R75 | 2011-11-08 | unknown | 05. Risk Closed | The technical team not able to identify all the plug-ins for Outlook and Lync. | Learning resource is not realistic as we do not know the numbers of 'plug-ins' for Outlook/Lync and the current resource is based on predominant use of Microsoft learning material and limited EY specific learning material. | We cannot size accurately the effort required for learning content development , together with the timescales for delivery. Any late changes to the Learning resource model could significantly affect overall roll-out schedule or quality of Learning material/delivery. | Change Management |  | Jackie Knight | Brigitte Ireland | Moderate | 01. Impact < 4 weeks | 03. Possible | 01. Low | 03. High | 01. Low | 02. Medium | not specific event, see cause | Mitigation | Additional Learning content developers | Ensure full business representation on requirements from all areas before end of December | 11-Jan: Investigations have identified as many areas as possible and we are working with the technical team on any bchanges that may occur due to office 365 where additional plug ins are going to be unlikely. Therefore the focus continues to be on the implications to Lotus Notes applications of moveing to Lync and Outlpook. The intention is to share this information with the countries as we engage with them to ensure preparation. We will be fully engaged with the business when we speak directly with sub-areas to identify any particular needs but in the mean time we will engage directly wth the key areas. e.g knowledge, HR, comms and Finance. 24/11 - benefits realisation candidate identified. Progress being made with SAS story to finalise benefits 9/11 - Requires SAS M&C story agreed to engage with Area reps to identify requirements lead. | 2012-01-11 | Program Director | 50% towards resolution | 2012-01-31 | 2012-01-11 |  | 135 | FALSE | TRUE | FALSE | TRUE | FALSE | FALSE | -51 | FALSE | TRUE
R103 | 2012-02-21 | IAM (Sirisha) | 02. Open & Assigned | There is currently NO Environment Manager managing the Coordination of Activities within EYDEV, EYQA, EYUA. | Testing environments inc the coordination activities are yet to be agreed/defined. This may impact our ability to get from EYDEV to EYQA | Multiple streams could be attempting to Test during the same time. | IAM | TF - Messaging | Ted Balfour | Adrian Mickleson | High | 01. Impact < 4 weeks | 03. Possible | 01. Low | 01. Low | 02. Medium | 02. Medium | Feedback from M&C that additional changes are required. | Mitigation | none | Although we will work with both M&C and the Vendor, there are no known mitigations plans for what we currently to not know. Therefore we need to accept the risk. | 15-Mar: on daily stand up, suggested due date of end of month, moved date out one week to match that. 14-Mar: M&C are working with QA to provide an environment Manager. Start Date is currently unknown. 13-Mar: Environments conversation scheduled for today. 28-Feb: Daren will reach out to M&C for updates. Call is set up for 29-Feb. 22-Feb: Awaiting feedback from M&C (Al/Adrian). 21-Feb: Opened per Sirsha; Reqd and awaiting further detail. 08-March: Environments manager to start by April 1 | 2012-03-14 | Program Manager | M&C to provide an Environment Manager | 2012-03-30 |  |  | 30 | TRUE | FALSE | TRUE | FALSE | FALSE | TRUE | 8 | FALSE | TRUE
R104 | 2012-02-21 | IAM (Sirisha) | 05. Risk Closed | No Off Prem Test Environment, this ID Sync cannot test (currently) the Off Prem Solution prior to going live. | ID Sync – Off Prem Lync and New Exchange Mail accounts cannot be tested in the EY environments, and thus the risk is we need M&C to provide a strategy to test this capability prior to going live (with the Off Prem capability). | May not be able to Mail Enable New Exchange Accounts of New Lync Accounts | IAM | TF - Messaging | Ted Balfour | Adrian Mickleson | Critical | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 04. Critical | 04. Critical | 03. High | 03. High | Confirm ation that this solution cannot be Tested Off Prem, prior to Production rollout. | Undecided | None | Raise risk with M&C M&C to provide Off Prem Testing capabilities | 15-Mar: On daily call confirmed can be closed. Howard sent the resolution statement. Closed. 14-Mar: M&C are exploring potential opportunities to provide either Hosted Off Prem Test environments, or links into EYs existing environments. Awaiting update from M&C. Msft has action from M&C daily call to update with anticipated approval date for CR addressing this. 28-Feb: Daren will reach out to M&C for updates; call set for 29-Feb. 22-Feb: Awaiting feedback from M&C (Al/Adrian). 21-Feb: Opened per Sirsha; Reqd and awaiting further detail. | 2012-03-14 | Program Manager | 15-Mar Howard: We are closing out the risk by creating a new Change Request for the Exchange Planning workstream to provide a “cloud simulation” environment for EY’s testing purposes prior to O365 “Service Ready”. The CR will be delivered next week. Expecting delivery to EY on Thursday. | 2012-04-02 | 2012-03-15 |  | 30 | FALSE | FALSE | TRUE | FALSE | FALSE | TRUE | 11 | FALSE | TRUE
R98 | 2012-02-21 | IAM (Sirisha) | 05. Risk Closed | The M&C requirement to go O365 means the solution for ID Sync has to change | Allows for scope creep until these docs are agreed, which in turn delays the project. | Needs additional requirements to be defined. Additional functionality is needed Both of the above requires an update to both the Vision & Scope and Functional Specs, which also require re-sign-off delaying the project, and impacts the costs both internally and externally. Also delays the project | IAM | TF - Messaging | Ted Balfour | Al Grljevic | Moderate | 01. Impact < 4 weeks | 01. Slight | 02. Medium | 00. Undecided | 03. High | 03. High | new req for O365 | Mitigation | none | Updated vision and scope req to facilitate new req. | 14-Mar: The item that I had due for today, R98, can be closed as we are obtaining sign-off and will raise a CR when the O365 changes are needed. This will now be managed through CR process; Ted confirmed can be closed in log. 14 Mar: Scope Lock discussions are due on the 26th-28 March in order to lock down the O365 scope. However, ID Sync is already building the Use and Test Cases for the known baseline requirements, inc O365 requirements from the previous workshop. Any change to this, could potentially delay the testing (and all that this entails) for ID Sync. 7-Mar: per Bharat, Daren has received 95% of his sign-off on the functional spec. Downgraded to moderate. 28-Feb: updates will be provided next week 21-Feb: Opened per Sirsha; Reqd and awaiting further detail. | 2012-03-14 | IAM Program Manager | Obtaining sign-off and will raise a CR when O365 changes are needed. Will be managed from here through CR process. | 2012-03-14 | 2012-03-14 |  | 30 | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | -8 | FALSE | TRUE
R1 | 2011-02-15 | unknown | 07. Risk has become an Issue | Due to the recent activities around the Msft cloud decision, we require additional team members (BAs, PMs, engineering, etc.) to face off against the various streams. | Availability of necessary resources within EY across all projects - long lead times in securing the required resources, PMs, BA's and other resources for the various projects | Impact of delivery of Lync and Outlook | M&C Program |  | Al Grljevic | Al Grljevic | Moderate |  | 04. Probable | 03. High | 03. High | 03. High | 02. Medium |  | Mitigation | Investigate 3rd party systems integrators (IBM) for resourcing needs | Work with resource planning team to Secure resources externally | 11-Jan: Al confirmed that this is an issue. Opened as I95. 5/12 - Location strategy is delaying work completed to date on resources 12/10 - Guy sending an updated resource request to Mo this week. 06/07 - Michelle will follow up with Al. 15/06 - Have made significant progress. Alex Hall would like to talk with Al / Brian on Fusion resourcing. 01/06 - Critical path: need BA's by 6/20 which is the start of req sessions. Need status from Al concerning IBM. 25/05 - Still working; a step closer to securing change manager. Should be joining in next 2 wks. 18/05 - Still working to secure resources, in progress. 11/05 - Lining up PMs and BAs. Defined end of June as deadline. Concern expressed over lumping all resources into one risk as other teams still lacking resources (e.g., Infrastructure Engineering). 27/04 - Much progress has been made, looking to validate staffing have/need. Have 7 outstanding lead developers and architect team. Need by beginning of July, so still ok time-wise. Continuing to work on securing resources. | 2011-10-19 |  | Complete all interviews and make job offers to selected PM's BA and program support. 11-Jan: became I95 |  | 11-Jan-2012 (became an issue) | I95 | 401 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | TRUE
R86 | 2012-01-03 | Bob Cooney | 02. Open & Assigned | M&C still planning; until this is completed, M&C can't provide what IAM needs in order to provide information in return. | If M&C requirements for (IAM) active directory activities (schema extensions (have 15-Feb), domain controller hardware requirements (have 15-Feb) and locations testing) are not delivered to the IAM program with appropriate lead time for evaluation, planning and deployment the M&C program will be delayed. | Program schedule will be impacted | IAM | TF - Messaging | Ted Balfour | Ted Balfour | Critical | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 02. Medium | 01. Low | 03. High | 02. Medium | If IAM does not get the needed information from M&C, will trigger. | Undecided |  |  | 16-Mar: We will have an environment ready for the start of April, what we still don't have is a set off acceptance criteria for IAM so can only hope the 2 pm's understood each other on whats needed. 15-Feb: About 75% there; have schema info, domain controller hardware reqs. The locations are the missing pc.; will come after O365 decisions are made. Review next week. 8-Feb: Ted needs info from M&C; he will follow-up with Ant. Paul Neave is the M&C contact; review next week. 25-Jan: Changed owner to Ted (from Bob). 18-Jan: Ken - no further detail; the team is working to ensure they have full understanding today or tomorrow. Review next week. 11-Jan: Ken - this is further complicated by the O365 decision. Additional planning to come in the next couple weeks. For on-premise, the open item is they are waiting for a CR (Bob or Dean) to say going from SP1 to SP2. (Teams are continuing under assumption of on-prem) 06-Jan: Bob scheduled a call with TF for Monday; from this meeting will determine risk response, mitigation/contingency plan and required risk resolution date. Still review Wednesday. 04-Jan: Bob has been working with Steve Jelf on this; the decision for the schema will be needed within a few weeks. Al will follow-up with Paul and Adrian, review next week. 03/01 - Bob sent the appropriate wording for the risk, opened from A19. | 2012-04-04 | Program Manager |  | 2012-04-04 |  | input: A19 | 79 | TRUE | FALSE | TRUE | FALSE | FALSE | TRUE | 13 | FALSE | TRUE
R107 | 2012-02-16 | Nick Coburn | 05. Risk Closed | Complex deployment | The complex deployment process for all aspects of the program may impact the design and adoption of the TOM. We will need to maintain Notes support not only for LN DBs but also for mail given the nature of the deployment and the cutover approach. |  | M&C Program |  |  | Nick Coburn | High | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 02. Medium | 03. High | 02. Medium | 00. Undecided | Unknown | Mitigation | Unknown |  | 7-Mar: Nick emailed that this item can be closed as it has been superceded by R108. 24/02: ACTION - Nick to re-word the risk | 2012-03-07 |  | superceded by R108; track there (per Nick Coburn) |  | 2012-03-07 | R108 | 35 | FALSE | FALSE | TRUE | FALSE | FALSE | TRUE | -40990 | FALSE | TRUE
R124 | 2012-03-14 | Daren Wicks | 02. Open & Assigned | Lync and Exchange will not be available to the FIM project until the 2nd April in EYDEV for the testing the Enablement of New Lync Accounts, and enablement of New Exchange mail boxes | Need Lync/Exchange fully built and available to the IAM ID Sync Project to start the E2E testing. | Delaying the ID Sync Project | IAM | TF - Messaging | Ted Balfour | Paul Neave/James Harrup-Brooke | High | 01. Impact < 4 weeks | 05. Certain | 01. Low | 01. Low | 02. Medium | 02. Medium | M&C not providing Lync/Exchange by the 2nd April | Mitigation | IAM to review what additional testing may be available whilst waiting on M&C | M&C to ensure these capabilities are built and available by the 2nd April | 14 Mar : Confirmation received as of the 13th March, from James HB that both capabilities are on track to be delivered into EYDEV by the 2nd April. Added to M&C log. 28-Feb: Daren will reach out to M&C for updates; call set for 29-Feb. 22-Feb: Await | 2012-03-14 | Program Manager | M&C (Tech F) to provide completed infrastructure inc Application "Readiness Testing", not just to OS layer, so ID Sync can Test the Enablement of New Lync and Mail Enable New Exchange Accounts | 2012-04-02 |  |  | 8 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 11 | FALSE | TRUE
R125 | 2012-03-14 | Daren Wicks | 02. Open & Assigned | The Lync Strategy may very well be chaning to: Off Prem or On and off Prem | This will impact the design that has currently been put in place, and the Vision and Scope, and Functional Spec, inc Use Cases and Test Cases that will have been agreed/built and potentially tested by the time this decision, and known impacts are agreed | Delaying the ID Sync Project creating a re-design for both the On Prem/Off Prem solution. Will require a further CR from Microsoft, as this will require additional coding Will require amendments to: Vision & Scope Functional Spec Operational Guide Config Doc Traceability Matrix Use Cases Test Cases Business Impact Re-asessment, which may may affect our DR solution Require re-testing of ALL Lync Test Cases | IAM | TF - Messaging | Ted Balfour | James Harrup-Brooke | Critical | 01. Impact < 4 weeks | 04. Probable | 03. High | 01. Low | 03. High | 03. High | M&C concluding the Lync solution will be either completely Off Prem, or partially On Prem, Partially Off Prem. | Acceptance | None | M&C to conclude as quickly as possible the Lync Strategy, and accept that the solution may not meet the current M&C timescales | 14 Mar : M&C to formally confirm proposed Lync Strategy; added to M&C log. | 2012-03-14 | Program Manager | M&C to confirm | 2012-03-30 |  |  | 8 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 8 | FALSE | TRUE
R11 | 2011-04-22 |  | 05. Risk Closed |  | Need to make sure that the focus continues to be about the future and not just today. Risk is that the team could re-create some of the issues that exist today. |  | M&C Program |  | Al Grljevic | Al Grljevic |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation | NA | Make sure the team documents requirements (What we need not how we do it) Challenge what is needed to verify that it is not a patch put in place to deal with an existing deficiency | 27/04 - Not a risk. Close. |  |  | Add to workplan. |  | 2011-04-27 |  | 335 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R110 | 2012-02-21 | Blaine Pardoe | 05. Risk Closed | IT Services budgets have been exceeded for the fiscal year | Impacts to the budget may negatively impact our work on TOM and other change activities. | Unknown at this time | M&C Program |  | Alan Guthrie | Blaine Pardoe | High | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 02. Medium | 03. High | 02. Medium | 00. Undecided | Unknown | Mitigation | Unknown | Dependent on the budget process | 13-Mar: on daily call, update that this is being managed outside of the RAID log; it is a regular budget activity/process. Close as it is not really a risk, an issue that is being dealt with. | 2012-03-07 | Executive Sponsor | On daily call, Alan and Ian agreed this is not a risk. It's an issue we are dealing with as part of regular activities. |  | 2012-03-13 |  | 30 | FALSE | FALSE | TRUE | FALSE | FALSE | TRUE | -40990 | FALSE | TRUE
R17 | 2011-04-22 |  | 05. Risk Closed |  | Data schemas vary dramatically among tools on different platforms and even within tools on common platforms (e.g., Lotus Notes). Further, there may be outdated content, duplicate content, and "bad" content or tagging. Quantity of content is vast. |  | M&C Program |  | Phil Stubbington |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation | NA | Application and Content Migration workstream is identifying today’s knowledge applications. These will be reviewed and a migration strategy for each will be developed | 27/04 - Not a risk, but a task. Verification to occur prior to SOW. Close. |  |  | Add to workplan. |  | 2011-04-27 |  | 335 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R21 | 2011-05-10 |  | 05. Risk Closed |  | In June there are planned to be a number of elaboration sessions for Lync, Exchange, SP Foundation and a Desing 0 Session. Currently the exact dates and locations of these sesssions cannot be confirmed. The cost of travel will continue to increase as the date come closer and key resources may not be available. Need to schedule sessions ASAP |  | M&C Program |  | Al Grljevic |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation | NA |  | 11/04 - Close here and make it a Critical Issue. |  |  |  |  | 2011-05-11 |  | 317 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R22 | 2011-05-10 |  | 05. Risk Closed |  | The MS hourly rates received from procurement are higher than the original plan. Working to determine the impact to the overall cost. |  | M&C Program |  | Michelle Edmonds |  |  |  | 04. Probable | 03. High |  |  |  |  | Acceptance | NA |  | 29/06 - SOW's signed - close. 08/06 - SOW have not been confirmed so it is still a risk. $'s are material and will have a cost impact. Support and guidance roles are affected - continue to work through details / SOWs. 25/05 - Michelle: No detail received yet; will talk with Rita. 18/05 - Haven't yet received final hourly rates. 11/05 - Unsure of impact as of now; wait for procurement to see where rates are. | 2011-06-29 |  |  |  | 2011-06-29 |  | 317 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R28 | 2011-05-11 |  | 05. Risk Closed |  | Delay in agreeing and signing off the Microsoft MOU, EA and Master Work Order. |  | M&C Program |  | Al Grljevic |  |  |  | 04. Probable | 03. High |  |  |  |  | Acceptance |  |  | 11/05 - Opened as risk and closed as Issue 3; waiting on legal sign-off. 18/05 - Still seem to be on track. Conversation with MS legal to push them harder. 25/05 - Still planning sign-off by 1-June; call scheduled this afternoon to determine how realistic this is and how to mitigate if it's not. Planning for all to be signed-off same day. 08/06 - Accept and Close. June 28th is the date for signing the MOU, EA, and Mater work order. | 2011-06-15 |  |  |  | 2011-06-08 |  | 316 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R30 | 2011-06-08 |  | 05. Risk Closed |  | 5 Managing Sponsors still need to be identified (Finance and 4 Area Sponsors) |  | M&C Program |  | Al Grljevic |  |  |  | 04. Probable | 03. High |  |  |  |  | Acceptance |  |  | 08/06 - accept the risk and close. 25/05 - Michelle and Al have communicated this to John; remains open. 01/06 - Discuss at Friday's IT Steering Committee meeting (and at Ken's meeting). 08/06 - John is aware of the need for the managing sponsors. Accept this as a risk and close. | 2011-06-08 |  | Michelle and Al have communicated this to John and he is aware of the need for the managing sponsors. Accept this as a risk and close. |  |  |  | 288 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R31 | 2011-06-08 |  | 05. Risk Closed |  | Identify MS Resources for the Envisioning Workshops in July. |  | M&C Program |  | Al Grljevic |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation |  | Work with Rita to assign roles / receive CV's for EY review. Provide Rita the July envisioning schedule so she can start assigning MS Resources. | 06/07 - 14 resources identified by Rita for Secaucus. Scott is working with Sourcing to on-board - close 29/06 - Need to touch base with Rita for MS Resources. 15/06 - CV's are due back shortly from MS. 08/06 - Adrian said since delay, MS has disbanded their team / clean sheet going forward. Need to review CV's / roles so we get MS resources assigned for July workshops. | 2011-07-06 |  |  |  | 2011-07-06 |  | 288 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R38 | 2011-07-06 | unknown | 07. Risk has become an Issue | As a result of strategy decisions, order hardware placements have been put on hold. | A managed services RFP is being run to select vendor for services for Lync, Exchange and SharePoint. There is a risk that we may impact hardware order dates. Decision had been taken to do prerequisite vendor workshops with 8 vendors to finalize RFP future state requirements. Workshops completing 28-October. | This would have an impact on the timeline. | M&C Program |  | Adrian Mickleson | Adrian Mickleson | High |  | 03. Possible | 03. High |  |  |  |  | Mitigation |  | Begin analysis / research of competing solutions. | 18-Jan: Adrian provided update - we are halfway through the RFP presentation week now; targetting Friday for completion. Review in two weeks. 04-Jan- expect feedback for SP and Exchange in the next two weeks, for Lync at end of month. Review in two weeks. 14/12 - Response due back from vendors in January. 07/12 - This risk ongoing until decision is made. Negotiations are underway this week. Leave as risk to be reviewed next week; if do not have an answer then, will become an issue. Brett suggested at some point splitting this item into the different RFP streams. 30/11 - Adrian said there are two actions occurring here: 1. prepping impact assessment (high level view of what will happen with RFP) for Guy and Alan for Friday, and 2. 2 vendors got RFP on Friday and it's due back just before Christmas. Al took an action to have Karen set up a meeting between Alan, Al and Adrian for Monday at the latest. Need to determine impact and what to do with CRs and resources. Laura took action to work with Adrian to open this as an issue and close as a risk. 23/11 - Adrian said the RFP decision should come Friday.Review next week. 02/11 - Al rec change review dates to 2 wks out. 12/10 - Determine risk after we have workshops. 05/10 - Decision had been taken to do prerequisite vendor workshops with 8 vendors to finalize RFP future state requirements. Workshops completing 28-October. 22/09 - Assign back to Adrian. Needs to be restated-- cloud is one scenario in RFP. 07/09 - We're about 2 weeks behind on the RFP; meeting with Forrester tomorrow to review. Very close to issuing to short list. Concern that we owe our consolidated plans to the Managing Sponsors in 2 weeks. Check with Adrian on rewording so risk is clear. 31/08 - 3 options still included In RFP. 24/08 - No update, but this is definitely still an option within RFP as currently stands. 17/08 - No update. 10/08 - No update, is this still in scope and budget? 27/07 - new issue, review next week. | 2012-02-01 |  | 8-Feb: per call with Paul and James, determined that 1. this item is an issue, and 2. it should be split out into the different streams since they are in different places, with different impacts, etc. Opened as I111 and I112 for Lync and Exchange and followed up with SP to see whether they have an issue around this or not. |  | 2012-02-08 | I111, I112 | 260 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | -40990 | FALSE | TRUE
R39 | 2011-07-27 |  | 05. Risk Closed |  | Inter-program dependencies around sharing resources (i.e. IAM resources) |  | M&C Program |  | Al Grljevic |  |  |  | 03. Possible | 03. High |  |  |  |  | Mitigation |  | Invite Steve and Ken to RAID call. | 10/08 - Bob and Ken have joined the M&C weekly RAID call. Daren Wicks identified to represent M&C Program for Inter-program dependencies. Close risk. 27/07 - Steve Betts will send list to Lauren so they can be included in the call. | 2011-08-10 |  |  |  | 2011-08-10 |  | 239 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R50B | 2011-10-10 |  | 05. Risk Closed |  | Need to validate we have the appropriate oversight for contractors / third parties with regards to work products, timesheets, invoices, expenses |  | M&C Program |  | Alan Guthrie |  |  |  | 03. Possible | 03. High |  |  |  |  | Mitigation |  | Assessment under way and analyzing risk to effort | 19/10 - Al said to close. | 2011-10-19 |  |  |  | 2011-10-19 |  | 164 | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | -40990 | FALSE | FALSE
R57 | 2011-10-04 |  | 05. Risk Closed |  | Final locations for in-country build-outs for Exchange, Lync and SharePoint cannot be finalized until a detailed evaulation of the Q&RM DCC due dilligence findings against the type of data for each of these solutions has been undertaken with Q&RM. This means that design & planning cannot be completed without significant assumptions being made. |  | M&C Program |  | Michelle / Adrian |  |  |  |  | 03. High |  |  |  |  | Mitigation |  | Use the locations specified by Q&RM | 14/12 - M&C Q&RM report was sent out by Susan. Adrian to sink up with Binu on his slide deck. 07/12 - Michelle said they are working through this; Brett has discussed with Siggi and John. It is a matter of pursuing the Q&RM angle or the in-country infrastructure (very expensive); not enough resources to go at it both ways. Will be ok for SP Phase 1, but will affect Exchange and SP Phase 2. Review next week. 23/11 - Adrian requested we move the review date out 2 wks. 02/11 - Q&RM steering comm reviewed the list and provided guidance. Reviewing note and confirming undertanding. Create business case for countries and confirm understanding. 02/11 - Al said Q&RM steering comm meeting tomorrow; update next week. 19/10 - Michelle - update new Impact column to reflect impact on budget and time. 12/10 - Susan Chakerian scheduling workshops for Q&RM. Focus of the workshops is to determine if we have the right support in the right locations. 04/10 - opened by Michelle. Examples: North America non US client data should be housed in Toronto as a main data center not Secaucus. As a team we need to confirm that operations, network, capacity, etc. are all ready in the Toronto DC to accept the work. Certain types of people data cannot be transferred out of country so how will this impact the People Profiles and the ability to find people globally and the servers needed to support that. | 2011-12-21 | [5 empty] | 170 | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | -40990 | FALSE | FALSE
R65B | 2011-10-26 |  | 05. Risk Closed |  | Lync Dormant Deployment - Currently the SMS deployment Gateway has "Operational Challenges" which is delaying the deployment of out package Currently we have a 1 week delay to the project, which is taking us very close to the moratorium date. Impact could be on Business Change |  | M&C Program |  | Adrian Mickleson |  |  |  | 01. Slight | 03. High |  |  |  |  | Mitigation |  | 09/11 - Adrian: this is on-going; review 2 wks. 02-11 Lync dormant deployment - Transition 2b - was distributed as per revised plan of 1st Nov. Confirmation being sought as to the current deployment status, as we have another Transition (2c) planned for Tuesday 8th Nov. No impact on Business Change, as they have confirmed there delivery is now based on the 31st Jan, and not as previously stated, the 9th Jan. 26/10 - Daren said can't get this escalated unless is is business or revenue-impacting. Daren to set meeting with Guy, Al, Mario and Martin to discuss. Raise with the package Deployment team for rollout using Level 3 Tier distribution servers | 23/11 - Adrian said this has been resolved and they got the green light to deploy last night. Close. | 2011-11-23 |  |  | 2011-11-04 | 2011-11-23 |  | 148 | FALSE | TRUE | FALSE | TRUE | FALSE | FALSE | -139 | FALSE | FALSE
R126 | 2012-03-14 | Daren Wicks | 02. Open & Assigned | No policies or procedures have been provided by M&C for Group Management | Policies required to ensure controls and constraints can be applied to the Service in order to maintain the EY environment, and offer the Users a great experience. | IAM will install the Group ID product, with all the capabilities, but Ops will struggle to identify which procedure belongs to which policy when enacting or creating Groups. The same applies to the Self Service Portal, i.e. Identifying what we should or should not allow the Users to do/not do in terms of setting up Groups (as an example) of 150 members. Also means we cant test these out prior to Production, hence delaying the project. | IAM | TF - Messaging | Ted Balfour | Nikolay Krastev | Critical | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 03. High | 03. High | 03. High | 02. Medium | M&C not providing relevant Group Management policies. | Mitigation | None | M&C to work with the various streams/business users to define Group Policies and procedures | 14 Mar: Risk raised with Nikolay on the 7th Feb. Awaiting feedback | 2012-03-21 | Program Manager | M&C to provide Group Management Policies and Procedures so they can be tested and signed off. | 2012-03-30 |  |  | 8 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 8 | FALSE | TRUE
R8 | 2011-03-17 |  | 05. Risk Closed |  | There is a risk that the Active Directory requirements for M&C program will not be delivered on time. This is currently a program that is yet to be kicked off. Users Groups Infrastructure |  | M&C Program |  | Peter Browne |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation | Consider tactical implementation of the AD needs for M&C program | Work with AD program sponsor to manage the dependencies between the programs 20/04 - Interim SOW working identify AD specific requirements. | 27/04 - 3-day workshop scheduled for next week; will allow for a better idea of the plan for 6 months. Adrian will follow-up with Peter to verify. Pertains to Interim SOW. Close. |  |  | Obtain and monitor time scales for other programs 15/04 - initial indication shows 6 months for completing the AD needs in order to migrate to Exchange. Detailed planning to be obtained once AD program is kicked off |  | 5/26/2011; Closed 27/04/2011 |  | 371 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R81 | 2011-12-05 | unknown | 07. Risk has become an Issue |  | Iteration overrun | Testing containment per iteration would be compromised, resources and overall plans impacted and complexity added to Config Management. | M&C Program |  | Michelle Edmonds |  | Moderate |  | 03. Possible | 02. Medium |  |  |  |  | Mitigation | Engage PM to escalate to Program Manager | Constant engagement with Project throughout every iteration to monitor possible and mitigate for possible overruns e.g. re-scheduling, re-prioritizing, additional resources, extended hours. | 05/03 - Laura emailed Michelle to determine whether this has been resolved, or if not what the current status/priority is. 05/12 - Risk opened. | 2011-12-07 | [5 empty] | 108 | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | -40990 | FALSE | TRUE
R106B | 2012-02-16 | Nick Coburn | 02. Open & Assigned | Current M&C replanning at project level | There is a risk that revised project timelines may impact the timeline of TOM design. If we do this too early we may not get buy in and could potentially create rework later in the process. | IT Services may become disengaged and disenfranchised with the change management process. Service Design will need to be reviewed for each time we define the Service Transition Plan. | M&C Program |  | Nick Coburn | Nick Coburn | High | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 02. Medium | 03. High | 02. Medium | 00. Undecided | Unknown | Mitigation | Unknown | Will need to revisit once all plans are baselined and following 30 day 'get to green' approach to assess if our current plan timeline remains valid. | 7-Mar: Nick provided additional detail for this item. | 2012-03-07 | Program Manager |  | 2012-03-31 |  |  | 35 | TRUE | FALSE | TRUE | FALSE | FALSE | TRUE | 9 | FALSE | TRUE
R108 | 2012-02-16 | Nick Coburn | 02. Open & Assigned | Complex deployment | The deployment approach for Outlook and SharePoint could significantly increased the cost associated with both internal and external support. | We will need to support Lotus Notes for a significant period of time following deployment of Exchange and SharePoint and this will potentially increase support costs for FY13. | M&C Program |  | Nick Coburn | Nick Coburn | High | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 02. Medium | 03. High | 02. Medium | 00. Undecided | Unknown | Mitigation | Unknown | Will be validated via Service Design approach and better understanding of external support costs from external vendors for Cloud and On Premise. | 7-Mar: Nick provided additional detail for this item. R107 closed as it is accounted for in this item. | 2012-03-07 | Program Director |  | 2012-06-01 |  |  | 35 | TRUE | FALSE | TRUE | FALSE | FALSE | TRUE | 71 | FALSE | TRUE
R109 | 2012-02-21 | Blaine Pardoe | 01. Open | This program is the most technically complex we have undertaken. It requires leaders to understand this technology and to be able to articulate it to their customers. This is far beyond just support people. | The knowledge proliferation efforts required by M&C are larger and more complex than for any previous technology initiative. It requires us to do things differently to ensure people are fully prepared for the transition. | We will need Proliferation plans in place beyond just support. | M&C Program |  | Blaine Pardoe | Blaine Pardoe | High | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 02. Medium | 03. High | 02. Medium | 00. Undecided | Unknown | Mitigation | Unknown | We will devise a knowledge proliferation plan. | 24/02: ACTION - On next call review with B. Pardoe & clarify / re-word the risk | 2012-03-07 | Other |  | 2012-05-11 |  |  | 30 | TRUE | FALSE | TRUE | FALSE | FALSE | TRUE | 50 | FALSE | TRUE
R115 | 2012-03-05 | Michelle Edmonds | 05. Risk Closed | FAST does not have the same interface as Autonomy. | FAST does not have the same tools for search management as Autonomy. Need to determine how FAST will be managed. | Requirements for a customized FAST management interface. | SharePoint |  | Stevens Sebastian | Andy Walsh | Moderate | 02. Impact > 4 Weeks < 3 Months | 00. Unsure | 02. Medium | 02. Medium | 02. Medium | 02. Medium | Search Admin Reqs are defined for FAST mgmt. | Mitigation | TBD | TBD | 7 Feb: working with the WSL to confirm if this is a RISK. 13 March - Closed will be planned for in serach work | 2012-03-14 | Managing Sponsor | Closed; will be planned for in Search work. | 2012-03-30 | 2012-03-13 |  | 17 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 8 | FALSE | TRUE
R116 | 2012-03-05 | Michelle Edmonds | 05. Risk Closed | Best Bets may not be approved for the Cloud | Management of 'best bets' on the cloud | Impact to the expected User Experience | SharePoint |  | Stevens Sebastian | Cem Aykan | Moderate | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 02. Medium | 02. Medium | 02. Medium | 02. Medium | HDL process does not allow for Best Hits in the cloud | Undecided | TBD | TBD | 7 Feb: Added and updated Risk. | 2012-03-07 | Project Manager |  | 2012-03-30 |  |  | 17 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 8 | FALSE | TRUE
R73 | 2011-11-01 | unknown | 02. Open & Assigned | General Lack of DR standards | Lack of Enterprise Standards for Disaster Recovery (DR) may affect quality of design deliverables | Incomplete or insuffiecient documentation being handed over to Operations. Resulting in increased recovery times in the event of a disaster. | M&C Program |  | Mike Laci | Operations | Minor | 03. Impact > 3 Months | 03. Possible | 01. Low | 02. Medium | 02. Medium | 02. Medium | Incomplete handover of information to Operations regarding the DR plan. | Undecided | NA | Review current DR strategy wth Ops and define next steps. | 2/1 - Lowered Risk level.1/11 - MCS - Project workstreams are concerned that EY has not communicated a standard as it relates to RPO/RTO and other DR/Business Continuity metrics. Decisions are being made at the project workstream level that may not meet business stakeholder expectations. | 2012-02-08 | Project Manager |  | 2012-06-30 |  |  | 142 | TRUE | FALSE | FALSE | TRUE | FALSE | FALSE | 100 | FALSE | FALSE
R85 | 2011-12-15 | unknown | 02. Open & Assigned | Schedule/location for the Olympic games | The Olympics & Paralympic Games are less than a year away (27 July - 12 August and 19 August - 9 September respectively). The majority of London based employees will be asked to work in differnet location or from home which means that the load on the VPN network may prevent items such as upgrades taking place.Need to evaluate what work will be taking place during this period and the possible impact. | Could hamper progress with deployment. Also with regards to staff getting on site | M&C Program |  | Ian Bourne | Ian Bourne | Moderate | 03. Impact > 3 Months | 04. Probable | 02. Medium | 02. Medium | 02. Medium | 02. Medium | Olympic Start date | Mitigation | Greater understand work taking place. Plan into plans. | Whilst corporate direction is not solid at present, need to understand possible impact from an M&C perspective. | 16-Mar: Ian suggested next review 18-April. Direction provided by Alan for Cross Org that all to work as normal. | 2012-04-18 | Program Director |  | 2012-05-01 |  |  | 98 | TRUE | FALSE | FALSE | TRUE | FALSE | FALSE | 40 | FALSE | TRUE
R119 | 2012-03-05 | Michelle Edmonds | 05. Risk Closed | Integration points across the Program | The amount of time required to complete DTU Phase #1 may be longer than the requested Phase #1 go-live date (soce and resource availability) | Not being able to have DTU included in Release 1. | SharePoint |  | Michael Cliffel |  | High | 03. Impact > 3 Months | 05. Certain | 03. High | 03. High | 03. High | 03. High | TBD | Undecided |  | TBD | 7 Feb: Added and updated Risk. This will be discussed on 3/7 mtg with the business. | 2012-03-14 | Program Manager | This item is being addressed as part of Blue print. | 2012-03-30 | 2012-03-07 |  | 17 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | 8 | FALSE | TRUE
R113 | 2012-03-05 | Rewa Bouji | 03. Action/Mitigation Plan Defined | Lack of clearly defined expectations between the program and the business sponsors | There is a risk that the business expects the UC stream to deliver the integration of legacy mail-integrated applications as part of the delivery of Outlook. The UC program is working with business application owners to explain that if they require a legacy mail-integrated tool to be compatible with Outlook, they will need to initiate - and pay for - a project to do this. It is not clear from conversations we have had with the business to date that they have budgeted for resource or project spend in FY13 to support this activity. If the application(s) is(are) required for Day 1 and the business will not accept Outlook deployment without it(them) being integrated, there is a risk that the program will need to deliver these and absorb the cost of doing so. This is not currently in scope or budgeted for. | Increase in program cost and resource needs, delays to the go-live date if the applications cannot be delivered for integration in time for the current Live deployment date | M&C Program |  | Rewa Bouji | Alan Guthrie | Critical | 02. Impact > 4 Weeks < 3 Months | 04. Probable | 04. Critical | 03. High | 04. Critical | 03. High | Decision by the business to include delivery of Mail-integrated apps into UC's scope | Mitigation | NA | Work with the Business Change and Deployment teams, and business application owners, to clarify UC scope and ensure that if they have an application that requires mail integration, that they have budgeted for this in the FY13 plan. AG to raise via Mo/Gina to ensure FY13 budgets provision for all transformational programs, not just M&C | 13/03/12: RB: Alan Guthrie took action at the stand up to raise via Mo/Gina (Global PMO) the requirement for all IT Services SD budgets to make provision to support all cross-org programs in FY13 . This will take place at the end of March. Workstream changed from UC to M&C Program as impacts all M&C workstreams, not just UC 06/03/12: RB: As agreed in standup meeting, ownership to be moved from Guy Morgan to Martin Kremmer 05/03/12: RB: Risk logged | 2012-03-07 | Executive Sponsor |  | 2012-03-31 |  |  | 17 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 9 | FALSE | TRUE
R127 | 2012-03-15 | Nicky Watson | 02. Open & Assigned | Shortage of additional environment domain to host a segregated Performance Testing environment for M&C | If performance testing needs to use either the QA integration or UAT environments, this may mean multiple projects will need to queue for environment use. Alternatively if Performance testing is carried out in an environment whilst other workstreams are performing test cycles, it may slow down testing | May cause schedule delays as the separate workstreams/projects may need to queue for scheduled slots to exclusively use the environment for their testing needs. Planning should factor this in. | M&C Program |  | Al Grljevic | Al Grljevic | High | 03. Impact > 3 Months | 04. Probable | 02. Medium | 03. High | 03. High | 02. Medium | Confirmation that no budget is available to build out a separate Performance Testing environment domain | Mitigation | Schedule Test Environment utilisation with enforced adherence to schedule | Use UAT or QA Integration environments for performance testing using controlled environment usage and scheduling | 15/03/2012: NW: Follow up with TF as to whether budget can be applied for to build a PT environment. Also assess needs and contention issues with PM's and Infrastructure Engineering. | 2012-03-30 | Program Director |  | 2012-04-30 |  |  | 7 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 39 | FALSE | TRUE
R122 | 2012-03-06 | Michelle Edmonds | 07. Risk has become an Issue | Changed priorities in M&C Program since Frog SOW was signed. | Frog user experience deliverables may not achieve desired goals | Disconnect between Blueprint and Frog current SOW. | SharePoint |  | Binoy Raj | Eric Wahl / Kevin Smyth | High | 03. Impact > 3 Months | 04. Probable | 04. Critical | 03. High | 04. Critical | 04. Critical | Scope creep on Frog's engagement | Mitigation |  | TBD | 7 Feb: Added and updated Risk. | 2012-03-21 | Managing Sponsor | Risk became issue, opened as I150. | 2012-03-16 | 2012-03-08 | I150 | 16 | FALSE | TRUE | FALSE | FALSE | FALSE | TRUE | -6 | FALSE | TRUE
R14 | 2011-04-22 |  | 05. Risk Closed |  | New process of "pair programming" impacts productivity and/or timeline |  | SharePoint |  | Michelle Edmonds |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation | NA | Monitor closely, especially early on to limit any adverse impacts | 27/04 - Not a risk, but a task. Close. |  |  | Add to workplan. |  | 2011-04-27 |  | 335 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R15 | 2011-04-22 |  | 05. Risk Closed |  | New process of automated testing impacts productivity and/or timeline |  | SharePoint |  | Michelle Edmonds |  |  |  | 04. Probable | 02. Medium |  |  |  |  | Mitigation | NA | Monitor closely, especially early on to limit any adverse impacts | 06/07 - Michelle will look into this. 27/04 - Nicole noted this is in-progress and she will have an update next week. | 2011-09-21 |  | Nicole to define 04-May. |  | 2011-05-04 |  | 335 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R16 | 2011-04-22 |  | 05. Risk Closed |  | New process of "continuous build" impacts productivity and/or timeline |  | SharePoint |  | Michelle Edmonds |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation | NA | Monitor closely, especially early on to limit any adverse impacts | 27/04 - Risk to plan for at this time. Close. |  |  | Add to workplan. |  | 2011-04-27 |  | 335 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R18 | 2011-04-22 | unknown | 07. Risk has become an Issue | Lack of a new vision and inability to change. | Recreating the current "siloed" approach to knowledge tools, rather than creating an integrated solution that can be leveraged firm-wide. With GSS and EYD starting SharePoint initiatives, we now have a growing number of separate solutions. | Additional cost of point solutions will may with SP | SharePoint |  | Michelle Edmonds | Alan Guthrie | High | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 03. High | 03. High | 03. High | 03. High | Assurance choosing Ovitas | Mitigation | NA | Strong cross-service line/stakeholder governance model Involving stakeholders in early strategy and feasibility sessions to encourage thinking ahead. Working with vendors and researching best practices to understand the art of the possible Starting with defined business requirements to understand WHAT functionality must be included before discussing how | 22-Feb: Brett and Michelle agreed on the call that the growing number of multiple instances is an issue. 5/10 - assessment will continue throughout the program 21/09 - assessment will continue throughout the program. | 2012-02-22 | Executive Project Sponsor | 22-Feb: Now an issue, I121. | 2012-03-01 | 2012-02-22 | I121 | 335 | FALSE | TRUE | FALSE | FALSE | TRUE | TRUE | -21 | FALSE | TRUE
R19 | 2011-04-22 |  | 05. Risk Closed |  | Lack of a voice from every end user may lead to missed requirements; It may be difficult to identify the correct resources from whom to elicit requirements. |  | SharePoint |  | Michelle Edmonds |  |  |  | 03. Possible | 02. Medium |  |  |  |  | Mitigation | NA | Representation from all service lines, EY Knowledge, and some CBS groups in workshops. Used feedback and reporting on external sites to understand some of external user requirements User group validation planned for future phases - design and implementation. Plan to conduct usability testing with “real” practitioners throughout design and implementation phases. An iterative approach will be used for further requirement gathering and build to increase flexibility in response to discovering “missed” or “changing” requirements. The effort will be divided into workstreams and phases to try to manage tackling too much at once. The business will identify primary SMR’s who will be able to reach out to additional contacts as needed. | 10/05 - discuss in the Thursday PM call. 27/04 - Need names of appropriate representatives by 21 May. | 2011-09-21 |  | See Mitigation Plan. |  | 2011-05-21 |  | 335 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R20 | 2011-04-22 |  | 05. Risk Closed |  | It may be difficult to identify the correct resources from whom to elicit requirements. |  | SharePoint |  | Michelle Edmonds |  |  |  | 03. Possible | 03. High |  |  |  |  | Mitigation |  | An iterative approach will be used for further requirement gathering and build to increase flexibility in response to discovering “missed” or “changing” requirements. The effort will be divided into workstreams and phases to try to manage tackling too much at once. The business will identify primary SMR’s who will be able to reach out to additional contacts as needed. | 27/04 - Combine with R19. Close. |  |  |  |  | 2011-04-27 | R19 | 335 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R36 | 2011-06-15 |  | 05. Risk Closed |  | SharePoint Developer Environments -- Performance / Sizing |  | SharePoint |  | Greg Van Valkenburgh |  |  |  | 03. Possible | 02. Medium |  |  |  |  | Acceptance | N/A | Waiting for Confirmation from Microsoft on the sizing -- e.g., especially RAM. Will not provide confirmation until signing and MS resources assigned | 15/06 - Microsoft SOW lacking detail. | 2011-07-27 |  | MS provided confirmation that 8GB is sufficient for baseline workstation. |  | ? |  | 281 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R37 | 2011-06-28 |  | 05. Risk Closed |  | Development Workstation Buildout - receiving MS requirements / direction so the 35 VM's (workstations) can be built for Fusion development team. |  | SharePoint |  | Scott Machovina |  |  |  | 03. Possible | 03. High |  |  |  |  | Mitigation |  | Work with MS to receive requirements prior to the start of development. | 27/07 - Nick Wood said to reach out and work with MS on load / config requirements - close risk. 06/07 - MS engaged - meeting to be scheduled to finalize dev workstation build. 29/06 -Microsoft needs to tell us what exactly they need. Brian and Greg to discuss off-line. | 2011-07-27 |  |  |  | 2011-07-27 |  | 268 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R43 | 2011-08-05 | unknown | 05. Risk Closed | We took action without knowing the People Strategy. We took requirements and design solutions. | The "People Strategy Refresh" is in process. Decisions/directions could be set that would change or alter approaches and strategy that could affect Fusion. Strategy is to be presented in September, then going through an approval/vetting process, and a "working plan" targeted for November. | Decisions/directions could be set that would change or alter approaches and strategy that could affect Fusion. | SharePoint |  | Michelle Edmonds | Michelle Edmonds | Minor | 03. Impact > 3 Months | 01. Slight | 01. Low | 01. Low | 01. Low | 01. Low | If the People Refresh Strategy significantly changes decisions on the People workstream. | Acceptance | Need to wait until strategy is defined | Evaluate impact when strategy is accepted/announced | 5/10 - still need to assess impact when strategy is announced. 21/09 - still need to assess impact when strategy is announced. 08/05 - new risk opened | 2012-03-28 | Project Manager | Will be addressed by the WSL | 2012-03-29 |  |  | 230 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | 7 | TRUE | FALSE
R44 | 2011-08-09 | unknown | 05. Risk Closed | The RFP time takes longer than initial plan. | Prioritization of all work for Phase 1 will not be possible due to the need to have 3rd party components for items such as Taxonomy Management | The end date of the effort will not be able to be projected | SharePoint |  | Michelle Edmonds | Michelle Edmonds | Minor | 01. Impact < 4 weeks | 03. Possible | 02. Medium | 01. Low | 02. Medium | 02. Medium | RFP decision. | Mitigation |  | Priorizite all work with the information known to date | 31-Jan: Incorporating changes in the re-plan 5/10 - assessment will continue throughout the program 28/09 - in process | 2012-02-22 |  |  | 2012-02-01 |  |  | 226 | FALSE | TRUE | FALSE | FALSE | TRUE | FALSE | -50 | FALSE | FALSE
R45 | 2011-08-09 |  | 05. Risk Closed |  | If the placeholders used to gauge the work for Phase 1 are significantly less than the detailed estimates, the team size could be off. | Wrong size of the development team, excess capacity or not enough capacity or not enough of the right type | SharePoint |  | Michelle Edmonds |  |  |  | 03. Possible | 02. Medium |  |  |  |  | Mitigation |  | Review work load as new information becomes available. Use best practices from similar efforts to verify estimates. Review weekly with the any new information available | 5/10 - assessment will continue throughout the program 28/09 - in process | 2012-01-01 | [5 empty] | 226 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R49B | 2011-10-10 | unknown | 07. Risk has become an Issue | The go live of SharePoint | Level 4 Support Team for Post Phase 1 Go-Live has not been confirmed (IT Solutions Teams are structured by Portfolio) | Resources not available causng existing resources to be used and less functionality in Phase 2 | SharePoint |  | Guy Morgan Alan Guthrie | Mike Laci | High | 03. Impact > 3 Months | 03. Possible | 03. High | 03. High | 03. High | 03. High | Go Live | Mitigation | Current team will do fixes after Go Live | We need to define the Level 4 Support Team | 07/12 - Per Alan, Skip. Review next week. 12/10 - Application Engineer support needed. Guy will follow up with Alan. | 2012-02-01 | Executive Project Sponsor |  |  |  |  | 164 | FALSE | FALSE | FALSE | TRUE | FALSE | TRUE | -40990 | FALSE | TRUE
R51B | 2011-10-10 | unknown | 05. Risk Closed | Unclear responsibilities | EY needs to make sure we do not accidentally take Microsoft responsibilies for Architecture, Design and Development | EY would have paid too much to mitigate a risk that they had taken | SharePoint |  | Michelle Edmonds | Michelle Edmonds | Minor | 03. Impact > 3 Months | 01. Slight | 03. High | 03. High | 02. Medium | 03. High | EY decision to deviate from Microsoft recommendation. | Mitigation | Make sure we fully communicate Roles and Responsibilities across the MS / EY Teams. | Make sure we fully communicate Roles and Responsibilities across the MS / EY Teams. | 7 Feb: This Risk will be throughout the project. | 2012-10-07 | Program Manager | Will be addressed as part of the replan | 2012-10-07 |  |  | 164 | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | 199 | FALSE | FALSE
R52B | 2011-10-10 |  | 07. Risk has become an Issue |  | We may not have time to complete Phase I delivery for Assurance depending upon the decision at the end of Nov. (Assurance Knowledge Tool). | GAAIT replacement would be delayed | SharePoint |  | Michelle Edmonds |  |  |  | 03. Possible | 03. High |  |  |  |  | Mitigation |  | We will continue to work with the Core Team to confirm plan. We will work with them to look at the deliveries to confirm what is possible for Phase I. | 1/11 - Decision will now be in December working with the Assurance on the Ovitas and the other 3 solutions | 2012-01-01 |  |  | 2012-03-01 |  |  | 164 | FALSE | TRUE | FALSE | TRUE | FALSE | FALSE | -21 | FALSE | FALSE
R56 | 2011-09-21 |  | 07. Risk has become an Issue |  | Open resource needs for SharePoint workstream (QA Lead, QA, Lead Developers, Release Manager, Solution Arch's, PM's, BA's) |  | SharePoint |  | Michelle Edmonds |  |  |  | 03. Possible | 03. High | [6 empty] | Continue to assess and work with Resource Planning to fill open positions. | 12/10 - placed as a Critical issue 5/10 - Receiving / reviewing resumes for QA Lead, Release Mgr, PM, and BA open positions. 28/09 - continue to work with Cross Portfolio resource planning team to fill open requests. 21/09 - Submitted all open resource requests with Resource Planning Team. Weekly meetings scheduled to review with resource planning and sourcing. | 2011-10-12 |  |  |  | 2011-10-12 | Issue ? | 183 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R69 | 2011-11-01 |  | 05. Risk Closed |  | IPM was the forum to have cross workstream communication and awareness. Executive Sponsors concerned about effectveness and expense of meeting. |  | SharePoint |  | Michelle Edmonds |  |  |  | 03. Possible | 02. Medium |  |  |  |  | Mitigation |  | Changed IPM and implemented a cross group meeting to address this risk | 1/11 - Met with team today to define options. Will continue to monitor. | 2011-11-02 | [5 empty] | 142 | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | -40990 | FALSE | FALSE
R7 | 2011-03-17 |  | 05. Risk Closed |  | Document conversion service for SharePoint Online is not on the current Microsoft offering, but on the roadmap. The timing of the implementation of DCS may not fit in with our time scales. |  | SharePoint |  | Adrian Mickleson |  |  |  | 03. Possible | 01. Low |  |  |  |  | Mitigation | Implement SharePoint Modules that require DCS on premises | This is on the basis that all SharePoint workloads will be implemented in the cloud. | 06/07 - Not going BPOS, don’t know what other managing service position would be on this. 27/04 - The team provided a recommendation to John C. He is reviewing the recommendation. Hold open until hear back from John. | 2011-08-17 |  | Monitor MS progress for DCS 19/04 - Current recommendation from the IT team is to implement all SharePoint services on premises. |  | 2011-05-11 |  | 371 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R70 | 2011-11-01 |  | 05. Risk Closed |  | Prioritization of work across workstreams. Original plan will not work. |  | SharePoint |  | Michelle Edmonds |  |  |  |  | 01. Low | [6 empty] | Duplicate of another risk | [7 empty] | 142 | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | -40990 | FALSE | FALSE
R71 | 2011-11-01 |  | 05. Risk Closed |  | Limited/reduced EY participation in SharePoint Foundation Planning workshops may affect quality of SharePoint Foundation Planning activities & deliverables | wrong infrastructure would cause delays | SharePoint | [6 empty] | 01. Low |  |  |  |  | Mitigation |  | Provide resource and let other items not be completed | 1/11 - MCS - Limited/reduced EY participation in Planning Workshops may affect quality of Design/Planning workshops; Dan Mulligan does not appear to be the correct resource to represent Infrastructure; Michelle Edmonds not available for Week 2; Kerri Keller not available to represent her area. | 2012-01-01 |  |  | 2011-11-01 |  |  | 142 | FALSE | TRUE | FALSE | TRUE | FALSE | FALSE | -142 | FALSE | FALSE
R77 | 2011-11-22 |  | 05. Risk Closed |  | The SharePoint Foundation team used knowledge of current service delivery efforts and has specified an environment for external collaboration. If during requirements ECMA significantly varies from this the infrastructure will have to be redesigned | The infrastructure would have to be rebuilt for those items incorrect and the environments would be delayed or not meet the needs | SharePoint |  | Michelle Edmonds |  |  |  | 03. Possible | 03. High | [7 empty] | 07/12 - Michelle said to push next review to February. | 2012-02-01 | [5 empty] | 121 | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | -40990 | FALSE | FALSE
R80 | 2011-12-05 |  | 05. Risk Closed |  | Reuirements Gaps between mock up screens and use cases may compromise QA test coverage | Testing delayed or incomplete | SharePoint |  | Kerri Keller |  |  |  | 03. Possible | 02. Medium |  |  |  |  | Mitigation | Engage PM to escalate to Requirements Owner | Gaps in design and hence test coverage to be closed by aligning the documentation and reflecting this in TFS Requirements. | 05/12 - Risk opened. | 2011-12-07 | [5 empty] | 108 | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | -40990 | FALSE | FALSE
R83 | 2011-12-05 | unknown | 05. Risk Closed | Team members unable to represetn end user needs. | The SharePoint team is using intermediaries to capture requirements, not end users this means that requirements might change as the items are shown to end users | Additional cost and time needed to deploy the solutions | SharePoint |  | Michelle Edmonds | Michelle Edmonds | High | 03. Impact > 3 Months | 04. Probable | 03. High | 03. High | 03. High | 03. High | Functionality does not meet end user need | Mitigation | Defined in methodology | need to have sessions with the end user to show the functionality and gather feedback | 22-Feb: continue to monitor; next review date 3-4 weeks. 31-Jan: Reassess as workstream leaders are assigned. | 2012-03-21 | Managing Sponsor | Will be addressed by the WSL | 2012-01-15 |  |  | 108 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | -67 | FALSE | TRUE
R84 | 2011-12-06 |  | 05. Risk Closed |  | External vendors (frog) wants to interview client serving personel and E&Y customers. This could be a data privacy risk | Effectiveness of User Experience designs. | SharePoint |  | Binoy Raj |  |  |  | 04. Probable | 02. Medium | [7 empty] | 06/12 - Being reported to Q&RM team. | 2011-12-07 | [5 empty] | 107 | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | -40990 | FALSE | FALSE
R89 | 2012-01-06 | Norm Lambert | 05. Risk Closed | O365 | User Experience needs to take into consideration O365 decision | Setting expectations that won't be met or performing work beyond O365 intent to use out of the box. | SharePoint |  | Michelle Edmonds | Guy Morgan | High | 01. Impact < 4 weeks | 04. Probable | 03. High | 03. High | 03. High | 03. High | Focus on OOB | Acceptance | Modify the Contract | Discuss with Frog the decision of O365 | 25-Jan: Michelle said they are working with FROG to make this happen. 11 - Jan Item opened. Guy to communicate to Team. | 2012-02-01 | Program Manager |  |  |  |  | 76 | FALSE | FALSE | TRUE | FALSE | FALSE | TRUE | -40990 | FALSE | TRUE
R94 | 2012-01-31 | Binoy Raj | 05. Risk Closed | Service lines are not identifying their particpants to the project team. | Slippage of the user experience timeline | Might impact ideation session planned by end of February. | SharePoint |  | Michelle Edmonds | Eric Wahl / Kevin Smyth | High | 01. Impact < 4 weeks | 04. Probable | 01. Low | 02. Medium | 04. Critical | 03. High | resources not identified by February 3rd | Mitigation | Release 1 will not include Frog deliverables. | Escalate to Bob Reiner | 7 Feb: Replanning in progress. Eric Wahl to meet on 3/7 to discuss further. 29-Feb: This will be decided next week after the output FSG mtg. Slippage will be quantified next week as well. 22-Feb: The UX timeline moving out about 2 wks; this has been escalated for Change Control. Keep open until have it signed off. 07-Feb: Slippage on identifying participants from TAX, escalated to Bob Reiner. Mitigation plan being discussed with frog. 31-Jan: Risk opened | 2012-03-14 | Executive Sponsor | Will be addressed by the WSL | 2012-03-16 |  |  | 51 | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | -6 | FALSE | TRUE
R13 | 2011-04-22 |  | 05. Risk Closed |  | Need to determine where in country servers are required |  | Tech Foundation |  | Adrian Mickleson |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation | NA | Define scope & number of in country servers. | 27/04 - Not a risk, but a task. Close. |  |  | Add to workplan. |  | 2011-04-27 |  | 335 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R2 | 2011-02-15 |  | 05. Risk Closed |  | Provisioning standard user object has a direct impact on end users, are we in the position to provide the support needed for every user globally within the timeline |  | Tech Foundation |  | Anthony Harper |  |  |  | 03. Possible | 03. High |  |  |  |  | Mitigation | Consider work performed by the AD group provisioning project and how that can be expedited for the needs of the M&C program | Interim SOW approved to engage Microsoft to determine appropriate approach for AD requirements | 27/04 - Related to Interim SOW, has been mitigated. Close. |  |  | Kick off interim SOW work 19/04 - superceeded by the wider Active Directory risk |  | 5/10/2011; Closed 27/04/2011 |  | 401 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R120 | 2012-03-05 | Michelle Edmonds | 02. Open & Assigned | External Requirements not clearly defined | External environment may not be ready for go-live | Internal capabilities only will be in Release 1 | SharePoint |  | Michelle Edmonds | Jeremy Brown | Moderate | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 03. High | 02. Medium | 03. High | 03. High | Client facing DTU is confirmed to be in scope in Release 1. | Undecided |  | Confirm with WSL's if external requirements need to be delivered in Release 1. | 14-Mar: Michelle to update mitigation plan. New due/review date: 30-Apr-2012 7 Feb: Added and updated Risk. 12 Mar - Not necessary for Phase (Relase 1) SP 20 Mar - Asigned to Jeremy to falitate the discussion with the appropriate BPO | 2012-04-30 | Program Manager | Not necessary for Phase (Release 1) SP. | 2012-04-30 |  |  | 17 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 39 | FALSE | TRUE
R114 | 2012-03-05 | Norman Beard | 02. Open & Assigned | Estimated license counts not accurate enough | The initial EY FAST Software license contains less licenses than the Dec infrastructure meeting had estimated | Increase in Costs to the program. | SharePoint |  | Michelle Edmonds | Travis Clayton | Moderate | 03. Impact > 3 Months | 03. Possible | 01. Low | 03. High | 01. Low | 03. High | More FAST infrastructure requirements than current licenses purchased | Mitigation | Assess overall needs to evaluate license requirements | Need to review and action appropriately | 19 Mar - Risk will be reassessed as content is entered 7 Feb: Created this Risk. | 2012-06-01 | Managing Sponsor |  | 2012-07-01 |  |  | 17 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 101 | FALSE | TRUE
R117 | 2012-03-05 | Michelle Edmonds | 02. Open & Assigned | Unclear deployment and environment setup processes. | No clarity on how to promote taxonomy values between development, testing, staging etc | Impact to Testing cycle | SharePoint |  | Norman Beard | Tom Beerley | Minor | 01. Impact < 4 weeks | 01. Slight | 01. Low | 01. Low | 01. Low | 01. Low | Unable to populate taxonomy information across the environments | Mitigation |  | Export to Excel and then re-import into various environments | 19 Mar - Norm Beard identified to run down root cause 7 Feb: Added and updated Risk. | 2012-06-01 | Program Manager |  | 2012-06-01 |  |  | 17 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 71 | FALSE | FALSE
R29 | 2011-06-01 | unknown | 05. Risk Closed |  | SP Foundation - Infrastructure needs SP Enablement business requirements. |  | Technology Foundation |  | Adrian Mickleson |  | Moderate |  | 04. Probable | 02. Medium |  |  |  |  | Mitigation | CR raised on MS to provide additional resource | Use current non-functional requirements to help drive to sessions regarding SP Architecture. | 18-Jan: Al confirmed that this is closed. Norm and Mark have it in hand. 05/10 - CR being raised on MS to restart SharePro Foundation and provide additional resource to capt NFRs from Fusion. Expectation that BRs will be confirmed by end Nov '11. 08/06 - due to delay in envisioning until July, reduce risk to moderate. The requirements will be known before the sessions. 01/06 - Use current non-functional requirements to help drive to sessions regarding SP Architecture. Develop initial global architecture for the firm and refine it as solutions are determined. | 2011-10-05 |  | Accept that BRs will be confirmed by Fusion for Phase 1 as of end Nov '11 | 2011-10-05 | 2012-01-18 |  | 295 | FALSE | TRUE | FALSE | FALSE | TRUE | FALSE | -169 | FALSE | TRUE
R3 | 2011-03-25 | unknown | 06. Deferred | 8-Feb: The current solution is no e-mail archiving. | As the current solution is that there will not be e-mail archiving, the team is working toward this end. There is a risk then that should there be a need for e-mail archiving, we would need to create a solution. | Any requirement for email archiving will impact timelines and cost. | Technology Foundation |  | Adrian Mickleson | Adrian Mickleson | Moderate | 01. Impact < 4 weeks | 04. Probable | 02. Medium | 01. Low | 02. Medium | 02. Medium | If there is a legal requirement for archiving of e-mail, will trigger. | Mitigation |  | 1. Steve Jelf to obtain final Q&RM position. 2. (Adrian) Align with arch. RFP (ensure vendors have capability) | 05-Mar: This is not a risk, but a decision. Could be an issue depending on decision (ie if we decide need email archiving). Track as decision; if need be, open as an issue. 08-Feb: Changed syntax; this item was very outdated. Corrected year on the due date from 2011 to 2012. Desc used to read: "The timing of the implementation of the required Archiving solution to integrate with Exchange Online services. The German firm have a mail archive solution where we keep full copies of a users Notes mail file (up to 10 years of data) on a small set of Domino servers attached to lots of storage (45TB and growing). This in essence is a home grown mail archiving solution for Germany. There is a looming end of support date for the storage system that will hit us end of March 2012 ish." 06/07 - Brett said there is no global reason for global archiving. Reduce risk to Low. 22/06 - RFP is being circulated for review / confirmation. 01/06 - 1 week behind in releasing draft of RFP. Internal meeting planned for Friday to review and complete. 25/05 - Need vendor decision by July at latest; working on RFP; will work with internal decision makers and vendors to drive down time frame. 18/05 - Need to gain idea of timescale of suppliers and look at how coordinates with our plan. 11/05 - This risk is based on the approach determined by Issue 1. Leave as is for this week. 27/04 - Progressing successfully; archive solution should be ready very quickly, next week. Checking to ensure all requirements are gathered. R10 combined here and closed. | 2012-02-15 | Program Director | Track through decisions (already open, D80). Marked as Deferred, depending on the decision that is made, may need to open an issue (do so from this item and update status accordingly). | 2012-05-31 | 2012-03-05 | D80 | 363 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | 70 | FALSE | TRUE
R32 | 2011-06-14 |  | 05. Risk Closed |  | Absense of BPOS POC prevents validation of migration and coexistence tools |  | Technology Foundation |  | Mark Reade |  |  |  | 04. Probable | 02. Medium |  |  |  |  | Acceptance |  |  | 10/8 - BPOS is not in scope - close risk. 15/06 - Mark added this as a potential risk. BPOS POC was not validated up front. Revisit in 2 weeks. | 2011-07-27 |  | TBD |  |  |  | 282 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R33 | 2011-06-14 |  | 05. Risk Closed |  | Group Management solution is required to manage the Active Directory groups prior to commencement of UAT, Lync and Outlook. |  | Technology Foundation |  | Daren Wicks |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation |  | 27/07 Work on GLMS(plane a) being planned, and RFP underway for Third Party (Plan b) (Plan a) Looking at modifying GLMS to add the required extra content and formatting (plan b) looking at alternative 3rd party tools such as Imanami 22/6 - Work on both plan A and B progressing, Plan A (modification of GLMS) appears to split into two phases, co-existance and exchange, 3rd party tool still looks to be potentially viable option. | 14/09 - Close as a risk and open as a critical issue, Issue 35. 07/09 - RFP responses received and are currently being evaluated. Program interdependency stated in enterprise plan. 31/08 - RFP responses due back close of business today. Only expecting 2 responses as there were legal implications with the third. 24/08 - Responses due back from vendors by 31-Aug; will forward change request when know what cost is; no further updates. 17/08 - In process; RFP out for solution. 10/08 - next steps are to complete the RFP and figure out how / who is going to pay for it. 27/07 Work on GLMS(plane a) being planned, and RFP underway for Third Party (Plan b) (Plan a) Looking at modifying GLMS to add the required extra content and formatting (plan b) looking at alternative 3rd party tools such as Imanami. 22/06 - Work on both plan A and B progressing, Plan A (modification of GLMS) appears to split into two phases, co-existance and exchange, 3rd party tool still looks to be potentially viable option. 15/06 - Risk added by Steve - continue to work with MS on ITAP analysis. | 2011-09-21 |  |  |  | 2011-09-14 |  | 282 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R34 | 2011-06-14 | unknown | 05. Risk Closed | The product we are usinig today doesn't transfer to the Msft platform. | Encrypted E-mail solution needed (Identified by ITAP) | E-mail will not be encrypted in SP. | Technology Foundation |  | Ted Balfour | Paul Neave / Dean White | Moderate | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 02. Medium | 01. Low | 02. Medium | 00. Undecided | If we can't get approval on an SOW and guaranteed resources from Msft in time, this risk will occur. | Avoidance |  | Rights management Server is MS solution for Exchange encrypted e-mail, working to see if this should be part of IAM project (its very focused on Identity and Access) or M&C | 8-Feb: Ted emailed, "Yes, RMS will be the solution used for encryption so this item can be closed." 8-Feb: James and Paul believe this item can be closed; AD RMS has been id'd as the tool and if implement AD RMS won't be doing encrypted mail. Laura em'd Ted to double check on closure suggestion. 26-Jan: Changed owner to Ted from Bob Cooney. 06-Jan - This item did not previously have a required risk resolution date; added 1-May as that date. 05/10 - This will form part of discussion at the planning workshops scheduled to commence 10/10. Re-visit after these w/c 17/10 15/06 - this will be explored during the envisioning sessions with MS. Revisit after sessions. | 2012-02-08 | Project Manager | 8-Feb: Ted, Paul, James said we will be using AD RMS and if implement AD RMS won't be doing encrypted e-mail. Close. | 2012-05-01 | 2012-02-08 |  | 282 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | 40 | FALSE | TRUE
R4 | 2011-02-15 |  | 05. Risk Closed |  | Timely availability of system logs (SMTP logs, SharePoint Logs) hosted in the cloud for Forensics & Investigation to support EY legal obligations. |  | Technology Foundation |  | Ken Iloka |  |  |  | 03. Possible | 03. High |  |  |  |  | Mitigation | Implementing an archiving solution or confirmation that we can use email back ups should resolve this risk. | Investigate an on premise archiving solution | 27/04 - Close. |  |  | Kick off review of potential vendors 19/04 - linked to archiving risk above |  | 4/18/2011; Closed 27/04/2011 |  | 401 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R42 | 2011-07-29 |  | 05. Risk Closed |  | Environment buildouts are based on assumptions for Phase 1; however, they could change as new requirements are identified which may cause infrastructure changes. |  | Technology Foundation |  | Adrian Mickleson / Michelle Edmonds |  | Minor |  | 03. Possible | 01. Low |  |  |  |  | Mitigation |  | Made assumptions based on the existing Vision and Scope documents from the business. Review monthly | 18-Jan - On call with Al, he confirmed that this is closed. Norm and Mark have it in hand. 29/07 - new Risk opened during the Development / Architecture task list discussion. | 2011-12-01 |  | Norm and Mark have this in hand; wasn't reviewed for many months and at time of review 18-Jan, can be closed. |  | 2012-01-18 |  | 237 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R47 | 2011-04-01 |  | 05. Risk Closed |  | A number of prerequisites activities will need to be completed in time for the commencement of the SOWs Decided 11-May that this issue will be specific to "Active Directory" work. Moved from Issue to Risk on 24-Aug. |  | Technology Foundation |  | Adrian Mickleson / Daren Wicks |  |  |  |  | 03. High | [7 empty] | 31/08 - Closed. 24/08 - Closed as Issue 4 and opened as a new risk. Daren has done first pass review with GCL5 team; will be ongoing. Still gathering requirements specific to AD. For prior log entries, see Issue 4 (closed). | 2011-08-31 |  |  |  | 31/08/11 |  | 356 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R48 | 2011-08-24 |  | 07. Risk has become an Issue |  | Availability / time-line of the development VM boxes (config & software) and the deployment environments (development, QA, Production) for iteration 2. 1. Ver 2 - Developer Workstations - Nov 22 '11 2. Ver 2 - Component Integrated Development Environment - Dec 1 '11 3. Ver 2 - Deployment Integrated Development Environment - Dec 1 '11 4. QA Environments (Intranet, Extranet, Security) - Dec 1 '11 5. Staging Environments (Intranet, Extranet) - Jan 3 '12 6. UAT Environments (Intranet, Extranet) - Jan 15 '12 |  | Technology Foundation |  | Adrian Mickleson |  | High |  | 03. Possible | 03. High |  |  |  |  | Mitigation | CR bring raised on MS to specify design, build to be fast tracked once approved | Repurpose 2xVMs for an interim Iteration #1 QA build use the build expedite group where possible to reduce the time required to builid the servers | 10-Jan: Michelle reqd this item become an issue, #94. 04-Jan: Michelle will followup with Norm and Adrian; there was a call with Msft over break on which they assigned some resourcesto get environments up. We will review next week and at that point either close or create an issue. 14/12 - Concern of holding up Fusion. The end of the week environments will be discussed. 30/11 - Adrian said review next week; needs to catch up with Mark on this one. 23/11 - Adrian confirmed this should still be open and high because the CR hasn't been approved. Review next wk. 09/11 - Mark, Michelle and Msft discussed this morning. Should have answer two weeks. 11/4 - SP and foundation will be meeting together for the next two weeks and will wok to resolve this risk 11/4 - Input the dates for the non-production environments in the issue 19/10 - Michelle and Adrian to discuss off-line. 05/10 - MC agreed to repurposing 2 VMs currently being rebuilt so that an interim QA environment can be provided 22/09 - The risk is that any delay in firming up the design for Iteration 2 will impact our ability to deliver. Change ownership from Mark/Rita > Mark/Mike. 14/09 - The interim solution has been provided. Keep as High; there could be some potential risks here with the VMs. Teams will monitor. 07/09 - updated description so the risk is specific to Iteration 2, not 1. Have interim solution, but there are other environments we'll be targetting. The date we're handing over iteration 2 environments is later than we'd like. 31/08 - Working through this now. 24/08 - Rita opened; Mark and Rita to discuss off-line. | 2012-01-11 |  | CR to be submitted and VMs repurposed where necessary 10-Jan: Risk became an issue; opened as Issue #94 |  | 10-Jan-2012 (became an issue) | I94 | 211 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | -40990 | FALSE | TRUE
R49A | 2011-08-24 |  | 05. Risk Closed |  | TFS infrastructure: can it handle the expected load in future? What is the process if proxy goes down? |  | Technology Foundation |  | Mark Reade/Rita Seibel |  |  |  |  | 03. High | [7 empty] | 07/09 - Brian Blinco confirmed we accept this. We have a process for this; it is not an issue. Close. 31/08 - Mark not on call; Nicky doesn't think they suspect issues, but need to check with Mark. 24/08 - Rita opened; Mark and Rita to discuss off-line. | 2011-09-07 |  |  |  | 2011-09-07 |  | 211 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R5 | 2011-03-28 | unknown | 05. Risk Closed |  | The timing for the implementation of the required WAN optimisation solution for BPOS / Cloud Computing. This may require engagement with 3rd party suppliers and likely to add to the overall schedule. Not a constraint to Lync implementation. |  | Technology Foundation |  | Adrian Mickleson | Adrian Mickleson | Critical |  | 03. Possible | 01. Low |  |  |  |  | Mitigation | Align the program to the GWAN program and decouple non dependent work streams such as Lync. | Kick off the GWAN program as soon as possible and adject the plans to reflec lead times for GWAN delivery. | 08-Feb: Paul and James suggested this can be closed since the subsequent Riverbed risk has been opened (R92). Al and those on the 15-Feb RAID call agreed; close here. 06/07 - move to Low since BPOS is off the table. 22/06 - review in 2 weeks. 01/06 - discussed with John, no issue. If plan is received this Friday, should be able to decrease impact level. 25/05 - weekly meeting with Brendan's group. They have ongoing transformation program for GWAN optimization. If don't go BPOS, would want to jump on as soon as possible. John brought up a dependency concern with regards to DCC. To be discussed further off-line. (John) 18/05 - PM designated: Steven Bates Meeting earlier this week, high level expectation still 6 mos to deliver. In next two weeks will look at feasibility of 6 mos. Action: Work with Steve to get the dependencies/requirements for the high-level program pertaining to GWAN decision. 1/05 - Brendan not on call; dependent on BPOS. This (compared to R9) is BPOS-related network concern as opposed to more general, internal network stuff. 27/04 - Brendan to provide update tomorrow. He has provided a high-level plan. | 2012-02-15 |  | This is duplicate of newer items around Riverbed/bandwidth (R92). Close here. | 2011-05-31 | 2012-02-15 |  | 360 | FALSE | TRUE | FALSE | FALSE | TRUE | TRUE | -296 | FALSE | TRUE
R72 | 2011-11-01 |  | 05. Risk Closed |  | Absence of dedicated EY SharePoint Architect may affect quality of SharePoint Foundation Planning activities & deliverables Note: This item refers to a matching EY resource for the Msft Architect. |  | Technology Foundation |  | Adrian Mickleson |  |  |  |  | 03. High | [6 empty] | Need Full-Time EY Architect assigned to the SPF project | 30/11 - There is an EY architect in place. The team agreed on the call this can be closed. 23/11 - specified that this refers to a matching EY architect, review next week. 1/11 - MCS - Need Full-Time EY Architect assigned to the SPF Project; A Full-Time EY Architect will be required to ensure the success of SPF planning activities; This role is critical to the Planning workshops to lead EY position. | 2011-11-30 |  |  |  | 2011-11-30 |  | 142 | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | -40990 | FALSE | FALSE
R79A | 2011-12-05 | unknown | 05. Risk Closed | We are at planning stages in program. | There is a risk that the testing environments will be unavailable for when we need to start testing. | If cannot get test environment available, will impact schedule. | Technology Foundation |  | Adrian Mickleson | Adrian Mickleson | Critical | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 01. Low | 03. High | 04. Critical | 03. High | Inability to specify and provision in the next month (from 8-Feb) | Mitigation | Purchase representative hardware and accept that it's not going to be fully representative of the full design. | To gain agreement on the architecture and then go to the procurement process; agreement from project and ops sides. | 29 Feb: Issue is reducing, there is an unknown element. blurprint is being worked on. this only applies to SP. 8-Feb: Paul and James updated all columns on this item. Norm Beard said this is still a risk for timeline, impacting SP. There is a workshop in Cleveland next week with discussion sched.on environment management. Review 2 wks. 05/12 - Risk opened. | 2012-03-14 | Project Manager |  | 2012-02-17 |  |  | 108 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | -34 | FALSE | TRUE
R79B | 2011-09-27 |  | 07. Risk has become an Issue |  | The current UC approach to collecting User Requirments is on a different timeline to the TF Architecture & Design phase for Lync & Outlook which is currently preceeding it. | If additional requirements are driven out by the UC requirements work then they will not have influenced the TF design for Lync & Outlook and could require Change to the designs incurring additional costs and delaying implementation | Technology Foundation |  | Adrian Mickleson | Adrian Mickleson |  |  | 04. Probable | 03. High | [7 empty] | 04-Jan: Al said this is now an issue; close as a risk and open as issue. Next review mid-February. Issue 85. 14/12 - Flying Hemant to London in January to close gap. | 2012-01-04 |  | Became an issue 4-Jan. |  | 2012-01-04 | I85 | 177 | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | -40990 | FALSE | FALSE
R82 | 2011-12-01 | unknown | 05. Risk Closed | This is due to a lack of requirements resources. | AD RMS work, which we need to enable encryption in Outlook, is not likely to deliver till after we plan to start testing. Also introduces a risk of AD RMS not being in place for UAT, pilot etc. | Will extend the timeline for the Exchange. Will dictate the goes we can use for UAT and pilot and will dictate the countries we can migrate to. Will impact the ability to encrypt internal e-mail. | Technology Foundation |  | Adrian Mickleson | Ted Balfour / Ken Sponaugle | High | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 03. High | 03. High | 02. Medium | 02. Medium | The timelines within the AD RMS SOW. | Mitigation | Put in place a workaround for testing ensuring that AD RMS is prioritised in the test environment | Could go live without the abliity to encrypt internal e-mail, if that is acceptable. | 29 Feb: Complete by integration solution. SAW in hand and delivered. 08-Feb: Ted said they rcvd the updated SOW (inc. O365) last Fri. Looking to complete reviews end of this week/early next week. Al confirmed more information on the pilot will emerge in the next 7-9 days, review 2 wks. This will either be closed (Look/See pilot) or moved further out. 26-Jan: Changed Ass. to to Ted from Bob C. 18-Jan: This may be reframed in light of O365 decision to come next week. Will change timeline dramatically. Workshops next week; review in 2 weeks. 11-Jan: added Ken/Bob as assigned to. Ken working on SOW from msft (in draft). It was decided yesterday this will be put on hold until BPOS decision is made. Update provided by Al that an interim SOW will be put in place this week of next. Ant is working with John Bruce to get a headstart. Review next week. 14/12 - Need determination after workshops on whether it is only initially Exchange or including SharePoint. | 2012-02-22 | Program Director |  | 2012-01-30 |  |  | 112 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | -52 | FALSE | TRUE
R9 | 2011-03-17 | Rewa Bouji | 07. Risk has become an Issue | Due to strategic change in the approach of delivery to Lync | There is a risk that the managed services RFP for hosted services may include options based on cloud technology. Therefore, network requirements must be provided to the network team in a timely manner. | Impact on timeline and budget. | Technology Foundation |  | Adrian Mickleson, Peter Browne |  | High |  | 01. Slight | 03. High |  |  |  |  | Mitigation | Consider tactical implementation of the network needs for M&C program | Work with GWAN program sponsor to manage the dependencies between the programs | 08-Feb: Syntax outdated as we are now 99% sure going to the cloud. Close from a risk perspective and open as an issue (I113) since the impact is certain - that users won't have as rich a Lync experience based on local bandwidth capabilities. 04-Jan: Changed date in the desription from 28-Oct to 14-Feb (per Al on call). Review mid-Feb. 14/12 - continuing with working assumption of on-prem. 23/11 - should get the green light Friday; review next week. 09/11 - Adrian should have answer end of this week. Review next week. 05/10 - This will be clarified by week ending 28-October. Greg will also reach out to Mike O'Donnell for clarity. Greg's action closed 19/10. 22/09 - Greg, Adrian and Brett to restate the risk: what was the original intention with this item? May even need to close this and start a new one. 14/09 - Changed owner from Daren to Adrian. Change probability from High to Low. Impact to stay at High. Move review date out one month. 31/08 - Daren caught up with Steve Yeomans; should clear this up and the enterprise plan, too. 2 year plan for WAN optimization. 17/08 - Adrian's RFP will determine what will happen with regards to network requirements. Will decide which option (inhouse, 3rd party, hybrid) by 2nd or 3rd week of Sept. If go to external environment, 6 months lead time. 10/08 - Peter met with team and they are still on track. Adrian to restate risk. 3/08 Steve reports that IAM and GWAN teams are now invited to Raid call. Meeting scheduled next week to start to sync GWAN and M&C plans. 27/07 - Program started, Steve Betts to invite Steve Yeomans to next week's call. 06/07 - The Network program has kicked off. Meeting Scheduled with Brendan and team. 15/06 - Working on DCC rollout program to see how it will affect user migration mapping (ongoing discussion). Network requirements will come from envisioning sessions. 18/05 - Work with Steve on high-level requirements/dependencies. 27/04 - Adrian will follow-up with Peter. 11/05 - Action to Al: Set meeting to discuss offline. This is related to SharePoint and internal, more general network concerns (as compared to R5). | 2012-02-08 |  | Obtain and monitor time scales for other programs |  | 2012-02-08 | I113 | 371 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | -40990 | FALSE | TRUE
R118 | 2012-03-05 | Michelle Edmonds | 02. Open & Assigned | Separate SP development ahead of SP Program. | No clarity on how to blend the EYD content types into taxonomy | More than one Metdata Model | SharePoint |  | Michelle Edmonds | Lee Eichelberger | Moderate | 01. Impact < 4 weeks | 03. Possible | 02. Medium | 02. Medium | 02. Medium | 02. Medium |  | Undecided |  |  | 19 Mar - Currently accounted for in the metadata management plan and escalated issue to executiive sponsors 7 Feb: Added and updated Risk. | 2012-04-15 | [5 empty] | 17 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | -40990 | FALSE | TRUE
R91 | 2012-01-25 | Brett van Gelder | 07. Risk has become an Issue |  | There is a risk that we have not undertaken an impact assessment that looks at the anticipated required bandwidth from each location with Outlook users to the anticipated site for the relevant Exchange server(s) to determine and/or confirm that adequate bandwidth is available (or will be available) for deployment. |  | Technology Foundation |  | Adrian Mickleson / Al Grljevic | Paul Neave / Nick Wood / John Murray | Critical |  | 03. Possible | 01. Low | 03. High | 03. High | 03. High |  |  |  | 1. Complete the exercise to review all country connections in to the MPLS cloud. | 8-Feb: Opened as I114. 25-Jan: Opened, as identified by Brett and Al. Action is with Paul, Nick and John to complete the exercise to review all country connections to the MPLS cloud. | 2012-02-01 | Project Manager | 8-Feb: per call with Paul and James, this is an issue. Opened as I114. Paul said they are currently trying to get this assessment started. |  | 2012-02-08 | I114 | 57 | FALSE | FALSE | TRUE | FALSE | FALSE | TRUE | -40990 | FALSE | TRUE
R92 | 2012-01-25 | Brett van Gelder | 05. Risk Closed | Msft 365 has recommended that we don't use Riverbed, as they believe this will cause siginificant problems. | Program has been built on the assumption that riverbed would work; Microsoft has indicated that Riverbed won't work or may cause challenges. It is a significant risk to the program that we do not know whether they will work or not. | The user experience could be impacted if we are unable to use optimization. | Technology Foundation |  | Adrian Mickleson / Al Grljevic | Adrian Mickleson | Critical | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 04. Critical | 04. Critical | 04. Critical | 04. Critical | Once we've installed Riverbed, if we find it does not work. Working under assumption that Riverbed will work. | Mitigation | Run unoptimized if they don't work; we are contractually bound to remove the Riverbed devices if they are found to cause a problem. | 1. In discussions with Riverbed, trying to find reference clients who have used it with O365. 2. Test Riverbed with Exchange. | 5-Mar: got positive references from vendors using Riverbed; close. 8-Feb: added due date 1.5 mos, review date = 1 mo. This item is hugely critical; Al said we are months away from understanding how to address it. Action opened for Al to make Alan explicitly aware of this risk. 25-Jan: Brett raised this item. We need to know from Msft whether riverbed will work. The alternative (plan b) is to buy more network; not a real plan b. We will raise this as a risk in the management pack. | 2012-03-07 | Program Director | Received positive feedback/references from Msft clients using Riverbed with O365. Close. | 2012-03-21 | 2012-03-05 |  | 57 | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | -1 | FALSE | TRUE
R93 | 2012-01-25 | Steve Jelf | 05. Risk Closed | Additional infrastructure / additional costs / resource requirements | The assumed Q&RM recommendation is to enable external chat history from the servers. If this is validated, there will be implications to the design and the functional spec for Lync. The design would need to incorporate in-country infrastructure which doesn't currently exist and the program would need to plan accordingly. If "archiving of external chats" needs to be enabled from back end servers and this is a formal requirement from Q&RM specifically relating to countries where data cannot reside outside of country borders, further infrastruture will be required in those countries. | Significant scope / budget / resourcing would be required assuming some level of email archiving would be required for "day 1" | Technology Foundation |  | Steve Jelf | Adrian Mickleson / Al Grljevic / Steve Jelf | High | 02. Impact > 4 Weeks < 3 Months | 02. Doubtful | 03. High | 00. Undecided | 00. Undecided | 00. Undecided | TBD | Undecided | TBD | Investigate further as to what this actually is. | 6-Mar Steve: Q&RM have now confirmed that this request / requirement no longer exists. No saving of external chats are required. 29th Feb :- Q&RM Chair reaching out to key participants of the Legal Exec Committee to recommend that this requirement is no longer worth pursuing given the impact. Awaiting feedback. 20th Feb ; - Risk Probability downgraded to Doubtful based on further conversations. 15th Feb: Q&RM briefed. Risk reduced - however further work required in providing a view on costs / effort and impact. 8-Feb: Need to ensure that Q&RM understand this risk. Action opened for Steve to go to Q&RM to ensure they are aware of this, then Al, Adrian and Steve will take it to the engineering team to discuss costs. Review next week. 8-Feb: there are still a lot of questions around this item as the team is still unsure whether this is needed. Currently seeking more info. 1st Feb: Meeting to be arranged by Claire Love (Susan Chakerian's PA) Not yet set up. 25-Jan: Steve opened on call. It has been proposed that "archiving of external chats" needs to be enabled from back end servers. However if this is a format requirement from Q&RM specifically relating to countries where data cannot reside outside of country borders, further infrastructure will be required in those countries. It is believed that this has not been factored into solutions design or budget at this point | 2012-03-08 | Program Director | Steve Jelf: Q&RM confirmed that this request / requirement no longer exists. No saving of external chats are required. |  | 2012-03-06 |  | 57 | FALSE | FALSE | TRUE | FALSE | FALSE | TRUE | -40990 | FALSE | TRUE
R10 | 2011-04-06 |  | 05. Risk Closed |  | The German firm have a mail archive solution where we keep full copies of a users Notes mail file (up to 10 years of data) on a small set of Domino servers attached to lots of storage (45TB and growing). This in essence is a home grown mail archiving solution for Germany. There is a looming end of support date for the storage system that will hit us end of March 2012 ish. |  | Unified Communications |  | Nick Wood | Nick Wood |  |  | 03. Possible | 03. High |  |  |  |  | Mitigation | Investigate alternative archving solution for Germany | Determine what the archiving solutions should be by the end of the envisioning phase of Exchange. | 27/04 - Combine with R3; close. |  |  | Determine: 1)What is the true legal / QRM requirement to keep mail for Germany ? 2)What the long term archiving solution will be and do we plan to suck in the Notes mail ? 3)When the solution is likely to be available so that if necessary alternative plans can be made. |  | 2011-04-27 | R3 | 351 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R121 | 2012-03-05 | Michelle Edmonds | 02. Open & Assigned | GAAIT POC activity is underway prior to Requirements elaboration. | External and internal experience for GAAIT is not defined | User Experience on Assurance Technical Solution is not acceptable | SharePoint |  | Michael Cliffel | Ritesh Verma | Moderate | 03. Impact > 3 Months | 03. Possible | 03. High | 03. High | 03. High | 03. High | Business does not accept user experience. | Undecided |  |  | 19 March - working with Assurance to document the governance 14-Mar: update on daily call is that Howard is looking into this. 7 Feb: Added and updated Risk. | 2012-04-01 | Program Manager |  | 2012-03-30 |  |  | 17 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 8 | FALSE | TRUE
R132 | 2012-03-15 | Binoy Raj | 02. Open & Assigned | Inability to arrange a second client interview - with frog, for conducting user research | The frog team has been able to have just one session with an E&Y client - to perfrom their research into the E&Y Extranet. The business has not been able to provide a timely response - towards identifying atleast one more client. Alan Guthrie's efforts to arrange Microsoft as the 2nd client has also failed | Insufficient data for conduting research on the UX for Extranet - impacting the quality of the deliverable from frog | SharePoint | SP - User Experience | Michelle Edmonds | Eric Wahl / Kevin Smyth | Moderate | 01. Impact < 4 weeks | 04. Probable | 01. Low | 03. High | 02. Medium | 01. Low | Frog closing the discover phase without sufficient interactions with E&Y's clients | Mitigation |  | Eric and kevin to explore if any alternate plans are possible | 19-Mar: Risk identified |  | Program Director |  |  |  |  | 7 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | -40990 | FALSE | TRUE
R100 | 2012-02-03 | Tim Brinkman | 03. Action/Mitigation Plan Defined | Decision to deploy Lync and Outlook packages dormantly without testing of activation process | The "Activated" Lync & Outlook clients remain untested pending a decision upon the mode of activation & the delivery of a backend infrastructure environment. Entry into a "Technical Pilot" with untested "activated" Lync & Outlook Clients presents a risk. | The Dormant Lync Client has been deployed to 150K users and the Dormant Outlook Client will be similarly deployed over the next few months. Without a tested/validated "Activation Strategy" the impacts of activating these clients is unknown. Activation impacts to "On Prem" users are unassessed. There will be an impact on the deployment timeline if we cannot get authorisation to deploy untested packages | Technology Foundation |  | Al Grljevic | James Harrup-Brook (Lync) / Paul Neave (Exchange) | High | 02. Impact > 4 Weeks < 3 Months | 04. Probable | 03. High | 03. High | 03. High | 03. High | Activation of dormant Lync client results in unforeseen adverse impacts to users | Mitigation | NA | Introduce environment that will allow us to do testing. Strategy workshops are required to decide the mode of activation of the Dormant Outlook & Lync clients. Testing the "Activation" Approach would follow production of "Activated Client Functional Specification" Documents for nboth the Outlook & Lync clients. Will GCL5 be inscope for the client activation - if so it will also need to be tested for the dormant clients & deployed across the entire user base. | 6-Mar: Added mitigation strategy: to introduce environment that will allow us to test. Changed review and date date from 28-Feb to mid and late April. (when environ. will be ready) 16-Feb: Daren said this is really assigned to James and Paul. Owner has to be from our call (Al/Adrian). Waiting for contingency plan from James and Paul. 15-Feb: Laura em'd Daren for update, per Al's suggestion. 8-Feb: Declared Daren as the owner and assignee and invited him onto the call. Seek update from him next week when he joins. | 2012-04-25 | Program Manager | 2012-05-05 | 2012-05-05 |  |  | 48 | TRUE | FALSE | TRUE | FALSE | FALSE | TRUE | 44 | FALSE | TRUE
R12 | 2011-04-22 | unknown | 07. Risk has become an Issue |  | The requirement to save content on a regular basis for GAAIT content (Q&RM) could require significant storage. Need to determine most efficient means to provide this functionality. |  | Technology Foundation |  | Adrian Mickleson | Adrian Mickleson / Steve Jelf | Moderate |  | 04. Probable | 02. Medium |  |  |  |  | Mitigation | NA | Once platform is chosen, need to options to enable this functionality | 06-Mar: Due date added. Review date set out a month.The storage risk may go away with the GAAIT replacement solution. Sits with Adrian now; Steve Jelf will have to take through Q&RM gate, as well. 06/07 - no update. 11/05 - No update, but requirement is captured in the Archiving RFP. 27/04 - No update at this time. | 2012-04-11 |  | This risk has been superceded by I110. Close as a risk. | 2012-04-18 | 2012-03-19 | I110 | 335 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | 27 | FALSE | TRUE
R101 | 2012-02-03 | Tim Brinkman | 03. Action/Mitigation Plan Defined | Decision to deploy Lync and Outlook packages dormantly without testing on GCL5 environment | GCL5 availability for dormant/activated Lync/Outlook Client testing. The dormant Lync/Outlook Client testing will need to be revisited & run against GCL5 in addition to the Activated Client testing if it has been confirmed that GCL5 will be the Go-Live Loadset. Even if the Program goes live with GCL4 the requirement to test against GCL5 remains, pending its introduction. | GCL5 compatibility with both the cloud & On Prem Lync and Outlook/Exchange infrastructure is untested & unvalidated. Retesting GCL5 after Lync & Outlook Go-Live could present significant cost & delay to the deployment of GCL5 and may have engineering impacts on the Lync & Outlook/Exchange infrastructure. Impact on Program Scope & compatibility with new Global Core Loadset | Technology Foundation |  | Al Grljevic | Kenny Phipps (Lead PM for GCL5) | Moderate | 03. Impact > 3 Months | 04. Probable | 03. High | 03. High | 03. High | 03. High | Deployment of dormant Lync/Outlook client on GCL5 environment results in unforeseen adverse impacts to users | Mitigation | NA | Upon completion of GCL5 development & testing, start a test project to test the Lync & Outlook Dormant and Activated Client Packages against GCL5 | 15/03/12: NW: Discussed with Al and agreed testing responsibility will sit with the project deploying into Prod second, i.e. if Lync/Outlook deploy first, then responsibility for retrospectively testing on GCL5.0 will sit with GCL5.0 project. This only needs to be re-visited for planning purposes once deployment plans and dates are confirmed for both M&C and GCL5.0. Hence review date 1 July. 6-Mar: changed next review date and due date to mid and late april, since the environ wont be ready until that time. 29/Feb :testing against GCLS5. 16-Feb: Daren suggested Kenny Phipps provide the contingency plan, as the responsibility to test this with the GCL5 Loadset is theirs. For this they were provided access to the package at the back-end of last year so this task could be completed. 15-Feb: Laura em'd Daren for update, per Al's suggestion. 8-Feb: This is about getting the dormant package activated and then deployed and activated on the right core loadset. Will need to test the package with GCL4 and 5. It had been the assumption that when user gets GCL5, are already migrated to Lync and Outlook, but now that the timelines have changed, unsure. This may need to be deferred until the GCL5 environment is ready for testing. Will need to test activation and that it works against the backend infrastructure. Action opened for Daren to sync up with GCL5 and make sure what they are building today is what we expect. Provide update for this team next week. | 2012-07-01 | Program Director |  | 2012-04-25 |  |  | 48 | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | 34 | FALSE | TRUE
R35 | 2011-06-14 |  | 05. Risk Closed |  | MS have not confirmed the limitations of functionality i.e. coexistance that migrating to a hybrid estate will present |  | Unified Communications |  | Mark Reade |  |  |  | 03. Possible | 02. Medium |  |  |  |  | Mitigation |  | Envisioning workshops are scheduled to discuss - however these will be after the event of contract | 05/10 - Mark closed. 04/10 - R Bouji: Discussions with Binary Tree on 21/09 discussed some of the co-existence risks/challenges/ and functionality that can be offered by Binary Tree to address these. Additional discussions on co-existence to be held in Design & Planning workshops with Microsoft and Binary Tree w/c 10/10. High level plan for addressing co-existence issues to be in place by end Oct 15/06 - Risk added by Mark, to be discussed during the envision sessions. | 2011-09-28 |  |  |  | 2011-10-05 |  | 282 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R40 | 2011-07-27 |  | 05. Risk Closed |  | Risk opened by MS - SameTime and Group discussion around migration (buddy list). |  | Unified Communications |  | Rita Seibel / Adrian Mickleson |  |  |  | 03. Possible | 03. High |  |  |  |  | Mitigation |  | EY to raise risk up to Mgr Sponsors to get resolution. | 10/08 - Decision made and moving forward. Close risk. 27/07 - Raise risk to Mgr Sponsors for resolution. | 2011-08-10 |  |  |  | 2011-08-10 |  | 239 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R41 | 2011-07-27 |  | 05. Risk Closed |  | Risk opened by MS - Lack of Business Stakeholder presense in envisioning sessions (Messaging and Lync). |  | Unified Communications |  | Rita Seibel / Adrian Mickleson |  |  |  | 03. Possible | 02. Medium |  |  |  |  | Mitigation |  |  | 10/08 - Acknowledge risk and working to address lack of business presence. 27/07 - new risk opened by MS. | 2011-10-05 |  |  |  | 2011-08-10 |  | 239 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R46 | 2011-08-10 |  | 05. Risk Closed |  | Need decision on Service Pack versions for Exchange and Lync during Planning after Envisioning. This affects the date that the AD has to be ready for the pre-production environment and it is noted that current SLA for delivery of AD changes is 4-6 weeks. |  | Unified Communications |  | Daren Wicks |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation |  | 17/08 - Assumption of Service Pack 1 unless told otherwise. 10/08 - Anthony to finalise with MSFT - John Bruce. Also work to reduce the 4-6 week delivery SLA where possible | 31/08 - Got response from John Bruce. Service Pack 2 not due out until later in the year for Exchange so may need to stay with Service Pack 1 for now and go to 2 later. (For Lync there really isn't a Service Pack, just updates.) 24/08 - No update; Anthony going to touch base with John Bruce for confirmation. Follow-up next week. 10/08 - New risk opened. Request out to Microsoft for most recent service packs / versions. If not received, then build with current version. | 2011-08-31 |  |  |  | 2011-08-31 |  | 225 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R6 | 2011-03-17 |  | 05. Risk Closed |  | Integration of Good using Exchange Web Services protocol for mobile messaging for BPOS is currently not available. Good have indicated that this is on their road map, however cannot commit to a time scale. May have impact on migration groupings/release management. |  | Unified Communications |  | Juan Torres |  |  |  | 04. Probable | 03. High |  |  |  |  | Mitigation | Alternative options for the integration of mobile messaging will need to be investigated | Monitor time scale for the implementation of Good integration for BPOS | 27/07 - close since issue 18 was opened. 06/07 - opened new issue since BPOS is off the table. 29/06 - Now transfered to Issue #18 22/06 - Good to send committment by the 23rd. Plan B was shared with Peter. 08/06 - Email was sent to Good requesting written committment - no response. Adrian will follow-up with Good. 50/50 level of confidence. Adrian will share plan B draft with Peter. 01/06 - Meeting held with Good and received a verbal committment to support integration. Identified right people at Good to provide committment in writing. Plan B is to go with another product. Adrain to create mitigation plan. 25/05 - Meeting scheduled for tomorrow. 18/05 - Good meeting pushed to next week. Juan and Peter to look into a Plan B if Good does not work out. 11/05 - Not spending time here until decide on BPOS. Meeting on Good next week; Juan will provide update then. 27/04 - Determined may have impact on migration groupings/release managemnent. | 2011-07-27 |  | Monitor Good timelines. Commence investigation of alternative approaches. |  | 2011-07-27 |  | 371 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R76 | 2011-11-07 | Rewa Bouji | 05. Risk Closed | Lack of clearly defined expectations between the program and the business sponsors | It is not yet known whether the business wishes UAT to be conducted by the business itself, and whether it is prepared to commit business resources to the execution of UAT, or whether the business will "in-source" UAT to the QA team and allow the program to execute UAT on behalf of users. If the business wishes to execute UAT itself, we must begin the process of identifying the resource effort required by the business and presenting this to them for approval so that business resource for UAT can begin to be identified and preparations can be made | If the business wishes to conduct UAT themselves, there will be a need for program resource to facilitiate the identification of UAT participants and the provision of training, support, materials etc. Alternatively if the business wishes the program to conduct UAT on its behalf, additional test resources must be planned for, approved, and recruited appropriately, with commensurate impact on timelines and budget | Unified Communications |  | Rewa Bouji | Martin Kremmer | High | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 03. High | 02. Medium | 02. Medium | 02. Medium | Lack of decision from FSG on UAT participation by end of January | Mitigation | Use program QA resources to execute UAT based on scripts signed off by Business Deployment and Business Change | Decision on UAT approach will be sought from the FSG | 06/03/12: RB: Jeremy Brown confirmed decision in standup meeting with AG. Risk closed 29 feb: still no clarity, going into FSG. 27/02/12: RB: No update 22/02/12: RB: No update. Action with Guy and Alan 14/02/12: RB: Lack of clarity on decision-making forum for UC hampering confirmation of this decision. Awaiting feedback from Guy and Al on approach to creating UC sponsor group 8-Feb: Martin said yes that business users will participate; Rewa just waiting for sponsorship approval. Review next week. 25/01/12 - M Kremmer stated he expects business users to conduct UAT, managed by the Program - awaiting confirmation that this has been validated by BR/FSG 18/01/12 - Investigating with MK whether this decision can be made by the Business Sponsor instead of the FSG to try and speed up decision making process 11/01/12 - Was scheduled for decision at next FSG meeting, to be presented by AM, however meeting shortened and cut from the agenda. QA need to know by end of Jan to start ramping up resources and planning. Await update on next FSG meeting and agenda 14/12- On agenda to go to FSG meeting for decision in January. Gearing towards TF. 30/11 - On next FSG agenda (this past one was cancelled); review 14/ 23/11 - Adrian said this is on the agenda for next Tues; review next wk. 08/11: R Bouji raised this to A Mickleson for escalation to the FSG. Adrian Mickleson to seek decision from the FSG on 15 November during the F2F sessions. Next steps to follow decision | 2012-02-29 | Managing Sponsor |  | 2012-01-30 |  |  | 136 | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | -52 | FALSE | TRUE
R123 | 2012-03-13 | Steve Jelf | 05. Risk Closed | Draft revised Baseline plans not in place by requested date of 19th March for Tech Foundation | Unlikely that TF or UC will have any further updates for Lync or Exchange until the end of the month (March), missing the deadline for re-drafts to be completed by the 19th March | Delay in revising baselining plans | Technology Foundation | TF - Lync | Steve Jelf | Steve Jelf | High | 01. Impact < 4 weeks | 04. Probable | 00. Undecided | 00. Undecided | 00. Undecided | 00. Undecided |  | Undecided |  | Raise as part of 30 day get to green - potentially revise draft date ? | 17TH March - Risk accepted. therefore this is being closed. Low confidence levels known and accepted. 15-Mar Steve: The update on this is that for the TF Lync program, there will be a low confidence level in the current dates until 18th May when a detailed plan can be finalised and committed to from the eventually chosen vendor. 13/3 - Escalate to A Guthrie as part of daily checkpoint meeting | 2012-04-18 | Managing Sponsor | Risk accepted. therefore this is being closed. Low confidence levels known and accepted. | 2012-05-18 | 2012-03-17 |  | 9 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | 57 | FALSE | TRUE
R90 | 2012-01-11 | Al Grljevic | 02. Open & Assigned | Need for headsets | Procurement of headsets for 150,000 users globally | The success of the program may not be fulfilled due to lack of hardware availability. | Technology Foundation | TF - Lync | Al Grljevic | Jean-Michel Bouhier | Minor | 01. Impact < 4 weeks | 01. Slight | 00. Undecided | 00. Undecided | 00. Undecided | 00. Undecided |  |  |  |  | 13-Mar Jean-Michel: So far I have not identified any risks, but as it is quiet complicated to get this kind of agreement (confirmation that supplier can meet our demand) I will not say that they will meet our demand. But they should be able make it. Keep as Minor, due with global agreement beg of May. 12-Mar: Rewa confirmed with Raymond the process - countries pay for headsets when get them, then charge back to program. 12-Mar, Jean-Michel: As the headsets will not be procured globally, and as we don't know how many headsets will be really procured as some countries may decide to use those they already have even if they are not optimal for Lync, it was not planned to have such a date anymore. Nevertheless, we target to have a Global agreement with Jabra and Plantronics using Dell and Lenovo as resellers end of April beginning of May. 9-Mar: following up with Jean-Michel for a confirmaiton on dates that headsets can be delivered globally; in daily standup there is an action for Rewa to determine who will pay for the headsets. 11-Jan: Opened on call. Al concerned about the ability to procure 150,000 headsets globally. Jean-Michel said at a high level, they have received the ok on 150,000 headsets for May 1 and the same from Plantronics (sp?). Added to log as a low priority item. | 2012-04-25 | Project Manager |  | 2012-05-04 |  |  | 71 | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | 43 | FALSE | FALSE
R128 | 2012-03-19 | Mark Reade / Carlos Vasquez | 01. Open | SharePoint PM resource allocation | Assigned O365 PM is managing other projects and may not have sufficient time to enable the successful and timely delivery of the project |  | Technology Foundation |  | Al Grljevic | [9 empty] | Undecided |  | Assign a Single fulltime dedicated resource to take over responsibility as Office 365 PM and use current SharePoint PM as a resource to the workstream Or, assign additional resource to assist SharePoint PM | 19-Mar: a decision is required whether EY should accept these risks and the consequence of potentially delaying O365 | [6 empty] | 3 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | -40990 | FALSE | FALSE
R129 | 2012-03-19 | Mark Reade / Carlos Vasquez | 01. Open | Messaging PM resource allocation | Assigned O365 PM is managing other projects and may not have sufficient time to enable the successful and timely delivery of the project |  | Technology Foundation |  | Al Grljevic | [9 empty] | Undecided |  | Assign a Single fulltime dedicated resource to take over responsibility as Office 365 PM and use current Messaging PM as a resource to the workstream Or, assign additional resource to assist SharePoint PM | 19-Mar: a decision is required whether EY should accept these risks and the consequence of potentially delaying O365 19-Mar: E&Y PM team is working in identifying leads in the Network, Messaging, SharePoint, Active Directory, and Support. Other leads will be needed after Plan phase | [6 empty] | 3 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | -40990 | FALSE | FALSE
R130 | 2012-03-19 | Mark Reade / Carlos Vasquez | 01. Open | Technical Leads | Technical Leads have not been formally assigned | Technical leads will be the SME on Office 365 Service Description and will coordinate the work as well as report back to the PM on activity status. | Technology Foundation |  | Al Grljevic | [9 empty] | Undecided |  | Need management involvement to ensure that a top/down assignment is issued. | 19-Mar: a decision is required whether EY should accept these risks and the consequence of potentially delaying O365 19-Mar: Various meeting are occurring without the involvement of the E&Y PM group. This uncoordinated meetings may have a negative impact on the ability of the E&Y PM team to effectively manage all Office 365 workstreams. | [6 empty] | 3 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | -40990 | FALSE | FALSE
R131 | 2012-03-19 | Mark Reade / Carlos Vasquez | 01. Open | Communications Protocol | E&Y PM’s not included in various meeting discussing Office 365 activities | E&Y PMs must be empowered to coordinate all efforts and implement mechanisms to feed information back to the management team. | Technology Foundation |  | Al Grljevic | [9 empty] | Undecided |  | May need E&Y management involvement | 19-Mar: a decision is required whether EY should accept these risks and the consequence of potentially delaying O365 | [6 empty] | 3 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | -40990 | FALSE | FALSE
R102B | 2012-02-10 | Tim Brinkman | 02. Open & Assigned | Lack of clarity around specification and delivery schedule for environments to support UAT | Environment constraints for Cloud and On-prem may delay UAT | Test environment contention is likely to result if UAT environment provision is delayed, particularly for testing of plug-ins with the new Outlook client, as well as Lync UAT. It is also unclear how cloud services will be simulated in the UAT environment. | Unified Communications |  | Tim Brinkman | Al Grljevic | Moderate | 03. Impact > 3 Months | 04. Probable | 03. High | 03. High | 04. Critical | 03. High | Lack of costings to ascertain if three integrated test environments can be built within the Test Environment budget | Mitigation | Schedule Test Environment utilisation with enforced adherence to schedule | Obtain costings on building three integrated test environments as opposed to two & examinae budgetary impact | 13/03/12: RB: Risk re-worded to distinguish between UAT and performance testing risk, which belongs to TF. Nicole Watson to raise new risk to address performance testing. 06/03/12: RB: Risk downgraded to moderate as UAT environment provision now kicked off by TF 27/02: RB chased TF for update, no response 22/02: RB has not seen the deck yet (as mentioned by Al last week). Tim out for 2 wks. Still open, no progress. 15/02: Al said they have a deck ready that they have put together with QA and others, waiting on cost info and will then present to Guy, Alan and Siggi. Review next week. LM em'd Tim for due date. | 2012-02-29 | Program Director |  | 2012-03-31 |  |  | 41 | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | 9 | FALSE | TRUE
R105 | 2012-02-27 | Rewa Bouji | 02. Open & Assigned | Assumptions pre-dating the O365 decision about migration strategy are challenged as a result of O365 and the parallel running of the DCC program | It is not known whether O365 and On-prem migrations will run concurrently, whether O365 users will be migrated first and On-prem second, or vice versa. A negotiation between DCC, TF Exchange, UC and Business deployment is required to agree the order of migration so that the infrastructure provision aligns to the deployment strategy. | As long as the deployment strategy is missing, assumptions will have to be made about the order of provision for hardware. For on-prem countries this raises the risk that hardware provision is prioritised for countries who do not wish to migrate in earlier phases, or that hardware is not available early enough for countries who want to be part of the earlier migration waves | Unified Communications |  | Rewa Bouji | Martin Kremmer (Deployment strategy), Paul Neave (TF Exchange) | High | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 02. Medium | 03. High | 02. Medium | 00. Undecided | Unknown | Mitigation | Unknown | Work with MSFT to determine approach to migration and work with Business Deployment, Change Management, Transition Management and Operations to develop Impact assessment and revalidation approach for current migration assumptions | 09/03/12: RB: Meeting scheduled for 21/03/12 to agree migration strategy and velocity, and determine how these will be agreed with Microsoft, Ops, and Business 27/02/12: RB: Risk added to distinguish between two distinct topics: challenged assumptions around migration velocity (R97) and challenged assumptions around migration strategy R105 | 2012-03-14 |  |  | 2012-03-31 |  |  | 24 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 9 | FALSE | TRUE
R111 | 2012-03-05 | Rewa Bouji | 02. Open & Assigned | Assumptions about migration velocity pre-dating the decision to consider a cloud solution for Lync are challenged for a variety of reasons (see right). Based on this, the overall migration timeline, based on ~40,000 users per weekend, over 4 weekends, is no longer valid | Current Transition and Business Deployment planning assumptions for the Lync migration schedule are challenged by: - Lync cloud vendor not yet selected, therefore unable to provide any migration guidelines or indications of possible constraints to current plan/assumptions - absence of a deployment schedule or validation of weekend-only migrations assumed to date - operations have already challenged the migration of tens of thousands of users over a single weekend as being unsupportable by the current helpdesk capability - Questions around network bandwidth are unresolved with respect to the number of users that can be migrated. | We are unable to estimate when deployment will be complete for all users, how many users will be migrated in each wave, nor what support volumes the Operations team will need to support during migration and over what timescale | Unified Communications |  | Rewa Bouji | Martin Kremmer (Deployment schedule andstrategy), James Harrup-Brooke/John Murray (bandwidth), Mike Laci (Operational support model) | High | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 02. Medium | 03. High | 02. Medium | 00. Undecided | Unknown | Mitigation | Unknown | Work with TF Lync team to determine approach to migration and work with Business Deployment, Change Management, Transition Management and Operations to develop Impact assessment and revalidation approach for current migration assumptions | 05/03/12: RB: Further discussion needed with TF Lync team, Business Deployment, and Transition Management, on how to resolve this. Will be difficult to validate planning assumptions until Lync vendor is known and available to engage in detailed migration planning discussions | 2012-02-29 | Project Manager |  | 2012-03-31 |  |  | 17 | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | 9 | FALSE | TRUE
R112 | 2012-03-05 | Rewa Bouji | 02. Open & Assigned | O365 decision has raised new challenges to the migration that are still now being discovered and which relate to our legacy provisioning of user accounts | There is a risk that multiple accounts will be created for users in the new Exchange environment as a result of multiple legacy accounts being migrated to the AD. This creates a risk of errors in the migration of mailfile data to the incorrect account in the O365 Exchange environment which will impact end users during the migration | End users (estimated to be around 5,000 at this time) will experience issues logging onto their mail files and may raise help desk queries to try and resolve these | Unified Communications |  | Rewa Bouji | Neil Langston | Moderate | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 02. Medium | 03. High | 02. Medium | 00. Undecided | Unknown | Mitigation | Unknown | Working with the Migration Lead, IAM program team and Microsoft to determine approach to resolution | 05/03/12: RB: Risk logged | 2012-03-07 |  |  | 2012-03-31 |  |  | 17 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 9 | FALSE | TRUE
R78B | 2011-11-08 | Rewa Bouji | 02. Open & Assigned | Lack of communicated schedule for DCC delivery | It is not yet confirmed in which order the DCC program will stand up the MS Exchange infrastructure, or the schedule for doing so. The Unified Comms stream cannot roll out to users unless the infrastructure is provisioned and ready for deployment, and the deployment schedule is therefore dependent on DCC confirming infrastructure availability. | Without a planned schedule for when each GDC and each in-country DC will be ready, the UC stream cannot begin to plan its deployment schedule. This is impeding our ability to confirm to the Transition and Operations intake teams the timeline for deployment that they will need to support | Unified Communications |  | Rewa Bouji | Adrian Mickleson | Minor | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 01. Low | 01. Low | 02. Medium | 01. Low | Requirement to provide the business with a schedule for Lync & Outlook deployment | Mitigation | Develop a list of countries that will need in-country server deployments based on what is currently known (latest list provided by Brett van Gelder) and use as draft for deployment schedule | Push for publication of schedule by DCC team | 09/03/12: RB: Meeting scheduled for 21/03/12 to agree migration strategy and velocity, and determine how these will be agreed with Microsoft, Ops, and Business 06/03/12: RB: PN has provided a draft schedule to UC and this has been shared with Business Deployment. UC/BD will use this as the basis of the deployment plan pending further updates from DCC. As a result, risk downgraded to Minor 27/02/12: RB: Latest TF plan suggests country schedule ready end of March 08-Feb: removed "Lync" from the desc; this is only for Exchange. John/Alan are aware of the timelines and implications. Review in 1 mo. 25/01/12 - Paul Neave meeting with DCC team on 30th for update. 18/01/12: Final deployment list still under discussion. Awaiting update 11/01/12: Rewa: Paul Neave sent an update earlier this week on his discussion with DCC Program. Still waiting on in-country builds. DCC team will have a dedicated PM coming on to assist with in-country buildouts, which will mitigate that portion of the risk. The open question is around what to do with the countries we don't have requirements for? Review 2 weeks. 11/01: (RB) Paul Neave (TF) has now provided updated list of where in-country builds likely, and "Waves" for DCC delivery. This has been shared with Business Deployment Lead, and can be used as the basis for deployment planning. Still awaiting decision on "market driver" country builds however, so keeping risk open 04-Jan: Leave open until next week; Michelle seeking confirmation that this can be closed. 14/12 - Will change after decision of whether to go BPOS. 30/11 - Added Adrian as the owner (instead of MIke O'Donnell). This is being managed as a dependency also; will have significant impact, most sits around RFP decision. Paul Neave working on impact assessment to determine cost of in-country builds. Review next week. 11/11 - R Bouji - P Neave confirmed that the DCC program is expecting to provide the final list of countries for deployment and a potential deployment schedule by end of the year. PN to provide update to RB when known | 2012-03-21 | Program Director |  | 2012-04-30 |  |  | 135 | TRUE | FALSE | FALSE | TRUE | FALSE | FALSE | 39 | FALSE | FALSE
R96 | 2012-02-21 | Rewa Bouji | 02. Open & Assigned | Lack of clarity on coexistence challenges as a result of O365 | It is not yet confirmed how three-way look up will work across O365, Exchange On-Premise and Lotus Notes. | If three-way look up is not possible, there will be significant end user impacts that will need to be communicated and managed | Unified Communications |  | Rewa Bouji | Paul Neave | Minor | 03. Impact > 3 Months | 03. Possible | 03. High | 03. High | 03. High | 00. Undecided | Unknown | Mitigation | Unknown | Work with MSFT to determine approach to three-way look up | 15/03/12: RB: CR026 with CCB for approval. Risk downgraded to minor but not to be closed until design is delivered. 12/03/12: RB: CR has been raised by TF Exchange to Microsoft to produce the design for 3-way coexistence. This has not been done before by Microsoft 27/02/12: RB: Update received from PN: "The change request to introduce the work to define the 3-way coexistence into the exchange On-Prem SOW, is still being drafted by Microsoft. We expect it to be delivered to us this week. We do know BinaryTree have a established POC of the threeway in their lab." 22-Feb: Paul and TF in conversations with Msft. Awaiting response from Msft. 21/02/12: RB: Added as output from Assumptions log. Assumption cannot be revalidated (A72) | 2012-04-30 | Project Manager |  | 2012-04-30 |  | input: A72 | 30 | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | 39 | FALSE | FALSE
R97 | 2012-02-21 | Rewa Bouji | 02. Open & Assigned | Assumptions pre-dating the O365 decision about migration velocity are challenged for a variety of reasons (see right). Based on this, the overall migration timeline, based on 10,000 users per weekend, over broadly 17 weekends (excluding "firebreaks"), is no longer valid | Current Transition and Business Deployment planning assumptions for the Outlook migration schedule are challenged by: - absence of a deployment schedule - we cannot yet revalidate assumptions held to date about weekend-only migrations in order to provide MS with a deployment schedule to determine how many users can be migrated, and against what schedule (weekday, weekend, or both) - MS migration "ramp" does not align with previous UC/TF assumptions of 10k users per weekend - MS's past experience of other migrations point to constraints posed by support capacity on migration volumes, and it is as yet unclear what EY's ability to handle migration volumes would be - MS has highlighted that none of their customers has ever attempted to undertake weekend-only migrations and has provided many reasons for this which challenge our initial weekend-only migration assumptions - Questions around network bandwidth are unresolved with respect to one-off initial download of new mailboxes by newly provisioned users, and are also likely to limit the number of users that can be migrated. | We are unable to estimate when deployment will be complete for all users, how many users will be migrated in each wave, nor what support volumes the Operations team will need to support during migration and over what timescale | Unified Communications |  | Rewa Bouji | Martin Kremmer (Deployment schedule andstrategy), Paul Neave/John Murray (bandwidth), Mike Laci (Operational support model) | High | 02. Impact > 4 Weeks < 3 Months | 03. Possible | 02. Medium | 03. High | 02. Medium | 00. Undecided | Unknown | Mitigation | Unknown | Work with MSFT to determine approach to migration and work with Business Deployment, Change Management, Transition Management and Operations to develop Impact assessment and revalidation approach for current migration assumptions | 09/03/12: RB: Meeting scheduled for 21/03/12 to agree migration strategy and velocity, and determine how these will be agreed with Microsoft, Ops, and Business 27/02/12: RB: Wording amended. Further discussion needed with Business Deployment, Transition Management, TF and MSFT to agree how to resolve these 22-Feb: Brett clarified: Msft does offer weekend migrations; the open question is that they have never had a client do only weekend migrations. EY had an assumption of weekend migrations in large part because we assumed we could do roll backs, which Msft has now told us with O365 they don't do rollbacks. EY needs to rethink assumptions on migration, thinking through the reasoning, Msft experience, etc. Rewa took an action to update the syntax of this item to reflect Brett's comments above. 21/02/12: RB: Added as output from Assumptions log. Assumption cannot be revalidated | 2012-02-29 | Project Manager |  | 2012-03-31 |  | input: A75 | 30 | TRUE | FALSE | TRUE | FALSE | FALSE | TRUE | 9 | FALSE | TRUE
R133 | [28 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R134 | [28 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R135 | [28 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R136 | [28 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R137 | [28 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
R138 | [28 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[29 empty] | 40990 | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
[31 empty] | TRUE | FALSE
[31 empty] | TRUE | FALSE
[31 empty] | TRUE | FALSE
[31 empty] | TRUE | FALSE

## Issues Log
# | Date captured | Identified by | Status | Input Reference # | Issue Description | Impact: Scope | Impact: Quality | Impact: Schedule | Impact: Cost | Priority | Issue Owner | Assigned to | Program / Workstream | Project / Workstream | Planned Resolution | Next Review Date | Required Resolution Date | Update Log | Escalation level | Actual Resolution | Actual Resolution date | Output Reference | Past Due |  | 2012-03-22 | Critical or High | Days Open | 30-90 days | 91-180 days | 181+ days | Days until Due | Due in the next week | Critical, High, Moderate
I1 | 2011-03-29 | unknown | Closed | NA | The decision for the implementation of the required Archiving solution to integrate with Exchange. Currently the assumption is no archiving platform will be delivered by TF, however there are believed to be some countries that may have regulatory/legislative limitations which require archiving facilities to be deployed. The impact will be in terms of scheduling migrations. | 03. Medium | 03. Medium | 04. High | 03. Medium | 02. Minor | Adrian Mickleson | Adrian Mickleson | Technology Foundation |  | Gain agreement from the working governance group as to the approach needed for archiving. | 2012-02-15 | 2011-10-30 | 6-Mar: This is the same as R3, which was closed in honor of D80 (pending decision on email archiving). Closed here. 19/10 - Assign to Adrian, Tech Fdtn, priority = Low. 11/10 - R Bouji - Meeting with N Wood, B van Gelder, and J Schoemaker 7 Oct. D Mulligan currently completing discovery work, N Wood will validate and handover to R Bouji. R Bouji to arrange meeting with J Robert ans S Chakerian to discuss outcomes of analysis and determine next steps with Q&RM and the Global Messaging Policy Group which is being formed. 04/10 - R Bouji - Discovery/analysis of local archiving solutions currently in place underway within Engineering/Ops. Awaiting provision of list. R Bouji will then follow up with global and in-country owners to determine archiving requirements in Exchange/Outlook environment. May also be impacted by planning and design workshop outputs; due date remains end of October for the moment 28/09 - Met with J Schoemaker 26/09 to understand scope of impact assessment underway on archiving. Agreed that this is one of many areas where analysis and requirements gathering needs to be undertaken as part of the UC requirements scope, and not in a piecemeal fashion. Meeting to be held between UC & TF program teams, AE and Application Management 29/09 to agree next steps. Likely that design decisions out of the MSFT workshops weeks of 10-24 Oct may help provide structure for addressing this and a variety of other business requirements 22/09 - Remove "Online Services" from description as this applies to Exchange in general now. 21/09 - Per Mark, changed stream from TF > UC and ownership from Adrian/Mark > Rewa. Rewa provided this update: An impact assessment is currently being undertaken by the Application Management team to understand where these requirements might exist, and if so, what solution(s) will be required to meet them. This will also need to be fed into the design work with Microsoft. Update in two weeks. 14/09 - Have statement from Q&RM that there will be no requirement going forward for the archiving of e-mail. Nick and Brett reviewed initial discovery work on Monday and while they have further questions, it looks like there might be only 2-3 areas to discuss with Q&RM. Hoping to finalize discovery this week and work with Q&RM next week to arrive at final conclusions. Review in 2 weeks. 07/09 - Brett: We will not implement email archiving solution unless we discover something that makes us change mind. Brett concerned that we are not effectively managing this. Discovery will drive the next step; review next week. 10/08 - Received feedback from Q&RM - investigate if there is a direct impact for migrating email that may require archiving but it is not because of legal requirements. Don’t archive unless something tells us we have to - reduce risk to high and review in 4 weeks. 27/07 - Update will be provided next week. There is a legal requirement so communicating with Q&RM for additionall information. 06/07 - If there are additional archiving requirements a report needs to be sent back to QRM. RFP in process and being reviewed. 29/06 - Q&RM have revised requirement, confirm there is no requirement to journal emails to archive. Need to confirm whether deferal of an archiving solution will impact the firms' abilities to remain compliant in local geographies, subject to confirmation following further investigation (Base line investigation and report back to team). 15/06 - Draft of RFP in process, plan for RFP submittal in mid August. Environment up and piloted by end of year. EYD has reqs to be included in the RFP - Jeff Kocsis. 01/06 - 1 week behind in releasing draft of RFP. Internal meeting planned for Friday to review and complete. 25/05 - Have run 2 workshops with one more Friday to gather requirements for RFP. Adrian working with Mark Reade and representatives from all major groups. Vendor selection needs to happen in July at latest. Need to determine which individuals will make the vendor decision and drive down dates (July) really hard with them and the vendor. Work toward technical RFP. 18/05 - Did not hold follow-up from last week. Refinement of high level reqs 4 days behind. Concern expressed regarding origin of requirements not representing all groups (e.g., Enterprise Arch.). Adrian and Nick meeting tomorrow, will work to determine timebox; will circulate and get others involved thereafter. 11/05 - The SWOT - completed. High level pricing estimation - completed. High Level Requirements for Request for Information - completed. Short-list - Agreed. Now proceeding direct to RFP (no RFI required). Conversation regarding EA involvement and budgeting ensued. Action: Adrian, Martin, Brett and Peter to discuss off-line. 04/05 - 5 potential vendors, working through SWOT analysis; high level requirements underway; have made a conservative estimate of 6 mos for RFI, but once select a vendor will confirm a timline with them. Aiming for end of June to reduce the priority on this issue. 20/04 - It has been agreed to kick off investigation of the Archiving solution. KI to include in one of the work streams. Verify what the budget is and where that is covered. 19/04 - initial vendor analysis commenced 04/04 - Initial meeting with Bob Wasserman to commence vendor analysis Discuss with Klara what has been done to date on this issue and who is driving this discussion. |  | This is the same as R3, which was closed in honor of D80 (pending decision on email archiving). Closed here. | 2012-03-06 | D80 (R3) | TRUE | 1 |  | FALSE | 359 | FALSE | FALSE | TRUE | -144 | FALSE
I10 | 2011-04-22 |  | Closed |  | We need to decide the approach for archving for SharePoint. |  |  |  |  | 04. High |  | Adrian Mickleson | Technology Foundation |  |  | 2011-04-27 | 2011-04-27 | 27/04 - Part of requirements. Close. |  | Included in requirements. | 2011-04-27 |  | TRUE | 1 |  | TRUE | 335 | FALSE | FALSE | TRUE | -330 | FALSE
I140 | 2012-03-06 | Neil Sahdev | Active | Risk 102 | The IT SD teams are not reviewing the Rediscovery reports as they don't have the bandwidth or budget therefore delaying applications from being decommissioned or archived | 02. Low | 02. Low | 04. High | 04. High | 05. Critical | Neil Sahdev | Neil Sahdev | App and Data Migration |  | Agree priority of the review of the Rediscovery reports with the IT SD leads and CLT vs. other programs | 2012-03-23 | 2012-03-30 | 14/03 - Summary of effort required for FY12 distributed 14th Mar'12 - awaiting approval 06/03 - Issue raised given Risk 102 has been realised |  |  |  |  | FALSE | 0 |  | TRUE | 16 | FALSE | FALSE | FALSE | 8 | FALSE | TRUE
I101 | 2012-01-24 | Al Grljevic | Closed | NA | We will require additional PMs to manage the Lync project, Exchange on-premise solution and Exchange cloud solution. Impact: The programme won't secure the relevant resources in time to achieve successful delivery. |  |  |  |  | 04. High | Al Grljevic |  | Technology Foundation |  |  | 2012-01-25 |  | 15-Feb: This is a duplicate of Guy's issue, Issue 95. Team on call suggested close this item and keep the other open. 24-Jan: Laura added to log per Al. |  | Duplicate of I95; closed. | 2012-02-15 |  | FALSE | 0 |  | TRUE | 58 | TRUE | FALSE | FALSE | -40990 | FALSE | TRUE
I141 | 2012-03-06 | Neil Sahdev | Active | Risk 26 & Risk 67 | The A&DM Operating Model is yet to be agreed and communicated to all IT Service Delivery Leads - until agreed the following activities are being impacted : - The A&DM resourcing strategy cannot be baselined therefore impacting the initiation of the RFP for vendor(s) for portfolio teams who are due to start 1st Jul'12 - The Phase 1 project team are being challenged by some IT SD teams ref who should deliver the replatformed applications | 04. High | 02. Low | 04. High | 04. High | 05. Critical | Neil Sahdev | Neil Sahdev | App and Data Migration |  | CLT to agree A&DM Operating Model | 2012-03-23 | 2012-03-30 | 16/03 - As Margaret could not attend provisional slot Neil now arranging for w/c 19/03/12 12/03 - Neil to arrange meeting with Alan, Margaret, Chris and Bob to agree Operating Model 06/03 - Issue raised given Risks 26 & 67 have been realised |  |  |  |  | FALSE | 0 |  | TRUE | 16 | FALSE | FALSE | FALSE | 8 | FALSE | TRUE
I103 | 2012-01-25 | Neil Sahdev | Closed | NA | The date which Microsoft are expected to start work on the Phase 1 project was brought forward to 6th Feb'12 without an understanding of the impact. | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 05. Critical | Martin Stutchbury / Neil Sahdev | Nicola Cooper | App and Data Migration |  | Reprioritise work to accomodate the revised start-date. The consequence is that the Engagement pack for the first three applications for Phase 1 will not be complete). In addition there are a number of items that still need resolving in the SoW (i.e. who will provide the development environements, location of MS onshore resources.....) | 2012-02-15 | 2012-02-06 | 14-Feb: Decision made to stand-down MSFT development team until key inbound dependancy dates are known (i.e. design of sharepoint components). Issue can be closed. 8-Feb: Neil would like this item inc in mng pack. SOW needs to be ironed out. 25-Jan: Neil opened. Nicola is working with Microsoft to mitigate. Msft is struggling to start by 6-Feb, as well. Review in 2 weeks. | Program Director | 15-Feb: Decision made to stand-down Msft development team until key inbound dependency dates are known (i.e. design of SP components). This has been communicated, agreed. | 2012-02-15 |  | TRUE | 1 |  | TRUE | 57 | TRUE | FALSE | FALSE | -45 | FALSE | TRUE
I104 | 2012-01-25 | Neil Sahdev | Closed | R87 | The discovery team are largely staffed with IT advisory resources for a finite period of time. As the Rediscovery project is now expected to complete June 2012, there is a need to extend the resources of the team. If the resources can't be extended, we will lose them. We will have to identify and onboard new resources, therefore affecting the timelines. | 02. Low | 02. Low | 04. High | 04. High | 04. High | Neil Sahdev | Akos Rabi | App and Data Migration |  | Identify and onboard replacement resources | 2012-03-07 | 2012-01-27 | 06-Mar: Issue closed as restaffing of the Rediscovery team being managed as a BAU activity 29-Feb: Two candidates interviewed to join the Rediscovery team as permanent resources - Rediscovery PM to now decide whether to make an offer to them 22-Feb: Decision made to offboard remaining 2 ITA resources who were progressing with the data analysis (due to budget reasons) - as a result the Rediscovery team now only comprises of a PM (who joined 21/02/12 and 3 offshore technicians); review next week. 15-Feb: continuing to review CVs; review next week. 08-Feb: Search for backfil for data analysts continue 07-Feb: Backfil identified for PM role; search continues for backfil for data analysts 25-Jan: Opened as issue from R87. 25-Jan: 3 x ITA resources expected to leave end-Jan'12/early-Feb'12. 2 x resources (1 PM and 1 data analyst) required to backfill however no suitable candidates identified so far. As of 30-Jan, will not have a PM for Rediscovery; the stream will be running without a dedicated PM for 3 weeks. Someone is coming to help with the handover, and the team will absorb the workload. | Program Director | Issue closed as restaffing of the Rediscovery team being managed as a BAU activity | 2012-03-06 |  | TRUE | 1 |  | TRUE | 57 | TRUE | FALSE | FALSE | -55 | FALSE | TRUE
I105 | 2012-01-25 | Rob Dekker | Closed |  | Request to run a pilot in May will require resources to spend their time addressing this pilot as opposed to their role in the overall solution. |  |  |  |  | 04. High | Al Grljevic | Al Grljevic | Technology Foundation |  |  | 2012-02-15 | 2012-02-15 | 15-Feb: The team has received confirmation that there are no pilots required now ahead of service requirements (Outlook and Lync). Close! 25-Jan: Raised on call. Laura added; following up with Al for assistance clarifying the details. |  | 15-Feb: Confirmation that there are no pilots required ahead of service requirements (Lync and Outlook). | 2012-02-15 |  | TRUE | 1 |  | TRUE | 57 | TRUE | FALSE | FALSE | -36 | FALSE | TRUE
I106 | 2012-01-25 | Rewa Bouji | Closed |  | Lack of business SMEs nominated to act as Business Requirements Leads from whom to gather and validate requirements and configuration is delaying the completion of Outlook configuration settings and Day 1 expected application integration. Requirements definition approach to date has leveraged existing Global Mail Templates, policies etc, and escalated to DA/QRM Steering Group as appropriate for technical/policy decisions respectively. However neither governance group can determine business criticality of mail-integrated applications required on Day 1. UC Business Analysts unable to conduct analysis systematically across each area to ensure total coverage, nor determine relative priority of requirements. Currently working with IE and AM to conduct impact analysis of migration to Exchange, and present cost/schedule impact of integration around key categories (eg Room booking, Faxing, Group Management, etc) for presentation to FSG on what is a Day 1 integration requirement. Resource constraints in IE/AM will extend timeline for completion of impact assessment work. Challenge of this approach is the delay to determining final scope of Day 1, which impacts planning and potentially O365 scope freeze as we may not be able to identify applications impacted by O365 in time for design to complete, resulting in adverse business impact. | 05. Critical | 04. High | 04. High | 03. Medium | 04. High | Rewa Bouji | Rewa Bouji/Martin Kremmer | Unified Communications |  | Work with Business Deployment team to build network of Business Requirements Leads/ Configuration Working Group who are empowered to approve Outlook/Lync specification | 2012-02-29 | 2012-03-31 | 12/03/12: RB: Combined with I40 to address overall lack of business engagement/decision-making 27/02/12: RB: No update available 22/02/12: RB: Discussed engagement strategy with Sophie and Jackie. Overall M&C engagement approach still under discussion, but interim approach agreed to enable BA team to press ahead with engagement on mail enabled applications 14/02/12: RB: Lack of engagement strategy creating challenges as service line and area engagement beginning to result in confusion/duplication of effort for BA team and stakeholders. Clarity also needed on Business Change approach to engagement with ITSD Leads to ensure they are aware of engagement with their portfolios 26/01/12: Issue added to log to highlight continued impact of lack of business engagement on Lync and Outlook requirements. Business deployment and Business change still to develop engagement strategy for requirements leads - awaiting further discussions on agenda of Area Stakeholder Engagement Workshops to try and highlight need for business involvement in requirements gathering and approval, as well as decision-making authority for Day 1 configuration and application integration set. | Managing Sponsor | Combined with I40 to address overall lack of business engagement/decision making. | 2012-03-12 | I40 (combined) | FALSE | 0 |  | TRUE | 57 | TRUE | FALSE | FALSE | 9 | FALSE | TRUE
I107 | 2012-01-31 | Michelle Edmonds | Closed |  | Need communication to the business regarding required changes in plans due to financials, O365, etc. | 03. Medium | 02. Low | 03. Medium | 03. Medium | 05. Critical | Sophie Boiron | Guy Morgan | SharePoint |  | 2012-03-17 | 2012-03-07 | 2012-02-15 | 13-Feb: Action opened on daily call for the end of this month (Alan) to ensure that a comm went out. This includes all programs, not just M&C. Can close here and will follow-up through that action. 8-Feb: Mike specified should still be part of SP workstream, assigned to Guy. SP will clean up further for next week. 31-Jan: Issue opened. | Program Director | Communciation Occurred Action opened on daily call for the end of this month (Alan) to ensure that a comm went out. This includes all programs, not just M&C. Can close here and will follow-up through that action. | 2012-03-13 |  | TRUE | 1 |  | TRUE | 51 | TRUE | FALSE | FALSE | -36 | FALSE | TRUE
I108 | 2012-01-31 | Martin Stutchbury | Closed |  | The EY implementation of O365 development standards don't exist for cloud based solutions. This covers integration, interaction, UX etc. Work will begin on Phase 1 Feb 6th and there is a risk that re-work will be required to conform with the standards that are under development. | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 04. High | Michelle Edmonds | Brett van Gelder | SharePoint |  | TBD | 2012-03-07 | 2012-03-30 | 08-Mar: O365 development standards sent by Norm Beard to Neil Sahdev on 08/03/12 22-Feb: M&C Program is the leader program and thus must develop standards and practices (create where they don't exist). Confirm that this is what is being sought by A&DM (in opening this item). Ed is working on this; review in March. Updated syntax per Brett; rather than "no standards exist" > "the EY implementation of O365 devel. standards..." 15-Feb: on call, team said this belongs to SP. LM em'd michelle for details. | Program Manager | O365 development standards sent by Norm Beard to Neil Sahdev on 8-Mar-2012. | 2012-03-08 |  | FALSE | 0 |  | TRUE | 51 | TRUE | FALSE | FALSE | 8 | FALSE | TRUE
I109 | 2012-02-01 | Mike Laci | Closed |  | Lack of sufficient (100+) BU testers is delaying the next phase of transition testing for Outlook Dormant Deployment | 05. Critical | 05. Critical | 05. Critical | 05. Critical | 05. Critical | Mike Laci | Mike Laci / Daren Wicks / Martin Kremmer | Technology Foundation |  | Martin Kremmer is working on creating a list of BU testers who would be able to assist with with Outlook Dormant testing. Need a list of at least 70 if not 100 BU testers for a valid test. Martin Kremmer to identfy BU resources. | 2012-02-15 | 2012-02-16 | 15-Feb-2012: Martin confirmed have testers in Copenhagen. Close. 8-Feb-12 - Martin Kremmer has suggested using Denmark Advisory and TAS as BU testing audience. Martin will validate with BU in Denmark and will report back in 48 hours from 8 Feb. Requirement that the SCCM team clear backloged reporting queue of reporting in the SCCM environment | Program Manager | Martin Kremmer confirmed there are testers in Copenhagen that we will use. Close. | 2012-02-15 |  | TRUE | 1 |  | TRUE | 50 | TRUE | FALSE | FALSE | -35 | FALSE | TRUE
I11 | 2011-04-27 |  | Closed |  | Program name needs to be determined. |  |  |  |  | 04. High |  | Al Grljevic/John Costello | M&C Program |  |  | 2011-06-01 | 2011-06-01 | 27/04 - identified the ongoing issue of determining program name. 04/05 - Team members to send 2 name options to Laura; Laura will consolidate list and send out for a vote. 11/05 - Voting occurred; Share top 5 names with John so he may decide. 18/05 - Shared with business last wk, not much feedback. No decision as of yet. Leave for next week. 25/05 - Had given the names to John and requested decision. Will follow-up. 01/06 - close issue. John was provided the information. |  | Name agreed upon. | 2011-06-01 |  | TRUE | 1 |  | TRUE | 330 | FALSE | FALSE | TRUE | -295 | FALSE | TRUE
I91 | 2012-01-10 | Neil Sahdev | Active | R25 | Timeline for conversion of 15 applications by Microsoft shows 20+ week schedule which if extrapolated for remainder of the applications would indicate Program would not complete by mid-2013. | 02. Low | 02. Low | 05. Critical | 04. High | 05. Critical | Neil Sahdev | Neil Sahdev | App and Data Migration |  | Determine way forward; there are numerous options at present. | 2012-03-30 | 2012-03-30 | 13-Mar Neil: This issue should remain open until it is widely accepted that the duration of the A&DM Program will extend beyond mid-2013. To progress this issue I am working with Gavin Bell to define the Business Benefits Case for A&DM (i.e. investment needed over time vs. fiscal and non-fiscal benefit). I therefore suggest we set the next review date of this issue as Friday 30th Mar'12. 06-Mar: Presentation sent to Alan and Brett. Neil and Brett to meet Friday 09/03/12 to refine the IBM SSSO licencing details 29-Feb: Presentation outlining assumptions that drive the program duration now drafted and undergoing internal review / update before being sent to Alan on 01/03/12 22-Feb: Meeting held (Alan, Neil, Martin, Brett, Rob Taub) on 21/02/12 to discuss assumptions that support A&DM Program duration of five years. Neil/Martin now preparing a presentation for Alan to present at the CLT meeting scheduled w/c 27/02/12; review next week. 14-Feb: Program Plan, resource schedule and budget updated accordingly. PMO now consolidating with other Programs' E2E plans for presentation to Cross-Org leadership team; 15-Feb: keep open until accepted. 07-Feb: Program plan assumes A&DM Program will complete 2017 (assuming first two portfolio teams start 1st Jul'12) which therefore means the firm will be dependant on Lotus Notes beyond Jun'13. Neil took an action to socialize within IT Services ASAP. 10-jan: Opened from R25. | Program Director |  |  |  | FALSE | 0 |  | TRUE | 72 | TRUE | FALSE | FALSE | 8 | FALSE | TRUE
I111 | 2012-02-08 | Paul Neave / James Harrup-Brook | Closed | R38 | Managed services RFP to select vendor for services for Lync. This is affecting hardware order datesThere is a risk that we may impact hardware order dates. Decision had been taken to do prerequisite vendor workshops with 8 vendors to finalize RFP future state requirements. |  |  |  |  | 04. High | Adrian Mickleson | Adrian Mickleson | Technology Foundation |  |  |  |  | 15-Feb: It has been decided that we will not be ordering hardware since we are going the vendor route for Lync. Close. 8-Feb: Opened from R38. Currently looking at which services to be offered, which to put in the cloud. This is impacting hardware order dates. Looking at how else it is impacting the program. |  | 15-Feb: Not ordering hardware since going the vendor route. Close. | 2012-02-15 |  | FALSE | 0 |  | TRUE | 43 | TRUE | FALSE | FALSE | -40990 | FALSE | TRUE
I112 | 2012-02-08 | Paul Neave / James Harrup-Brook | Closed | R38 | A managed services RFP is being run to select vendor for services for Lync, Exchange and SharePoint. There is a risk that we may impact hardware order dates. Decision had been taken to do prerequisite vendor workshops with 8 vendors to finalize RFP future state requirements. |  |  |  |  | 04. High | Adrian Mickleson | Adrian Mickleson | Technology Foundation |  |  |  |  | 15-Feb: Did the RFP for Exchange, and this is not an issue. Close. 8-Feb: Opened from R38. Currently looking at which services to offer. |  | 15-Feb: Did RFP activity for Exchange; this is not an issue. Close. | 2012-02-15 |  | FALSE | 0 |  | TRUE | 43 | TRUE | FALSE | FALSE | -40990 | FALSE | TRUE
I40 | 2011-10-04 | Rewa Bouji | Active |  | Lack of business SMEs to input in requirements gathering, requirements validation and sign off on both Lync and Outlook requirements, and Day 1 Outlook Plug-ins risks rejection of the solution by the business. Lack of governance group for Lync/Outlook decisions and sign off hampering confirmation of Day 1 service scope. Lack of insight into migration strategy planning (as well as business impact of these) may risk solutions being rejected, or delays to the planned deployment timeline. [Change Management]: Whilst this is pressing it needs to be sensitive to the order of events given that the 'story' for M&C is being developed to engage with Senior stakeholders. Ideally this would be completed first before seeking resource. However timescales will not necessarily allow for everything to work serially. | 03. Medium | 05. Critical | 04. High | 03. Medium | 05. Critical | Jeremy Brown | Sophie Boiron / Martin Kremmer | Change Management |  | Area engagement plan produced in January 2012 and will be activated from 1-Feb-2012 | 2012-03-26 | 2012-03-31 | 19-Mar-12: Rewa and Jackie have produced a proposed model for review and approval of requirements. This has been reviewed by Jeremy Brown and Rewa, Rachel and Jackie will take this to individual stakeholders in the Areas and Functional Groups for their input and advice. 12-Mar-12 (RB): Issue wording updated to combine with I106 in order to avoid duplication, as ultimate resolution is the same for both issues. Owner assigned as Jeremy Brown. JB drafted governance model to address this, being reviewed by UC and Change. Due date amended to end of March in line with delivery of overall M&C governance 09-Mar: Engagement with the business is awaiting for overal decision on M&C program engagement model including IT service delivery leads. In discussion with Margerat Walsh 22-Feb: had engaged with business, but are receiving pushback as of late since the business is being contact by numerous programs; looking for integration. Sophie restarting this piece. The drop dead date is the end of April and the team will be pushing at the max to complete by then. Ammended due date from 7-Dec-2011 to end of April. Review next week. 05-Feb: Requirement gathering discussion started wit AsiaPac. Plan to engage with Americas and Japan shortly and with EMEIA other the next couple of weeks (still waiting for EMEIA rep to be decided). 26-Jan: RB: Issue re-worded to reflect focus on business engagement more aligned to the business deployment and business change scope which spans SharePoint and ADM as well as UC. New issue (I106) raised to highlight the issue arising from lack of business engagement specifically on Unified Comms requirements scope 25-Jan: Meeting with Rebecca Chan on Monday to discuss Change Network for Asia Pacific. Conversation on call around whether it is realistic that the team will get agreement from the FSG on this. Rewa said an alternate route is being taken to find a focused group to make these decisions. The Q&RM scope is narrow and make more recommendations than decisions. Off-line discussion to be had around the critical point when not having these decisions will delay the program. Rewa will split this item back out (used to be two separate items) so that one is a risk that the lack of decisions being made will h hamper progress. The longer these decisions make, the longer until we can move forward. She will include the O365 decision in the description and assign the item to Ian, Guy and Alan to resolve. 10-Jan: I49 blended into this. Action completed.Added Martin to "Assigned to" 04-Jan: Jackie said this is linked with I49; keep open and she will update. (Laura opened action) 07/12 - Jackie said this is essentially the same issue as the Area Engagement one. She is working on cleaning up these items. 30/11 - On call, decided to change due date from 30-Oct to next week. Engaged with business, this has been escalated to Jeremy, Bob and Alan. Jackie said she will take the action to work with James to rationalize this. Adrian also said that this is on the agenda for Liz King's workshop next week. Review next week. 09/11 - Jackie said that they are presenting SAS story, first draft at FSG meeting next week.Still showing very critical dates around resource placements. Increase to Critical. 26/10 - Adrian suggeted this be owned by Jackie and Sophie. 19/10 - Adrian has been struggling due to lack of sponsorship in FS groups. The need for business engagement is beginning to impact the program and consequently not moving forward well in UC. Review next week when Jeremy is on the call. 11/10 - R Bouji - Discussions with J Brown continuing, suggestion to hold briefing sessions in AsiaPac, EMEIA, and Americas with key area SMEs to present program and elicit nominations for business resources to fill key UC Deployment Area Manager roles, as well as validate engagement model and deployment strategy straw man. Scope and objectives of briefing sessions, attendees, dates etc TBA by M&C UC and Change teams. 4/10 - RB and AM presented proposed engagement model to J Brown 21/09. Acknowledged the challenge in finding resources with capability and capacity to fill roles. Also presented to IT Area Management Leads (APAC, Americas), and agreed to hold a planning workshop to validate engagement approach, deployment and transition plans, and try to identify/nominate resources for key SME roles to sit within Program team and within business/IT. Workshops to be held in October (dates TBC). | Managing Sponsor |  |  |  | FALSE | 0 |  | TRUE | 170 | FALSE | TRUE | FALSE | 9 | FALSE | TRUE
I148 | 2012-03-14 | David Shapiro (Bharat Sambyal) | Active |  | Impact of O365 on M&C designs and its implications on AD prep deliverables. | 01. Undecided | 01. Undecided | 01. Undecided | 01. Undecided | 04. High | Ted Balfour | David Shapiro | IAM |  | Coordinate with M&C to incorporate the changes in AD Prep design. | 2012-03-30 | 2012-03-30 | 15-Mar: On daily standup call, Ted took action to talk to David and validate whether this is a risk or issue. Alan suggested due date of end of the month. 14-Mar: Added to this M*C log. Was raised to the IAM log 28-Feb. | Program Manager |  |  |  | FALSE | 0 |  | TRUE | 8 | FALSE | FALSE | FALSE | 8 | FALSE | TRUE
I115 | 2012-02-22 | Michelle Edmonds | Closed |  | Synchronization between cloud and on-prem is not currently confirmed | 04. High | 04. High | 04. High | 04. High | 04. High | Michelle Edmonds | Norm Lambert | SharePoint |  | We will do a POC to determine solution options. We will put this on the Roadmap for the cloud to turn on managed metadata services. | 2012-03-14 | 2012-03-16 | 14 Mar: The POC from MS proved that this is possible, closing 13-Mar: On daily call, Michelle said she is confirming with Microsoft and will close today. 12-Feb: Confirming if same approach for Profiles will work (O365 inbound web services) Norm Lambert to estimate work. 29-Feb: Currently assessing 3 alternatives and have narrowed it down to one option. We will formulate questions for O365 Team. | Program Manager | POC from Msft proved that this is possible, closed. | 2012-03-14 |  | TRUE | 1 |  | TRUE | 29 | FALSE | FALSE | FALSE | -6 | FALSE | TRUE
I116 | 2012-02-22 | Michelle Edmonds | Closed |  | We may not be able to use a vendor for Managed Metadata as they are not approved in the cloud. | 04. High | 04. High | 04. High | 04. High | 04. High | Michelle Edmonds | Norm Lambert | SharePoint |  | Plan to be defined. | 2012-03-14 | 2012-03-16 | 14 Mar - Decision on how to manage best bets confirmed with Search Team 13-Mar: michelle said there is an approach worked out with Ed Dale and she will update and close today. 12-Feb: Working with vendor on architectural view to determine how to configure. 29-Feb: We have broken down to a dependency on whether or not we can sync. Potential for some features (ie. Auto tagging) to not be implemented with O365 unless they are certified. Currently assessing further. | Program Director | Decision on how to manage best bets confirmed with Search Team. | 2012-03-14 |  | TRUE | 1 |  | TRUE | 29 | FALSE | FALSE | FALSE | -6 | FALSE | TRUE
I117 | 2012-02-22 | Gregory Van Valkenburgh | Closed |  | People Profile synchronization between the cloud and on-prem needs to be assessed | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 03. Moderate | Michelle Edmonds | Norm Lambert | SharePoint |  | Currently analyzing the implication of building separate solutions | 2012-03-14 | 2012-03-16 | 13-Mar: LM em'd Michelle for resolution description. 12-Feb: Documenting OOB vs. added features. Mtg with Microsoft being scheduled and working with Ken Hammond to resolve. 29-Feb: Currently assessing what would show with social features and without. | Program Manager |  | 2012-03-13 |  | TRUE | 1 |  | FALSE | 29 | FALSE | FALSE | FALSE | -6 | FALSE | TRUE
I118 | 2012-02-22 | Michelle Edmonds | Closed |  | Newsgator / Nuedesic (not approved in the cloud) decision is taking longer then expected. | 04. High | 03. Medium | 04. High | 04. High | 04. High | Michelle Edmonds | Gregory Van Valkenburgh | SharePoint |  | Targeting final decision by 15-March | 2012-02-29 | 2012-03-15 | 15 March - using Newsgator as an assumption for planning 12-Feb: Vendor to provide Architecture. 29-Feb: Still assessing, follow up mtg with the core team this week. 23-Feb: Greg provided the escalation level. For the due date, he said the initial recommendation is for 29-Feb, but they are targeting a final decision by 15-March. | Program Manager | 15 March - using Newsgator as an assumption for planning | 2012-03-15 |  | TRUE | 1 |  | TRUE | 29 | FALSE | FALSE | FALSE | -7 | FALSE | TRUE
I119 | 2012-02-22 | Michelle Edmonds | Closed |  | We need firm decisions on Time, Budget and Scope in order to finalize the Re-Plan | 04. High | 04. High | 04. High | 04. High | 05. Critical | Michelle Edmonds | Guy Morgan | SharePoint |  | TBD | 2012-02-29 | 2012-02-22 | 22-Feb: Michelle wrote a note to Alan, no response as of yet, and had a discussion with Guy. Need Guy and Alan's help with this right away. | Program Director | replan will address | 2012-03-09 |  | TRUE | 1 |  | TRUE | 29 | FALSE | FALSE | FALSE | -29 | FALSE | TRUE
I12 | 2011-05-11 |  | Closed |  | In June there are planned to be a number of elaboration sessions for Lync, Exchange, SP Foundation and a Design 0 Session. Currently the exact dates and locations of these sesssions cannot be confirmed. The cost of travel will continue to increase as the date come closer and key resources may not be available. Need to schedule sessions ASAP |  |  |  |  | 05. Critical |  | Al Grljevic/Adrian Mickleson | Technology Foundation |  |  | 2011-06-01 | 2011-05-27 | 11/05 - Was R21; moved here as critical issue. 18/05 - June 13: Lync, Exchange, SP- will run 2 weeks, in-person. June 9-10: Design Level 0. Time constraint: All managing sponsors can't be in either London or Frankfurt (or other) due to scheduling surrounding the 9-10. Very important because a delay here delays Fusion. Tomorrow will discuss with business the impacts of not having all managing sponsors there on 9-10 June. 25/05 - Adrian still planning on 2 wks with possible overflow in 3rd wk being conducted virtually. Need to send out a placeholder; Adrian to confirm with Laura to send out. More detailed schedule/invitations to be sent once receive further info from MS. 01/06 - close issue. Rooms scheduled and resources identified. Invitations to be sent. |  | Rooms scheduled and resources identified. Invitations to be sent. | 2011-06-01 |  | TRUE | 1 |  | TRUE | 316 | FALSE | FALSE | TRUE | -300 | FALSE | TRUE
I120 | 2012-02-22 | Neil Sahdev | Closed |  | Decision made to offboard all ITA and IBM resources and two contractors from the A&DM Program leaving only a skeleton Phase 1 and Rediscovery team in place (no overall leads). As a consequence all delivery plans have slipped - impact to the business: - First application replatforms won't now be delivered until Q2'13 (was Q4'12) - Application decommissions won't now commence until Q4'12 (was Q2'12) therefore delaying financial incentives - The delivery factories won't now come onboard until early 2013 (was Jul'12) therefore extending the end-date of the overall program | 05. Critical | 02. Low | 05. Critical | 05. Critical | 05. Critical | Neil Sahdev / Martin Stutchbury | Guy Morgan | App and Data Migration |  | Agree priority of the A&DM Program relative to other initiatives to determine when and how to resource the team to enable delivery to recommence at scale | 2012-02-29 | 2012-02-24 | 06/03 - Issue closed as replanning of both Phase 1 and Rediscovery projects being managed as BAU 29/02 - Change request summarising the resource reduction and the associated schedule and cost impact presented during CCB held 24/02/12 - the CR is currently awaiting approval by Alan and Bob 22/02 - Detailed impact assessment sent by Martin and Neil to Guy Morgan (highlighting impacts to Program); rev next week. | Program Director | 06/03 - Issue closed as replanning of both Phase 1 and Rediscovery projects being managed as BAU | 2012-03-06 |  | TRUE | 1 |  | TRUE | 29 | FALSE | FALSE | FALSE | -27 | FALSE | TRUE
I153 | 2012-03-14 | Daren Wicks (Bharat Sambyal) | Active |  | Although a review has taken place with respect to O365 impacts on ID Sync, it should be noticed that the M&C, O365 discovery process has NOT completed, and thus there may be additional impacts/requirements that are currently unknown. | 01. Undecided | 01. Undecided | 01. Undecided | 01. Undecided | 05. Critical | Ted Balfour | Daren Wicks | IAM |  |  | 2012-03-30 | 2012-03-30 | 15-Mar: Ted will meet with Daren and determine way forward. Alan suggested due date of end of the month. 14-Mar: Added to this M*C log. Mar 12 : updates next week Mar 6: Raised a Change request Feb 28: Daren will reach out to M&C for Updates Feb: 22 Awaiting confirmation from M&C that the discovery piece has completed, and there are NO changes that will affect ID Sync | Program Manager |  |  |  | FALSE | 0 |  | TRUE | 8 | FALSE | FALSE | FALSE | 8 | FALSE | TRUE
I23 | 2011-08-03 | unknown | Closed | NA | IAM is waiting for a list of critical applications, for analysis by the Enterprise Application Team to review which apps will require dev work due to non-conformity with AD Attributes. Impact is our ability to (with confidence) lock down the Global attributes, with an (80%) level of confidence of not negatively impacting the Critical Applications. Impact is on the delivery of ID Sync and Group Management - due 31st & 6th Jan respectively) and the 6th Feb for M&C, as we will use these attributes for Lync and Exchange. | 01. Undecided | 01. Undecided | 01. Undecided | 01. Undecided | 04. High | Ted Balfour | Ted Balfour/Ken Sponaugle | IAM |  | TBD | 2012-03-21 | 2012-03-21 | 15-Mar Ted: For issue 23, more cross validation is required so this Issue should be moved out to next Wednesday, 21 March. 13-Mar: Ted has a list of critical apps (287). He has a meeting later this week to cross reference with another list; daily call action due Friday. (Alan suggests it can then be closed since Ted will have the list he needs. Ongoing actions part of regular activities) 28-Feb: Angelda Goldman is assigned as Application remediation PM. Updates will be provided in the next week. 15-Feb: have sent e-mail to key 8 app owners; additional `287 app owners to reach out to; working on that message.There is a new PM starting on the 27th who will focus on app remediation targets. 2 wks for review. 8-Feb: Ted said he has a list; needs to cross-reference with another list they have. Review in one week. 26-Jan: Changed owner/assigned to to Ted from Bob C. 18-Jan: Has the list, but working to ensure have appropriate communication on what needs to be done. This comm is in progress, remains high, review next week. 11-Jan: Ken has the list, but it needs review. Review next week. 04-Jan: Bob C. said they made progress here; identified owners for 350 business-critical applications. Working on a communication strategy to owners to ensure they review the applications and whether or not they will be impacted. Review next week. 14/12 - Bringing to steering group tomorrow to see if we can accept risk. 07-12 Senior Management discussions are ongoing with respect to how this process will be managed (between IAM and D&A), and what D&A need to do, to hit the end of Feb timeline. Still do not understand the criticality of the issue. Review next week. 30-11. We are now looking at working with the Discovery and Asesment Team to manage this prcocess, which will provide a more cohesive Review and/or Remediation approach across the various programs, reducing the number of individual and multiple contacts, questions etc each team are likely to requested of the SDMs/App Owners. 23/11 - Bob said they sent comm to Service Delivery COT and are working on a second comm for manager level. Scheduling series of workshops to discuss; will complete in 2 weeks. Review then. 09-11 - Approval delay in comms, has caused this to slip. Expected to be approved by Zach Haberer (CBS Service Delivery Lead) on 10th Nov. This will then be communicated to the Service Delivery Team by the 11th Nov. This will then be sent to the SDMs. 02-11. Comms has been confirmed. Meetings are currently being arrnaged with the Service Delivery Managers 26-10 - Comms have been pulled together to present the Strategy to the SDLs - IAM to reach out to Service delivery Leads by W/E Friday 4th Nov, and gain agreement for the Comms to go out to the Service Delivery Managers with the objective to inform the Application Owners Re M&C Programme, and the potential impacts of locking down the attributes. IAM will also create a "feedback loop" regarding confirmation that the Comms plan has been communicated to said SDMs, and provide supporting activities therein. 19-10- Proposal communicated to the Area Relationship Manager. The next challenge is to communicate this to the Service Delivery Leads which is being targeted for W/E 24th Oct. Keep Critical until communications go out. 12-10 Application Remediation – Proposal developed (as listed below). Customer Relationship managers have agreed to this process. Next step is to glean confirmation from Service Delivery Leads. 04-10 . A Proposal being developed to communicate the challenge to the Service Delivery Leads and OSS to support in relation to potential application remediation review and thus resolution strategy. Bob plans to present the proposal at the Steering Committee meeting this Friday so they can move it forward. Due date still unknown. 22-09 - We've escalated to Margaret Walsh - Markets IT Service Delivery Leader (DR to MO) IAM are discussing a variation on the tactical ID Sync solution for a Country by Country Group Attribute population Policy. This is going to need validating with M&C, and also raised at the IAM Design Authority for agreement. Bob is meeting with Peter, Dana and Sara from IAM tomorrow; he will invite Adrian, as well. Further, Daren will pass along to Adrian to raise this issue at the ITS Steering Committee meeting tomorrow. Due date unknown until know how many critical applications there are. 21/09 - Portfolio Team are New and thus we are in parallel touching base with Joint Discovery again for guidance/support. 14/09 - Filters to arrive at the list of critical apps have been agreed upon. Working with Portfolio Management team to determine how long it will take to review the applications and further how long it will take to potentially remediate. Should have dates by next week's call. (Bob: application remediation piece in M&C; collapse of root domain is outside M&C). 07/09 - Discovery and assessment team provided list of 10,000 apps from Gain, which will be filtered based on business criticality framework. Different filters result in different number of critical apps. Will determine in meeting Friday which filters will be using. By the end of next week hope to have understanding of which apps have to go through remediation. Neil and Daren to talk off-line re: Lotus Notes apps. Note: This is the first pass with the goal of avoiding attribute clashes only. 31/08 - Daren had call with GCL5; they have been doing due diligence with respect to which apps are critical. Will provide status update tomorrow and then team can look at what remediation activities will be needed. In parallel - discovery work: meeting tomorrow to review output from original scope to see if it will suit our needs. John Lawler expressed concern. Discuss off-line. 24/08 - Much has been going on here; working with discovery (James Harvey and team) for assessment. Meeting Tues. to review capabilities and scope of assessment team. Can they meet requirements from IAM? Still working with GCL5. Still unsure whether we can get down to the level of information we need: critical apps and analysis. Need impact assessment so we know what to do in case that don't identify an app. 17/08 - Daren still awaiting list from GCL. Once Madonna's team grabs the apps and determines which are critical, Alex Hall's team will remediate and fix the necessary attributes. But- don't know how many, so don't know how long will take, so don't know impact. Anthony (intimately involved in ITAP) out 2 wks, Bob will talk to Dana and Azul for clarity. 10/8 - Steve / Anthony is still seaking a further list of critical apps or some statement that the 8 he has is the full list - action on GCL5 team to provide list. 3/08 - Anthony has been working with Madonna on list of apps, challenge getting this info.Q&RM sent back list of 8 apps.There is a question around how to define critical applications; possible solution is to mitigate on the fly as these scenarios are identified. Adrian, Daren to determine risk management approach. status of Critical App list from Madonna Swanson (GCL5). | Managing Sponsor | More initial discovery is required and the list of applications will be re-addressed at a later stage | 2012-03-19 |  | TRUE | 1 |  | TRUE | 232 | FALSE | FALSE | TRUE | -1 | FALSE | TRUE
I123 | 2012-02-22 | James Harrup-Brook | Closed |  | Infra. Strategy not confirmed, affects all assumed EY tasks and Functional Spec as these were based on assumptions that infra. Would be on prem | 05. Critical | 04. High | 04. High | 04. High | 04. High | Adrian Mickleson | J Harrup-Brook / Steve Jelf | Technology Foundation |  | Deep dive with all on all EY tasks, revisit assumptions, communicated with vendors if allowed | 2012-04-11 | 2012-04-18 | 13-Mar: This is closed as the action is to provide CR's for SP and Messaging. 9-Mar: TF team determined this is due mid-April with selection of Lync vendor. Added a due date. James assigned to, esc level proj manager. 6-Mar: Laura sent James a note to clarify; will probably close. | Project Manager | Closed per Al; this will be a part of CR for SP and Messaging. | 2012-03-13 |  | FALSE | 0 |  | TRUE | 29 | FALSE | FALSE | FALSE | 27 | FALSE | TRUE
I124 | 2012-02-29 | Martin Stutchbury | Closed |  | The A&DM delivery timeline is being heavily impacted by other projects and programs (i.e. Sharepoint, DCC, GCL5...) which means that the Program is not being delivered using the best approach | 02. Low | 03. Medium | 03. Medium | 03. Medium | 03. Moderate | Neil Sahdev | Neil Sahdev | App and Data Migration |  | Agree priority of the A&DM Program relative to other initiatives to determine approach to take | 2012-03-07 | 2012-03-09 | 06/03 - Issue closed as priority of A&DM relative to other Programs being reviewed by CLT / IT SD leads as part of FY13 planning | Program Director | Issue closed as priority of A&DM relative to other Programs being reviewed by CLT / IT SD leads as part of FY13 planning | 2012-03-06 |  | TRUE | 1 |  | FALSE | 22 | FALSE | FALSE | FALSE | -13 | FALSE | TRUE
I125 | 2012-03-05 | Michelle Edmonds | Closed |  | People & Communities technical teams are running out of work. Remaining work is dependent upon Social Features decision | 04. High | 04. High | 04. High | 04. High | 04. High | Greg Van Valkenburgh | TBD | SharePoint |  |  | 2012-03-07 | 2012-03-14 | 7 Feb: Added Issue. A mtg will be scheduled to discuss timing and expectations around Release 1. | Program Director | Team is being reassinged to help until replan is complete. WSL leaders engaged and realigning tasks | 2012-03-09 |  | TRUE | 1 |  | TRUE | 17 | FALSE | FALSE | FALSE | -8 | FALSE | TRUE
I126 | 2012-03-05 | Michelle Edmonds | Closed |  | Implementation of Social features product is unlikely to be available for Calendar year 2012 deployment | 04. High | 04. High | 05. Critical | 04. High | 04. High | Greg Van Valkenburgh | TBD | SharePoint |  |  | 2012-03-07 | 2012-03-14 | 14-Mar: Michelle closed; this is being incorporated into the plan being prepared for Tuesday. 7 Feb: Added Issue. A mtg will be scheduled to discuss timing and expectations around Release 1. |  | To be determined as part of the replan | 2012-03-14 |  | TRUE | 1 |  | TRUE | 17 | FALSE | FALSE | FALSE | -8 | FALSE | TRUE
I127 | 2012-03-05 | Michelle Edmonds | Closed | I133 | UX views have added functionality not previously discussed with the business | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 03. Moderate |  |  | SharePoint |  |  |  |  | 9 Feb: This is a duplicate issue (I133). This item will be closed and activity will be tracked under I133. |  | This is a duplicate issue (I133). This item will be closed and activity will be tracked under I133. | 2012-02-09 |  | FALSE | 0 |  | FALSE | 17 | FALSE | FALSE | FALSE | -40990 | FALSE | TRUE
I100 | 2012-01-24 | Al Grljevic | Active | NA | There are a number of workshops that need to run in parallel. Due to a limited number of leads per stream, these sessions need to run in series. Impact: delivery schedule and budget. | 02. Low | 02. Low | 04. High | 04. High | 04. High | Al Grljevic | Al Grljevic | M&C Program |  | The team has to live with this issue; if bring in new leads, schedule and budget will still be impacted due to the time it would take to bring them up to speed. There will have to be some type of CR against the schedule and budget at the appropriate time. | 2012-05-23 | 2012-06-13 | 15-Feb: added impact ratings and planned resolution. Per discussion on call, there is nothing really that can be done about this issue, but it does exist. Review in 3 months, potentially due in four, but this will probably be ongoing. 24-Jan: Laura added to log per Al. | Program Manager |  |  |  | FALSE | 0 |  | TRUE | 58 | TRUE | FALSE | FALSE | 83 | FALSE | TRUE
I102 | 2012-01-25 | Al Grljevic | Active | NA | Lack of a decision-governing body within the programme. Impact: This introducing additional work and noise to the programme that would otherwise by managed externally is causing confusion and churn on the programme. | 04. High | 04. High | 04. High | 04. High | 04. High | Al Grljevic | Al Grljevic | M&C Program |  | Develop a decision-making plan to reduce this churn. | 2012-03-07 | 2012-03-14 | 15-Feb: Guy, Alan, John and others are working on a decision-making plan to reduce the churn on the program. Hoping to put together a group that would be available on a weekly basis to review decisions, impact if don't get decision, etc. Will continue to work offline, review 1st or 2nd week of March, potentially due thereafter. 25-Jan: Laura added per Al. | Program Director |  |  |  | TRUE | 1 |  | TRUE | 57 | TRUE | FALSE | FALSE | -8 | FALSE | TRUE
I13 | 2011-05-11 |  | Closed |  | A number of prerequisite activities will need to be completed in time for the commencement of the SOWs once approved. This issue specific to Group Management. Split out the group mgmt from GLMS. GLMS was addressed and can be closed. |  |  |  |  | 04. High |  | Adrian Mickleson/Nick Wood/Daren Wicks | Technology Foundation |  |  | 2011-08-10 | 2011-06-08 | 10/8 - Steve - AD Group Management business case approved and RFP underway. Close issue and keep the Group Mgmt Risk (R33) open. 3/8/2011 Steve has completed preliminary work on Tminus plan and Ant has reviewed it. Will use the plan as basis for running an RFP for the Tactical Group Management purchase. Anthony is waiting for a business case sign-off before he can start the process. Daren Wicks will track for M&C 27/07 - Steve and Anthony working on the T-Plan. Review in 2 weeks. 06/07 - Nick havs taken GLMS plans for the co-existance phase to the Design Authority. Steve and Anthony will devise a t-plan. Meeting was held to move forward. 29/06 - Steve and Nick will take a presentation to Design Authority to move forward. 15/06 - continue to research 3rd party tools. GLMS - 2 options: modify GLMS to populate existing directory or use 3rd party tool. Suggest looking at tactical tool for integrated AD solution, call arranged for Friday 6/17. 01/06 - internal meetings scheduled to address and come up with possible tactical solutions. Raise issue at IT Steering Committee so John is aware of project impact. 25/05 - Nick Wood leading; technical workshops early next week; have identified the participants. 18/05 - Meeting between Nick and Adrian scheduled to look at technical solution. 11/05 - Adrian, Martin, Brett and Peter to review tactical solution for Group Management in an off-line meeting |  | 10/8 - Steve - AD Group Management business case approved and RFP underway. Close issue and keep the Group Mgmt Risk (R33) open. | 2011-08-10 |  | TRUE | 1 |  | TRUE | 316 | FALSE | FALSE | TRUE | -288 | FALSE | TRUE
I110 | 2012-02-07 | Brett van Gelder | Active | R12 | Currently GAAIT replacement, while nominally within the scope of the SharePoint Research Tools workstream, is being conducted largely as an independent project with direction being provided by Assurance and with architecture engagement both outside of the context of the M&C program. There is lack of consistent governance (program, business and architectural) in an area where there is potential significant investment and architectural impact. There is also long term implication for our "single global content management system" strategy depending on how this is executed. |  |  |  |  | 04. High | Guy Morgan / Alan Guthrie | Guy Morgan / Alan Guthrie | M&C Program |  |  | 2012-03-20 | 2012-03-22 | 19 Mar - Working to document governance structure and gain approval 15-Mar: determined on daily calls that this sits with Alan for an update Tuesday. 14-Mar: Call scheduled today to discuss. 22-Feb: Need Guy and Alan to say definitively whether GAAIT is part of this program. Michelle said Alan and Margaret were talking to Mo, but she hasn't heard back. Review week after the FSG meeting (may be an update there). 15-Feb: Brett not on call; Sophie suggested this is mainly about Change; review this next week when Brett is on the call. 7-Feb: Brett opened. Included: (now D99) We need a decision on whether GAAIT (and Ovitas work) are part of M&C or not and if they are they need to be properly re-absorbed into our governance structures. If not I'd like to know so that I can ensure that Enterprise Architecture is differently engaged than is currently the case. | Executive Sponsor |  |  |  | FALSE | 0 |  | TRUE | 44 | TRUE | FALSE | FALSE | 0 | FALSE | TRUE
I131 | 2012-03-05 | Michelle Edmonds | Closed |  | Lack of clarity on the approach for the Content management workstream | 04. High | 04. High | 04. High | 04. High | 04. High | Michael Cliffel | Cheryl Faust | SharePoint |  | TBD | 2012-03-07 | 2012-03-30 | 7 Feb: Added Issue. Currently replanning activity. 3/6 WSL mtg to discuss further. | Managing Sponsor | Approach determined and the team is workign on the replan | 2012-03-09 |  | FALSE | 0 |  | TRUE | 17 | FALSE | FALSE | FALSE | 8 | FALSE | TRUE
I132 | 2012-03-06 | Michelle Edmonds | Closed |  | Business availability to continue requirements work in other areas due to blueprint activities | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 03. Moderate | Michelle Edmonds | Guy Morgan | SharePoint |  | TBD | 2012-03-07 | 2012-03-30 | 7 Feb: Added Issue. Currently replanning activity. | Managing Sponsor | Will be addressed as part of the replan | 2012-03-09 |  | FALSE | 0 |  | FALSE | 16 | FALSE | FALSE | FALSE | 8 | FALSE | TRUE
I133 | 2012-03-06 | Michelle Edmonds | Closed |  | Frog 'quick hits' contain new functionality and changes to previously defined functionality (SA/Dev assessment to confirm if quick hits creates custom coding) (BA review to confirm if new Reqs have come in from Frog assessments) | 04. High | 04. High | 04. High | 04. High | 04. High | Binoy Raj | Kevin Smyth / Eric Wahl | SharePoint |  | TBD | 2012-03-21 | 2012-03-16 | 7 Feb: Added Issue. Currently replanning activity. Eric and Kevin to set direction as part of the replanning of UX. | Program Manager | Use the quick hits is yet to be determined. | 2012-03-09 |  | TRUE | 1 |  | TRUE | 16 | FALSE | FALSE | FALSE | -6 | FALSE | TRUE
I139 | 2012-03-08 | Martin Kremmer | Active |  | Disconnect between the current need for engagement with the business/application owners and the model agreed with the ITSD leads. This is impacting UC and A&DM timelines. Model is agreed, but no resources to be provided until new FY | 04. High | 04. High | 04. High | 03. Medium | 04. High | Martin Kremmer | Martin Kremmer | M&C Program |  | Short terms agreement to be instituted. Utilise program BA's with aircover from ITSD leads | 2012-03-22 | 2012-03-31 | [5 empty] | FALSE | 0 |  | TRUE | 14 | FALSE | FALSE | FALSE | 9 | FALSE | TRUE
I142 | 2012-03-09 | Iain Matheson | Active |  | The integrity of the programme finances are suspect due to various historical factors such as a number of policy, system and staff handovers, bespoke complexities added, lack of clarity in Finance inputs etc. | 02. Low | 02. Low | 02. Low | 04. High | 04. High | Ian Bourne | Ian Bourne | M&C Program |  | Alternative Financial model to be proposed and implementation plan developed by Fri 23rd Mar. Proposed parallel run through Apr with existing process/tools and final cut-over end Apr. | 2012-03-23 | 2012-04-30 |  | Program Director |  |  |  | FALSE | 0 |  | TRUE | 13 | FALSE | FALSE | FALSE | 39 | FALSE | TRUE
I14 | 2011-05-24 |  | Closed |  | 5 Managing Sponsors still need to be identified (Finance and 4 Area Sponsors) |  |  |  |  | 05. Critical |  | Al Grljevic | M&C Program |  |  | 2011-06-15 | 2011-05-27 | 25/05 - Michelle and Al have communicated this to John; remains open. 01/06 - Discuss at Friday's IT Steering Committee meeting (and at Ken's meeting). 08/06 - John is aware of the need for the managing sponsors. Accept this as a risk and close. |  | Sponsors identified. | 2011-06-15 |  | TRUE | 1 |  | TRUE | 303 | FALSE | FALSE | TRUE | -300 | FALSE | TRUE
I143 | 2012-02-10 | Mike Laci | Active |  | Need to recruit a significant number of additional resources into the program. Recruitment of skilled staff proving very difficult and will impact schedules. | 02. Low | 02. Low | 02. Low | 02. Low | 02. Minor | Nick Coburn | Nick Coburn / Mike Laci | M&C Program |  | Onboard additiona Transition resources | 2012-03-31 | 2012-04-30 | 24/02: ACTION - N.Coburn schedule a session for when in US to discuss what the organisation would look like / people requirements. Pull together transition management capability and what would look like for M&C. | Executive Sponsor |  |  |  | FALSE | 0 |  | FALSE | 41 | TRUE | FALSE | FALSE | 39 | FALSE | FALSE
I144 | 2012-02-10 | Mike Laci | Active |  | Need to determine if a charge code should be established independent of current work streams. | 02. Low | 02. Low | 02. Low | 02. Low | 02. Minor | Nick Coburn | Nick Coburn / Mike Laci | M&C Program |  | Estabish a charge code for Transtiion activity | 2012-03-16 | 2012-03-31 | 02/03: N. Coburn waiting to hear back from Ian on next steps. 24/02:ACTION - N. Coburn to set up meeting next week with Ian Bourne to discuss budget / structure. Ensure M. Laci is also involved in the meeting. 17/02: Mike's time is currently allocated across the workstreams. | Other |  |  |  | FALSE | 0 |  | FALSE | 41 | TRUE | FALSE | FALSE | 9 | FALSE | FALSE
I145 | 2012-02-10 | Mike Laci | Active |  | Discussing the need to realign the IT Transition group and Transition Mangers under a single group under M&C or Cross-Org to better manage IT Transition as a service. | 02. Low | 02. Low | 02. Low | 02. Low | 02. Minor | Nick Coburn | Nick Coburn / Mike Laci | M&C Program |  | Establish IT Transition as its own group under M&C and Cross-Org | 2012-03-31 | 2012-05-31 | 02/03: ACTION - N. Coburn to have a first draft view by 16th March. | Executive Sponsor |  |  |  | FALSE | 0 |  | FALSE | 41 | TRUE | FALSE | FALSE | 70 | FALSE | FALSE
I146 | 2012-02-21 | Blaine Pardoe | Active |  | We do not have the new technology (i.e. SharePoint available to IT Services personnel to use on a day-to-day basis. | 03. Medium | 03. Medium | 03. Medium | 02. Low | 03. Moderate | Blaine Pardoe | Blaine Pardoe | M&C Program |  | Allow key IT Resources outside of M&C to use M&C Technologies on a day-to-day basis | 2012-03-14 | 2012-04-30 | 02/03: Action - B. Pardoe to raise on the Program Level RAID Log. | Project Manager |  |  |  | FALSE | 0 |  | FALSE | 30 | TRUE | FALSE | FALSE | 39 | FALSE | TRUE
I147 | 2012-03-08 | Michelle Edmonds | Closed |  | Lack of clarity on the SharePoint 15 adoption/features | 04. High | 03. Medium | 03. Medium | 04. High | 04. High | Michelle Edmonds | Alan Guthrie | M&C Program |  | Meeting in Cleveland, week of 12-March to resolve. | 2012-03-14 | 2012-03-22 | 19 March - Wave 15 has been reviewed and will be considered for Social features 16-Mar: Michelle took action to update and close today. 13-Mar: Update on daily stand up call that a meeting is occurring later this week to resolve. | Project Manager | Wave 15 has been reviewed and will be considered for Social features | 2012-03-19 |  | FALSE | 0 |  | TRUE | 14 | FALSE | FALSE | FALSE | 0 | FALSE | TRUE
I152 | 2012-03-12 | Brett van Gelder | Active | NA | Currently MSFT Program Architect (Vel Stoyanchev) is a key resource on the business blueprint activity. This role is resourced and funded through the MCS PMO and is a key role across the entire M&C Program including TF, UC etc. Focus on blueprint has an impact on other items not getting the same level of focus. | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 03. Moderate | Brett van Gelder | Alan | M&C Program |  | Work with MCS to re-assign resources to balance focus.Blueprint project needs to document their resource requirements so that they can be considered and resourced relative to other work. | 2012-04-06 | 2012-04-06 | Note: Required Resolution Date set for end of 30 Day Plan, but this can't be actioned without resource plan from blueprint. 13-Mar: Required resolution should be by the time that the plan is agreed as this needs to be documented out of the blueprint requirements. Blueprint project needs to document there resource requirements so that they can be considered and resourced relative to other work. Brett is the owner, but escalation is to Alan/Guy who own the MSFT PMO engagement budget from where the MSFT program architect is funded. 12-Mar Brett: current action - Discussions with Vel and MCS PMO to establish/clarify role and focus | Program Director |  |  |  | FALSE | 0 |  | FALSE | 10 | FALSE | FALSE | FALSE | 15 | FALSE | TRUE
I73 | 2011-12-06 | unknown | Active |  | Lack of clearly defined roles and responsibilities. Will either have duplicate work or work not being done. Right people are not being engaged, morale is suffering. | 04. High | 04. High | 04. High | 04. High | 04. High | Work Stream Managers/Ian Bourne | Ian Bourne | M&C Program |  | Workstream leads to created goals for direct staff and then for these to be cascaded to their teams. PMO to track progress | 2012-03-23 | 2012-03-23 | 12th March 2012 - Ian B - R&R's to be resolved as part of 30 day plan excercise. 15-Feb: Ian - Using the goals process to determine roles/responsibilties. Much progress has been made and further action on this underway. Review in 2 wks. 25-Jan: Still up to the leads; some of this will be thought out in the replanning occurring presently. Review in 2 weeks. 11-Jan: Ian continues to chase, but this really comes down to program leads. These are based on the objectives Alan sent out prior to the holiday. If the leads don't have this, they can get it from Guy. Review 2 weeks. 04-Jan: Ian chasing on behalf of Alan and Guy. Al sent out goals and expectations documents; he said this may change, at least for Lync and Exchange. This is primarily up to each project lead to manage. 19/12/11 - Ian said this is being tracked within each workstream. Stays open, will be ongoing. 14/12 - Program is doing a deep dive on the 8th and 9th of January to discuss. 07/12 - Assigned to Ian (as opposed to Guy and Alan). He is currently working a program org chart; subsequently address roles and responsibilities and roles within program. Review next week. 06/12 - Issue opened. | Program Director |  |  |  | FALSE | 0 |  | TRUE | 107 | FALSE | TRUE | FALSE | 1 | TRUE | TRUE
I90 | 2012-01-06 | Steve Jelf | Active | NA | Dependency alignment is 31%. . No traction being made on reducing the outstanding dependencies. | 02. Low | 03. Medium | 04. High | 01. Undecided | 04. High | Steve Jelf | Steve Jelf | M&C Program |  | Plan a gradual increase and expect to be at least 50% aligned by 5th April | 2012-04-05 | 2012-04-05 | 17th March - As expected, dependencies have reduced in alingment due to new plans being submitted. Resolution will be (a) Ensure Org restructure is known to determine if dependencies still exist. Secondly fortnightly meetings occuring on aligning dependencies throughout the M&C program 7th March - Dependencies are still likely to reduce over the next weeks whilst plans are now being refined based on potential org structure changes. 29th Feb - Dependency Alignment will dip further over the next 2 / 3 weeks as new plans replace the originals. Dependency alignment meeting with key external programs booked every 2 weeks from 15th March 15th Feb - Dependency alignment reduced to 51% - SharePoint and TF Lync plans are effectively shelved and a new plan is being constructed. Dependencies will be mis-aligned at least until 1st March, 31st Jan - Dependency alignment 58%. 2 plans will be dropped (Lync and SharePoint) as a complete replanning exercise is required. Therefore dependency alignment is projected to drop further. 23rd Jan - Dependency alignment 53%. There are a number of dependencies that could be aligned , but due to significant replaninng tasks being undertaken, current plans are effectively shelfed at this point. 17th Jan - Dependency alignment 49%. This will continue to drop as plans need validation. 11-Jan: Steve thinks got up to 60% this week, but this will probably reduce as replan on account of BPOS. As for a req. resolution date, this is dependent on re-planning of the SP and Exchange streams. For now, TBD; review again end of February. 06th - Jan. Dependency management meetings held with M&C Program Managers and external programs every 2 weeks, but in certain work streams sufficient priority isn't given to resolving this. | Program Manager |  |  |  | FALSE | 0 |  | TRUE | 76 | TRUE | FALSE | FALSE | 14 | FALSE | TRUE
I97 | 2012-01-18 | SP & EM DA | Active |  | We do not currently have in place the mechanisms for tracking, storing and reusing assets and components. The work to create the necessary process is underway but will take some time. EYD, FAST and M&C are all tracking this item within program RAID logs. There is therefore a risk to these programs, across these programs and to the firm as a whole that standardization of components and reuse of standardized assets will not be as effective as assumed or planned for. |  |  |  |  | 04. High | Michelle Edmonds, Adrian Mickleson, Norm Beard | Michelle Edmonds | M&C Program |  | The work to create the necessary process is underway but will take some time. | 2012-03-07 | 2012-03-22 | 22-Feb: discussion scheduled for FSG meeting 28-29 Feb. Review thereafter. 25-Jan: Michelle said this is sort of on-going; they are taking it up in planning at present. Review mid-Feb; hope to have a Req. Res. Date by end of Feb. 18-Jan: Opened this item; FAST, EYD and MC are all tracking this item in their logs. This was discovered by the SP & EM DA. | Program Manager |  |  |  | FALSE | 0 |  | TRUE | 64 | TRUE | FALSE | FALSE | 0 | FALSE | TRUE
I149 | 2012-03-08 | Michelle Edmonds | Closed |  | No clarity on the whether we are developing a DTU solution or a generic S&D solution | 04. High | 03. Medium | 04. High | 04. High | 04. High | Michael Cliffel | Bob Reiner/ Alan Guthrie | SharePoint |  |  |  |  | 8-Mar : Issue added | Managing Sponsor | Blue print to determine | 2012-03-09 |  | FALSE | 0 |  | TRUE | 14 | FALSE | FALSE | FALSE | -40990 | FALSE | TRUE
I15 | 2011-05-24 |  | Closed |  | TFS / Defect Management Process - HP Quality Centre (QC) has been proposed as a possible defect reporting tool. The team can not confirm timing of tool availability and this direction conflicts with current MS SOW. |  |  |  |  | 03. Moderate |  | Nicole Watson | M&C Program |  |  | 2011-06-29 | 2011-06-03 | 29/06 - Decision was made to move forward with HP QC as the defect tracking tool with an availability date of July 18th. SOW was updated to reflect the change. 5/06 - Making good progress on the interface between TFS and QC. TFS removed from SOW. 01/06 - Working with MS to change the SOW by this Friday. QC will be used across the M&C Program. 25/05 - Team recognizes this will involve a Change Control for SOW due to conflict. Michelle will confirm with Rita that we cannot change it now before it is signed. Final confirmation of QC usage should come soon; Nicky is pushing for it. |  | Decision was made to move forward with HP QC as the defect tracking tool with an availability date of July 18th. SOW was updated to reflect the change. | 2011-06-29 |  | TRUE | 1 |  | FALSE | 303 | FALSE | FALSE | TRUE | -293 | FALSE | TRUE
I150A | 2012-03-12 | Michelle Edmonds | Closed | NA | DTU scope for calendar year 12 delivery needs to be confirmed | 04. High | 04. High | 04. High | 04. High | 04. High | Michael Cliffel | Jeremy Brown | SharePoint |  |  | 2012-03-12 | 2012-03-14 | 12-Feb: Item added. Per Alan release 1 scope can be reduced, but need to confirm scope. 12 - Mar - Out of scope for Phase (release 1) CLOSED | Managing Sponsor |  | 2012-03-19 |  | TRUE | 1 |  | TRUE | 10 | FALSE | FALSE | FALSE | -8 | FALSE | TRUE
I150B | 2012-03-08 | Michelle Edmonds | Closed |  | Lack of clarity on what is in the scope of governance and what is in the scope of WSL's responsibility | 04. High | 04. High | 04. High | 04. High | 04. High | Michelle Edmonds | Alan Guthrie | SharePoint |  |  |  |  | 8-Mar : Issue added | Managing Sponsor | Verified with the Governance leader. | 2012-03-09 |  | FALSE | 0 |  | TRUE | 14 | FALSE | FALSE | FALSE | -40990 | FALSE | TRUE
I98 | 2012-01-18 | Al Grljevic | Active |  | Assumptions and Decisions made to this point in the program need to be revalidated in light of the recent cloud decision. | 04. High | 04. High | 01. Undecided | 01. Undecided | 05. Critical | Laura Murphy / Ian Bourne | Program leads | M&C Program |  | Leads and PMs to review and revalidate all Assumptions and Decisions made to this point in light of the recent cloud decision. The impact of any invalidated items needs to be considered and tracked, and consequent issues, risks and CRs should be opened as necessary. Laura sending weekly update of missing data and data to be reviewed. | 2012-04-05 | 2012-04-05 | 16-Mar: due date should align with close of 30 day plan. 14-Mar: Most Decisions and Assumptions have been reviewed; there remains a chunk to be revalidated that are hinging on a CR (for Tech Foundation) and replanning (SP). Mark said CR backed up a little (was due end of last week) due to Travis's holiday; should be through this week. 22-Feb: Reiterate importance of revalidating these! Laura will schedule indiv meetings where needed to complete. 15-Feb: Laura added place in comments column of assumptions to include name/date of revalidation (22 assumptions); will add column to decisions for date of revalidation (131 decisions). 25-Jan: Laura sending weekly update of what is to be reviewed/filled in. 18-Jan: Opened. All items to be revalidated. | Program Manager |  |  |  | FALSE | 0 |  | TRUE | 64 | TRUE | FALSE | FALSE | 14 | FALSE | TRUE
I121 | 2012-02-22 | Michelle Edmonds/Brett van Gelder | Active | R18 | Due to the lack of a new vision and inability to change, recreating the current "siloed" approach to knowledge tools, rather than creating an integrated solution that can be leveraged firm-wide. With GSS and EYD starting SharePoint initiatives, we now have a growing number of separate solutions. Additional cost of point solutions will may with SP. | 04. High | 04. High | 04. High | 04. High | 04. High | Guy Morgan / Alan Guthrie | Guy Morgan / Alan Guthrie | SharePoint |  | Former mitigation plan (from R18): Strong cross-service line/stakeholder governance model Involving stakeholders in early strategy and feasibility sessions to encourage thinking ahead. Working with vendors and researching best practices to understand the art of the possible Starting with defined business requirements to understand WHAT functionality must be included before discussing how | 2012-02-29 | 2012-03-22 | 19 March - Escalated to executive sponsors 22-Feb: From R18 to I121. what does the M&C Program need to do to coordinate and keep from falling apart? IT Services is not effectlively managing this, along with the fact that we need to stop the demand for services that are undeliverable. This is a CLT-level type discussion. Guy and Alan to own. | Executive Sponsor |  |  |  | FALSE | 0 |  | TRUE | 29 | FALSE | FALSE | FALSE | 0 | FALSE | TRUE
I128 | 2012-03-05 | Michelle Edmonds | Active |  | Need clear direction on the languages to be supported on the content | 04. High | 04. High | 03. Medium | 04. High | 04. High | Michelle Edmonds | Andy Walsh | SharePoint |  | Being managed with Andy on daily standup calls; working with Andy/Governance to get list of languages. | 2012-03-23 | 2012-03-22 | 15-Mar : Decision that more than one language is needed has been provided. Working to get the entire list. 13-Mar: meeting with Msft today; final decision should come today. (LM updated due date from 2011 to 2012) 12 Feb: Currently confirm with Andy and providing follow up analysis to make a decision. | Program Manager |  |  |  | FALSE | 0 |  | TRUE | 17 | FALSE | FALSE | FALSE | 0 | FALSE | TRUE
I129 | 2012-03-05 | Michelle Edmonds | Active |  | Need clear direction on the languages to be supported on the user interfaces | 04. High | 04. High | 03. Medium | 04. High | 04. High | Michelle Edmonds | Andy Walsh | SharePoint |  | Review with Governance Team | 2012-03-23 | 2012-03-22 | 15 March Decision to use more than one langauge provided. Governance to provide the entire list 13-Mar: meeting with msft today; final decision should come today. 12-Feb: Currently working with Andy and providing follow up analysis for him to make a decision. 7 Feb; Added Issue. This needs to be raised to the Governance Team for resolution. | Program Manager |  |  |  | FALSE | 0 |  | TRUE | 17 | FALSE | FALSE | FALSE | 0 | FALSE | TRUE
I130 | 2012-03-05 | Michelle Edmonds | Active |  | Current FAST Notes connector does not meet the business requirement (or Security requirements) | 04. High | 04. High | 04. High | 04. High | 04. High | Stevens Sebastian | Cem Aykan | SharePoint |  | POC to evaluate | 2012-04-30 | 2012-04-30 | 16-Mar: Meeting scheduled for Monday. 15-Mar: on daily stand up call, Michelle gave update she is working with Ed Dale on a plan for how to do this; Andy wants high value Notes connector in release 1. 12-Feb: Currently evaluating another option(Autonomy). Planned POC to validate due 30 April. 7 Feb: Added Issue, currently working on POC to assess viability. Team will be regrouping with WSL and Executive Sponsors to discuss further. | Program Manager |  |  |  | FALSE | 0 |  | TRUE | 17 | FALSE | FALSE | FALSE | 39 | FALSE | TRUE
I150 | 2012-02-09 | Michelle Edmonds | Closed | R122 | Frog user experience deliverables may not achieve desired goals (Phase 1 Layouts) | 04. High | 04. High | 04. High | 04. High | 04. High | Binoy Raj | Jeremy Brown | SharePoint |  | Eric and Kevin to discuss with Frog and Replan UX. | 2012-03-10 | 2012-03-23 | 19 March - Release 1 planning decision has been made with Kevin and EriC 12-Feb: This covers Layouts for Phase 1. 9 Feb: Issue converted from a Risk on 3/9. Mtg with Frog on 3/9 to discuss further | Managing Sponsor | Release 1 planning decision has been made with Kevin and EriC | 2012-03-19 |  | FALSE | 0 |  | TRUE | 42 | TRUE | FALSE | FALSE | 1 | TRUE | TRUE
I151 | 2012-03-12 | Michelle Edmonds | Closed | NA | GAAIT Replacement Front-End confirm that it is in scope for Release 1. | 04. High | 04. High | 04. High | 04. High | 04. High | Michelle Edmonds | Jeremy Brown | SharePoint |  |  | 2012-03-14 | 2012-03-14 | 19 March - Working with GAAIT team to understand - Will not be part of R1 but work will need to go on during that time period 12-Feb: Item added. | Managing Sponsor | Working with GAAIT team to understand - Will not be part of R1 but work will need to go on during that time period | 2012-03-19 |  | TRUE | 1 |  | TRUE | 10 | FALSE | FALSE | FALSE | -8 | FALSE | TRUE
I74 | 2011-12-06 | unknown | Closed |  | Not a clear understanding of how the process currently being used on Blueprint integrates with standard IT methodology. Not a clear understanding of plan and dates being driven to verify that they support the infrastructure and other plans currently underway. May not be able to achieve cost savings and strategic alignment of the Program. | 04. High | 04. High | 04. High | 04. High | 04. High | Michelle Edmonds | Guy Morgan | SharePoint |  | Define Integration with Executive Sponsors. | 2012-03-07 | 2012-03-30 | 13-Mar: Blueprint meeting scheduled for tomorrow, 14-Mar. 12-Feb: Methodology will be engaged to assist. 29 feb: Meeting with MS, blueprinting still not complete. 06/12 - Issue opened. | Managing Sponsor | 16-Mar: On daily standup call, Michelle and Alan confirmed this can be closed; a meeting occurred and the blueprint process is how understood. | 2012-03-16 |  | FALSE | 0 |  | TRUE | 107 | FALSE | TRUE | FALSE | 8 | FALSE | TRUE
I83 | 2011-12-12 | unknown | Active |  | The common SP infrastructure for the firm does not have clear business ownership therefore we need new governance that will be responsible long term for communication of emergency outages and planning for regular maintenance System will not meet expectations post go live as it may not be available (due to an emergency, without prior communication) and patches may not occur per the schedule causing instability | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 03. Moderate | Michelle Edmonds | Mike Laci | SharePoint |  | To be determined via new Support model needed to support Sharepoint | 2012-03-22 | 2012-05-31 | 29-Feb: To be discussed at the M&C Transition Planning mtg in Secaucus. 31-Jan: Added to list of decisions needed by the newTarget Operate Model 25-Jan: Mike has meeting tomorrow with Binu and Mark around infrastructure 17-Jan: In process of integrating with operating model plan. 11-Jan: no owner of Tier 4 long term activities. Mike has put in charge to run this down for Alan overall. Focused on application side of SP. Review when Mike on call next week. 04-Jan: Michelle said this is still open due to external influences. The team said it should be assigned to Mike Laci instead of Guy. Mike not on these calls so maintained Guy's name, as well. Review next week. 19/12/11 - Guy took an action on the dec and assumptions review call to e-mail Chris d'Arcy, copying Alan and John. (LM emd reminder) 12/12 - Opened at the infrastructure meeting | Other |  |  |  | FALSE | 0 |  | FALSE | 101 | FALSE | TRUE | FALSE | 70 | FALSE | TRUE
I96 | 2012-01-17 | unknown | Active |  | Request for accessbility items to be included in scope | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 03. Moderate | Michelle Edmonds | Michelle Edmonds | SharePoint |  |  | 2012-03-14 | 2012-03-22 | 19 March - On it's way to the DA currently in the plans 13-Mar: Further discussions and decisions scheduled to drive this this week. 12-Feb: We are currently evaluating what OOB vs Accessibility will provide to understand customization. 29-Feb: CR has been approved, working on defining standards. Will need to take to the DA as well. 07-Feb: Change request submitted to PMO for approval. 31-Jan: Part of re-plan 25-Jan: Michelle to submit change request 17-Jan: Change request needs to be submitted to accommodate changes to scope. |  |  |  |  | FALSE | 0 |  | FALSE | 65 | TRUE | FALSE | FALSE | 0 | FALSE | TRUE
I16 | 2011-06-01 |  | Closed |  | Timing of Business Resources. Delay to signoff on project documentation (Charter, V&S, and Requirement Specification) and delivery. |  |  |  |  | 02. Minor |  | Jackie Knight / Michelle Edmonds | SharePoint |  |  | 2011-10-12 | 2011-10-15 | 12/10 - close, names have been received and process has been confirmed. 5/10 - Functional Stakeholders to provide names to SharePoint team - this came out of last week's meeting in DC. 28/09 - Program Meeting in DC this week - topic on the agenda. 21/09 - continue to be assessed by Managing Sponsors and Core Team. 31/08 - Issue being monitored and addressed by managing sponsors. Reduce priority to Low. 24/08 - Have been working with Managing Sponsors; continue to monitor. 17/08 - In process; continue to monitor. 10/08 - no update, continue to monitor. 03/08 - Jackie working on engaging with Managing Sponsors about overview/SP training; still open. (Michelle) 27/07 - Jackie owns training going forward. SP Training being planned. 06/07 - Next week is training week for business across the board (Fusion, Managing Sponsors and Chief of Staffs). Training on iterative SDA, SP training, and M&C program overview. 29/06 - Meeting held with Managing Sponsors - next step is to provide training on the iterative development process so they can assign the proper team members. Training to be held on July 7th and 8th. 22/06 - Resources are being assigned but have not received all the names. This is keeping the team from gathering requirements. This risk was accepted and will continue to move forward. 15/06 - continue to work with managing sponsors to assign business leads. 08/06 - Draft of the Org Structure will be discussed next week after design level zero. 01/06 - Managing Sponsors organization structure - need Participants week of 6/13. Currently working with existing business folks. |  | close, names have been received and process has been confirmed. | 2011-10-12 |  | TRUE | 1 |  | FALSE | 295 | FALSE | FALSE | TRUE | -159 | FALSE | FALSE
I113 | 2012-02-08 | Paul Neave / James Harrup-Brook | Active | R9 | As we are almost certainly going to the cloud, there is an issue that end users will not have as rich of a Lync experience based on their local bandwidth capabilities. Will impact timeline and budget. | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 04. High | Adrian Mickleson | Adrian Mickleson | Technology Foundation |  | Work with engineering team to id areas of low, med, high bandwidth. | 2012-03-14 | 2012-06-06 | 15-Feb: Al said they are reviewing this weekly with the engineering team to determine areas with Low, Medium and High bandwidth. Review mid-March. 8-Feb: opened from R9. This risk was outdated as the cloud decision has been made. | Project Manager | [6 empty] | TRUE | 43 | TRUE | FALSE | FALSE | 76 | FALSE | TRUE
I17 | 2011-06-07 |  | Closed |  | Delay in the signing of the SOW / reschedule envisioning sessions. |  |  |  |  | 05. Critical |  | Al Grljevic | M&C Program |  |  | 2011-06-29 | 2011-06-29 | 29/ 06 - SOW's signed and envisioning sessions scheduled. - close issue. 22/06 - The expectation is for the SOW to be signed-off tomorrow (23/06). 15/06 - July envisioning session's hold the date invite sent to workshop attendees. Detailed meeting invites to follow. Rooms confirmed in Secaucus for July. 08/06 - Delays envisioning sessions to July. Adrian and Mark are working on the schedule for July. Another issue is that there are 3 other EY Program workshops that week (Information Security needs to be at all 3). Al will talk with Ken about the other workshops. 07/06 - Final SOW signing delayed to end of June. Envisioning sessions rescheduled to July 11th. |  | SOW's signed and envisioning sessions scheduled. | 2011-06-29 |  | TRUE | 1 |  | TRUE | 289 | FALSE | FALSE | TRUE | -267 | FALSE | TRUE
I18 | 2011-06-01 |  | Closed |  | Absence of Mobile Messaging solution to support Cloud Computing. |  |  |  |  | 05. Critical |  | Adrian Mickleson / Juan Torres | Technology Foundation |  |  | 2011-08-31 | 2011-06-30 | 31/08 - Close. RFP includes three options; on-prem, on-prem with internal cloud managed by external party, straight cloud. Vendors will respond accordingly. Juan still has to meet with Good. 24/08 - Adrian to restate description; will catch up with Juan off-line to talk through potential impacts of solutions. 17/08 - Adrian moving along with RFP, making a requirement in RFP to handle this structure. Timeline of RFP: working toward final this Friday, short list of vendors by Friday. 10/08 - no update, review next week. 27/07 - Juan spoke with Good and they committed a move to web services by 4th quarter. RIM and BES is now an issue for onpremise solution. Open new issue to address EWS support. 06/07 - Juan will send a message on Monday to GOOD that we are not going BPOS but are still looking for a managing service. Since we are going onpremise, are there issues with RIM we need to address? 29/06 - Juan Torres working to receive a response from GOOD - final warning message sent to GOOD. Adrian will reach out to Iggy to figure out the next step (issue RFP to market). 01/06 - T- minus plan proposed to seek alternate solution providers in the absence of dovcumented undertakings from GOOD to support services in BPOS |  | Close. RFP includes three options; on-prem, on-prem with internal cloud managed by external party, straight cloud. Vendors will respond accordingly. Juan still has to meet with Good. | 2011-08-31 |  | TRUE | 1 |  | TRUE | 295 | FALSE | FALSE | TRUE | -266 | FALSE | TRUE
I114 | 2012-02-08 | Paul Neave / James Harrup-Brook | Active | R91 | We have not undertaken an impact assessment that looks at the anticipated required bandwidth from each location with Outlook users to the anticipated site for the relevant Exchange server(s) to determine and/or confirm that adequate bandwidth is available (or will be available) for deployment. | 02. Low | 04. High | 04. High | 04. High | 05. Critical | Adrian Mickleson / Al Grljevic | Paul Neave / Nick Wood / John Murray | Technology Foundation |  | 1. Complete the exercise to review all country connections in to the MPLS cloud. | 2012-04-18 | 2012-04-25 | 7-Mar: LM reqd update, per Al. Paul said there is no update; this is now underway with John Murray. Looking at mid-April completion date. 6-Mar: added due date of 25-Apr. Nrd: mid-April. This will start to come together following call with Steve Yeomans tomorrow. 15-Feb: This is linked to Riverbed; testing will occur in the next 1.5 months; also gathering information from current Riverbed clients. Should have additional information late next week; review 2 wks. 8-Feb: opened from R91. Paul said they are currently trying to initiate this impact assessment. Risk was opened 25-Jan, as identified by Brett and Al. The action is with Paul, Nick and John to complete the exercise to review all country connections to the MPLS cloud. | Project Manager |  |  |  | FALSE | 0 |  | TRUE | 43 | TRUE | FALSE | FALSE | 34 | FALSE | TRUE
I2 | 2011-03-17 |  | Closed |  | The lack of decision on whether the Messaging and Collaboration solution will be implemented on BPOS or on premise is delaying the full program initiation and launch |  |  |  |  | 05. Critical |  | John Costello | M&C Program |  |  | 2011-07-06 | 2011-05-26 | 06/07 - Not going forward with BPOS. Still considering alternatives for Cloud computing. Close this issue and open new issue around alternative price could be more and additional timeline for RFP, etc. 15/06 - SOWs are assumed that we will go BPOS. There is a general risk about contracts not being signed. Require final decision by envisioning sessions in July.1 01/06 - no update from John. Juan commented that he is close to a decision / closing the gap on RIM (1.5 million). This issue will be raised at Friday's IT Steering Committee meeting with John. This is a critical path item for Outlook and we need a decision before the envisioning sessions. 25/05 - Reached an impasse; gap of over 5 million $ not changing. John will meet with MS tomorrow and give them a final date to give us their best price offer. We need to be prepared to walk away if don't close the gap. 18/05 - Meeting held last week; John's statement: it is ok to proceed with BPOS if can resolve issues through negotiation of T+Cs. Regarding the gap, Microsoft sending revised numbers this week. Barb said nothing was resolved with regards to security, depends on Gillian; Barb and Gillian will meet 1-June. Action: Call on Friday to attempt to bring gap reduction conclusion. 11/05 - Final reference call (GSK) yesterday; Martin passed latest TCO calc to Trey; Legal meeting scheduled for today, which will involve John and Gillian. Awaiting John's feedback at this point, then will decide how to move forward. 04/05 - Still working through showstoppers: Exchange-TCO, SharePoint-single data centre, latency; carefully reviewing all info. available to make best decision; if make decision within next 30 days, shouldn't hinder envisioning. 27/04 - John C. to provide update once UK team returns from holiday. 20/04 - KI to send a note to JC to confirm when the final decision will be made. 9/04 - IT team have made a final recommendation to John Costello regarding BPOS. Final decision to be made by John and leadership team. Open actions for the resolution of the outstanding BPOS issues being managed and reviewed on a weekly basis. |  | Not going forward with BPOS. Still considering alternatives for Cloud computing. Close this issue and open new issue around alternative price could be more and additional timeline for RFP, etc. | 2011-07-06 |  | TRUE | 1 |  | TRUE | 371 | FALSE | FALSE | TRUE | -301 | FALSE | TRUE
I20 | 2011-07-27 |  | Closed |  | Timeline for gathering requirements for Tech Foundation and dependencies on Fusion workstream. List of questions that need answered. |  |  |  |  | 04. High |  | Mark Reade / Michelle Edmonds | Technology Foundation |  |  | 2011-08-24 | 2011-09-15 | 24/08 - Close as an issue and mark as normal action item for Mark and Michelle. Create and manage timeline; put deliverable dates around open items by October 1. Rita to work with Mark and Michelle. 17/08 - Recommendations for configuration and setup of other environments continue to come in from Microsoft. Rita provided list of what needs for SP Foundation Vision/Scope to Michelle (will also send to Mark) and if gets info to them quickly, they are targetting Sept. 14 for completion of Vision/Scope docs. 10/08 - Microsoft provided list to Michelle and meeting scheduled for this week. 03/08 - Meetings have been scheduled to discuss what is in each of the SOWs and where the work lies. Need to establish a timeline to agree to the actions Tech Foundation needs to take to meet expectations of Fusion (dependencies). 27/07 - List of questions presented to Fusion. Meeting scheduled to address. |  | Close as an issue and mark as normal action item for Mark and Michelle. Create and manage timeline; put deliverable dates around open items by October 1. Rita to work with Mark and Michelle. | 2011-08-24 |  | TRUE | 1 |  | TRUE | 239 | FALSE | FALSE | TRUE | -189 | FALSE | TRUE
I21 | 2011-08-02 |  | Closed |  | Demand continues within the space that was previously met from Domino/Notes platform. Need a plan / process to effectively manage and fill the gap that will exist between Notes/Domino and SharePoint until SharePoint is a mainstream service / platform. |  |  |  |  | 04. High |  | Adrian Mickleson | Technology Foundation |  |  | 2011-12-07 | 2011-12-14 | 19/12/11 - On Decisions/Assumptions review meeting today, Alan and Guy confirmed this can be closed here. This is being managed outside the M&C program. 30/11/11 - Added due date of 14-December (this was previously blank). Adrian said has impact assessment and deck due to Chris this Friday and a conversation scheduled for Monday. Should have update next week. 23/11 - Adrian had a call with Chris this morning and will have a deck for him next Friday that includes description of the tiers planned for SP Fdtn. Review thereafter. 09/11 - Adrian provided update that call with Chris is scheduled for next week to discuss; looking to include Siggi and John C, as well. 26/10 - No ITS meeting last week; Adrian to raise this week. 19/10 - Adrian to raise to IT SC Friday and DA on Tuesday. 05/10 - Adrian provided date (when infrastructure will be ready) to Chris. Chris to develop strategy. 14/09 - Concerns expressed that this is more of a "watch-out" item than an issue and also that it's not M&C responsibility. The bottom line is the same as previous: Adrian to provide Chris the date when infrastructure will be ready such that other programs can begin building in SharePoint. Chris will then develop strategy. 07/09 Adrian to provide dates to Chris - target date is no later than 23/09 31/08 - There is a need for a process for app requests that would have been built in Notes with a lifespan over 12 months. Adrian to provide Chris the plan dates for when infrastructure will be ready. Chris will then draw up a proposed strategy. 24/08 - Adrian to talk to Michelle and Neil about getting necessary info/update from Vito. 17/08 - Vito is dealing with this front and center, dealing with this through current processes. Leaving as High for update next week from Vito. The team can determine what to do with it thereafter. 10/08 - question raised as to who owns this issue. 03/08 - Current process: If the lifespan of the solution is 12mo or less, Notes viable solution; if greater than 12 mos, go through exception process. Need to cover day day to demand with a consistent process, set an expectation, feed into queue for Fusion, etc. When will SP platform be mainstream technology to be used by any project to deliver their solutions (currently handled with Notes/Domino)? Change Management / Foundation workstreams: BAU SP engineering going forward; does Foundation's infrastructure map up with the functionality planned for delivery (Fusion)? Currently, answer is we are undergoing huge transformation, have an exception process in place, will know exact dates in about 3 months. |  | On Decisions/Assumptions review meeting today, Alan and Guy confirmed this can be closed here. This is being managed outside the M&C program. | 2011-12-19 |  | TRUE | 1 |  | TRUE | 233 | FALSE | FALSE | TRUE | -99 | FALSE | TRUE
I22 | 2011-08-03 |  | Closed |  | Need to figure out how devices such as webcams and headsets will be handled - potentially a headset will be required for each Lync user (everyone?) |  |  |  |  | 03. Moderate |  | Rewa Bouji | Unified Communications |  |  | 2011-11-02 | 2011-11-18 | 07/11 - RB - meeting held on 2 November between UC program team, Engineering, Architecture and Global Procurement. Approach, roles and responsibilities agreed, high level milestone plan drafted for review. Propose risk closed as action plan now underway to resolve. 25/10 - RB: Discussions with F Tinsley-Roy on approach to working with Global Procurement yielded a number of next steps and a process flow has now been developed, alongside the milestone plan, for how the Program will deliver the device ranging piece into Procurement; expected to complete 18 Nov. Still to clarify how Procurement will manage local activities to ensure devices can be secured. 04/10 - R Bouji: Decision taken by the programme to avoid an RFP route and instead provide the compatible devices list and program deployment requirements to Global Procurement who will validate against existing vendor agreements and then work with in-country procurement teams to ensure all in country supply channels are in place ahead of the Lync 2010 UAT deployment. Procurement to confirm acceptance and timeline for completion by end Oct 28/09 - Discussions with Global Procurement and with Architecture continue; unclear whether Procurement have in place a comprehensive view of accessory procurement channels across all countries. RFP decision remains TBD - further discussions required. Update in 2 weeks 21/09 - Revised approach accessories now underway. This will involve putting in place preferred accessories with preferred supplier list and price ranging, which will then require each country to ensure they can procure these as required. Analysis underway with additional BA resource recently assigned to support this. RFP needs still to be determined with Global Procurement and EA. Next update in 2 weeks. 14/09 - Individual who went through this on another project is helping here to gather requirements, RFP process, etc. If have to do an RFP, should take us to December and we'll be able to deliver devices along with pilot. Review again in 2-3 weeks. Updated owner to Rewa Bouji as opposed to Daren W. Moved priority to Medium. 07/09 - Still gathering info; engaged with someone who was responsible for this aspect of other projects. 31/08 - Daren kicked off convo with Juan; helping gather requirements and will then work with procurement on getting it into a document. Will confirm a spec (next couple weeks) and engage with procurement and determine who will fund it. 24/08 - Daren will talk to Peter and Enterprise Architecture next week on how to work forward; Adrian and Martin Versteeg agreed importance of maintaining a quality device. Still don't know who pays for this (so far not in our budget). 17/08 - missed on call; Laura will ask Daren for update. 10/8 - Steve - started process of working with Procurement and Technical Architects - keep tracking weekly 03/08 - What is the policy around this; could be a potential change request to the budget. We are making p to p audio available, maybe video: need to be able to provide these features to users (headset, webcam). Obligation of team to do preliminary analysis. We believe that it is NOT the responsibility to provide (everyone?) with a headset but we will work with Global procurement to build a list of recommended/supported devices which will have to be purchased in-country through the normal channels. Direction required. |  | 07/11 - RB - meeting held on 2 November between UC program team, Engineering, Architecture and Global Procurement. Approach, roles and responsibilities agreed, high level milestone plan drafted for review. Propose risk closed as action plan now underway to resolve. | 2011-11-11 |  | TRUE | 1 |  | FALSE | 232 | FALSE | FALSE | TRUE | -125 | FALSE | TRUE
I122 | 2012-02-22 | James Harrup-Brook | Active |  | Submitting a plan based on 'sample' plan provided by vendor during the RFP process, plans based on high level assumptions and without detailed discovery | 04. High | 04. High | 04. High | 04. High | 04. High | Adrian Mickleson | J Harrup-Brook / Steve Jelf | Technology Foundation |  | Commutate this fact to PMO, revise plan when discovery completed | 2012-04-11 | 2012-04-18 | 14- Mar Target date down selection of Vendor is Mar 23rd 13-Mar: Al confirmed this needs to stay open, due mid-April. Due date moved from 25-March. Vendor selection, planning. 6-Mar: added due date of end of March; NRD end of March. | Project Manager |  |  |  | FALSE | 0 |  | TRUE | 29 | FALSE | FALSE | FALSE | 27 | FALSE | TRUE
I24 | 2011-08-03 |  | Closed |  | MS - Efficiency of review process for Envisioning documentation; need to make sure right EY resources are engaged on calls (2 hours/day planned). |  |  |  |  | 04. High |  | Mark Reade | Technology Foundation |  |  | 2011-08-24 | 2011-08-10 | 24/08 - Close per Mark. 17/08 - 100% Messaging, Lync will be 100% as of Friday. Mark and Rita to discuss off-line (Friday) an efficiency strategy as continue with SharePoint Foundation and move into subsequent phases. 10/08 - MS reported that they are still having issues with review process and appropriate people being available. Continue to work with Mark to drive efficiency, review again next week. 03/08 - MS (Rita) needs Mark to send list of appropriate invitees by workstream for document review calls. |  | Envisioning complete. | 2011-08-24 |  | TRUE | 1 |  | TRUE | 232 | FALSE | FALSE | TRUE | -225 | FALSE | TRUE
I25 | 2011-08-03 |  | Closed |  | Limited EY Resource availability for review of documentation and deliverables due to vacation. Will impact Vision & Scope, SOWS, planning. |  |  |  |  | 04. High |  | Mark Reade / Adrian Mickleson / Michelle Edmonds | Technology Foundation |  |  | 2011-08-31 | 2011-08-10 | 31/08 - We have passed the critical point on this; can close. 24/08 - Addressing now; review next week. 17/08 - Expecting to conclude reviews for Lync and Messaging Friday. Missing piece: In Brett and Juan's absence, Chris d'Arcy's ok to move forward in their absence is pending. Adrian still trying to contact him. 10/8 - Impacting timeline - teams are working to provide coverage - EY provided fill-in resources. Keep open and review next week. 03/08 - Action: Mark to update agenda of who is available which weeks. Adrian work with Rita on new calendar. Adrian and Michelle determine impact on planning. |  | We have passed the critical point on this; can close. | 2011-08-31 |  | TRUE | 1 |  | TRUE | 232 | FALSE | FALSE | TRUE | -225 | FALSE | TRUE
I26 | 2011-08-09 |  | Closed |  | Need sign off names from Advisory, IT Services and Markets for the Charter and Vision & Scope by workstream/ Solution. |  |  |  |  | 04. High |  | Guy Morgan | SharePoint |  |  | 2011-08-31 | 2011-08-10 | 31/08 - Names have been provided. This issue can be closed. 24/08 - Still working; nothing formalized yet. Review next week. 17/08 - Advisory and IT Services ok. Markets outstanding. 10/8 - Michelle / Guy working with Managing Sponsors to receive names. |  | 31/08 - Names have been provided. This issue can be closed. | 2011-08-31 |  | TRUE | 1 |  | TRUE | 226 | FALSE | FALSE | TRUE | -225 | FALSE | TRUE
I27 | 2011-08-09 |  | Closed |  | Microsoft assistance for specifying and building the "Test" environment is in a phase of Technology Foundation that has not yet been started nor funded. This issue has caused the end date of SharePoint to be moved out and the cost of the program to increase as current resources cannot be effective and are waiting to do their work. Need a decision within the next week whether or not to continue with onboarding the testing team. |  |  |  |  | 05. Critical |  | Guy Morgan | SharePoint |  |  | 2011-12-07 | 2011-11-22 | 07/12 - Alan said he and Guy have signed change control; this can be closed. 06/12 - Need decision from Guy. 30/11/11 - Adrian provided update that Guy has a call on this tonight. Review next week. 22/11 - SOW with Guy Morgan 1/11 - SOW still under review by Michelle, Mark, and Rita. 25/10 - The interim test environment that we have will not meet our needs. Environment must be ready to test on Nov 22. 19/10 - Dates from Microsoft will not meet SharePoint timeline. Working with Tech Foundation to determine options. Action to Adrian to work with Mark on CR to get environment set up. 12/10 Discussion to move to 3 Change Controls from 1 (in Draft). 5/10 - SOW still under review by Michelle, Mark, and Rita. 28/09 - Guy returned the SOW to Michelle and Rita to work through the details. 21/09 - SOW changes still in review at the M&C Program Mgmt. No updates received. Michelle and Rita meeting at 5pm today. Currently in Tech Foundation SOW, MSFT has no responsibility to help with test environment; Michelle wants to bring this into scope, requires change request. Per Mark, changed ownership from Michelle/Adrian/Guy > Michelle. 07/09 - RFP sent to Guy for review; meeting this Friday to discuss. 31/08 - Michelle submitted RFP to Guy Morgan this week for review / approval. 24/08 - Rita met with Michelle Monday, putting together proposals. First draft will be written Friday. 17/08 - Rita will talk to Michelle and Guy this week. 10/8 - requires offline discussion - Rita / Adrian / Michelle will address and report back next week. |  | 07/12 - Alan and Guy have signed change control; this can be closed. | 2011-12-07 |  | TRUE | 1 |  | TRUE | 226 | FALSE | FALSE | TRUE | -121 | FALSE | TRUE
I28 | 2011-08-09 |  | Closed |  | Markets has not been able to partipate in the program recently. Following up with them. |  |  |  |  | 03. Moderate |  | Al Grljevic | SharePoint |  |  | 2011-08-24 | 2011-08-17 | 24/08 - Kick-off next Tuesday; close. 10/8 - no update |  | Resolved with kick-off. | 2011-08-24 |  | TRUE | 1 |  | FALSE | 226 | FALSE | FALSE | TRUE | -218 | FALSE | TRUE
I29 | 2011-08-10 |  | Closed |  | IAM are unable to finalise and submit to QRM for approval the complete list of AD User attributes as a standard, until M&C provide Group requirements for Exchange, Lync and SharePoint Original concern was the timescale to get approval from Q&RM would be 4 weeks+. Confirmed as being within a few days, to a week. Impact is High, as the approval process is within the timescale required. Implementation date (6 weeks to production) is well within required timescales (based on current known requirements). Issue a really that we haven't had any further feedback from the SharePoint team. |  |  |  |  | 04. High |  | Bob Cooney/Ken Sponaugle | Technology Foundation |  |  | 2011-11-30 | 2011-12-07 | 30-11 - Confrimation to be provide by the 5th Dec Workshop. NOTE: Agreed on this 30-Nov call that we will close this item since the Q&RM issue has been resolved, and Daren will open a different one around getting SharePoint attribute requirements for communities. 23/11 - Bob will confirm with Ant that they received the AD User attributes and that they have what they need. Opened action. 09-11 - Discussions ongoing between Gerd and Anthony. Ongoing Sharepoint Workshop to define and clraify these requirements 02/11 - Status same; comm went out this week; Ken did not receive. Suggestion to work with _ Ickowitz around comms (Jackie sent to Ken). 26-10 - This is with reference to New "SharePoint Communities" Requirement. Had call with SharePoint PM (Gregory Van Valkenburgh). Been pointed towards Gerd H. Daren to send note to have this raised on this weeks Design Authority Call (which Gerd Attends). 19-10 - Still waiting on SharePoint requirements. Michelle has these. Action for Daren to e-mail Michelle and tell her to whom she should send the requirements. 12-10 - Still awaiting requirements from the SharePoint Team. 04-10 Ongoing dialogue with SharePoint Team to produce their list of requirements. 22/09 - Awaiting SharePoint requirements, inc 1st pass of attribute list. Source is also being requested. Impact is medium, as the approval process is within the timescale required. Impact to be changed to medium. Implementation date (6 weeks to production) is well within required timescales (based on current known requirements). Due date changed from 30-Aug > 31-Oct. 21-09 - Initial set of Attribute List has been sent to QRM for review. 07/09 - Anthony spoke with James; Daren collating high level list of attributes to share with Q&RM to gauge whether they are on the right track. Klara will be involved here, too. Review in two weeks. 31/08 - Have now identified what we need to do in terms of who we need to provide information. Will be scheduling meetings starting tomorrow. 24/08 - Mark and Daren will follow-up with Anthony on his return early next week. Revisit 31 Aug. 17/08 - Mark and Daren will review for next week. 10/08 - new issue - the approval process will not be completed 'soon', and subsequent development efforts around ID Sync and AD Custom schema extensions can not be implemented. |  | Agreed on this 30-Nov call that we will close this item since the Q&RM issue has been resolved, and Daren will open a different one around getting SharePoint attribute requirements for communities. | 2011-11-30 |  | TRUE | 1 |  | TRUE | 225 | FALSE | FALSE | TRUE | -106 | FALSE | TRUE
I3 | 2011-03-21 |  | Closed |  | Delay in agreeing and signing off the Microsoft statements of work. |  |  |  |  | 05. Critical |  | Al Grljevic | M&C Program |  |  | 2011-05-11 | 2011-06-14 | Further SOW reviews planned 5th & 6th April to progress 19/04 - Final reviews scheduled w/c 18th April 27/04 - Signature date still 1 June. QA review 3-6 June. Legal reviews thereafter. 04/05 - 5 out of 6 SOWs in legal. Still waiting on BPOS decision (as such, dependent on resolution of issue 2). 11/05 - Closed and moved to Risks as now waiting on legal sign-off. |  | Further SOW reviews planned 5th & 6th April to progress | 2011-05-11 |  | TRUE | 1 |  | TRUE | 367 | FALSE | FALSE | TRUE | -282 | FALSE | TRUE
I30 | 2011-08-17 |  | Closed |  | EY Fusion SharePoint resources: don't have matching resources for Microsoft employees. Particularly in case of solution architects and Lead Developers. E&Y costs will remain high as Microsoft will need to remain engaged. Not all work is being completed such as release management. True ownership of designs will not be established. | 02. Low | 02. Low | 02. Low | 04. High | 04. High | Michelle Edmonds / HR / Alan Guthrie | Michelle Edmonds / HR / Alan Guthrie | SharePoint |  |  | 2012-02-15 | 2011-04-04 | 25/1 - Replanning will reassess resource needs 03/1 - Continuing to work with HR to hire full time employees. 14/12- Have one of five people in contract after six months. Continuing to review resumes. 06/12 - Updated impact. Costs are being realized. 8/11 - Resumes are being received 1/11 - Job descriptions have been sent to HR for posting, resume review to begin shortly. 25/10 - Received two openings from Mo for full time people and are in process of getting them posted. 19/10 - Guy and Alan took resource requests to Mo for review. 12/10 - Moved to Critical, includes Lead Devs, SP Admin, QA Lead, RM 5/10 - Continue to work with management team to address open resource requests. 28/09 - One additional Solution Architect assigned out of Secaucus. Continue to work with management team to address open resource requests. 21/09 - The approach / engagement model for E&Y Solution Architects across multiple SharePoint projects (Fusion, FAST, EYD, EMF) is in process. 2 Solution Archs requests for Fusion remain open. 14/09 - Solution architects hired; one is starting the 16th. Downgrade to priority=LOW. 07/09 - 2 people starting the 19th (Cleveland). Keep open until they start. 31/08 - Per Brian Blinco, actively interviewing for the 2 open Architect requests. 24/08 - 3 out of 5 positions filled, working to engage these individuals (located in Secaucus). Working with Retain on the other 2 positions. 17/08 - Mike and Rita to talk off-line to solidify list. Michelle has been working to identify resources. |  | Replanning will reassess resource needs | 2012-01-25 |  | TRUE | 1 |  | TRUE | 218 | FALSE | FALSE | TRUE | -353 | FALSE | TRUE
I31 | 2011-08-23 |  | Closed |  | RFP timeline may impact Fusion delivery schedule. A streamlined RFP process is required to meet our aggressive schedule. The Taxonomy management capabilities will not be able to be met out of the box. Early identification of components indicate that a RFP will be required. This needs to be managed in an expedited fashion in order to not delay the effort Per Fusion iteration plan, the Metadata Mgmt tool purchase is required by the end of iteration 4 (11 November). Delay in RFP process would impact the implementation of a Metadata Mgmt tool for phase 1. |  |  |  |  | 05. Critical |  | Scott Machovina | SharePoint |  |  | 2011-10-05 | 2011-10-14 | 5/10 - Attended the DA call to review Metadata Mgmt RFP and received approval to move forward. The team will present back to the DA after vendor reviews. Close as Issue. 28/09 - Fusion team is documenting the RFQ/RFI/RFP process flow to better understand who / what documentation is required. 21/09 - No update on status of IT approval from John Costello. Working with procurement; issue has been raised to Guy but have not heard back. Managing Sponsors are also aware of this. Doubt expressed around 14-October due date. Escalated to Critical. 14/09 - Have not yet received business case approval; continue to fill out RFP questionnaire. 07/09 - Working on RFP questionnaire, waiting for approval. 31/08 - RFP business case submitted to procurement. Next steps: receive approval to proceed with RFP from Procurement team and start filling out the RFP questionnaire. 24/08 - reached out to procurement, rcvd doc to fill out. Will get RFP underway and expedite quick as possible. 23/8 - Greg containing Procurement to start RFP process and also engaging with Strategy on the list of possible products. |  | Attended the DA call to review Metadata Mgmt RFP and received approval to move forward. The team will present back to the DA after vendor reviews. Close as Issue. | 2011-10-05 |  | TRUE | 1 |  | TRUE | 212 | FALSE | FALSE | TRUE | -160 | FALSE | TRUE
I32 | 2011-08-24 |  | Closed |  | TFS - HPQC (ALM) synchronization: no process defined for synchronization. Automated end to end traceability (requirements, dev tasks, test cases, defect tracking) can not be met using two separate tools that don't fully integrate. Impact to resourcing, budget, management and traceability of the overall SharePoint Program. Potentially adding duplicate data entry across the systems. |  |  |  |  | 04. High |  | Alan Guthrie | SharePoint |  |  | 2011-11-09 | 2011-11-23 | 8/11 - Approved by Alan 1/11 - Resource found, waiting for IT Management to approve. 25/10 - Continue to work with teams towards integration. Realization that Phase 1 will be manual traceability. Currently evaluating full mpact and change requests. John Wootton and Msft will discuss. Michelle looking to add people for manual effort. 19/10 - Three interfaces will be built to connect TFS to ALM, team will use manual processes until interfaces are built. Project status reporting will always remain a manual step between the two. 12/10 - Moved back to SharePoint (from M&C Program level). Decision made to use both products. Team currently working on defining flow and quantifying the amount of manual work involved 4/10 - We have not been able to close this issue and therefore we have moved this issue from medium to critical. Though some defects are being synchronized today, complete synchronization between TFS and HP ALM is not yet available for requirements, test cases, and project linking. Additional analysis still taking place. Moving forward: meeting with the two teams, will look at 5 scenarios that depict what they are trying to do. Once they are on the same page around targeted use, can determine how to proceed. 14/09 - Nicky spoke with Rita and this is not a high priority issue anymore. Move to priority=medium. The fundamental issue is automated traceability; Nicky has accountability to work on this and escalate if it becomes more of an issue in the future. 07/09 - Nicky is meeting with Sue Maguire on Friday to discuss; another individual who was contributing has been out the last week. Review next week. 31/08 - Nicky and Michelle will keep moving this forward; Nicky looking at extending the scope / requirements for ALM pilot and production release. Ken mentioned TFS is the enterprise tool for requirement management and is part of the roadmap. 24/08 - Rita opened this; Michelle and Nicky Watson taking this forward for whole TFS Integration. Al will check with Brian Ford and Nicky Watson and report back. |  | Approved. Close. | 2011-11-08 |  | TRUE | 1 |  | TRUE | 211 | FALSE | FALSE | TRUE | -120 | FALSE | TRUE
I33 | 2011-08-31 | Juan Torres | Closed |  | We don't have confirmation of which countries are going on-prem. As part of DCC and Q&RM review it has been decided that data from countries other than the US should not be migrated to the Secaucus data centre. Secaucus Data Centre will be used to host (a) Global Applications (e.g. GFIS) (b) any applications, global or otherwise, containing US client work papers. If a BIA highlights that DR is necessary for any of these applications, the DR site will be Dallas (i.e. relevant data will remain within the US). Toronto data room will be used to host any data originating from Canada and MECASA and Buenos Aires data room will be used to host any data originating from SASA. To host data that could originate from outside of the US into the Secaucus data centre (for example, when moving application data into a new or existing Global Application hosted in Secaucus) would be dependent on the full agreement from Q&RM and GCO. M&C Program will need to enter into discussions with Q&RM and GCO for all data that is not explicitly US in order for the solution to be hosted in Secaucus. If not hosted in Secaucus it is not clear that service continuity or operational capabilities are in place in either Toronto or Buenos Aires to provide the level of service that would be expected from Secaucus causing significant potential timing and cost impact. | 04. High | 04. High | 04. High | 04. High | 04. High | Adrian Mickleson / Al Grljevic | Adrian Mickleson / Al Grljevic | Technology Foundation |  | Get confirmation from business strategy and operations as to which countries we need to build in-country. | 2012-03-14 | 2012-03-15 | 6-Mar: Closed this issue; will track from the decision on the same topic, D92. 15-Feb: Work in progress (working with Siggi and John); open in decisions, as well. will be 1-1.5 months before we understand this. Review 1 month. 11-Jan: Brett said we have the Q&RM report that says with exception of India, others in the red box will be on-premises. Al took an action to provide Adrian a list of countries building in or not building in (this will prob. come from Bob Reiner). Review beg. February. 04-Jan: Review next week; this is mostly resolved but we need Adrian's update (might be just about 8 remaining countries now) 23/11 - Adrian suggested we push review out 2 weeks as more clarity is sought around this. The next round of discussed are scheduled for this Thursday. 26/10 - Adrian said this is complex and at this point sits in hands of Q&RM and Brett. Next review date mid November. 19/10 - Adrian has questions around this. Laura to schedule meeting for Adrian and Brett to discuss. 05/10 - Brett provided updated description/impact. Assign to Mark/Paul to take it forward. Action created to engage with Q&RM for Lync, Outlook and SharePoint to determine exactly which data are restricted from the Secaucus data centre. 22/09 - There is an assumption that Secaucus in the data centre for the Americas. There are 16-28 countries that will now require data to be maintained in-country. EA, Strategy and Q&RM are working through the implications to clarify what planning is needed to move forward. 14/09 - Brett sent updated description to Adrian. Action for Adrian to update accordingly. Brett has a colleague who is chairing activities to clarify with Q&RM a far more detailed approach. We won't know the impact until following these activities. 07/09 - A number of discussions going on in Enterprise Architecture to determine what the implications are. Follow-up next week to see if we've determined anything further (Brett). 31/08 - Opened by Juan. | Executive Sponsor | This is being tracked through D92. | 2012-03-06 | D92 | TRUE | 1 |  | TRUE | 204 | FALSE | FALSE | TRUE | -7 | FALSE | TRUE
I34 | 2011-09-07 |  | Closed |  | Need to receive/distribute ID Sync SOW from Microsoft and determine approval process. Until this has occurred, the team can not progress with ID Sync. |  |  |  |  | 04. High |  | Ant, Daren, Ken, Rita | Unified Communications |  |  | 2011-09-14 |  | 14/09 - Received SOW from MS, reviewed and had review with Microsoft this afternoon. John Bruce will incorporate revisions and provide update by end of week. Close this issue. 07/09 - Opened issue. Rita is following up on this SOW to ensure ready to distribute. She will send it to Ant for wider distribution. Review next week. |  | 14/09 - Received SOW from MS, reviewed and had review with Microsoft this afternoon. John Bruce will incorporate revisions and provide update by end of week. Close this issue. | 2011-09-14 |  | FALSE | 0 |  | TRUE | 197 | FALSE | FALSE | TRUE | -40990 | FALSE | TRUE
I35 | 2011-09-14 |  | Closed |  | Group Management solution is required to manage the Active Directory groups prior to commencement of UAT, Lync and Outlook. Assuming we get procurement sign-off at the end of Nov, this give us 2 weeks to get this into production (based on current dates of 6th Jan), and 6 weeks based on the 6th Feb (and this assumes we wont be impacted by the Jan moratorium) Impact is M&C programme have a drop dead date of the 6th Feb. Affects Lync, Exhange and Sharepoint. |  |  |  |  | 04. High |  | Bob Cooney/Ken Sponaugle | IAM |  |  | 2011-11-30 | 2012-02-29 | 30-11. Contract sorted, progressing this project with suport from Imanami. This Issue should now be closed. 23/11 - Bob said the contract was signed last night by both parties; review this item in 2 wks. 09-11- Group Management Workshop Complete as of 9th Nov 02-11 - Group Management Project is now kicking off, W/C 7th Nov. Drop dead date has now moved back, and thus this project can deliver by 28th Feb, with no impact (as confirmed by Paul N). 26-10 - Pricing has been agreed with Imanami. In fact, license costs have been reduced from $480k down to $280k. Procurement are currently working through the BRET Process. Expectation is that the Project budget is signed off w/e 28th Oct, with project kick-off commencing W/E 4th Nov. Subject to resource availability. IAM are also currently using an Evaluation License from Imanami Re product setup The delivery date is as yet TBC. However, with agreement from M&C Exchange program, we have moved the date back to the 3rd Feb. 19-10 - Imanami have been confirmed as the vendor of choice. Currently negotiating price. Next steps is the licensing agreement etc. Procurement are targeting a completion timescale of circa 2 weeks (2nd Nov). 12-10 - The Team have chosen Imanami as the Vendor of choice. Next step is Customer Relationship Manager to confirm appointment, and then procurement to progress vendor through the vetting process. Current anticipated timescale to complete process is 6-8 Weeks (worst case end of Nov), which puts in jeopardy our delivery date of the 6th Jan. Need support to expedite this process. 04-10 RFPs received & Presentations completed by both Imanami and Quest. Vendor selection due for completion w/e 7th October. Should be removed from risk list 22-09 - Required date from M&C is currently 6th Feb. deliver Date from IAM is currently the 6th Jan. Impact should be reduced to Medium. (IAM team agreed to reduce priority from Crit > Med.) Vendor presentations have been set up for 28th/29th Sept. 21-09 - Vendor responses received, and currently being Scored". Vendor choice due W/C 3rd Oct. 14/09 - Closed as Risk 33 and opened as a Critical Issue. Prior update as Risk: 07/09 - RFP responses received and are currently being evaluated. Program interdependency stated in enterprise plan. |  | Contract sorted, progressing this project with suport from Imanami. | 2011-11-30 |  | TRUE | 1 |  | TRUE | 190 | FALSE | FALSE | TRUE | -22 | FALSE | TRUE
I36 | 2011-09-19 |  | Closed |  | RFP timeline may impact SharePoint delivery schedule. A streamlined RFP process is required to meet our aggressive schedule. The SharePoint Social Features capabilities will not be able to be met out of the box. Early identification of components indicate that a RFP will be required. This needs to be managed in an expedited fashion in order to not delay the effort People workstream requirements will go to hold as of the end of Iteration 3, 16th Dec. |  |  |  |  | 05. Critical |  | Alan Guthrie | SharePoint |  |  | 2011-12-07 | 2011-12-14 | 07/12 - Michelle said they had thought they needed Alan's decision, but this was resolved with John Costello. Close. 06/12 - Need decision from Alan. 05/12 - Team had thought this was approved to proceed and closed the item after 4-Nov, but it is not and SP team needs to do some further analysis on it. Working on it again now. Reopened with Priority = High. Michelle = owner, due date next week's call date, 14-Dec (was previously 31-Dec). 4/11 - Executive sponsor decided to move forward with the RFP in progress 1/11 - Waiting on Executive Sponsor decision 19/10 - Microsoft meeting 26th or 28th of October, drafting RFP in case decision is to proceed. Downgrade to Medium. 12/10 - Escalating to Microsoft Management (Sales and Delivery) 5/10 - Documenting requirements / gap analysis for Functional Stakeholder presentation. Next steps are to get MS roadmap in this space. 28/09 - Fusion team is documenting the RFQ/RFI/RFP process flow to better understand who / what documentation is required. 21/09 - Available options to be presented to Managing Sponsors next Thursday for review and approval to begin the RFP process. Doubt expressed around 14-Oct due date. Escalate to critical. 19/09 - Opened by Greg. |  | Resolved with John Costello. | 2011-12-07 |  | TRUE | 1 |  | TRUE | 185 | FALSE | FALSE | TRUE | -99 | FALSE | TRUE
I37 | 2011-09-21 |  | Closed |  | There is a general lack of definition of accountability of the EY and MSFT architects. There is no clear understanding of where the accountability for design and delivery lies |  |  |  |  | 05. Critical |  | Michelle Edmonds/Brett van Gelder | M&C Program |  |  | 2011-10-05 | 2011-09-28 | 5/10 - Roles and Responsibilities defined by Michelle E., Brian B., and Brett. Brett also presented new Enterprise / Solution Architecture Shared Architecture Teams model in the last DA meeting. Issue can be closed. 21/09 - Opened by Al. We are looking for absolute clarity here: Michelle and Adrian (for Fusion and UC, respectively) will send e-mails to Guy and cc this group around how they came up with MSFT's responsibilities in creating the SOWs. (Michelle sent email 21/9, awaiting response) |  | 5/10 - Roles and Responsibilities defined by Michelle E., Brian B., and Brett. Brett also presented new Enterprise / Solution Architecture Shared Architecture Teams model in the last DA meeting. Issue can be closed. | 2011-10-05 |  | TRUE | 1 |  | TRUE | 183 | FALSE | FALSE | TRUE | -176 | FALSE | TRUE
I38 | 2011-09-21 |  | Closed |  | Agreement of MS CR for SharePoint Foundation Resources assigned to Planning and Design are required to document requirements to baseline Fusion requirements until end Oct. This will delay the start of D&P by 6 weeks |  |  |  |  | 04. High |  | Mark Reade | Technology Foundation |  |  | 2011-10-05 | 2011-10-14 | 05/10 - CR redrafted to include Fusion and SPF changes, awaiting agreement within ITS, due for release to MS 6/10. Team determined that this is a duplicate item, close. 28/09 - Approach for Planning & Design discussed with MS PM. MS identifying activities in P&D that are not dependant on further Fusion requirements and will highlight those that need to evolve further. MR to draft CR for discussion with Michelle and Al with a view to maintaining momentum of P&D whilst still supporting Fusion 22/09 - Rita met with Guy yesterday and Michelle this morning; this is moving along but will impact timeline. Agreed that Mark should own this (infrastructure issue that should be owned by infrastructure group). Michelle is helping it along also. Al deemed this a priority for today and tomorrow; PM to ensure this gets distributed/approved appropriately. Al will forward Mark copy of CR. Move from Critical to High. 21/09 - Opened by Mark. |  | 05/10 - CR redrafted to include Fusion and SPF changes, awaiting agreement within ITS, due for release to MS 6/10. Team determined that this is a duplicate item, close. | 2011-10-05 |  | TRUE | 1 |  | TRUE | 183 | FALSE | FALSE | TRUE | -160 | FALSE | TRUE
I39 | 2011-10-04 |  | Closed |  | The locations of the global and in country SP Farms and what information is allowed to be placed in each location Examples: North America non US client data should be housed in Toronto as a main data centre not Secaucus. As a team we need to confirm that operations, network, capacity, etc. are all ready in the Toronto DC to accept the work. Certain types of people data cannot be transferred out of country so how will this impact the People Profiles and the ability to find people globally and the servers needed to support that. |  |  |  |  | 05. Critical |  |  | SharePoint |  |  | 2011-10-05 |  | 04/10 - Opened by Michelle. Changed to a RISK 05/10. CLOSE HERE. |  | Was changed to a risk and not needed to be tracked here. Close. | 2011-10-05 |  | FALSE | 0 |  | TRUE | 170 | FALSE | TRUE | FALSE | -40990 | FALSE | TRUE
I4 | 2011-04-01 |  | Closed |  | A number of prerequisites activities will need to be completed in time for the commencement of the SOWs Decided 11-May that this issue will be specific to "Active Directory" work. |  |  |  |  | 04. High |  | Adrian Mickleson / Daren Wicks | Technology Foundation |  |  | 2011-08-24 | 2011-06-08 | 24/08 - Closed as an issue and opened as Risk 47 as this has gone from being an issue to a Risk. 17/08 - Daren working with leads from channel programs (e.g., GCL5) to gather requirements specific to AD, hopes to have completed by next week. Bob: first cross-program dependency meeting today; each have agreed to meet independently, discuss and clarify dependencies and meet back to discuss next week. Focusing on critical dependencies, defined as due in next 6-8 weeks. 10/8 - Steve - first plans coming from IAM - Daren Wicks has been loaned to IAM to help form plans, continue to track weekly. 3/8 - IAM need a plan and a Project Manager to complete the work on the various Streams for M&C, IAM- Ken Sponaugle to confirm arrangements for PM resource? Daren Wicks will be tracking for M&C. Milestones will be adjusted by this Friday (8/5- Bob). 27/07 - Steve says Envisioning completed, most of the activities will be completed by the IAM Group in co-operation with M&C 06/07 - Steve AD review and analysis work is ongoing, with the object of getting as much information before envisioning. Part of the envisioning workshop. 29/06 - Steve reported that final 12 hours of MS ITAP time spent on AD Attribute analysis report. IAM needs to Plan how to take ownership of the global attributes and start to communicate that Plan to current owners, will need Sponsor buy-in. Needs to be in hand before Envisioning gets started. 22/6 - Work agreed to use 12 days Microsoft Time left from ITAP for Attribute collision analysis. 15/06 - Steve mentioned that Anthony / Adrian went back to ITAP work. Verbal closure on the last 3 items, written closure on the first 14 items. Attribute reuse will need to work with MS - 2 phased approach under ITAP: 1st is high level analysis which was complete, 2nd part to build into each and every user object (more detail analysis required). Work with Bob Held, Raymond Cansick, prior to going back to MS. 08/06 - Steve reported that MS hasn't finished the ITAP analysis so we still need the analysis and an effort in place to remediate application's atttributes. Adrian to follow-up wih MS for next steps. 01/06 - Scripts were run and there is a meeting tomorrow to review the analysis. Initial feedback is that there are a few issues. ITAP SOW analysis complete - meeting to review analysis. 25/05 - Still due by 27-May and on track; had a hiccup in that Discovery scripts were not run last wknd, but rather yesterday and day before. MS will use the scripts to ensure there are no red flags. 18/05 - Prereqs on track through ITAP SOW. AD workshop next week. On track to complete by 27-May. 11/05 - About 60% through impact analysis doc. Target moved back a week from 20 May. Still looking at 6 month duration for AD work, will have update at culmination of ITAP. 04/05 - There is a massive dependency on AD. AD workshops going on now. Interim SOW seeking to determine full impacts of AD; won't know all until Interim SOW ends, approx. 2-3 wks. Estimate 6 mos for AD to be up and running. Ken: Action to look into the 6mo. estimate: is this accurate? 27/04 - Ken's team has made much progress in the creation of a prerequisite plan. Michelle, Adrian, Nikki, Brian, and Nick: Leads to sit down and determine resource needs. Al would like a list of the categories of items we hope to achieve (not too much detail in this list). Once UK team returns from holiday, will set up calls to initiate. 19/04 - further planning sessions this week Update 08/04 - kick off session to agree plans to complete prerequisite activities. Collate all prerequisites tasks, including those in the SOW, and create a plan to complete them. |  | Closed as an issue and opened as Risk 47 as this has gone from being an issue to a Risk. | 2011-08-24 | R47 | TRUE | 1 |  | TRUE | 356 | FALSE | FALSE | TRUE | -288 | FALSE | TRUE
I137 | 2012-03-07 | Klara Neginsky | Active |  | In the case that there is a break/error in the communication between the designated Domain Controllers for O365, O365 requires a "fall back" route to establish a connection with another DC within the EY Environment to maintain the service. The fall back could be to any DC anywhere in the world, potentially exposing security weaknesses in the EY network and impacting on the performance experience for Users using cloud services. | 02. Low | 05. Critical | 04. High | 04. High | 05. Critical | Paul Neave |  | Technology Foundation |  | Set up "secure DCs" within the GDCs as the fall back route for O365 DCs | 2012-03-08 | 2012-03-16 | 09-Mar: In Discovery doc for Messaing O365. 08/03/12 - Early feedback from Microsoft is the "secure Daces" option is not acceptable to O365. If this is the case EY will need to upgrade 418 DCs to NTLMv2 and remediate many applications in the process. 07/03/12 - Potential issue with the "secure DCs" as will include data currently not able to be managed outside the local country (Canada, Japan) | Program Manager |  |  |  | TRUE | 1 |  | TRUE | 15 | FALSE | FALSE | FALSE | -6 | FALSE | TRUE
I41 | 2011-10-10 |  | Closed |  | SharePoint physical Build server needs to be built and development ready. Impact to the development cycle and deployment of builds across the SharePoint program. |  |  |  |  | 03. Moderate |  | Michael Cliffel | SharePoint |  |  | 2011-11-02 | 2011-11-01 | 1/11 - Completed 31-October. 25/10 - Build server currently in process, targeted delivery is Friday. 19/10 - Build server request was processed on the 18-Oct 12/10 Currently working to obtain EAM resource to assist with infrastructure buildout. |  | Server built. | 2011-11-01 |  | TRUE | 1 |  | FALSE | 164 | FALSE | TRUE | FALSE | -142 | FALSE | TRUE
I42 | 2011-10-10 |  | Closed |  | FROG SOW has not been signed off on. If frog SOW is not signed before Nov 15th, we will miss our June date. |  |  |  |  | 03. Moderate |  | Michelle Edmonds | SharePoint |  |  | 2011-11-30 | 2011-12-01 | 06/12 - SOW was signed off. 22/11 - SOW continues to be in review, pending sign-off. Kickoff TBD. Planning sessions from 29th Nov. 8/11 - SOW in review and being updated. Plan for the kickoff on 28 November 1/11 - Received frog SOW, MSA signed. 25/10 - If frog SOW is not signed before Nov 15th, we will miss our June date. Alan getting things moving here. 19/10 - SharePoint Phase 1 dates are at risk. Looking to get clarity in meeting tomorrow. 12/10 - Expected start date is tentatively Nov. 1, Bob and Kevin are working with Frog Design. |  | SOW signed off. | 2011-12-06 |  | TRUE | 1 |  | FALSE | 164 | FALSE | TRUE | FALSE | -112 | FALSE | TRUE
I43 | 2011-10-10 |  | Closed |  | We need to formalize the process to receive, validate and approve SharePoint invoices from Microsoft. Microsoft may not be getting paid in the time expected. |  |  |  |  | 03. Moderate |  | Scott Machovina Howard Jones | SharePoint |  |  | 2011-10-19 | ASAP | 19/10 - Met internally(with Al and Finance team) to discuss process going forward . 12/10 Scott is following up with Howard to resolve open items. |  | Process determined. | 2011-10-19 |  | FALSE | 0 |  | FALSE | 164 | FALSE | TRUE | FALSE | #VALUE! | #VALUE! | TRUE
I44 | 2011-10-10 |  | Closed |  | We need a formal process to communicate new resource (changes to resources) Roles and Responsibilities across the M&C Program. Communication may be lost. Items may not be delivered on a timely basis. |  |  |  |  | 04. High |  | Guy Morgan | M&C Program |  |  | 2011-11-02 | 2011-11-02 | 02/11 - 2 junior PMs hired, starting Monday. They will take care of this from here. Close item. 26/10 - no update. 12/10 item opened. |  | 2 junior PMs hired, starting Monday. They will take care of this from here. | 2011-11-02 |  | TRUE | 1 |  | TRUE | 164 | FALSE | TRUE | FALSE | -141 | FALSE | TRUE
I45 | 2011-10-10 |  | Closed |  | Communication from Functional Stakeholder meetings needs to be disseminated across all teams (currently inconsistent). Causes confusion across the Team. Also creates churn. |  |  |  |  | 04. High |  | Guy Morgan Jeremy Brown | M&C Program |  |  | 2011-11-09 |  | 09/11 - Comms lead and PM starting in near future; can close this item per Al. 26/10 - no update. 12/10 item opened. |  | Comms lead and PM starting in near future | 2011-11-09 |  | FALSE | 0 |  | TRUE | 164 | FALSE | TRUE | FALSE | -40990 | FALSE | TRUE
I46 | 2011-10-12 |  | Closed |  | SOW for ID Sync has not been signed off which is impacting our ability to engage Microsoft, and hence progress the project which is an Inbound dependency to M&C Impact could be the delay to Lync/Exchange Testing which is due to start on 6th Feb |  |  |  |  | 02. Minor |  | Bob Cooney/Ken Sponaugle | IAM |  |  | 2011-11-02 | 2012-01-31 | 23/11 - Bob confirmed this can be closed. 02-11 - ID Sync SOW has now been signed off. Issue can be closed 26-10 - Expected SOW sign-off is W/E 28th Oct. Setting up Envisioning workshop with the E&Y team and Microsoft W/C 31st Oct. IAM have communicated (to M&C) a NEW delivery date of 29th Feb. TBC based on Planning Output session with MS. M&C impact assessment to be carried out and conveyed to IAM. 19-10 - CR is being raised. Review taking place with respect to whether a formal CR is required, or an FYI as IAM budget could potentially subsume the cost. Al said that this needs to be escalated to Adrian and his team as it will impact the timeline. Action created for Bob to send a formal email to Adrian and cc Al and Guy, so that he can raise it to the ITS Steering Committee. 12-10 - SOW is currently sitting with Legal for sign-off. We need this signed off (or confirmation as to why it isn't) so that we can engage Microsoft into progress the project. Current we are essentially at a standstill. |  | ID Sync SOW has been signed-off. | 2011-11-23 |  | TRUE | 1 |  | FALSE | 162 | FALSE | TRUE | FALSE | -51 | FALSE | FALSE
I47 | 2011-10-01 |  | Closed |  | Agreement to resource to Change plan Unable to provide key areas of Business Change support to all 3 programs |  |  |  |  | 04. High |  | Sophie Boiron | Change Management |  |  | 2011-11-02 |  | 26/10 - Approved. Close. 21/10 - All resource requirements approved Recruitment process started 19/10 - Awaiting feedback from Guy's meeting with Mo Osborne. Should have more info end of next week. Sophie/Jackie will update due date and impact columns. |  | resources approved. | 2011-10-26 |  | FALSE | 0 |  | TRUE | 173 | FALSE | TRUE | FALSE | -40990 | FALSE | TRUE
I48 | 2011-10-01 |  | Closed |  | Learning lead to replace Gabrielle Pirzad Learning activities will cease. Momentum will be lost and limited handover will be possible loosing work covered to date |  |  |  |  | 03. Moderate |  | Sophie Boiron | Change Management |  |  | 2011-11-16 | 2011-11-09 | 23/11 - Brigitte Ireland is now officially the M&C Learning Lead. This issue can now be closed. 23/11 - SOW for 5 days for Gabrielle to come back being signed. 09/11 - Jackie suggested since they have approval, reduce priority to Medium. 08/11 - A candidate within EY has been identified and discussions have taken place. Awaiting formal confirmation. Sophie has requested 5 extra days of Gabrielle's time for handover. SoW in process of being raised. 02/11 - No confirmation for learning lead.This will affect CM deliverables around learning, not go live of program. This to be resolved, asap, due next week. 26/10 - Still looking for Gabrielle's replacement. Sophie is working with a few people to see if they can extend Gabrielle until they find someone new. 25/10 - Sophie is talking to people including Knowledge and Learning. Reached every corner of the organisation. No one in place as of today's date. Sophie to discuss with Alan Guthrie re Gabrielle's time for transition TBD. 19/10 - Looking for M&C Learning Lead to replace Gabrielle (contract ends 31 Oct). |  | Brigitte Ireland is now officially the M&C Learning Lead | 2011-11-23 |  | TRUE | 1 |  | FALSE | 173 | FALSE | TRUE | FALSE | -134 | FALSE | TRUE
I49 | 2011-10-01 | unknown | Closed |  | Need to engage with Area representatives regarding the Change network and resource to the plan. Whilst this is pressing it needs to be sensitive to the order of events given that the 'story' for M&C is being developed to engage with Senior stakeholders. Ideally this would be completed first before seeking resource. However timescales will not necessarily allow for everything to work serially. Change network not in place and briefed. Consequently no local impacts and plans can be identified and established. IT implementation may be imposed with little business involvement if we remain with current go live dates | 03. Medium | 05. Critical | 04. High | 02. Low | 04. High | Sophie Boiron | Sophie Boiron/Martin Kremmer | Change Management |  | Area engagement plan produced in January 2012 and activated from 1-Feb-2012 | 2012-03-07 | 2012-03-07 | 06-March - Martin K: Issue closed as all areas are now engaged and it's part of the CH and Deployment plan to engage furhter at a local level. 22-Feb: Currently under discussions about whether change network required to be in place for Lync deployment phase 1. This will remain an issue if have to setup for Lync. This ties in with the Lync vendor work; Brett said there have been some issues with the RFP. Due date ammended from 28-Nov-2012 to 7-Mar-2012 (optimistic target). Review next week. 05-Feb: Engaged with Asia on the propose local network required despite lack of clarity on deployment dates. Further engagement with other areas in progress. 26-Jan: Issue re-opened after discussion on I40 being sp 10-Jan: closed this item into Issue 40. 19/12 - Change/deployment currently putting a plan together to enagage comprehensively at area level starting Feburary. 14/12 -Had meetings with IT relationship managers and there is a call with LIz King tonight to agree on the next steps. Nothing is formally in place. 07/12 - Jackie: had 1st meeting with AsiaPac, working to confirm that Japan IT reps are appropriate, still struggling with EMEIA. The main issue is getting sign-off on baseline requirements. FSG tomorrow afternoon - will detail the problem. Review next week. 30/11 - jackie said have session scheduled with AsiaPac for 5-December. Have some engagement from Americas/EMEIA, but still looking for representatives. Have someone lined up in Japan. Review next week. 24/11: On going discussion with the business team including the business deployment lead on best approach to engage with the business. Initial engagement with AsiaPac on 5th Dec to discuss M&C and gain insight re how to engage with the team in Asia. Jeremy/Adrian and Bob presenting. 9/11 - Call with Sarah Freeman (did change for CRM in ASiaPac) to discuss what they had done. Follow-on call on 10/11 with Sarah and Rebecca Chan (AsiaPac rep for IT). Jackie has drafted a Business engagement process, running through that with Adrian & Rewa. Critical impacts identified. Jackie working with Jeremy to agree what is needed from SAS work on M&C story to then follow-on to the schedule of engagement with Area leads. 8/11 Relationship Area managers meeting M&C (engagement meeting)14/12 Sophie/Jackie following up on next steps (keeping in mind the deployment approach being developped) 02/11 - Rewa has been in touch with Guy. Review in 2 weeks. 26/10 - Review next week. 25/10 - Bob and Jeremy are keen to create the picture of the future before engaging with senior Area representatives. A process is now in place, starting with Microsoft and SAS engagement to develelp the picture/story of future ways of workng for Outlook & Lync. +R1521/10 - Adrian and Jackie have sougght contacts in each area/country. 19/10 - Al requested action to Adrian to update the impact of this item. | Managing Sponsor | Martin K: Issue closed as all areas are now engaged and it's part of the CH and Deployment plan to engage furhter at a local level. | 2012-03-06 |  | TRUE | 1 |  | TRUE | 173 | FALSE | TRUE | FALSE | -15 | FALSE | TRUE
I5 | 2011-04-18 |  | Closed |  | Key EY IT resources spread across multiple work streams, creating a resource bottle neck. |  |  |  |  | 03. Moderate |  | Adrian Mickleson | Technology Foundation |  |  | 2011-07-06 | 2011-06-03 | 06/07 - issue has been mitigated - close issue. 01/06 - Invites going out today. Few challenges setting up the video conferencing. Change completion date to June 3rd and reduce priority to medium. 25/05 - Working through this, particularly with attention to Envisioning sessions, coming in June. To be further discussed in 1-June kickoff, upon receipt of agendas from MS. 18/05 - Resource requests being put into Retain, working to get names assigned. Pinchpt: sessions around envisioning and then BPOS workshop. Need min people to travel for June workshops, rest remote. Had to push a few items back to mid-week instead of all starting 6-June. Agenda will come with the SOWs. Note: items labelled as "spare days" currently will likely be filled. 11/05 - Working through resource scheduling system to ensure not demanding 1 resource in two areas at a time. Moved from High to Critical. Need dates and list of individuals for workshops; establish timeline and share with MS so they can plan their resources and move fwd. 04/05 - Ongoing. 27/04 - Will work continually to mitigate this risk; determine staffing/hours for the coming weeks. Mitigation plan: 1. Ensure all incoming resources provide vacation schedules, 2. Fully update Retain, 3. Maintain an open discussion with regards to external conflicts (e.g., other projects), 4. Each Program Manager to work with PMs regarding resource situations (will also approach business for their holiday info, etc.) 20/04 - identify back up resources during planning Identify other team members that need to be involved in the various workshops. |  | mitigated. | 2011-07-06 |  | TRUE | 1 |  | FALSE | 339 | FALSE | FALSE | TRUE | -293 | FALSE | TRUE
I50 | 2011-10-01 | unknown | Closed |  | As we do not know which applications will be in the first release for A&DM, Change cannot do any further planning No further planning for ADM can take place for release 1. Depending on the size and impact of the selected applications we could be poorly prepared for any change given current timescales. | 03. Medium | 02. Low | 03. Medium | 02. Low | 03. Moderate |  | Neil Sahdev | Change Management |  | Identify and baseline the 15 apps for Phase 1 | 2012-01-25 | 2011-11-28 | 03/01 - List received, work can begin to assertain the implications of these applications from a change perspective. Issue can be closed. 20/12 - Kathryn Bushby BA on A&DM is finalisaing the list and has shared that with the change team in its present form. 15/12 - Sophie/Martin K amd Jackie meeting on change approach 24/11 - Sophie/ Neil/Martin met on 24/11 and agreed on business change workshop to understand impact of ADM on end users to refine the change plan and agree imminent next steps 09/11 - No confirmation at this stage but regular engagement and update with A&DM team. 03/11 - Update from Neil on Application Candidate provides some information on applications identified but initial view is that it is not sufficient for Changeplanning. Jackie to work with Kathryn Bushby (BA) to see if further information is available or can be gathered 26/10 - 5 applications now identified for Phase 1; plan in place to identify and baseline remaining 10 applications. 24/10 Regular updates from ADM. Lkely to be Assurance applications which suggests an Assurance Change network. | Program Director | list received, work can begin to asceratin the implications of the applications from a Change perspective. | 2012-01-10 |  | TRUE | 1 |  | FALSE | 173 | FALSE | TRUE | FALSE | -115 | FALSE | TRUE
I51 | 2011-10-18 |  | Closed |  | Need business analysts for SharePoint workstreams. Issue impacted by recent resource location strategy. Team is managing resoures across workstreams to deal with high risk items, not all items are being completed. |  |  |  |  | 05. Critical |  | Michelle Edmonds | SharePoint |  |  | 2011-12-21 | 2011-12-15 | 14/12 - Continuing to review resumes/interview. 06/12 - Impact updated. 8/11 - One new BA found. New strategy put in place and employee BAs in process of being hired. 1/11 - Will determine how to support, it may affect ability to complete requirements, may not have enough work for coders. 25/10 - Need 3 BA's, talking to Microsoft about one. Guy said when in Cleveland next week will be looking at resource capacity issues. Michelle's team can't support Sec workshops week of 14-Nov. Adrian will talk to Mark about changes to the agenda/attendees of these workshops. 19/10 - Had a call with Todd Andrews and put out resource request to Microsoft. |  | Resolved. | 2012-01-01 |  | TRUE | 1 |  | TRUE | 156 | FALSE | TRUE | FALSE | -98 | FALSE | TRUE
I52 | 2011-10-18 | unknown | Closed | NA | Draft of Deployment Strategy is being affected by lack of resources. Delivery date may be impacted. | 03. Medium | 03. Medium | 04. High | 03. Medium | 02. Minor | Michelle Edmonds | Michelle Edmonds / Mike Laci / Martin Kremmer | SharePoint |  | Update to TM resourcing plan needed | 2012-02-29 | 2012-02-29 | 31-Jan: Currently assessing as part of the re-plan. 25-Jan: Making progress, interviews set up this week. 17-Jan: Have identified a set of CV's for transition for SharePoint. 11-Jan: Mike is recruiting (invited Mike on call starting 18-jan). The deployment strategy will be affected by O365. 19/12/11 - On decisions review call, team determined this should be assigned to Martin Kremmer, as well. 14/12 - On-boarded one resource, continuing to look for more. 07/12 - Michelle - MIke new resource as of Monday that will help with deployment strategy. Mike is working on additional resourcing. Review next week. 4/11 - Requested resources to assist with this effort. 1/11 - Moving forward. Waiting on management to approve resource requests. 25/10 - Meeting tomorrow to address the plan. 19/10 - Issue Opened. Michelle and Adrian to talk off-line and provide summary of decisions next week. | Managing Sponsor | will assess in re-plan | 2012-01-31 |  | TRUE | 1 |  | FALSE | 156 | FALSE | TRUE | FALSE | -22 | FALSE | FALSE
I53 | 2011-10-25 |  | Closed |  | Increase to scope due to EY reference architecture needs. Impact to resources and budget. |  |  |  |  | 04. High |  | Rita Seibel | SharePoint |  |  | 2011-11-30 | 2011-11-11 | 30/11/11 - Rita will update this item with details; have a resource who will work with Michelle's team. Should not have an impact from program perspective. Close. 23/11 - Rita said they are waiting on approval from EY PMO to develop the CR. Review next week. 1/11 - Waiting for Microsoft. 25/10 - Issue Opened. Looking to source with Microsoft. |  | have a resource who will work with Michelle's team. Should not have an impact from program perspective. Close. | 2011-11-30 |  | TRUE | 1 |  | TRUE | 149 | FALSE | TRUE | FALSE | -132 | FALSE | TRUE
I54 | 2011-10-25 |  | Closed |  | Risk that we currently have nothing in plan if Assurance decides to use Ovitas for a Content Management solution. Impact to resources and budget. |  |  |  |  | 04. High |  | Michelle Edmonds/Mike Cliffel | SharePoint |  |  | 2011-11-02 | 2011-11-30 | 1/11 - Met with Assurance(Bob Held, Margaret Walsh), if Ovitas is selected it will be an Assurance run effort and will not be part of our scope or budget. Team engaged delivering on front end. Team will continue to work on Content Management. 25/10 - Issue Opened. |  | Met with Assurance(Bob Held, Margaret Walsh), if Ovitas is selected it will be an Assurance run effort and will not be part of our scope or budget. Team engaged delivering on front end. Team will continue to work on Content Management. | 2011-11-01 |  | TRUE | 1 |  | TRUE | 149 | FALSE | TRUE | FALSE | -113 | FALSE | TRUE
I55 | 2011-10-26 | unknown | Closed |  | Outlook Dormant Depoyment - Additional Testing being requested by Operations regarding the fact that ALL E&Y Machines have Outlook Express, which was previously unknown. Impact is the delivery date of the 7th Feb is in jeopardy. Likely to be delayed by at least 1 week |  |  |  |  | 03. Moderate | Adrian Mickleson | Mike Laci | M&C Program |  |  | 2011-11-23 | 2012-02-07 | 30-Jan: Mike confirmed this can be closed. 09/11 - Martin V. approved some changes to testing requirements. No affect on timeline; reduce priority to medium and set date out two weeks. 26/10 - During Testing, it was found that every E&Y machine has Outlook Express. We have been infomred by Martin Versteeg that we need to carry out additional testing. This will delay the project, and put in joepardy our current delivery date. We are running "Metering" to determine how many users are using Express, how often etc. Initial output due w/e 28th. If low use. Will look to NOT carry out addiotnal testing. Daren taking action to set up meeting with Guy, Al, himself and operations to discuss impact, issue, delay and make decision. |  | 30-Jan Mike Laci: It was agreed with Martin V. that we would create and publish a Tier 1 TSC article that would outline the steps to upgrade to and activate Outlook 2010 dormant installation. This article was created and is published. | 2012-01-30 |  | TRUE | 1 |  | FALSE | 148 | FALSE | TRUE | FALSE | -44 | FALSE | TRUE
I56 | 2011-11-01 |  | Closed |  | The SharePoint Foundation team used knowledge of current service delivery efforts and has specified an environment for external collaboration. If during requirements ECMA significantly varies from this the infrastructure will have to be redesigned Re-design |  |  |  |  | 04. High |  | Bob Reiner | SharePoint |  |  | 2011-11-22 | 2011-11-14 | 22/11 - Issue moved to risks 7/11 - Meeting scheduled for next week in London 1/11 - Issue Opened |  | Moved to risks. Close. | 2011-11-22 |  | TRUE | 1 |  | TRUE | 142 | FALSE | TRUE | FALSE | -129 | FALSE | TRUE
I57 | 2011-11-01 |  | Closed |  | Need business lead for Communities workstream. Team can't get through requirements in the time alloted for each iteration. |  |  |  |  | 03. Moderate |  | Michelle Edmonds | SharePoint |  |  | 2011-11-02 | 2011-11-04 | 3/11 - Name provided issue closed 1/11 - Issue Opened. Cindy Hope to provide Michelle a name by the end of the week. |  | Received name. | 2011-11-03 |  | TRUE | 1 |  | FALSE | 142 | FALSE | TRUE | FALSE | -139 | FALSE | TRUE
I58 | 2011-11-01 |  | Closed |  | The business has not been availble per our original plan due to resources being assigned to more than one workstream. Schedule will move out or we find more resources. Could make more progress if we had a business leader for each workstream. |  |  |  |  | 03. Moderate |  | Michelle Edmonds | SharePoint |  |  | 2012-01-01 | 2011-11-14 | 8/11 - Altering schedules of the People and Communities workstreams to fit the communities lead schedule 1/11 - Issue Opened. |  | Altering schedules of the People and Communities workstreams to fit the communities lead schedule | 2011-11-08 |  | TRUE | 1 |  | FALSE | 142 | FALSE | TRUE | FALSE | -129 | FALSE | TRUE
I59 | 2011-11-01 |  | Closed |  | Need to confirm Microsoft Application Transformation Project Start Date Need to schedule/confirm resources |  |  |  |  | 04. High |  | Martin Stutchbury / Guy Morgan | App and Data Migration |  |  | 2011-12-07 |  | 7/12/11 - Date moved out to March 2012 due to candidates being put on hold by the business (busy season for audit). On the call, Martin discussed with Alan - this is not an issue for EY. Msft had SOW months ago but we haven't started. Not an issue. Close on log. 30/11 - Hoping requirements for Phase 1 completed before xmas. Had told Msft not until January; hoping to have an answer next week; remove "SP" from item description. 09/11 - review in two weeks. 1/11 - Rita Seibel - Need to confirm Project Start Date (est. Mon 11/28) 22/11/11 - Meetings held with MS w/e 18/11/11 to advise that start date will be in New Year (exact date TBC nearer the time) |  | Not an issue for EY. | 2011-12-07 |  | FALSE | 0 |  | TRUE | 142 | FALSE | TRUE | FALSE | -40990 | FALSE | TRUE
I6 | 2010-11-10 | unknown | Closed |  | The information needed to profile the users is not available in the HR systems to the level of detail needed by the new EK solution (Geography, Rank and Service Line) Need to get the data updated in these systems and a process to keep it up to date going forward Bad data quality. | 02. Low | 02. Low | 02. Low | 02. Low | 03. Moderate | Michelle Edmonds | Michelle Edmonds | SharePoint |  | Assessment in process | 2012-03-14 | 2011-04-04 | 15 March - Data quality will be handled at hte source 13-Mar: LM emd for resolution description. 31-Jan: Design needs to be reworked pending Cloud principles, set next review date after plan has been recast. 19/10 - Design of interface in process. Testing of Iteration 1 will determine quality of data. 12/10 - Requirements gathering underway to confirm list of data 5/10 - no update but still an open item. 28/09 - no update. 21/09 - still an issue, no update. 06/07 - The People and Communities Team will asses the true impact around end of July. There is currently conflicting data between systems. 27/04 - Mitigation today on morning SOW call, lower priority now. 20/04 - Michelle to provide feedback Note that this issue has been documented a dependency in the business case as it will need to be fixed in order for the team to realize the benefit of this effort. | Program Manager | 15-Mar Michelle: Data quality will be handled at the source. | 2012-03-13 |  | TRUE | 1 |  | FALSE | 498 | FALSE | FALSE | TRUE | -353 | FALSE | TRUE
I60 | 2011-11-01 | unknown | Closed |  | Need EY to provide data required for Lync Functional Specification Lack of input will affect quality of Lync Functional Specification document |  | 02. Low | 02. Low |  | 03. Moderate | Juan Torres | Juan Torres | Unified Communications |  |  | 2012-02-08 |  | 28/02/12: RB: JT confirmed ok to close 6-Feb: Juan is waiting on a final confirmation on a few loose ends from James, and will then consider this closed. From a DA perspective, the document has been reviewed and approved. Although the functional spec is missing some pieces that we should have been able to add via the CR process (for example, Alcatel integration and details for Enterprise video), that has proved challenging. 18/01/12 - Lync Functional specification now delivered by Microsoft, under review by UC DA members. Lync configuration requirements due to complete end January 2012 11/11 - R Bouji - BA now assigned to develop Lync functional configuration requirements, working to a deadline of mid-December. Need for functional specification not raised to R Bouji prior to risk being logged. RB to seek clarification from Lync TF team. 1/11 - MCS - The Lync-Planning meeting agendas included information about data needed to develop the functional specification document. This was provided to EY on or about 10/3; As of 11/01, this data has not been sent to Microsoft. | Project Manager | JT: The functional spec has been approved by the project team and UC Design Authority. Although there are some small gaps that might be addressed in the form of a CR, the team was fairly satisfied with the deliverable so I think this one can be closed. | 2012-02-28 |  | FALSE | 0 |  | FALSE | 142 | FALSE | TRUE | FALSE | -40990 | FALSE | TRUE
I61 | 2012-01-31 | Mike Laci | Closed |  | Ongoing issues with the SMS / SCCM deployment environment are impacting the distributeion of Outlook Dormant Deployment. | 04. High | 04. High | 04. High | 04. High | 04. High | Mike Laci | Mike Laci | Technology Foundation |  | Obtain updated timeline from SCCM team for resolution | 2012-02-01 | 2012-02-17 | 8-Feb-12 - Closed. Requirement that the SCCM team clear backloged reporting queue of reporting in the SCCM environment | Project Manager | Agreement to move forward with next test phases with the understanding of possible delays to reporting information. | 2012-02-08 |  | TRUE | 1 |  | TRUE | 51 | TRUE | FALSE | FALSE | -34 | FALSE | TRUE
I61A | 2011-11-01 | unknown | Closed | NA | Quote received from CASAHL for use of their ecKnowledge toolset (required by Microsoft for Phase 1) is prohibitive Unless quote can be revised to a more reasonable figure (i.e. Tailored for Phase 1 only) then EY cannot provide Microsoft with required toolset | 02. Low | 02. Low | 02. Low | 04. High | 04. High | Neil Sahdev | Neil Sahdev | App and Data Migration |  | Work with CASAHL and Msft to obtain realistic quote for Phase 1. | 2012-01-18 | 2012-01-31 | 18-Jan: Rcvd quote from CASAHL that is in line with expectations. Working with procurement to proceed. Resolved here, can close. 18/01 - Revised Phase 1 quote received from CASAHL. Neil to arranging a PO with Finance required to procure the licences. 21/12/11 - Earlier today Neil dropped out a note to Jason requesting an update on the CASAHL quote, specifically the charges to EY. Given the Phase 1 project start-date has moved to the right I suggest moving the due date from 11/11/11 to 18th Jan'12 with a next review date of 4th Jan'12. 14/12 - Waiting on resolution from Jason. 7/12 - No response from Jason Ritchie @ Microsoft. Action opened for Martin to send e-mail again, copy Guy, Alan and Jean-Michel. Review next week. 30/11 - The action sits with Microsoft to resolve; should have an answer by next week. 01/11 - Review quote with CASAHL and tailor in-line with the requirement for Phase 1 22/11 - Revised quote received from CASAHL for Phase 1 is more transparent for licencing - query outstanding with CASAHL / Microsoft with the level of support included in the quote 31/1 - with procurement to progress | Program Director | 18-Jan: Rcvd quote from CASAHL that is in line with expectations. Working with procurement to proceed. Resolved here, can close. | 2012-01-18 |  | FALSE | 0 |  | TRUE | 142 | FALSE | TRUE | FALSE | -51 | FALSE | TRUE
I61B | 2011-11-22 | unknown | Closed |  | Core team sizes have grown beyond original intents. Difficult for team to get work done and difficult to keep people engaged. | 02. Low | 03. Medium | 03. Medium | 03. Medium | 03. Moderate | Michelle Edmonds | Jeremy Brown | SharePoint |  | WSL to define | 2012-04-03 | 2011-12-16 | 04-Jan: Michelle said they looked at this item yesterday and determined in should be moved out to April; this will be a Low ongoing priority. 14/12 - Have elicited new ideas and will be employing them in January. 07/12 - Michelle said there is a conversation scheduled for later today that will help with this. Review next week. 06/12 - Updated to reflect open items. 30/11 - Per Al, changed ownership from Bob Reiner (not an attendee of this call) to Sophie/Jackie. 22/11 - Issue opened. Assigned to address issue in I4 requirements. | Managing Sponsor | Will be addressed as part of the replan | 2012-03-09 |  | FALSE | 0 |  | FALSE | 121 | FALSE | TRUE | FALSE | -97 | FALSE | TRUE
I62 | 2011-11-22 | unknown | Closed |  | Delivery of QA environments scheduled for 1st December did not happen. This issue has caused the end date of SharePoint to be moved out and the cost of the program to increase as current resources cannot be effective and are waiting to do their work. Need a decision within the next week. | 05. Critical | 05. Critical | 05. Critical | 05. Critical | 05. Critical | Adrian Mickleson | Adrian Mickleson | Technology Foundation |  | Norm Beard and Adriian to work on defining the environment needs. Regular calls being set up to manage expectations and needs. | 2012-02-15 | 2011-11-30 | 15-Feb: Nothing can be done about this issue. It is an issue, but the only option is to accept it. Therefore, close here, as there is no point reviewing it. 11-Jan: changed ownership from Mark to Adrian (Mark not on this call). Looking to round off needs for all environments. Review 2 weeks. 04-Jan: Michelle said there is a risk open that is related to this. She will close that risk and include it in this issue. 19/12/11 - Owner = Norm; team reqd Norm and Gerd be invited on the calls. 14/12 - Environment will be ready next week, but interim platform not close to what we need. 07/12 - Working with Al and Mark to see what we can do. There are meetings over the next 24 hours. Review next week. 06/12 - Updated to be assigned to Guy. 22/11 - Issue opened. |  | 15-Feb: There is no resolution plan for this issue as nothing can be done about it. The only option is to accept it. Therefore, the team agreed to close this item in the log. Replanning is in progress at present, so this will be reflected accordingly. | 2012-02-15 |  | FALSE | 0 |  | TRUE | 121 | FALSE | TRUE | FALSE | -113 | FALSE | TRUE
I63 | 2011-11-22 | unknown | Closed |  | Requirements synchronization between TFS and ALM has not been planned nor targeted. Makes traceability of requirements a manual process. Defects not automatically linked back to requirements. Increase cost/decrease quality. |  |  |  |  | 03. Moderate |  | Sue Maguire / Ken Sponaugle | SharePoint |  |  | 2012-01-25 | 2011-11-30 | 25-Jan:Traceability will be manual. 11/01 Currently testing interface between TFS and HP ALM. Review next week after UAT. 06/12 - Expecting response from Ken. 30/11 - Update that this was turned on this weekend; there is a manual workaround in place. Downgrade to meduim, keep date for next week. 23/11 - Scott said the team opened this item yesterday. Since the short term plan does not allow for them to be synced, they are using a manual workaround. Action opened for Nicky to talk to Sue Maguire for dates. 22/11 - Issue opened. |  | Traceability will be manual. | 2012-01-25 |  | FALSE | 0 |  | FALSE | 121 | FALSE | TRUE | FALSE | -113 | FALSE | TRUE
I64 | 2011-11-22 | unknown | Closed |  | Lack of space in the Becket House, London office is preventing the current team from working in a co-located environment and will become an even greater problem in Jan'11 when another 18 resources are due to join the team. Team will have to work from alternate locations (i.e. Alternate EY offices, home...) impacting team's productivity. | 02. Low | 02. Low | 03. Medium | 02. Low | 03. Moderate | Neil Sahdev | Neil Sahdev | App and Data Migration |  | Get more space | 2012-01-25 | 2012-01-31 | 10-Jan - updated all columns; Neil provided new required risk resolution date of 31-Jan (from 28-Oct). Same as below, decision being made which teams will move to new space. 21/12/11 - Alan & Guy have confirmed that additional space has been procured in a nearby office and that a decision will be made by w/e 23/12/11 outlining which team(s) will be moving there and when. The due date should be left 'as is' given lack of space is a current issue and reviewed during the next RAID call (4th Jan'12). 14/12/11 - This issue increases in criticality in Feb'12 when the portfolio teams are onboarded 7/12/11 - Seen email with confirmation of new space acquired, but no further details received. The holiday period buys some time since many will be out of the office. Alan urged Martin and Neil to update this item with the date on which it will become an absolute issue 30/11/11 - As a temporary mitigation, have asked people to work from home on Monday instead of Friday since there is more desk space available on Fridays. This has been escalated to Mo and is being worked on. 22/11/11 - Escalated from a risk (# R66) to an issue. Neil has raised this to Guy and Alan. Review next week. | Program Director | Additional office space procured at Fleet Street, London. | 2012-01-30 |  | FALSE | 0 |  | FALSE | 121 | FALSE | TRUE | FALSE | -51 | FALSE | TRUE
I65 | 2011-11-30 | Daren Wicks | Closed | I29 | Daren will update this issue around getting the SharePoint attribute requirements for Communities.(This is the item that broke off from Issue 29, closed 30-Nov as Q&RM issue has been resolved.) | [5 empty] | Adrian Mickleson | Daren Wicks | Technology Foundation |  |  | 2012-01-11 |  | 01-Feb: Daren said this item can be closed. Project just beginning; Group Management workshop scheduled for next week which will provide the answers Daren needs. 06-Jan: Bob C. confirmed that Daren needs to provide the details for this item. He heard from Anthony Harper that this is 99% mitigated, but Daren will be able to provide more information. |  | 1-Feb: Project just beginning; Group Management workshop scheduled for next week which will provide the answers Daren needs. | 2012-02-01 |  | FALSE | 0 |  | FALSE | 113 | FALSE | TRUE | FALSE | -40990 | FALSE | FALSE
I19 | 2011-07-27 | unknown | Active |  | EWS support for both products (RIM BlackBerry Enterprise Server and GOOD Mobile Messaging Server) is required for EY to move to Exchange in the cloud while keeping BES and Good on premises. To mitigate risk, we need to ensure that hosted BES and Good are included in the hosting RFP. However this is not ideal as it will certainly drive up costs. | 04. High | 03. Medium | 03. Medium | 03. Medium | 04. High | Adrian Mickleson / Juan Torres | Andrian Mickelson / Juan Torres | Technology Foundation |  | To mitigate the issue, we need to ensure that hosted BES and Good are included in the hosting RFP. However this is not ideal as it will certainly drive up costs. | 2012-05-16 | 2012-06-06 | 15-Feb: Release 2 of GOOD due out June/July timeframe; we won't know until then whether it will work on cloud. Review in May; due date when it will cross the critical path - June 2012. (Note: due date updated - was 1-Dec-2011, but in light of cloud decision was no longer appropriate). 31/01 - O365 does not support GOOD. Unless we get EWS for GOOD we will not be able to support Exchange Users on O365. 19/10 - Juan and Adrian watching this closely. Move to Medium and review early December. 03/10 - Met with Good, and they are committed to EWS however it will not be fully supported until May 2012. RIM will not support until end of 2012. Created action here to put a plan in place to validate impact (engineering testing to determine our tolerance). 14/09 - Move to priority = high; this was only critical when BPOS was being considered. If vendor hosts Good/BB or if it remains on-premise, it's not really an issue. Meeting with Good scheduled for this Friday; review next week. (Brett added that the pricing may still remain an issue.) 07/09 - Call with Good is being scheduled for next week. Peter and Juan will attend. 31/08 - Juan still persuing / meeting with Good. Review after this meeting. 24/08 - See above; Adrian will discuss with Juan potential impacts of solutions. 17/08 - Same as I18 - working towards this with RFP (Adrian). 10/08 - no udpate. 27/07 - opened issue. | Project Manager |  |  |  | FALSE | 0 |  | TRUE | 239 | FALSE | FALSE | TRUE | 76 | FALSE | TRUE
I67 | 2001-11-01 | unknown | Closed |  | Lack of resources and inconsistent processes are impacting the quality of the work on SharePoint and items are not able to be completed. Lower than expected quality will lead to rework, missed deliverables and burn out of employees as overtime continues to move higher. | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 04. High |  | Michelle Edmonds / Norm Lambert | SharePoint |  |  | 2012-01-25 | 2011-12-12 | 25-Jan: Will be factored into re-plan. 17/1 - Processes will be modified in replanning effort. 14/12 - Firming up processes. 07/12 - Michelle said the team is working to ensure this is addressed, identifying gaps and reaffirming processes. Michelle is going to separate this such that it becomes two issues: one around a general resource issue and the other on inconsistent processes. 5/12 - issue opened. Work will be prioritized due to risk . |  | Factor into replan. | 2012-01-25 |  | TRUE | 1 |  | TRUE | 3794 | FALSE | FALSE | TRUE | -101 | FALSE | TRUE
I68 | 2011-12-05 | unknown | Closed |  | Additional work is being added to the SharePoint team without the proper change control process (prioritization, impact on cost, schedule) Cost and schedule will increase. |  |  |  |  | 04. High |  | Ian Bourne | SharePoint |  |  | 2012-01-25 | 2011-12-18 | 17/1 - Will have weekly change control meetings 11-Jan: Ian said they will have a new person in to take this forward as of next week. Review in two weeks (for anticipated resolution). 04-Jan: Ian said they now have a process to deploy; next week will have someone on board to work on it. Review next week. 14/12 - Process is being peer reviewed, will hopefully share next week. 07/12 - Ian thinks draft of change control process will be completed this week, such that it can be reviewed next week. 5/12 - Confirmed that new items must go through the change control process. Need the PMO to document that process. |  | Will have weekly change control meetings | 2012-01-17 | [11 empty] | TRUE
I69 | 2011-12-05 | unknown | Closed |  | SharePoint Phase 1 delivery needs to include Mobile acccess and no team is currently engaged to complete this work per a defined schedule. Mobile access will not be delivered in Phase 1 |  |  |  |  | 04. High |  | Brett van Gelder | SharePoint |  |  | 2012-01-11 | 2012-01-16 | 11-Jan: Michelle and Brett (and agreed by team on call) said this item is closed. It will be added to the replanning effort to look at the scope of Phase 1. 04-Jan: Michelle said she will talk with Brett, Adrian and Klara off line and update accordingly. 07/12 - Michelle and Brett to talk off-line. Review next week. 5/12 - Issue opened. - Need to find the owner for this work. |  | 11-Jan: Michelle and Brett adding to the replanning a re-look at the scope of Phase 1. | 2012-01-11 |  | TRUE | 1 |  | TRUE | 108 | FALSE | TRUE | FALSE | -66 | FALSE | TRUE
I7 | 2010-11-11 |  | Closed |  | From the MS CM Workshop the team is concerned about how knowledge security will work within SP |  |  |  |  | 05. Critical |  | Michelle Edmonds | SharePoint |  |  | 2011-04-27 | 2010-12-10 | Working with MS to determine knowledge security options. Those options will be highlighted in the POC as possible solutions for the team to review 27/04 - Continue to work with MS. Close. |  | Continuing to work with Msft; action not issue any longer. | 2011-04-27 |  | TRUE | 1 |  | TRUE | 497 | FALSE | FALSE | TRUE | -468 | FALSE | TRUE
I70 | 2011-11-30 | Steve Jelf | Closed |  | Plans for overall change management work stream are 2 - 3 months out of date. 30 day plan activity cannot be rolled out to change currently as this plan is based on detailed MS Project plan files. | 02. Low | 03. Medium | 03. Medium | 02. Low | 03. Moderate | James Dibb-Simkin | Sophie Boiron | Change Management |  | Produce updated overall change plan | 2012-02-15 | 2011-12-12 | 15 Feb - Revised overall Change plans taking shape, and following the same process as other plans. Baselines are mandated for the end of the month (Feb) Therefore this issue is resolved. 01-Feb: Sophie to complete business change plan by Monday 5th March. 26-Jan: Meeting scheduled with Change Management (sophie B) 1st Feb to walk through the last Change Management plsn 25-Jan: Activity in progress but no further updates at this time. 06-Jan: Update from S. Jelf - I would like this issue to remain open. The issue as yet has not been resolved, so would like to suggest it remains open, until the replanning exercise has completed and the Change schedule has been updated. Next review can be set to late Jan / early Feb to take a further check point. 09-Dec: Sophie agreed with Steve J the overall business change milestone for M&C will be reviewed late January/early February. No more action required. Action closed 06-Dec: Raised by S. Jelf Change Management plan has not been updated since Sept. Overall Change Management plan needs to be updated to reflect the current thinking / structure of the program and revised timelines. From this, other higher level plan (30 day confidence based plan) etc can the be derived. Meeting requested for w.,c 5th Dec to review and agree date when plan can reflect the current status | Program Manager | Revised overall Change plans taking shape, and following the same process as other plans. Baselines are mandated for the end of the month (Feb) Therefore this issue is resolved. | 2012-02-15 |  | TRUE | 1 |  | FALSE | 113 | FALSE | TRUE | FALSE | -101 | FALSE | TRUE
I66 | 2011-12-01 | unknown | Active | NA | MS SP resource engaged to assist E&Y with SharePoint Governance no longer have time on their contract and E&Y resources are not ready to carry next activities forward. Lack of governance will cause re-work and may result in the system not meeting expectations | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 04. High | Guy Morgan | Fareed Naeem | Technology Foundation |  | Need decision on commitment to forming governance body (business, IT, operations) | 2012-03-07 | 2012-01-16 | 9-Mar: Fareed and Mark setting up a call to discuss. 6-Mar: Need decision on commitment to forming governance body (business, IT, operations); Al and Mark to discuss tomorrow. 15-Feb: This will be revisited in Dallas (FSG); team on call recommended review after Dallas. 25-Jan: Confirm Tech Foundation still has budget for this resource. 11-Jan: Andy is working with Guy to determine what resources we'll need for SP governance. 07/12 - Workstreams are moving forward; if there is a governance change, will present a problem. Andy Walsh and enablement center working on this from business side (don't need Msft until business piece is there). Next step is to review with Andy what he presented at the FSG meeting. Keep this action with Guy. 05/12 - Issue opened. | Program Manager |  |  |  | TRUE | 1 |  | TRUE | 112 | FALSE | TRUE | FALSE | -66 | FALSE | TRUE
I71B | 2011-12-06 | unknown | Closed | NA | Team needs a final decision on Active Directory vs SharePoint groups (or a mix of the two). The impact is that the Dev Team cannot design or develop solution against Member Management requirements. | 03. Medium | 02. Low | 02. Low | 03. Medium | 04. High | Michelle Edmonds | Michelle Edmonds | SharePoint |  | Adjusting Priority | 2012-03-07 | 2012-03-30 | 15 March - Decision made with Newsgator decision 12-Feb: Still OPEN. 29-Feb: Norm L. will update the deck and resend to the core Team for review. This will then go to the DA (target 3/13) for review and approval. 31-Jan: Reviewed and discussed at DA meeting today. Open discussion on formalizing policy. Need direction on whether SharePoint will have to integrate with the Group Management Tool. 25-Jan: Norm Lambert has meeting with Brett van Gelder tomorrow to discuss and determine next step. Possibilities are waiting on Group Management workshops or send to DA. 17-Jan: Waiting for Group Management workshops the week of February 6th. 11-Jan: This item split in two on the call (I71A and I71B). AD will clearly be impacted by cloud decision, but it is a large internal implementation regardless. Will have to replan around O365. 11/1 Gerd to take recommendation to the ARG mtg scheduled for next Tuesday 1/17 14/12 - Greg received information, there is a meeting tomorrow to discuss. 07/12 - Michelle and Brett to talk off-line. Review next week. 06/12 - Greg researching this issue​ 29/11- Met with Norm Lambert and EY internal IT reps, Ant will arrange for demo/meeting with Imanami 23/11- Per TF, this should no longer be a dependency on the TF workstrea 31/10 - Per Klara Neginsky - on the question of whether we use AD or SP groups -- if you need a call now, go with AD. If this direction does change, I recognize there is impact, and will have to surface the impact to management. |  | 15 March - Decision made with Newsgator decision | 2012-03-15 |  | FALSE | 0 |  | TRUE | 107 | FALSE | TRUE | FALSE | 8 | FALSE | TRUE
I72 | 2011-12-06 |  | Closed |  | Current assessment of Assurance technical solution has required more time from the team than expected. Increase the overall cost of the program, has not been assessed for upgrade ability to SharePoint 15. Impacting Research Tools, Content Management, Subscribe & Deliver, specifically Assurance technical solution vision & scope is on hold. | 03. Medium | 03. Medium | 04. High | 04. High | 05. Critical | Michelle Edmonds | Michelle Edmonds | SharePoint |  |  | 2012-02-29 | 2012-01-16 | 25/1 - POC moving forward, change control pending. 17/1 - Moving this to be a change control 03/1 - Will document change requests once process is defined. 07/12 - Team had estimated an amount of work and $ for Ovitas ($50K); POC came back at $850K and substantially more work than was expected. Working with Assurance and Ovitas to reduce scope, working with legal on viability of the vendor, architecture is working on a Plan B, procurement involved, as well. Has change control on status report, working on getting it into Ian's process. Michelle and her team have decks to frame the issue, suggests conversation between Margaret, Alan, Chris and Mike/Michelle on how to move forward. Opened action, review next week. 06/12 - Issue opened. |  | POC moving forward, change control pending. | 2012-01-25 |  | TRUE | 1 |  | TRUE | 107 | FALSE | TRUE | FALSE | -66 | FALSE | TRUE
I71A | 2011-12-06 | unknown | Active | NA | Team needs guidance and information on Imanami - the AD Group Management system. If Imanami - AD Group Management - solution is used, the dev team needs to understand product funcitonality, integration with AD, ​API for custom development integration. | 03. Medium | 02. Low | 02. Low | 03. Medium | 04. High | Adrian Mickleson | Adrian Mickleson / Daren Wicks | Technology Foundation |  | Daren and Adrian to get meeting with Imanami to gain clarity on how product will be used | 2012-03-20 | 2012-03-20 | 6-Mar: Added Due date 20-Mar, NRD 20-Mar. Need to ask Rewa if has received enough (anticipate closure on time in 2 wks). 18-Jan: Daren has a group management workshop scheduled for the week of 6-Feb. Adrian worried about alignment for this; date may be at risk. Preference is to keep this date; next week's meeting will determine. Ken and Adrian have an action to discuss next Tuesday. Update next week. 11-Jan: This item opened following weekly call; Issue 71 split in two. A Group Management workshop is currently being scheduled, impact assessment being undertaken, Msft 365 wll bring changes and will need to look at that with regards to Imanami. Review next week. | Project Manager |  |  |  | TRUE | 1 |  | TRUE | 107 | FALSE | TRUE | FALSE | -2 | FALSE | TRUE
I75 | 2011-12-06 | unknown | Active |  | There was a design concept for HR Profile attributes that had been approved but due to Data Center Strategy it has invalidated. Can't complete the Profile integration design until an alternate solution is proposed and approved. | 03. Medium | 03. Medium | 04. High | 02. Low | 04. High | Adrian Mickleson / Brett van Gelder | Adrian Mickleson | Technology Foundation |  | Continue working with Msft to reach resolution. | 2012-03-28 | 2012-03-28 | 9-Mar: Adrian will confirm this on next Wednesday 2pm call with IAM team. 7-Mar: Emd Ted, Mark, Adrian, Daren to determine who is responsible for gettng this closed off. 6-Mar: using AD sync replication; CR currently underway. Review end of March; added Required Resolution Date of end of March. 7-Feb: removed Brett from Assigned to (just Adrian); this falls to Adrian as at this time no progress will be made without the CR against SPF to get the re-factoring of the design done. 18-Jan: This needs to be redesigned for O365. The answer lies in a CR that needs to be implemented against the SPF design that has been completed based on the cloud decision. Some workshops next week; looking to nail down a second week of workshops for impact. The direction is for the Fusion Profiles team to work with SPF to address the design for Profile Sync. Adrian said that 8-February is the date when we will be able to look at this further. In the mean time, Michelle's team needs to assess impact on timing of their delivery. 11-Jan: SP > TF, ownership from Michelle/Greg > Adrian and Brett. SP design complete for on-prem; Msft needs to adjust this for cloud, but this won't be until have a resource assigned. Travis has already been re-assigned. Action opened for Brett and Adrian to take this off-line. Review next week. 11-Jan need to better understand the 0365 decision before we can move forward with addressing this item. 04-Jan: Michelle working with Norm L to get clarity on HR profile strategy. Review next week. 03/1 - Proposal can't be evaluated pending details of Office 365 decision and architecture. 06/12 - Issue opened. Norm has devised an alternate solution concept using AD as a primary source for attributes. To be discussed during Fusion Enterprise Architecture meeting Wednesday December 7th. Review next week. | Project Manager |  |  |  | FALSE | 0 |  | TRUE | 107 | FALSE | TRUE | FALSE | 6 | TRUE | TRUE
I78 | 2011-12-06 | unknown | Active |  | Environments for testing are not yet available (Lync or Exchange/Outlook to test SharePoint integration to). Impact: The proof of concept for this integration will be delayed. | 02. Low | 02. Low | 02. Low | 02. Low | 02. Minor | Adrian Mickleson | James Harrup-Brook | Technology Foundation |  | Adrian working with Lindsey to secure an environments manager (Technopark). | 2012-03-31 | 2012-04-04 | 15-Mar James: Dev environment has been built up to OS level. Lync and Exchange are currently being installed. Target date April 4 for completion. 14-Mar: Laura reqd updated description and resolution plan. 14-Mar Nicky: Having reviewed the issue, I think we should keep this relevant to the delay to environment specific to Sharepoint (if I am correctly interpreting). I agree with Mark that there is a larger issue across M&C relating to environments - clarity of usage and environment management & governance. Adrian and I have been working through this issue and I'm happy to raise a separate item on the RAID for this. 12-Mar Mark: This is a subject that Nicole Watson hopes to have an update on and may involve Experimentus. In short there are multiple project teams that want to make use of these integrations - hence each may have different expectations of how the environments are managed. until this is resolved then I'd be doubtful that any built environments will see integration in QA. More info should come from the governance work in process by Jeremy and Fareed. The real issue is not the date on which these environments are deployed but the ownership and governance of environments in QA. There are multiple project teams that want to make use of these integrations - hence each may have different expectations of how the environments are managed. This needs to be resolved in order for built environments to see integration in QA. 9-mar: technopark resource id'd, process of on-boarding about to begin. 8-mar, Mark: This is a SharePoint Enablement issue as far as I am aware no other impact. SPE should have 2 inbound dependancies 1) Lync to test presence and 2) to test ability to use Exchange messaging. In my opinion these are Med/Low impacts as the functionality is standard MS OOB - unless SPE have written custom code unsupported by MS (which I'd expect to be unlikely). James HB has been driving a plan to stand up the missing VMs in QA, but that will only be available for formal QA testing and not developer testing. I'd expect VMs to be stood up by late April. 6-Mar: I79 blended in here since issue is the same. Adrian getting from Lindsey names for environment manager. 17-Feb: LM em'd Mark for update. 06/12 - Issue opened. | Project Manager | [13 empty] | FALSE
I76 | 2011-12-06 |  | Closed |  | Build deployment is dependent upon appropriate SharePoint services and permissions to be turned on in the Iteration 1 development environments. Unable to deploy build to other environments for integration and functional testing. |  |  |  |  | 04. High |  | Mark Reade | Technology Foundation |  |  | 2012-01-04 |  | 04-Jan: The team on the call confirmed that this issue can be closed. It is no longer an issue, on John's work plan. 03/1 - John Spinella from Microsoft is working the issue, to provide update January 4th. 20/12/11 - Remedy tx raised to enable permissions, awaiting confirmation that permissions have been granted, John Spinella waiting on permissions to make changes to enable testing. 06/12 - Issue opened. Currently assessing. Dan Mulligan has been assigned. |  | John handling; no longer an issue. | 2012-01-04 |  | FALSE | 0 |  | TRUE | 107 | FALSE | TRUE | FALSE | -40990 | FALSE | TRUE
I77 | 2011-12-06 |  | Closed |  | The automated build process needs to be able to use/pass non-Prod credentials, because the builds are done in environment(s) outside of Prod. Solution for passing the credentials in automated build process has not been determined. Can't do automated builds. |  |  |  |  | 03. Moderate |  | Mike Cliffel | SharePoint |  |  | 2011-12-07 |  | 06/12 - Issue opened. |  | ??? | 2011-12-19 |  | FALSE | 0 |  | FALSE | 107 | FALSE | TRUE | FALSE | -40990 | FALSE | TRUE
I84 | 2011-12-12 | unknown | Active |  | The new SP infrastructure is dependent upon WAN accelerators and other WAN performance improvements installed and ready to be used. SP Foundation team is working with the proper people. Need to make sure plans align The SP infrastructure will not perfom as desired for those at the edge of the network or the go live will be delayed until the work can be completed | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 04. High | Adrian Mickleson | Adrian Mickelson | Technology Foundation |  | Alignment of rollout wave plans with DCC and GWAN teams. Weekly call set up to monitor this key dependency. | 2012-04-11 | 2012-04-18 | 19-Mar: Adrian provided planned resolution and amended due date to 18-April to be more realistic (was 21-Mar). 6-Mar: there are 2 items here -- one is the inbound dependency on DCC, which is putting in accelerators; the other is the issue that if all goes to cloud, could be performance issues with MySites in some locations. Action: Adrian to find out from DCC where they are. 12/112 - Opened at the SP Foundation meeting, teams are linked. Need to make sure plans are updated. | Project Manager |  |  |  | FALSE | 0 |  | TRUE | 101 | FALSE | TRUE | FALSE | 27 | FALSE | TRUE
I79 | 2011-12-06 | unknown | Closed |  | There isn't an Exchange/Outlook environment that we can test SharePoint integration to. The proof of concept for this integration will be delayed. |  |  |  |  | 02. Minor | Adrian Mickleson | Mark Reade | Technology Foundation |  |  | 2012-02-01 | 2012-02-01 | 6-Mar: closed, blending into I78, 17-Feb: LM em'd Mark for update. 06/12 - Issue opened. |  | Blending into I78 since the issue is really the same - need for environments for testing. | 2012-03-06 | I78 | TRUE | 1 |  | FALSE | 107 | FALSE | TRUE | FALSE | -50 | FALSE | FALSE
I8 | 2011-04-22 |  | Closed |  | Need to figure out how the architecture work in SP will work - Engineering and Architecture |  |  |  |  | 04. High |  | Brian Blinco, Peter Browne, Michelle Edmonds | SharePoint |  |  | 2011-04-27 | 2011-04-27 | 27/04 - Brian, Nick and MS determined how the two teams will work together. Close. |  | Brian, Nick and MS determined how the two teams will work together | 2011-04-27 |  | TRUE | 1 |  | TRUE | 335 | FALSE | FALSE | TRUE | -330 | FALSE | TRUE
I80 | 2011-12-06 |  | Closed |  | Our ramp up of resources is slower than expected, and having turnover of existing resources. Impacts our ability to deliver to plan, productivity and quality of work. | 02. Low | 02. Low | 02. Low | 02. Low | 03. Moderate |  | Michelle Edmonds | SharePoint |  | Replan resource needs with O365 decision. | 2012-01-11 |  | 06/12 - Issue opened. |  | replan resource needs with O365 decision | 2012-01-10 |  | FALSE | 0 |  | FALSE | 107 | FALSE | TRUE | FALSE | -40990 | FALSE | TRUE
I81 | 2011-12-07 | unknown | Closed |  | Due to Audit busy period 6 candidates now placed on hold until at least March 2012 to confirm requirements from the business. Microsoft engagement for Phase 1 cannot start until new candidates are identified, baselined and requirements are available. 11-Jan: Down to 13 candidates for Phase 1. | 03. Medium | 02. Low | 04. High | 02. Low | 04. High | Martin Stutchbury | Martin Stutchbury | App and Data Migration |  | Identify replacement applications | 2012-02-29 | 2012-01-25 | 06/03 - Issue closed as replanning (incl. alignment of dependancies) being managed as a BAU activity 29/02 - Session scheduled with the Sharepoint Program for Friday 02/03/12 to understand both their scope and timelines to validate the applications currently in scope of Phase 1 07-Feb: Following further clarifications from the Sharepoint Program ref their scope some more applications are likely to be descoped from Phase 1; team are currently reviewing each to 're-baseline' the applications against the latest information provided by the Sharepoint program, review 2 wks. 11-Jan: have been able to replace some candidates; now lost 2, and are thus down to 13 candidates for P1. The risk is that they may find some that come off the list. Review 6-Feb. 10-Jan: updated all columns (Neil/Laura) 7/12/11 - Issue opened. On call: move review date to 11-January. | Program Director | Replanning (inc. alignment of depdencies) being managed as a BAU activity. | 2012-03-06 |  | TRUE | 1 |  | TRUE | 106 | FALSE | TRUE | FALSE | -57 | FALSE | TRUE
I82 | 2011-12-19 |  | Closed |  | ??? |  |  |  |  | 03. Moderate |  | Al Grljevic |  |  |  | 2011-12-20 | 2012-12-23 | 18-Jan: reviewed this item with Al, and he is unsure where it came from; seems to be a misalignment from a different item. Close here. 19/12 - When this was previously raised, Yvonne McGrory was assigned to cover the gap, however we understand that as from 16/12 Yvonne is no longer doing this role and another BA is joining in January (no formal confirmation of this). |  | Not an issue; just a data entry mistake. | 2012-01-18 |  | FALSE | 0 |  | FALSE | 94 | FALSE | TRUE | FALSE | 276 | FALSE | TRUE
I94 | 2012-01-10 | Michelle Edmonds | Active | R48 | Availability / time-line of the development VM boxes (config & software) and the deployment environments (development, QA, Production) for iteration 2. 1. Ver 2 - Developer Workstations - 20 Apr (was Nov 22 '11) 2. Ver 2 - Component Integrated Development Environment - 20 Apr (was Dec 1 '11) 3. Ver 2 - Deployment Integrated Development Environment - 20-Apr (was Dec 1 '11) 4. QA Environments (Intranet, Extranet, Security) - 20-Apr (was Dec 1 '11) 5. Staging Environments (Intranet, Extranet) - 2-Aug-2012 6. UAT Environments (Intranet, Extranet) - 2-Aug-2012 | 04. High | 04. High | 04. High | 04. High | 04. High | Adrian Mickleson | Adrian Mickleson | Technology Foundation |  | Norm Beard and Adrian to work on defining the requirements. | 2012-03-20 | 2012-04-20 | 15-Mar: Action to Norm Beard to have an update on Tuesday. 14-Mar: Mtg occurred; will have ready 19-Mar to have provisional plan out. 13-Mar: Meeting today - Al, Alan, Norm, Nick to discuss. 6-Mar: added new dates to description. Changed due date to 20-Apr from 5-Feb, since dates on builds have changed. Review 1 week prior. (From SPF RAID log mitigation plan: Estimated build time to complete all #2 builds and document ready for handover by 20th April '12, Interim remediation now complete, Repurpose 2xVMs for an interim Iteration #1 QA build, use the build expedite group where possible to reduce the time required to builid the servers, Iteration #2 build designs approved and moved to build order for April 16th target date) 29 Feb: open until delivered. 15-Feb: Michelle shared a baseline plan for environments, which provided a high level understanding. This is in-progress. Michelle not on call - Al looking for clarification: is this issue around the date or understanding of requirements? (LM em'd Michelle) 10-Jan: Opened issue from Risk 48, per Michelle's request. This ties also to Issue 62. #1- build ready. Will possibly ending up splitting this item in the future. | Project Manager |  |  |  | FALSE | 0 |  | TRUE | 72 | TRUE | FALSE | FALSE | 29 | FALSE | TRUE
I154 | [22 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
I85 | 2012-01-04 | Al Grljevic | Closed | R79B | The current UC approach to collecting User Requirments is on a different timeline to the TF Architecture & Design phase for Lync & Outlook which is currently preceeding it. If additional requirements are driven out by the UC requirements work then they will not have influenced the TF design for Lync & Outlook and could require Change to the designs incurring additional costs and delaying implementation | 04. High | 04. High | 04. High | 04. High | 04. High | Adrian Mickleson | Adrian Mickleson | Technology Foundation |  | Produce an impact asasessment by the middle of March. | 2012-02-15 |  | 15-Feb: This is no longer an issue; in light of O365 decision. Paul provided update that there are no Outlook configuration requirements until April, and UC has adjusted their plans. The Lync requirements are complete, too. At the requirements level, all complete. Close. 04-Jan: On call, Al said that this is now an issue. Closed as risk (79B) and moved here. He said the next review date will be mid-Feb. |  | This is no longer an issue; in light of O365 decision. Paul provided update that there are no Outlook configuration requirements until April, and UC has adjusted their plans. The Lync requirements are complete, too. At the requirements level, all complete. Close. | 2012-02-15 |  | FALSE | 0 |  | TRUE | 78 | TRUE | FALSE | FALSE | -40990 | FALSE | TRUE
I86 | 2012-01-04 | Michelle Edmonds | Closed | A33 | Long term governance of the technical SharePoint platform to allow other developers to use the platform. | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 03. Moderate | Michelle Edmonds | Mike Laci | SharePoint |  | To be determined via new Support model needed to support Sharepoint | 2012-03-22 | 2012-05-31 | 29-Feb: To be discussed during M&C Transition planning mtg in Secaucus. 31-Jan: Added to list of decisions needed by the new Target Operate Model 17-Jan: Issue updated. 04-Jan: Reviewed this as Assumption#33 - Michelle said it is now an issue; opened an action for Michelle to populate the remaining data related to this item. | Other | Governance team in process | 2012-03-09 |  | FALSE | 0 |  | FALSE | 78 | TRUE | FALSE | FALSE | 70 | FALSE | TRUE
I87 | 2012-01-04 | Michelle Edmonds | Closed | A37 | Infrastructure - SP technology foundation Goverance work will occur in the technology foundation workstream (22) Increases the scope of other workstreams | [6 empty] | Michelle Edmonds | SharePoint |  |  | 2012-01-11 |  | 04-Jan: Reviewed Assumption #37; Michelle said it is an issue. Opened action for Michelle to populate this item. |  | ??? | 2012-01-11 |  | FALSE | 0 |  | FALSE | 78 | TRUE | FALSE | FALSE | -40990 | FALSE | FALSE
I88 | 2012-01-06 | Steve Jelf | Closed |  | Previous planning cycles for TF Exchange / SP and Lync had a working assumption (for Infr build out) which is no longer accurate and therefore plan schedules are no longer accurate. This is hampering attempts at getting stream-lined cohesive plans in place in time for check points occurring weekly through February, leading up to the FSG 28/29th Feb | 02. Low | 05. Critical | 05. Critical | 01. Undecided | 04. High | Al Grljevic | Adrian Mickelson | Technology Foundation |  | Updated plan will be produced mid-March. |  | 2012-03-21 | 7th March - This issue is now being closed. "Get to Green" plan now being driven by A. Guthrie, and plans now baselined. although confidence levels are low. "Get to Green" plan will deliver increased confidence. 29th Feb - During the last checkpoint meeting 23rd Feb, it was again mandated that there WILL be a baseline plan in place for all workstreams (including Lync) by 1st March. As of Monday 5th March, all plans will be subject to Change Control processes. Email sent to all work stream leads outlning process. 15-Feb (on call): Al, Guy, Steve discussed on call; Alan agreed there won't be a baseline plan by the 28-29 Feb. There won't be a plan until mid-March; Al requested next review date of 3rd week of March. 15th Feb - CheckPoint meeting held with Alan on 9th Feb. Broad understanding now in place with A. Guthrie on what current state is. Further checkpoint email to be sent 17th Feb and a follow on checkpoint meeting scheduled for 23rd Feb. A. Guthrie has mandated that all plans must be baselined by the end Feb without exception, and then modified only under change control processes. - This has significant risk as in certain streams not enough information (ie no vendor selected) will be available at the end of the month to produce detailed enough plans. 31st Jan - Early awareness of current state provided to Alan Guthrie - further status update to be send 6th Feb. 23rd Jan - Requirement is to have detailed plans, assumptions, decisions and a resource plan being fed through for all streams during various check point meetings in Feb being set up with Alan Guthrie and then a final version being presented to the FSG on 28th / 29th Feb. 17th Jan - Added Issue of Lync hosting not confirmed which is having similar impact to the validity of the Lync Plan. 11-Jan: impact assessment for O365 for SP around the 2nd week of Feb, if get Msft eng sorted by then. Review Feb. 06th- Jan - Detail of decision is required prior to further workshops being held to understand impact to time / cost / scope and overall quality. TF Exchange SharePoint, UC and SharePoint plans are currently are in need of revalidation | Managing Sponsor | 7-Mar: "Get to Green" plan now being driven by A. Guthrie, and plans now baselined. although confidence levels are low. "Get to Green" plan will deliver increased confidence. | 2012-03-07 |  | TRUE | 1 |  | TRUE | 76 | TRUE | FALSE | FALSE | -1 | FALSE | TRUE
I89 | 2012-01-06 | Steve Jelf | Closed |  | ADM schedule no longer reflects reality and will run longer than expected as the Phase 1 plan cannot be baselined until inbound dependency owners have firmed up their plans (namely provisioning of environments, UI guidelines, and O365 strategic architecture). | 02. Low | 02. Low | 01. Undecided | 02. Low | 05. Critical | Neil Sahdev | Neil Sahdev | App and Data Migration |  | Identify and onboard a replacement PM | 2012-03-07 | 2012-01-31 | 06-Mar: Issues closed as replanning being managed as a BAU activity 29-Feb: Replanning underway following confirmation that many inbound dependancies won't be available for a significant amount of time later than required 08-Feb: description updated, as PM is now onboarded; Phase 1 issue now around dependencies. 07-Feb: Phase 1 plan cannot be baselined until inbound dependancy owners have firmed up their plans (namely provisioning of environments, UI guidelines and O365 strategic architecture) 18th Jan: Replacement Phase 1 PM onboarded (Nicola Cooper); targeting to have draft Phase 1 plan in place by 3rd Feb'12 06th - Jan : Current ADM schedule is out of date and needs to be revised as no current PM resource is available to drive phase 1 forwards | Program Director | Issues closed as replanning being managed as a BAU activity | 2012-03-06 |  | TRUE | 1 |  | TRUE | 76 | TRUE | FALSE | FALSE | -51 | FALSE | TRUE
I9 | 2011-04-22 |  | Closed |  | Who owns release management - Engineering, EAM or Development |  |  |  |  | 04. High |  | Brian Blinco, Peter Browne, EAM, Michelle Edmonds | SharePoint |  |  | 2011-04-27 | 2011-04-27 | 27/04 - Discussion of which group will execute release management. Resolved on call: Chris Whitman's team. |  | Resolved on call: Chris Whitman's team. | 2011-04-27 |  | TRUE | 1 |  | TRUE | 335 | FALSE | FALSE | TRUE | -330 | FALSE | TRUE
I155 | [22 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
I156 | [22 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
I92 | 2012-01-06 | Michelle Edmonds | Closed |  | Business users are requesting more than available OOB, we need a process prior to design for prioritization / approval. | 04. High | 04. High | 04. High | 04. High | 04. High | Michelle Edmonds | Alan Guthrie/Bob Reiner | SharePoint |  | 2012-03-30 | 2012-03-07 | 2012-03-30 | 21-Feb: Ian: related to a recent change that Bob has put into place around SP and also impacts who Michelle mow has to interact with; Michelle to confirm and update. 25-Jan: On a call in which the issue of customization came up, it was decided that there will be people from the business to be responsible; Bob is working to name these individuals. Laura and Ian will discuss off-line and follow-up with Alan or Bob. 11 - Jan Opened item. On call, selected Bob as the owner, came up on call with Alan. Trying to identify business person to be accountable for each area. This will make it clearer who is making what decision. | Managing Sponsor | WSL engaged to meke sure this does not happen | 2012-03-09 |  | FALSE | 0 |  | TRUE | 76 | TRUE | FALSE | FALSE | 8 | FALSE | TRUE
I93 | 2012-01-11 | Michelle Edmonds | Closed |  | O365 Decision will require replan | 04. High | 04. High | 04. High | 04. High | 04. High | Michelle Edmonds | Michelle Edmonds / Norm Beard | SharePoint |  | Complete replan and sign-off | 2012-03-07 | 2012-03-07 | 22-Feb: leave open until plan is signed off; should be in two weeks (due and review). 7-Feb: Meetings scheduled next week to discuss O365 implications for the workstreams. 25-Jan: Re-planning effort currently underway, targeted for 2-20 release 17-Jan: Have started \re-planning effort 11 - Jan Opened item. Next week starting to plan the approach to re-planning. 2 weeks to review; once approach determined will close. | Program Manager | Replan in process | 2012-03-09 |  | TRUE | 1 |  | TRUE | 71 | TRUE | FALSE | FALSE | -15 | FALSE | TRUE
I157 | [22 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
I95 | 2012-01-11 | Al Grljevic | Closed | R1 | Due to the recent activities around the Msft cloud decision, we require additional team members (BAs, PMs, engineering, etc.) to face off against the various streams. Availability of necessary resources within EY across all projects - long lead times in securing the required resources, PMs, BA's and other resources for the various projects Will impact delivery of Lync and Outlook | 04. High | 04. High | 04. High | 03. Medium | 05. Critical | Guy Morgan | Guy Morgan | M&C Program |  |  | 2012-03-07 | 2012-03-07 | 15-Feb: Guy said they are currently recruiting; work in hand. Due date and review 3 wks. 11-Jan: Per Al, this was R1, it is an issue. Opened here. On call, added Guy as the item's owner. Priority = Critical. Review beginning of Feb; due date TBD after conversations at end of Jan. |  | Work in hand; recruiting. | 2012-02-15 |  | TRUE | 1 |  | TRUE | 71 | TRUE | FALSE | FALSE | -15 | FALSE | TRUE
I158 | [22 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
I159 | [22 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
I160 | [22 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
I99 | 2012-01-24 | Al Grljevic | Closed | NA | The TF/UC Programme is missing a detailed breakdown of the collective tasks that need to be carried out. Impact: Difficult to assess the effort required to deliver the programme and asses resource requirements. | 03. Medium | 03. Medium | 03. Medium | 03. Medium | 04. High | Al Grljevic | Al Grljevic | Technology Foundation |  | Create this detailed breakdown once receive detailed plan from Msft. | 2012-03-14 | 2012-03-19 | 6-Mar: This item was opened because there wasn't a list of the # of resources a vendor would need. Have gotten this information together now (per Al and Adrian). Close. 15-Feb: Waiting on detailed plan from Msft re: cloud, Lync vendor, etc.; until we have this, don't know what we need vendors for, how long we need them, etc. Review mid-March. Laura em'd Al for details. 24-Jan: Laura added to log per Al. | Program Director | This item was opened because there wasn't a list of the # of resources a vendor would need. Have gotten this information together now (per Al and Adrian) | 2012-03-06 |  | TRUE | 1 |  | TRUE | 58 | TRUE | FALSE | FALSE | -3 | FALSE | TRUE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE
[23 empty] | FALSE | 0 |  | FALSE | 40990 | FALSE | FALSE | TRUE | -40990 | FALSE | FALSE

## Assumption Log
# | Identified by | Program / Workstream | Project / Workstream | Assumption (brief description) | Potential impact if assumption proves to be false | Forum/Individual | Validated by | Last review date | Next review date | Due Date | Status | Output Reference # | Comments | Overdue | 2012-03-22
A85 | Neil Sahdev | App & Data Migration |  | The A&DM Program budget assumes the use of Hexaware as the offshore delivery team for the Portfolio teams | A&DM Program budget may change | Alan Guthrie | To be validated | To be validated | 2012-03-30 | 2012-03-30 | Not yet validated |  |  | FALSE
A87 | Martin Stutchbury | App & Data Migration |  | Industry standard ratios for Lotus Notes Migrations indicates that we will end up with ~990 target applications. The assumption for resourcing, budget and planning purposes is that ~600 wil lbe built by the A&DM factory before tailing off to a very long tail. Many of the remaining ~390 applications will either be not required (natural end of life), or will be picked up and replatformed by BAU demand work undertaken by CBS/Markets as part of their normal annual activities. | Increased cost and timelines | Alan Guthrie | To be validated | To be validated | 2012-04-01 | 2012-04-01 | Not yet validated |  |  | FALSE
A25 |  | App & Data Migration |  | The Application Data Conversion work currently in the MS SOW will be covered by IBM and Hexaware | It wouldn't be clear which vendor (IBM vs Microsoft) would be doing the work. | [5 empty] | Obsolete |  | 26-Sept: Greg suggested obsolete. | TRUE
A1 |  | M&C Program |  | 80% of the user population will be hosted in the cloud and the remaining 20% on premises | SOWs and Plans will need to be reworked depending on what the final decision on BPOS | [5 empty] | Obsolete |  | 26-Sept: Greg suggested obsolete. | TRUE
A19 | Bob Cooney | M&C Program |  | Key AD requirements for M&C program will be delivered as a separate program of work and will meet the time scales for M&C program. | Program schedule will be impacted | [5 empty] | Output to Risk/Issue | R86 | 19-Dec: LM working with Bob to turn this into a risk. 03-Jan: Added to risk log, R86. | TRUE
A12 |  | M&C Program |  | SOWs from MS will be signed off by June 1 | Further delays in launching the program | [5 empty] | Obsolete |  | 26-Sept: Greg suggested obsolete. | TRUE
A13 |  | M&C Program |  | Key resource openings will be filled by June 1 | Further delays in launching the program | [5 empty] | Obsolete |  | 26-Sept: Greg suggested obsolete. | TRUE
A14 |  | M&C Program |  | Performance testing will occur in NC at the MS facility | EY will need to fund and implement a performance test environment, this could add to the costs and introduce delays. | [5 empty] | Obsolete |  | 26-Sept: Greg suggested obsolete. | TRUE
A2 | Adrian Mickleson | M&C Program |  | It is assumed that there is enough capacity and space in the global data centres for the installation of the required infrastructure for the M&C program | Additional space will need to be investigated, this could extend the timeline for the program. | John Lawler | Adrian, Al, Mark, others | 2012-03-06 | 2012-03-06 | 2012-03-06 | Validated |  | 6-Mar: It has been confirmed that Frankfurt will be the only data center (decision D210); assumption valid - there is sufficient capacity. | TRUE
A21 | unknown | M&C Program |  | The scope of this effort will include all knowledge of the firm including ey.com and ey online | Could reduce the scope of this effort | ? | Alan, Guy, team on 19-Dec review call | 2011-12-19 | N/A | ? | Validated |  | Validated by Alan on review call 19-Dec; agreed by team. Norm looking for sizing of this; will talk to Michelle about it. Revalidated following O365 decision: (add name and date here once the item has been revalidated) | FALSE
A27 | unknown | M&C Program |  | The cost of the new MS software license will not be included in part of this contract | If it is included, it would have to be included in the project budget. | ? | Alan, Guy, team on 19-Dec review call | 2011-12-19 | N/A | ? | Validated |  | Validated by Alan and Guy on 19-Dec review call. Team agreed. Revalidated following O365 decision: (add name and date here once the item has been revalidated) | FALSE
A84 | Rob Dekker | M&C Program |  | Until told otherwise as a result of ongoing MS-BPOS negotiations and RFP efforts, M&C teams are working under the assumption that we are going with an on-prem solution that is managed by EY. Continue as such until a CR is formally raised. | Significant changes in program (scope, organization, planning), design and transition. | M&C Program management |  | 2012-03-06 | 2012-03-28 | On-going until CR formally raised. | Not yet validated |  | 6-Mar: Review end of March (Lync vendor decision) 27-Feb Rob: I believe the assumption was raised in December. Nevertheless, as result of the O365 contract, the assumption is not valid anymore. I don't know whether a CR has formally been raised. For Lync and Exchange on Premise final decisions have not been made yet. I assume that for these parts the assumption is still valid. 23-Feb: LM followed up with Rob 04-Jan: Review end of January (decision process slated for then) | FALSE
A26 |  | M&C Program |  | The email production servers will be in place in October | Charges would increase on the server budget | [5 empty] | Obsolete |  | Greg noted this is not accurate; Adrian confirmed. 5-May-2011 | TRUE
A22 | unknown | SharePoint |  | This SP POC effort does not include document management | The scope would increase and require additional work, time and money | Michelle Edmonds | 04-Jan RAID call attendees | 2012-01-04 | N/A | N/A | Validated | December 20120 meeting with MS | 04-Jan: Michelle said this hs been validated; was from a meeting in December 2010. All docs have been updated accordingly. Revalidated following O365 decision: (add name and date here once the item has been revalidated) | FALSE
A23 | unknown | SharePoint |  | This SP POC effort does not need to document collaboration requirements | The scope would increase and require additional work, time and money | Michelle Edmonds | 04-Jan RAID call attendees | 2012-01-04 | N/A | N/A | Validated | December 20120 meeting with MS | 04-Jan: Michelle said this hs been validated; was from a meeting in December 2010. All docs have been updated accordingly. Revalidated following O365 decision: (add name and date here once the item has been revalidated) | FALSE
A24 | unknown | SharePoint |  | The functionality of this SP POC effort will be dependent upon 2010 (SP2010, Office 2010, Windows 7 and IE 8) | Less functionality will be delivered than what is seen | Michelle Edmonds | 04-Jan RAID call attendees | 2012-01-04 | N/A | N/A | Validated | December 20120 meeting with MS | 04-Jan: Michelle said this hs been validated; was from a meeting in December 2010. All docs have been updated accordingly. Revalidated following O365 decision: (add name and date here once the item has been revalidated) | FALSE
A30 | unknown | SharePoint |  | Structure - Workstream core team members are empowered to make decisions for the group they represent in Elaboration (11) | Additional decision makers or lack of clarity on decision makers cause delay | Michelle Edmonds | 04-Jan RAID call attendees | 2012-01-04 | N/A | N/A | Obsolete | Will be affected by Replan | 1/4/2012 - Michelle stated on call that this is true. Has been validated. Revalidated following O365 decision: (add name and date here once the item has been revalidated) | FALSE
A31 | unknown | SharePoint |  | Deployment - Decisions from the Design Authority will be received in 1 week (12) | Decisions that are not timely will cause delays | Michelle Edmonds | 04-Jan RAID call attendees | 2012-01-04 | N/A | N/A | Validated | Replanned | 1/4/2012 - Michelle stated on call that this is true. Has been validated. Revalidated following O365 decision: (add name and date here once the item has been revalidated) | FALSE
A35 | unknown | SharePoint |  | Process - The staffing for Phase 1 needs to include the ability to train offshore resources for the following phases (17) | Successful execution of subsequent phases are jeopardized if IT is not prepared | Michelle Edmonds | 04-Jan RAID call attendees | 2012-01-04 | N/A | N/A | Obsolete |  | 04-Jan: Michelle confirmed that this is true. List as validated/close. Revalidated following O365 decision: (add name and date here once the item has been revalidated) | FALSE
A36 | unknown | SharePoint |  | Process - Code must be able to be used by other SP solutions, where applicable (18) | Reusabilty strategy would not be realized | Michelle Edmonds | 04-Jan RAID call attendees | 2012-01-04 | N/A | N/A | Validated |  | 04-Jan: Michelle confirmed that this is true. List as validated/close. Revalidated following O365 decision: (add name and date here once the item has been revalidated) | FALSE
A40 | unknown | SharePoint |  | Phase 1 Delivery - the project team is responsible for developing development, architecture and design standards for the SP platform (25) | Standards will not be effectively established | Michelle Edmonds | 04-Jan RAID call attendees | 2012-01-04 | N/A | N/A | Validated |  | 04-Jan: Michelle said this is true and has been validated. Plans have been updated accordingly. 07-Oct-2011: BvG: Development of standards etc. under the direction of Enterprise Architecture Revalidated following O365 decision: (add name and date here once the item has been revalidated) | FALSE
A41 | unknown | SharePoint |  | Process - The team will use OOB, then 3rd party and then customizations to meet the business need (26) | IT product development strategy would be violated | Michelle Edmonds | 04-Jan RAID call attendees | 2012-01-04 | N/A | N/A | Validated |  | 04-Jan: Michelle said this is true and had been validated. Plans have been updated accordingly. Revalidated following O365 decision: (add name and date here once the item has been revalidated) | FALSE
A42 | unknown | SharePoint |  | Process - Work completed by the Embedded Knowledge team should be used to expedite the processes (27) | Work would not be expedited | Michelle Edmonds | 04-Jan RAID call attendees | 2012-01-04 | N/A | N/A | Validated |  | 04-Jan: Michelle said this is true and had been validated. Plans have been updated accordingly. Revalidated following O365 decision: (add name and date here once the item has been revalidated) | FALSE
A33 |  | SharePoint |  | Deployment - The IT Solutions delivery team will provide a longer term structure to support the maintance and support of the Shared Services and common components (14) | Successful maintenance and support are jeopardized if IT is not prepared for maintance and support of the Shared Services and common components |  |  | 2012-01-04 |  |  | Output to Risk/Issue | I86 | 04-Jan: Michelle said she will turn this into an issue. Laura assigned Issue #86 | TRUE
A37 |  | SharePoint |  | Infrastructure - SP technology foundation Goverance work will occur in the technology foundation workstream (22) | Increases the scope of other workstreams |  |  | 2012-01-04 |  |  | Output to Risk/Issue | I87 | 04-Jan: Michelle said this is now an issue; open as Issue 87. | TRUE
A17 |  | SharePoint |  | The candidate workloads for implmenting on BPOS for SharePoint are: Team Sites, My Sites and ad hoc collboration | Implementation of the full SharePoint workloads will need to be done on prem | Adrian Mickleson | TF Meeting | 2012-01-04 | 2012-01-18 |  | Validated |  | 04-Jan: Assigned Adrian, per call, with review date 18-Jan. This will have to be changed completely due to impact from change - BPOS. | TRUE
A29 |  | SharePoint |  | Integration - The only systems integrated with Lotus Connection are EYHP and ASK (7) | Any other integrations would increase effort and impact schedule | Michelle Edmonds | Michelle Edmonds | 2012-01-04 | 2012-01-11 |  | Obsolete |  | 04-Jan: Michelle said this is no longer true; she will update this item accordingly (including impact in comments and output reference if changed to issue or risk). 07-Oct-2011: BvG: There is also ad hoc integration via api frpom CHSs and other sites by using bizcard, etc. | TRUE
A34 |  | SharePoint |  | Infrastructure - The phase 1 rollout will include a build out for all countries needing SharePoint (16) | In Country solutions would not be in place, so SharePoint solutions could not be provided in county |  | Michelle Edmonds |  |  |  | Obsolete |  | 07-Oct-2011: BvG:Not realistic due to the situation with data transfer restrictions and the number of total country build-outs that will be required. Build out should match solution requirements. | TRUE
A32 |  | SharePoint |  | Deployment - The Help Desk will be prepared for calls from 500K business users (13) | Successful deployment is jeopardized if Help Desk is not prepared for support |  | Michelle Edmonds | 2012-01-04 | 2012-01-11 |  | Obsolete |  | 04-Jan: Adrian and Michelle to follow-up on this one. | TRUE
A38 |  | SharePoint |  | Schedule - frog will deliver the Phase 1 quick hits for use in the UX by late November (23) | Dependent schedules of other Fusion workstreams will be impacted |  | Michelle Edmonds | 2012-01-04 | 2012-01-11 |  | Obsolete |  | 4-Jan: this has changed and will have an impact. Michelle to update accordingly. 19-Dec: Norm said replanning will occur, around FROG's schedule. | TRUE
A39 |  | SharePoint |  | Process - The business will develop a governance group to help support consensus of different business groups where appropriate (24) | Business governance may not be effectively established |  | Michelle Edmonds | 2012-01-04 | 2012-01-11 |  | Obsolete |  | 04-Jan: Michelle said Andy W. will be handling governance issues; she is meeting with him tomorrow. Review next week. | TRUE
A43 |  | SharePoint |  | Process - Managing sponsors will be notified if the core team on a workstream does not think OOB will meet the business need (29) | Stakeholders would not be informed |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Process will be changed for each BPO | TRUE
A44 |  | SharePoint |  | 3rd Party Products - The group management solution in process by the Tech Foundation team will meet the needs of the business in Fusion (31) | Scope, schedule, and budget variances |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will not have the same effect due to Newsgator | TRUE
A45 |  | SharePoint |  | UAT - The business will take the training developed by the team and modify it to meet the appropriate end user needs (34) | End user training development would take longer |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Work with WSL to determine UAT | TRUE
A48 |  | SharePoint |  | Process - The HR, Information Security, Quality and Risk Management and GCO teams will provide responses to key questions in a timely basis (37) | Decisions that are not timely will cause delays |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  |  | TRUE
A49 |  | SharePoint |  | Process - The ELM process of linking TFS to HP QC will meet the BA/PM needs to automate traceability from requirements through design and development to the test case and test resuts to defects and change controls (38) | Lack of traceabilty will cause additional impact and product quality may be affected |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | 20 March 0 this process is working as needed | TRUE
A50 |  | SharePoint |  | Process - The business will provide feedback on key deliverables in 5 days (39) | Decisions that are not timely will cause delays |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | No longer needed with the replan | TRUE
A51 |  | SharePoint |  | Infrastructure - Ordering of hardware will take between 3-7 weeks (40) | Longer cycle times will impact schedule |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | No longer needed with the replan | TRUE
A52 |  | SharePoint |  | Infrastructure - The confguration of hardware will take 4 weeks (41) | Longer cycle times will impact schedule |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | No longer needed with the replan | TRUE
A53 |  | SharePoint |  | Process - Information Security will provide the keys to production prior to final sign off to help the team prove out global deployment processes with the understanding that the team will not use the structure until approve (42) | Proving out global deployment processes will be problematic |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be worked as part of the plan | TRUE
A46 | ? | SharePoint |  | Infrastructure - The technology foundation team will have the appropriate environments ready when needed (35) | Fusion schedule will be impacted | ? | Norm Lambert (on 19-Dec review call) | 2011-12-19 | N/A | N/A | Obsolete |  | 19-Dec: Norm said this has been invalidated; mark obsolete. | FALSE
A54 |  | SharePoint |  | Phase 1 Delivery - The team is responsible for determing how employees, clients and invited guests can be immediately removed from the platform for all products that will use the platform (45) | Immediate removal process for users would not be in place |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be reassed with the replan | TRUE
A55 |  | SharePoint |  | Staffing - The internal IT team will have adequate employee representation for the risk associated with the effort (46) | Successful deployment is jeopardized if internal IT team does not have adequate employee representation |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be reassed with the replan | TRUE
A56 |  | SharePoint |  | 3rd Party Prodcuts - Procurement will be able to help the team acquire 3rd party products in 9-12 weeks (48) | Longer cycle times will impact schedule |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be reassed with the replan | TRUE
A57 |  | SharePoint |  | 3rd Party Products - Only 3rd party products over $50K will be required to go to formal RFP (49) | Longer cycle times will impact schedule |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | Assumption has been validated | TRUE
A58 |  | SharePoint |  | Process - Client serving teams will receive regular updates from the effort to view the products as they are being developed (50) | Feedback from stakeholders cannot be included |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be reassed with the replan | TRUE
A59 |  | SharePoint |  | Process - ITS is responsible for making sure design and code components/elements are reused across workstreams (51) | Reusabilty strategy would not be realized |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be reassed with the replan | TRUE
A60 |  | SharePoint |  | Staffing - Operations will be ready to be trained on the new environment in April (52) | Successful deployment is jeopardized if Operations is not trained |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be reassed with the replan | TRUE
A61 |  | SharePoint |  | Infrastructure - In country build outs will be completed in 4 weeks (53) | Longer cycle times will impact schedule |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be reassed with the replan | TRUE
A62 |  | SharePoint |  | Training - First drafts of training will be completed with each iteration and then updated accordingly (54) | Training may not be completed on a timely basis |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be reassed with the replan | TRUE
A63 |  | SharePoint |  | Infrastructure - The Technology foundation team will have enough requirement to start forward on production on October 1st (55) | Infrastructure delivery is delayed |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be reassed with the replan | TRUE
A64 |  | SharePoint |  | Infrastructure - The review of the technology foundation items will only take 3 weeks (56) | Decisions that are not timely will cause delays |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be reassed with the replan | TRUE
A65 |  | SharePoint |  | Process - The team will work internal requirements first for People, Communites and then be able to add in External without significant rework (58) | If there is significant rework, schedule will be impacted |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be reassed with the replan | TRUE
A66 |  | SharePoint |  | Schedule - When the work with iteration 1 is complete the team will move into Iteration 2 (59) | Schedule will need to proceed, if not there will be schedule delays |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be reassed with the replan | TRUE
A67 |  | SharePoint |  | Schedule - The holidays at the end of year will consist of 2 week unavailability from the business, EY employees and Microsoft. The Hexaware team and 10% of the EY team will be available to continue working (60) | It's not likely deliverables and decisions can be counted on as normal, during this period |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | in the past | TRUE
A68 |  | SharePoint |  | Conversion - The March budget for Fusion will be modified to include the data conversion that is being moved in for Lotus Applications (61) | The Fusion budget would not be in line with the inclusion of the Lotus Applciations conversion scope |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Will be reassed with the replan | TRUE
A69 |  | SharePoint |  | Schedule - GAAIT replacement work has not yet been added to the plan (64) and will need to be added | Plan will need to be updated when this is defined |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | Working to determine which GAAIT work to add | TRUE
A77A | Mike Cliffel | SharePoint |  | The SharePoint Content Management System (CMS) Vision & Scope document is meant to obtain a common understanding of the vision of a global content management solution(s) (CMS), the types of content that need to be managed, the high-level capabilities that are needed, as well as the boundaries of the CMS. Specific features and business requirements for the content that needs to be managed by the CMS will be detailed in the Vision and Scope documents for specific solutions (e.g. Daily Tax Update, Communities, Research Tools, etc.) and mapped to the capabilities defined at the global level. | Risk of potential rework and that the solution may not meet the needs of the individual solutions. |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | vision and Scope contains that level | TRUE
A78B |  | SharePoint |  | In flight engagement teams would not be moved over to SP in process but will move after an engagement is finished | Will require additional work and storage. Could affect delivery dates and cost | [5 empty] | Not yet validated |  |  | TRUE
A79B |  | SharePoint |  | Existing ARC data will not be moved into SP but will remain in the current .NET application | Will require additional work and storage. Could affect delivery dates and cost | [5 empty] | Not yet validated |  |  | TRUE
A80 |  | SharePoint |  | Existing SP sites that were built on 2007 will not be converted into SharePoint (Fusion) | Will require additional work and storage. Could affect delivery dates and cost | [5 empty] | Not yet validated |  |  | TRUE
A81 |  | SharePoint |  | Data in files shares across EY will not be moved into SharePoint (Fusion) in an automated fashion | Will require additional work and storage. Could affect delivery dates and cost | [5 empty] | Not yet validated |  |  | TRUE
A82 |  | SharePoint |  | Approximate sizes of the Content management solutions is 10T and approximate size of the engagement data is approximately 80TB | Will require additional work and storage. Could affect delivery dates and cost | [5 empty] | Not yet validated |  |  | TRUE
A47 |  | SharePoint |  | The unified communications team will have the Lync and Exchange ready on the timeline (36) | Integrated Fusion scheduled would be impacted |  |  | 2012-01-18 | 2012-01-11 |  | Not yet validated |  | 18/01/12: TO be validated when revised TF & UC plans available pending O365 impact assessment | TRUE
A88 | Michelle Edmonds | SharePoint | SP - Metadata Management | No development changes will be made to the Taxonomy manager or the Auto classifier product | Would be more development and testing effort, higher risk. |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A89 | Michelle Edmonds | SharePoint | SP - Metadata Management | Autoclassifier and taxonomy manager products can be installed at different times | Baseline plan and approach would have to be changed, potential schedule/cost impact. |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A90 | Michelle Edmonds | SharePoint | SP - Metadata Management | Both the term store and the existing Taxi system will be kept up to date by the business until a decomission can be completed (It is a manual process to keep them up to date) | Any alternative automated solution would add additional development and testing effort, higher risk, schedule/cost impact. |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A91 |  | SharePoint |  | One view of EY externally that is consistent (external view could be different than internal) | Would have waited for Blueprint activities to design the external view. May be able to work on external front end sooner if assumption is false. |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A92 |  | SharePoint |  | Ovitas only receives taxonomy; does not update. | Complexity of Metadata Management increases if the system has to accept feeds from Ovitas. |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A93 |  | SharePoint |  | Anything in front end needs to be available in CMS / preview environment |  |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A94 |  | SharePoint |  | By end of April should have decision on whether to proceed with Ovitas. | Plan would need to be adjusted if Ovitas is not selected vendor. |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A95 |  | SharePoint | SP - CMS | CMS does not need to be released this calendar year. | Would have to be adjustments to plan to enable a calendar year 2012 delivery. |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A96 |  | SharePoint | SP - CMS | Will get answers from frog and Blueprint by end of June 2012. | Delay in understanding the ways end users will access and navigate content. |  | Michelle Edmonds | 2012-03-20 |  |  | Obsolete |  | Replan has been updated to reflect this | TRUE
A97 |  | SharePoint | SP - CMS | The goal of the POC is to validate that Workflow processes and metadata come together as expected for a sub-set of content | Increased scope of the POC, would require replanning. |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A98 |  | SharePoint |  | Scope provided in the detailed drafts will be the scope desired by BPO |  |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A99 |  | SharePoint |  | Infrastructure can be provided in the time on the plan |  |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A100 |  | SharePoint |  | Must deliver in calendar year 12 |  |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A101 |  | SharePoint |  | SP Cloud infrastructure will be delivererd in 30 or less weeks and then 8 weeks to implement initial profiles, my sites and communities to the cloud infrastructure |  |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A102 |  | SharePoint |  | Release 1 UX will be OOB SharePoint with only minor branding |  |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A103 |  | SharePoint |  | People Profiles, My Sites and Communities will be hosted in the cloud |  |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A104 |  | SharePoint |  | No performance testing of cloud workloads |  |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A105 |  | SharePoint |  | Delivery of the project will be done in smaller releases of functinoality |  |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A106 |  | SharePoint |  | Newsgator and Concept Searching will be selected and implemented with OOB configuration only |  |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A107 |  | SharePoint |  | SP Governance decisions will be defined and agreed to before needed by the SP workstreams |  |  | Michelle Edmonds | 2012-03-20 |  |  | Validated |  | In the current replan | TRUE
A15 | Adrian Mickleson | Technology Foundation |  | The networks requirements for M&C program can be delivered to meet the time scales for M&C program. Network requirements will be delivered as part of the GWAN program, which is yet to be kicked off. | Program schedule will be impacted | Brendan Millard |  | 2012-03-06 | 2012-06-15 | 2012-07-01 | Not yet validated |  | 6-Mar: This needs to be challenged with Brendan Millard; Laura em'd him the item for his awareness. John Murray's work will due to finish in June; would like to review mid-June with due beg-July. | FALSE
A83B | Daren Wicks | Technology Foundation |  | That the Dormant Deployment Project Team will be responsible for deploying the latest Microsoft Updates for both Lync and Outlook Dormant Client Packages until activation | None | Martin Versteeg |  | 2012-03-06 | 2012-03-21 | 2012-03-28 | Not yet validated |  | 20 March: Lync Dormant Deployment is complete. Official handover has been accepted by the Lync Project Team to include: Provide patch update when/where required Install Language Packs, when/where required Own Activation, inc testing - when/where required. All Other Activities relating to the Lync Project. The same agreement will be gleaned (when appropriate) for Outlook. The Project Costs are now associated to Tech Foundation 6-Mar: Adrian to discuss with Martin Versteeg. Review in 2 weeks; Due end of March. 29/02/12: Dormant deployment has now moved to TF. Action with Daren Wicks to validate 31/01/12: RB: not yet confirmed how this will happen. Discussions ongoing with Dormant Deployment Teams, Transition Lead, TF, and Ops, RACI needs to be developed for respective teams as to who does what in the activation process, as well as understanding implications of not applying service packs to the dormant clients until the point of activation 04-Jan: Adrian confirmed that this is valid. 14-11-11: Added by Daren Wicks. Implications is the Unified Comms project will need to pick up the resource costs until 2013, when full Activation has completed, and hand over to Operations has taken place. | FALSE
A10 |  | Technology Foundation |  | Assumption 50 day SLA to build a server | Additional lead times will add to the program schedule |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Obsolete |  | 4-Jan: Al and Adrian said that this should be marked obsolete; the length of time varies by location. Plans already took this into consideration and will continue to do so. | TRUE
A20 |  | Technology Foundation |  | It is assumed that the Data Centre Consolidation program will be delivering Disaster Recovery capability for in-country requirements in the next 24 months. M&C Program will design and implement DR & HA capability within the same site where DR is not available and be moved later once DR sites have been made available. | This will become an operational risk if once DR & HA infrastructure are deployed within the same data centre and DR capability is not in place. |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Obsolete |  | 4-Jan: Al and Adrian stated that this is incorrect for SP and Lync, correct for Exchange. This should be marked obsolete; refer to DCC program schedule. | TRUE
A3 |  | Technology Foundation |  | It is assumed that the lead time for the procurement of all required infrastructure will not exceed 6 weeks. | Additional lead times will add to the program schedule |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Obsolete |  | 4-Jan: Al and Adrian said this is obsolete; varies by country. DCC program has taken this into account. Refer to DCC Program Schedule. | TRUE
A4 |  | Technology Foundation |  | The rollout of the infrastructure will occur as a big bang | A staggered approach to roll out will increase the effort and time scale for the roll out. Plans will need to be revisited. |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Obsolete |  | 4-Jan: Al and Adrian said this is obsolete; Refer to DCC Program Schedule. | TRUE
A78A | Paul Neave | Technology Foundation |  | The current baseline plan for messaging assumes a 10 week planning phase with a start date of 03/10, with an output design sufficient to define a test environment after 2 weeks. | If the test Env design cannot be achieved with sufficient confidence to initiate provisioning and build of the test environment then the timeline will extend |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Obsolete |  | 04-Jan: Al and Adrian said that this is null and void - mark obsolete. We are past this point; no longer matters. 05-Oct-11: Added by P Neave | TRUE
A79A | Paul Neave | Technology Foundation |  | The current baseline plan for messaging assumes a 10 week planning phase with a start date of 03/10. The duration does not reflect the 30 week timeline in the draft SOW and is still required to be negotiated with Microsoft. If the timelines stay the same the baseline plan timeline is unachievable | If the timelines stay the same the baseline plan timeline is unachievable. The end date of the timeline will extend a day for every additional day that either the start is delayed or is injected into the duration of the planning phase |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Obsolete |  | 04-Jan: Already moved beyond this; mark obsolete. New SOWs since this was added. 05-Oct-11: Added by P Neave
A18 |  | Unified Communications |  | Lync will work seamlessly with Sometime during the transition phase | This will introduce additional technical complexity in the solution proposed, additional development will be required. | [5 empty] | Obsolete |  | 04-Oct-11: R Bouji: Superseded by Assumption #71
A5 |  | Unified Communications |  | The email conversion will only be in-box data and calendaring going forward | Would increase the amount of time needed for the conversion | [5 empty] | Obsolete |  | 04-Oct-11: R Bouji: Superseded by Decision #51. A Mickleson confirmed this outcome from FSG mtg in Washington
A16 |  | Unified Communications |  | Each individual's Sametime groups will not be moved as part of the Lync go live | This will introduce additional technical complexity in the solution proposed, additional development will be required. |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Validated |  | 04-Jan: Adrian confirmed that this has been validated. 04-Oct-11: RB: Superseded by Decision #52. A Mickleson confirmed this outcome from FSG mtg in Washington Revalidated following O365 decision: James Harrup-Brook, 28/02/12
A28 |  | Unified Communications |  | No data conversion is required to turn on Lync | Would require additional scope and budget for Lync effort. |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Validated |  | 04-Jan: Adrian confirmed this has been validated, for all countries including Japan. Revalidated following O365 decision: James Harrup-Brook, 28/02/12
A6 |  | Unified Communications |  | The email converison process can convert 15K boxes per week. | Would either speed up or slow down the overall conversion process |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Output to Risk/Issue | R91 | 21/02/12: RB: Network bandwith challenges may impact number of users able to be migrated. See R91 04-Jan: reworded from 5K boxes per night to 15K per week; then Adrian and Al confirmed it can be marked valid.
A7 |  | Unified Communications |  | Blackberry and iPhone users will be re-provisioned as part of the move to Exchange | Significant impact to business users using mobile messaging |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Validated |  | 04-Jan: Al and Adrian confirmed that this has been validated. Revalidated following O365 decision: Paul Neave, 27/02/12
A70 | Rewa Bouji | Unified Communications |  | Unified Comms will deliver Microsoft Outlook email integration for - eDocs - Faxing services - Local room booking | Deployment timescales may be delayed if additional applications are required to be integrated into Microsoft Outlook. Unified Comms will be running discovery/business analysis acitivity to determine what the total scope of mail-integrated applications in Lotus Notes are that must be integrated with Outlook, and present these to the FSG/design authority for agreement |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Obsolete |  | 21/02/12: RB: All plug in candidates will be subject to UC impact assessment process and taken to Lync & Outlook decision-making body to determine whether they will be Day 1 integrations. UC will not deliver the integration but will manage dependencies of individual projects set up to deliver the plugins if approved for Day 1 integration. This approach has been agreed by program lead and therefore assumption is now obsolete 04-Jan: Al and Adrian confirmed that this has been validated. 04-Oct-11: Added by R Bouji Revalidated following O365 decision: (add name and date here once the item has been revalidated)
A71 | Rewa Bouji | Unified Communications |  | Users will be able to operate Lync and Sametime simultaneously, (ie the two applications can co-exist on the users' desktop without adverse impact on performance of either application) however Lync users cannot communicate with users on Sametime, nor can Sametime users communicate with users on Lync. There is co-existence between the two applications, but no interoperability. Once all users have had Lync activated on their desktops and are "live", Sametime will be globally disabled | Benefit realisation of Lync user adoption will be impaired if users continue to have Sametime available and continue to use this instead of Lync. Support for two applications will also increase burden on global support services |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Validated |  | 04-Jan: Al and Adrian confirmed that this has been validated. 04-Oct-11: Added by RB Revalidated following O365 decision: James Harrup-Brook, 28/02/12
A73 | Rewa Bouji | Unified Communications |  | Global Core Loadset 5 (GCL5) will not support Lotus Sametime, therefore all EY users must be migrated onto Microsoft Lync before they can be upgraded to GCL5. This creates an outbound dependency from M&C Unified Comms into the GCL5 program | Delays to deployment of Lync and global disabling of Sametime will impact on when GCL 5 can begin deployment | Martin Versteeg |  | 2012-01-04 | 2012-01-11 | 2012-01-31 | Obsolete |  | 06-Feb: Confirmed that GCL5 will support Lotus Notes Sametime 8.5.3 per email from Brett van Gelder dated 18/01/12 04-Jan: Adrian and Al said that GCL5 will support Lotus Notes Sametime. Change text from will NOT. This is a valid statement. Laura hasn't marked valid yet; need to check on remainder of statement. 04-Oct-11: Added by R Bouji
A74 | Rewa Bouji | Unified Communications |  | Due to constraints on the amount of data that can be transferred, as well as constraints on the level of global helpdesk support that can be provisioned post-migration, the number of users in each deployment tranche from Lotus Notes to Microsoft Outlook is capped at approx. 10,000 users | Higher user numbers to be migrated will take longer to transition and will reduce the number of users that can be migrated in any given deployment window, as well as adversely impact the global support service due to an expected increase in support call volumes |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Obsolete |  | 04-Jan: Adrian and Al said to mark this item obsolete; this is the same as A6. 04-Oct-11: Added by R Bouji
A75 | Rewa Bouji | Unified Communications |  | The current window for migration is 15 hours per weekend, taking into account global office hours | Reduced window for migration may reduce the number of users that can be transitioned in each tranche |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Output to Risk/Issue | R97 | 21/02/12: RB: Output to R97 05-Jan: Al and Adrian confirmed this is valid. 04-Oct-11: Added by RB Revalidated following O365 decision: (add name and date here once the item has been revalidated)
A11 | unknown | Unified Communications |  | Email conversions are only done on Weekdays and the plan follows the sun | Migrations will take longer should there be restriction to the follow the sun approach | Paul Neave, O365 team, Transition management |  | 2012-01-18 | 2012-02-22 | 2012-02-28 | Output to Risk/Issue | R97 | 21/02/12: RB: Output to R97 14/02/12: RB: Needs to be confirmed with MSFT what the maximum number of migrations can be per window for O365, and to confirm with Transition Management what the maximum number of migrations can be for On-prem 18/01/12 - RB Needs to be confirmed with TF and Transition Management to determine what network impact will be if weekday vs weekend
A77B | Rewa Bouji | Unified Communications |  | CRM integration with Outlook is not expected to be delivered in Phase 1. | CRM integration has significant design implications, particularly for infrastructure, and design/planning to date has not assumed CRM integration. Requirement for CRM integration with Outlook in Phase 1 has been discussed but no formal Change Request has been raised to the program for its delivery. | FSG | Jeremy Brown | 2012-01-18 | 2012-01-11 | 2012-01-27 | Validated |  | 06/02/12: RB - confirmed via email from Martin Kremmer that CRM not in scope for Day 1 18/01/12: RB - Martin Kremmer seeking clarification from Bob Reiner by Jan 27th 28-Oct-11: Added by RB. N Wood confirmed that CRM integration is not built into current design/planning.
A8 |  | Unified Communications |  | Blackberry and iphone users by server will be part of the input to selecting migration waves | Significant impact to business users using mobile messaging |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Obsolete |  | 04-Jan: Adrian and Al said this is not valid, obsolete. No impact to program.
A83A | Rewa Bouji | Unified Communications |  | M&C must have migrated users onto Microsoft Outlook at least 4-6 weeks before GCL5 can roll out to those users | If this assumption is not proved there may be a need to revise the planned deployment approach and to remove the outbound dependency from M&C UC to GCL5 |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Obsolete |  | 04-jan: Adrian confirmed that this is valid. 01-Nov-11: Added by R Bouji. A Mickleson confirmed to UC & TF leads that UC must migrate users before GCL5 can be rolled out to those users Revalidated following O365 decision: (add name and date here once the item has been revalidated)
A72 | Rewa Bouji | Unified Communications |  | The following assumptions hold for migration from Lotus Notes to Microsoft Outlook: - During migration there will be co-existence of Lotus Notes to Microsoft Outlook across EY, but not for individual users, ie users cannot have both Lotus Notes and Microsoft Outlook as active mail clients - Microsoft Outlook and Lotus Notes users will be able to query live free/busy calendar data regardless of which mail client is being used by invitees; updates, reschedules, etc will be processed appropriately regardless of the mail client in use - Rich text items (links, buttons, sections etc) in eg global communications will be replicated appropriately for the user's mail client (exact mechanism for this TBD) - Contacts will appear in global mail lists regardless of the mail client the user is on | Lack of co-existence and interoperability (eg on calendar and contact lookups) will have significant business impact and reduce likelihood of operational acceptance, as well as increase risk of adverse impact on global support services | Paul Neave, O365 team |  | 2012-01-18 | 2012-02-22 | 2012-02-17 | Output to Risk/Issue | R96 | 21/02/12: RB - TF Exchange team still working through the three way co-existence that will be required to ensure three way free/busy and any limitations there may be. RB has raised R96 14/02/12: RB: Needs to be confirmed with MSFT what co-existence constraints will exist as part of O365 18/01/12: To be validated pending O365 impact assessment and detailed discussions with Binary Tree 04-Oct-11: Added by RB
A9 |  | Unified Communications |  | Outlook packages can be deployed before hand and left inactive and be activated on desktops at the time of Migration | Additional deployment step in sequence will be required and may add to the timeline. |  | 04-Jan RAID call attendees | 2012-01-04 |  |  | Validated |  | 21/02/12: RB: Awaiting response from Paul Neave on revalidation 04-Jan: Adrian confirmed that this is valid. Revalidated following O365 decision: Paul Neave, 221/02/12
A76 | Rewa Bouji | Unified Communications |  | A Pilot phase will operate for both Lync and Outlook deployments. The following assumptions stand for each Pilot: - Pilot user volumes will ramp up from 0 to ~5000 users over 4-6 weeks, with full Phase functionality – devices included - Pilot groups will be located in at least two separate geographies - A Go /No-go decision point for full deployment will be made based on the outcomes of the Pilot phases | Risk that the business will not accept global deployment of Lync and Outlook unless a Pilot can "prove" successful live operation | FSG/ Business Deployment Lead |  | 2012-01-18 | 2012-02-22 | 2012-03-31 | Not yet validated |  | 15/03/12: RB: Pilot for Lync and Outlook agreed in principle, however volumes and duration still subject to agreement with Business Deployment and Operations (who will need to be ready to support Pilot volumes). Deployment/migration schedule and volumes to be discussed in meeting on 21/03/12 14/02/12: RB: Awaiting deployment strategy from Martin Kremmer 18/01/12: RB - To be confirmed with Martin Kremmer following development of business deployment plan 04-Oct-11: Added by RB
A86 | Rewa Bouji | Unified Communications |  | UC has inherited the working assumption that countries will bear the cost of purchasing peripherals (headsets, webcams etc) to be used with Lync, rather than the program, however it has been found that this assumption has not previously been logged or validated | Significant increase to program costs not budgeted for | FSG |  | 2012-01-31 | 2012-02-22 | 2012-02-28 | Obsolete |  | 12/03/12: RB: Confirmation received from R Cansick that process is for IT to make provision in country budgets for the total device spend. Whilst countries will pay for devices when purchased, these will be charged to the country itself, but then cross-charged back to IT via the settlements process. Provision of $10m has been made in M&C budget for FY13. 14/02/12: RB: Cost model for projected device spend per country being developed with Global Procurement and OSS - aim to have early draft of costs by 28/02/12 for delivery to Alan Guthrie 31/01/12 - RB: Added to Assumption Log. Decision required (decision pending created on Decision log)
A108
A109
A110
A111
A112
A113
A114
A115
A116
A117
A118
A119
A120

## Decision Log
# | Date Opened | Identified by | Assigned to | Program / Workstream | Project / Workstream | Status | Target Date | Decision date | Decision makers | Decision Description and Impact | Revalidated in light of cloud decision | Comments | Decisions 1-186 to be revalidated in light of the cloud decision. Include date in column K; decisions after 18-Jan should already take into account the cloud decision. | Overdue | 2012-03-22
D88 | unknown | Steve Jelf | Steve Jelf | App & Data Migration |  | Closed | 2012-02-15 | 20th Feb | Q&RM | Generic process decision on accessing Lotus Notes apps Agree approach to enable access to 50k+ Lotus Notes databases, other than complete delegation. | 2012-02-20 | 20th Feb - Confirmation obtained that process is fit for purpose, however a separate process is required "Sensitive" databases plus databases that are hosted in "red box" (where data cannot be moved outside of country borders) countries. 31st Jan - Q&RM have tentatively accepted recommendation, Awaiting formal confirmation from S. Chakerian. "23rd Jan Single frame risk profile received from ADM work stream. (NS / MS) Work stream to confirm what out of scope for this process (Partners servers / applications, Legal counsel data / applications etc) and what the suggested process will be for these applications. SC - Process needs to be validated / with Infosec / and certain Q&RM members.(which SC will complete). |  | TRUE
D75A |  |  |  | App & Data Migration |  | Closed | 2011-11-30 |  | each of the Service Line / CBS Functional Stakeholders | Who is the person accountable (by Service Line / CBS function) for determining the future state of each of the applications they own |  | Closed. FSG provide final sign off after agreement at the working group level. (prev DP22) |  | TRUE
D75B | unknown | Martin Stutchbury | Neil Sahdev | App & Data Migration |  | Pending | 2012-03-30 |  | Core Leadership Team | We need a decision on the ADM Operating Model and Resourcing Strategy. i.e. Will Markets/CBS be given the budget and be tasked with resourcing and delivery 200 additional applications/year, or will it sit within the Cross-Org team (with the indistrialised delivery model). |  | 06-Mar-2012: Request for decision raised Q4'11 - now impacting the initiation of the RFP for vendors for portfolio teams (refer to Issue 141) |  | FALSE
D184A | unknown | Martin Stutchbury | Neil Sahdev | App & Data Migration |  | Pending | 2012-03-23 |  | UC | Decisions around integrated room booking, faxing, catering and AV booking is needed. Currently this is in the scope of UC, but if a non-integrated solution is required it could be delivered out of ADM - however a significant CR would be required as we do not have budget or resources for this. Identifying a suitably skilled team to deliver this could take a long time and impact the roll out schedule of TF/UC. |  | 19-Mar: Neil scheduled a session to discuss Wed. AM. |  | FALSE
D209 | 2012-03-05 | Neil Sahdev | Neil Sahdev | App & Data Migration |  | Pending | 2012-05-31 |  | Enterprise Architecture and Information Architecture | Agreement on the Master Data Management direction for the period between now and when the E&Y Enterprise Data Warehouse solution will be available |  |  |  | FALSE
D46 |  |  |  | Change Management |  | Closed |  | 2011-09-28 | Participants in September 2011 Functional Stakeholders meeting Washington DC | Generic Knowledge renamed to User Experience. | 2012-02-13 | 13-Feb: This is not affected by O365 decision; consider revalidated. |  | TRUE
D98 | unknown | Al Grljevic | Al Grljevic | M&C Program |  | Closed |  | 2012-01-25 | Adrian Mickleson, Nick Wood | M&C will rebuild Good and BES on exchange on the appropriate versions | 2012-01-25 | Action: Determine cost and take forward to the CR meeting |  | TRUE
D10 | unknown | unknown |  | M&C Program |  | Closed |  | 2010-04-21 | Michelle Edmonds, Adrian Mickleson | Each workstream will have its own project plan with a roll-up of milestones and dependencies to the program level / plan | 2012-02-27 | Confirmed as revalidated by Ian Bourne, 27-Feb. |  | TRUE
D11 | unknown | unknown |  | M&C Program |  | Closed |  | 2010-04-21 | Michelle Edmonds, Adrian Mickleson | There will be one Business Case for the entire program |  | 12-Mar Ian: In progress. 27-Feb: investigation required prior to revalidation (Ian B. took action) |  | TRUE
D13 | unknown | unknown |  | M&C Program |  | Obsolete |  | 2010-04-21 | Michelle Edmonds, Adrian Mickleson | The Cleveland Team (Michelle) will own reconciliation of actual hours versus budgeted hours for the entire Program (also take into consideration Time and Expenses vs. Fixed, etc) |  | Only active data will need to be converted 27-Feb-2012: obsolete. Laura and Ian reviewed; new process in place. Opened D192 to represent the new process, which will be confirmed in the very near future. |  | TRUE
D14 | unknown | unknown |  | M&C Program |  | Obsolete |  | 2010-04-21 | Michelle Edmonds, Adrian Mickleson | Change Request Log will be managed at the workstream level / Program level variances will be taken to the Steering Committee |  | 07-Oct-2011: BvG:Note that "community data" could include Quickr as well as a range of Lotus Connections data 27-Feb-2012: Obsolete. New process in place; opened D193 to represent the new decision around the Change Control process. |  | TRUE
D12 | unknown | unknown |  | M&C Program |  | Closed |  | 2010-04-21 | Michelle Edmonds, Adrian Mickleson | Produce a Vision and Scope document for each workstream: A&DM, Change, SharePoint, Tech Foundation and Unified Comms. | 2012-02-27 | 27-Feb: Ian said we agreed each stream should have a scope doc (including Tech Foundation, Change, and A&DM). Laura sent note to leads about the modification to previous decision. Decision edited from: "Only produce a Vision and Scope document for Fusion and Unified Comms workstreams." |  | TRUE
D2 | unknown | unknown |  | M&C Program |  | Obsolete |  | 2010-11-11 | Chris D'Arcy | The reports will not be customized from MS reporting services |  | 27-Feb-2012: Laura em'd Chris for clarification. As there is no context with this item, Chris does not recall to what is refers. Requested it be marked obsolete. |  | TRUE
D39 | unknown | unknown |  | M&C Program |  | Obsolete |  | 2011-09-27 | Participants in September 2011 Functional Stakeholders meeting Washington DC | The current vision meets the needs and does not need to be modified. |  | 27-Feb-2012: This item is no longer accurate, marked obsolete (per Ian Bourne). The vision has been altered as a result of the O365 decision and replanning is underway. |  | TRUE
D15 | unknown | unknown |  | M&C Program |  | Closed |  | 2010-04-21 | Michelle Edmonds, Adrian Mickleson | PM Tool - entry will be at the M&C program level | 2012-02-27 | 07-Oct-2011: BvG:Duplicate of #19 above 23-Feb LM: cant find D19 that applies to PM tool 27-Feb-2012: Revalidated by Ian Bourne. |  | TRUE
D44 | unknown | unknown |  | M&C Program |  | Closed |  | 2011-09-28 | Participants in September 2011 Functional Stakeholders meeting Washington DC | Face to face meetings for Functional Stakeholder Group will be scheduled and managed on an on-going basis. | 2012-02-27 | 27-Feb-2012: Laura and Ian adjusted item from, "Next face to face meeting for functional stakeholders: 15-16 Nov LONDON. Jan (US TBD)" |  | TRUE
D5 |  |  |  | M&C Program |  | Obsolete |  | 2010-11-11 | Team | List of languages supported are as follows, from a note from Laura |  | no list of languages; Kerri confirmed 04/Oct that no final decision has been made here. Obsolete. |  | TRUE
D49 | unknown | unknown |  | M&C Program |  | Closed |  | 2011-09-28 | Participants in September 2011 Functional Stakeholders meeting Washington DC | Agreement to cancel the weekly Functional Stakeholder call and reschedule for every other week. | 2012-02-27 | 27-Feb-2012: confirmed as revalidated by Ian Bourne. |  | TRUE
D9 | unknown | unknown |  | M&C Program |  | Closed |  | 2010-04-21 | Michelle Edmonds, Adrian Mickleson | Each workstream (SharePoint, Technical Foundation, Application & Data Migration, Unified Communications, Change Management, PMO) will have its own charge code | 2012-02-27 | 27-Feb-2012: Ian Bourne confirmed; added PMO to the list as it too has its own charge code. |  | TRUE
D8 | unknown | unknown |  | M&C Program |  | Pending | 2012-03-30 |  | Ian Bourne / Laura Murphy | We will have one RAID for the entire Program … |  | 14-Mar: changing - planning to move doc to different format. Other changes may occur out of 30 day plan. 27-Feb-2012: Ian and Laura confirming process for workstream RAID management. 21-Apr-2010 decision had been: We will have one RAID for the entire Program / each workstream may need a supplemental RAID |  | FALSE
D95 | unknown | Al Grljevic | Al Grljevic | M&C Program |  | Obsolete | 2012-02-01 |  | RFP-Managed Service - Siggi Hauer | End state Target Operating Model (TOM) for collaborative platform support Significant challenge to transition workstream |  | 9-Feb: Al - this is not a decision, but an action for transition management team to resolve. Marked obsolete and added to actions log. |  | TRUE
D87 |  | Steve Jelf |  | M&C Program |  | Obsolete |  |  | FSG | Legal Holds How would Q&RM apply a legal hold on data (including mail or / documentation / content created from a member of staff who has left the firm? What technology is available to support this Q&RM requirement? Could a global process exist? It is not known if SharePoint (out of the box) can accommodate the Q&RM high level requirements |  | 2nd Feb - Further work is required by IT Services on this one prior to a decision being required. (SC/JR) to formulate high level requirements for review by Steering Group for further discussion" |  | TRUE
D193 | 2012-02-27 | Ian Bourne |  | M&C Program |  | Closed |  | 2012-02-27 | Ian Bourne | All Changes will now be managed through the defined and agreed Change Control process. The process document may be found here. | 2012-02-27 | 27-Feb: This item was opened as a result of D14 being marked obsolete (described an outdated change control process). |  | TRUE
D99 | 2012-02-07 | Brett van Gelder | Alan / Guy | M&C Program |  | Pending | 2012-02-22 |  | Guy Morgan / Alan Guthrie | We need a decision on whether GAAIT (and Ovitas work) are part of M&C or not and if they are they need to be properly re-absorbed into our governance structures. If not Brett would like to know so that he can ensure that Enterprise Architecture is differently engaged than is currently the case. (linked to I110) |  | 22-Feb: on RAID call discussed I110, hoping to get more info at FSG meeting next week. |  | TRUE
D192 | 2012-02-27 | Ian Bourne | workstream leads | M&C Program |  | Closed | 2012-03-07 | 2012-03-12 | Ian Bourne | Each workstream, in conjunction with the PMO, will validate hours and expenses; process to be communicated in the very near future. | 2012-03-12 | 12-Mar Ian: This process is in place. 27-Feb: Opened this decision as a result of D13 being marked obsolete. |  | TRUE
D212 | 2012-03-13 | M&C team | M&C team | M&C Program |  | Closed | 2012-03-13 | 2012-03-13 |  | Mobile enablement will not be rolled out as part of Phase 1. | 2012-03-13 | 13-Mar: This had been an action in the daily stand up callls and this update was provided today. Jeremy sending a comm to the workstream leads for their awareness. The team may architect for mobile in P1, but not design and deliver. We will not paint ourselves in a corner for P2 and on. |  | TRUE
D101 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-10-15 | 2011-10-15 | Guy Morgan | Requirement Sessions will stop on the 20 December and will resume after the new year | 2012-02-27 | Decision in the past; No impact as result of cloud |  | TRUE
D102 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-10-15 | 2011-10-15 | SharePoint team | Iteration 3 requirements will end on December 16th to support the 3 day Thanksgiving holiday in the US | 2012-02-27 | Decision in the past; No impact as result of cloud |  | TRUE
D103 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-11-07 | 2011-11-07 | Michelle Edmonds | In order to provide the Design Authority completed analysis with the appropriate level of detail, the SharePoint team will do work on items open with the Design Authority and will document the options for the DA. The work will be appropriately modified to reflect any items from the DA. | 2012-02-27 | Decision in the past; No impact as result of cloud |  | TRUE
D104 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-11-07 | 2011-11-07 | SharePoint team | Iteration 4 requirements will end on January 16th to support the lost time over the holidays | 2012-02-27 | Decision in the past; No impact as result of cloud |  | TRUE
D105 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-11-07 | 2011-11-07 | Michelle Edmonds | Open questions about requirements will be logged in TFS and not in the documentation. This way they can be tracked and disposed | 2012-02-27 | Decision in the past; No impact as result of cloud |  | TRUE
D16 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | 2011-09-23 | 2011-09-23 | Program Management | Phase 1 Delivery - Phase 1 delivery will consist of 4 Shared Services for the platform (Search, Taxonomy, Content Management, and People Profile) (1) | 2012-03-18 | 27-Feb: Reviewed - Decision in the past; Impacted by cloud and replan |  | TRUE
D17 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | 2011-09-23 | 2011-09-23 | Program Management | Search - FAST Search will only Search new SharePoint content (2) | 2012-03-18 | 27-Feb: Reviewed - may no longer be true |  | TRUE
D176 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-12-08 | 2011-12-08 | John Costello | Approval to send out the Social Features RFP | 2012-02-27 | Decision in the past; No impact as result of cloud |  | TRUE
D177 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-12-08 | 2011-12-08 | Bob Wasserman, Sharon Rahav, Scott Machovina, Michelle Edmonds | The translation RFP will be modified to do an art of the possible session with the vendors in order to help the business users understand the features and functions available in tools | 2012-02-27 | Decision in the past; No impact as result of cloud |  | TRUE
D18 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-23 | 2011-09-23 | Program Management | Conversion - No existing SP sites will be connected to the environment they will need to be converted to the new environment (3) | 2012-03-18 | 27-Feb: Reviewed - Decision in the past - Need to confirm at Replan; May be impacted |  | TRUE
D19 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-23 | 2011-09-23 | Program Management | Taxonomy - Only new applications will be required to use the new taxonomy (4) | 2012-03-18 | 27-Feb: Reviewed - Decision in the past - Need to confirm at Replan; May be impacted |  | TRUE
D20 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | 2011-09-23 | 2011-09-23 | Program Management | Search - Search internally will federate with the Autonomy search (5) | 2012-03-18 | 27-Feb: Reviewed - Decision in the past - Need to confirm at Replan; Impacted |  | TRUE
D21 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-12 | 2011-09-23 | Program Management | Conversion - People will convert data from Lotus Connections only (6) -- may be partially automated or manual | 2012-02-27 | Decision in the past - Need to confirm at Replan; No impact based on cloud decision |  | TRUE
D26 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | 2011-09-23 | 2011-09-23 | Program Management | Taxonomy - Only new SP solutions will use the new taxonomy (19) |  | decision in the past |  | TRUE
D22 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | 2011-09-23 | 2011-09-23 | Program Management | 3rd Party Products - 3rd party products needed for Phase 1 will be identified in the first 3 iterations (8) | 2012-02-27 | 07-Oct-2011: BvG:Communities likely including at least some Quickr content, e.g., AACE content Confirm at replan; No impact based on cloud decision |  | TRUE
D23 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-23 | 2011-09-23 | Program Management | Phase 1 Delivery - There will not be delivery in Phase 1 for Managing Clients and Engaging Accounts (9) | 2012-02-27 | Decision in the past - Need to confirm at Replan; No impact based on cloud decision |  | TRUE
D24 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-23 | 2011-09-23 | Program Management | Phase 1 Delivery - Historical data will not need to be converted to SharePoint (10) | 2012-02-27 | Confirm at replan; No impact based on cloud decision |  | TRUE
D25 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-23 | 2011-09-23 | Program Management | Conversion - DTU, people, community and credentials data are all that is needed for Phase 1 data migration (15) | 2012-02-27 | Confirm at replan; No impact based on cloud decision |  | TRUE
D27 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-23 | 2011-09-23 | Program Management | Taxonomy - The two taxonomy solutions will be kept in synch, where appropriate, manually (20) | 2012-02-27 | Confirm at replan; No impact based on cloud decision |  | TRUE
D28 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-23 | 2011-09-23 | Program Management | Taxonomy - The business will update the tagging of the content as needed (21) | 2012-02-27 | Confirm at replan; No impact based on cloud decision |  | TRUE
D29 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | 2011-09-23 | 2011-09-23 | Program Management | Process - The team is using the standard ITS Iterative SDA for the delivery of the project - as explained at the training in July (28) | 2012-02-27 | Confirm at replan; No impact based on cloud decision |  | TRUE
D3 |  | Michelle Edmonds |  | SharePoint |  | Obsolete |  | 2010-11-11 | Team | The languages to be used as part of the MS POC will be French and a double byte language | 2012-02-27 | Confirm at replan; No impact based on cloud decision |  | TRUE
D30 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | 2011-09-23 | 2011-09-23 | Program Management | Phase 1 Delivery - The team will coalesce into one content management solution (31) | 2012-02-27 | Confirm at replan; No longer true due to GAAIT need for an Ovitas like solution |  | TRUE
D31 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-23 | 2011-09-23 | Program Management | UAT - The business will create it's own test cases for UAT (32) | 2012-02-27 | Confirm at replan; No impact based on cloud decision |  | TRUE
D32 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-23 | 2011-09-23 | Program Management | UAT - The business will administer the UAT and create their own data (33) | 2012-02-27 | Confirm at replan; No impact based on cloud decision |  | TRUE
D33 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-23 | 2011-09-23 | Program Management | Conversion - The eRooms, etds, and Quickr conversions will begin post go live of the new environment (43) | 2012-02-27 | Confirm at replan; No impact based on cloud decision |  | TRUE
D34 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-23 | 2011-09-23 | Program Management | Phase 1 Delivery - Each new team space will go through the formal provisioning process (44) | 2012-02-27 | Confirm at replan; No impact based on cloud decision |  | TRUE
D35 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-23 | 2011-09-23 | Program Management | Process - BA will not re-document the functionaltiy that is OOB with SP (47) | 2012-02-27 | Confirm at replan; No impact based on cloud decision |  | TRUE
D36 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-23 | 2011-09-23 | Program Management | Infrastructure - Ordering of hardware will occur before the design is complete; some infrastructure will be able to be purchased prior to the final production architecture approval (57/65) |  | Confirm at replan |  | TRUE
D37 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | 2011-09-23 | 2011-09-23 | Program Management | Schedule - The iterations will be 3 weeks in length starting on Tuesday and ending on Monday (62) | 2012-02-27 | Confirm at replan; Impacted - no longer true |  | TRUE
D38 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | 2011-09-23 | 2011-09-23 | Program Management | Schedule - All workstreams will remain on the same iterative schedule (63) | 2012-02-27 | Confirm at replan; Impacted - no longer true |  | TRUE
D4 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | 2010-10-15 | 2010-10-15 | Team | The MS POC will only focus on items that need to be proved before a decision can be made. This is not a prototype but only a POC | 2012-02-27 | Confirm at replan; No impact based on cloud decision |  | TRUE
D40 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-27 | 2011-09-27 | Participants in September 2011 Functional Stakeholders meeting Washington DC | Convergence of EYD is now part of Phase 2 (SharePoint). | 2012-03-20 | 27-Feb; Reviewed - Confirm at replan; May be impacted - check with Jeremy Brown |  | TRUE
D41 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-27 | 2011-09-27 | Participants in September 2011 Functional Stakeholders meeting Washington DC | Policies now removed from Phase 1 (SharePoint). | 2012-03-20 | Confirm at replan; may be impacted |  | TRUE
D42 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | 2011-09-27 | 2011-09-27 | Participants in September 2011 Functional Stakeholders meeting Washington DC | The requirement approval approach presented was agreed to (business core team to make decision and approve requirements). | 2012-03-20 | 27-Feb: Reviewed - Confirm at replan; May be impacted |  | TRUE
D43 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | 2011-09-27 | 2011-09-28 | Participants in September 2011 Functional Stakeholders meeting Washington DC | DELIVER includes DTU. - No longer true | 2012-03-20 | Confirm at replan; may be impacted (check D25, too, which includes DTU in the description for P1 data migration) |  | TRUE
D45 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-27 | 2011-09-28 | Participants in September 2011 Functional Stakeholders meeting Washington DC | Fusion will be renamed to SharePoint. | 2012-02-27 | Decision in the past; No impact as result of cloud |  | TRUE
D47 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-27 | 2011-09-28 | Participants in September 2011 Functional Stakeholders meeting Washington DC | Agree to including Internal Team Sites (Communities of Interest and Practice) in Phase 1 (SharePoint). | 2012-02-27 | Confirm at replan; No impact based on cloud decision |  | TRUE
D48 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2011-09-27 | 2011-09-28 | Participants in September 2011 Functional Stakeholders meeting Washington DC | SP requirements sessions will start the week of Oct. 10th, as opposed to week of Oct. 3rd. | 2012-02-27 | Decision in the past; No impact as result of cloud |  | TRUE
D6 |  | Michelle Edmonds |  | SharePoint |  | Closed | 2010-11-11 | 2010-11-11 | Team | The team will not be showing the customization screen and process to the executives as part of the EK POC | 2012-02-27 | decision in the past No impact based on cloud decision |  | TRUE
D69 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | ASAP | 2011-11-01 | Ken Hammond | Need a workstream leader for communities | 2012-02-27 | Louis Lorton was provided as the lead (prev DP16); No impact based on cloud decision |  | FALSE
D70 | unknown | Michelle Edmonds | Michelle Edmonds | SharePoint |  | Closed | ASAP |  | Bob Reiner | Need a designated team to review the SharePoint Open Items List | 2012-02-27 | (prev DP17) No impact based on cloud decision |  | FALSE
D71 | unknown | Michelle Edmonds | Michelle Edmonds | SharePoint |  | Closed | ASAP |  | Bob Reiner | Need a decision on the business team to engage with on Managing Accounts / Engaging Clients - using blueprint process | 2012-02-27 | (Prev DP 18) No impact based on cloud decision |  | FALSE
D72 | unknown | Michelle Edmonds | Michelle Edmonds | SharePoint |  | Obsolete |  |  | Business | Need decision on who should participate in the User Experience workstream | 2012-03-15 | Decision was made and the sessions occurred |  | TRUE
D73 | unknown | Michelle Edmonds | Michelle Edmonds | SharePoint |  | Obsolete |  |  | Business | Need to undertand how internal / external collaboration with clients will work - Open with Blue print team | 2012-03-15 | With the bluerpinting team |  | TRUE
D74 | unknown | Michelle Edmonds | Michelle Edmonds | SharePoint |  | Obsolete |  |  | Business | Need resolution of individuals assigned to more than one workstream. | 2012-03-15 | Decision is not longer necessary due to replanning and workstream leaders |  | TRUE
D77 | unknown | Michelle Edmonds | Michelle Edmonds | SharePoint |  | Obsolete |  |  | Bob Reiner | Need the names of those business individuals that should participate in the frog Kickoff Session in late November | 2012-02-27 | No longer needed |  | TRUE
D7 |  | Michelle Edmonds |  | SharePoint |  | Obsolete | 2010-11-11 | 2010-11-11 | Team | All desktop units will be deployed with 2010 for the POC - No longer true | 2012-03-20 | 27-Feb: Reviewed - decision in the past; Impacted |  | TRUE
D186 | 2012-02-15 | Michelle Edmonds |  | SharePoint |  | Closed |  | 2012-02-15 | O365 Feb 12 team | SAML will not be needed for SP O365 and no workarounds are needed. The OOB solution will meet the needs. | 2012-02-15 | Decided in the O365 session w/o 12-Feb in Cleveland. |  | TRUE
D187 | 2012-02-16 | Norm Lambert |  | SharePoint |  | Closed |  | 2012-02-15 | O365 Feb 12 team | Subscribe and Deliver is an On-Premises solution. | 2012-02-15 | Decided in the O365 session w/o 12-Feb in Cleveland. |  | TRUE
D188 | 2012-02-16 | Norm Lambert |  | SharePoint |  | Closed |  | 2012-02-15 | O365 Feb 12 team | External Facing content would not be stored in Office 365 due to cost of partner licenses. Office 365 partner access to be used only for non client partners (working with a specific vendor for collaboration). | 2012-02-15 | Decided in the O365 session w/o 12-Feb in Cleveland. |  | TRUE
D189 | 2012-02-16 | Norm Lambert |  | SharePoint |  | Closed |  | 2012-02-15 | O365 Feb 12 team | Delivery Engine is an On Premise solution due to FAST integration and that it will be architected as either a Windows Service or a SharePoint Service Application, neither of which is supported in Office 365 dedicated. | 2012-02-15 | Decided in the O365 session w/o 12-Feb in Cleveland. |  | TRUE
D190 | 2012-02-16 | Norm Lambert |  | SharePoint |  | Closed |  | 2012-02-15 | O365 Feb 12 team | Amount of customization will be high for front end components and would have to be duplicated between the cloud and on premises. Since limited code can be implement on a bi-weekly basis will take considerable time to implement all Subscribe and Deliver customizations to the cloud. | 2012-02-15 | Decided in the O365 session w/o 12-Feb in Cleveland. |  | TRUE
D191 | 2012-02-16 | Norm Lambert |  | SharePoint |  | Closed |  | 2012-02-15 | O365 Feb 12 team | Since the data is EY Sensitive it could live in the Extranet and secured similarly to EY Delivers (would have to confirm the data classification with the businiess). Content would not have to be moved between On Premises Intranet and Extranet if all data was in the Extranet | 2012-02-15 | Decided in the O365 session w/o 12-Feb in Cleveland. |  | TRUE
D194 | 2012-02-28 | Michelle Edmonds | FPG | SharePoint |  | Closed |  | 2012-02-28 | Bob Reiner | If multiple templates (My Sites) are chosen for each Service Line it is not a concern for the technical team | 2012-02-28 |  |  | TRUE
D195 | 2012-02-29 | FPG | FPG | SharePoint |  | Closed |  | 2012-02-28 | FPG | The solutions for SP need to be designed to work on multiple devices | 2012-02-28 |  |  | TRUE
D197 | 2012-01-09 |  |  | SharePoint |  | Closed |  | 2012-01-09 | Executive Sponsors | Adoption of Microsoft O365 cloud | 2012-03-06 | Added in retrospect - to provide a reference |  | TRUE
D76 | unknown | Michelle Edmonds | Michelle Edmonds | SharePoint |  | Closed |  |  | Bob Reiner | Andy Walsh has a SP governance model in process Need to determine how should particpate in the SP Governance sessions |  | (prev DP23) |  | TRUE
D93 | unknown | Al Grljevic | Al Grljevic | Technology Foundation |  | Pending | 2012-04-02 |  | GDC - Siggi Hauer | In which countries are we prepared to go wihtout DR sites? Implications: without a DR site, we would have backups, which implies additional cost and that we won't be able to state an RTO/RPO. PN – Without a decision on this we risk impacts on being able to finalise and deploy the On-premise Excjhnage solution wherever there is still doubt as to whether there is going to be a DR site. It will also delay the completion of testing across On-Prem and Cloud environments and identification of any performance and/or network bottlenecks. Delay will also impact the finalisation of the Managed service (Microland )negotiations on how many sites they are supporting and could threaten the viability of this as an option . |  | 16-Mar: Moved due date from end of Feb to 2-Apr per Al to accurately reflect the target. 20-Feb: JC - Will be decided in discussion with COO. |  | FALSE
D92 | unknown | Al Grljevic | Al Grljevic | Technology Foundation |  | Pending | 2012-04-02 |  | GDC - Siggi Hauer | Final decisions around GDCs and in-country locations; Impact to technical pilot for Exchange on-prem and to giving list of names to DCC. Massive impact on Hardware deployment plan. What is the decision on Market Drivers? PN – Without a decision on this we risk impacts on being able to finalise and deploy the On-premise Exchange solution. It will also delay the completion of testing across On-Prem and Cloud environments and identification of any performance and/or network bottlenecks. Delay will also impact the finalisation of the Managed service (Microland )negotiations on how many Users they are supporting and could threaten the viability of this as an option . |  | 16-Mar: Moved due date from end of Feb to 2-Apr per Al to accurately reflect the target. 5-Mar: Al to set up a meeting early next week to review the updated deck 20-Feb: JC - We are waiting on the presentation from Al and Brett that we can use with the area COO's. |  | FALSE
D94 | unknown | Al Grljevic | Al Grljevic | Technology Foundation |  | Pending | 2012-03-23 |  | RFP-Managed Service - Siggi Hauer | Decision on Lync topology, i.e. cloud. All vendor responses estimate 6 more months from contract signature to pilot. All project planning, visibility of risks and issues and further decisions are dependant on this decision. |  | 20-Feb JC - My assumption is cloud but we need to finish the negotiations with the vendor. 9-Feb James H.-All project planning, visibility of risks and issues and further decisions are dependent on this decision. |  | FALSE
D97 | unknown | Al Grljevic | Al Grljevic | Technology Foundation |  | Closed | 2012-01-20 | 2012-03-06 | Siggi Hauer | Decision: Plan for Germany on-premise. Include Germany in O365 migration counts or not? QRM view is Germany cannot have data hosted by a 3rd party though John disagrees with their interpretation. Without this decision in place will have difficulty in defining the Outlook Exchange deployment plan. | 2012-03-06 | 5-Mar: Plan on premise; Al confirmed this is closed. Team is planning for on-premise. 20-Feb JC - Siggi is working on this. 1-Feb: Need confirmation from Siggi. |  | TRUE
D96 | unknown | Al Grljevic | Al Grljevic | Technology Foundation |  | Pending | 2012-04-02 |  | DA - Brett / Susan | Decision around treatment of countries where only a portion of the population needs to remain in-country with respect to move to Hosted Service e.g., UK and Australia. UK position is that all email must stay in-country despite any restriction only applying to a small subset of uses working on government client engagements. Without this decision in place will have difficulty defining the Outlook Exchange deployment plan. There are no mechanisms in place to move users readily back and forth and since engagement roles change we believe that countries need to be treated as a whole and if any position needs to remain in-country then the whole country needs to do so. Example 200 users in AU who need email data to remain in-country prevents AU from moving GDC or to O365. The users will not remain static; the variance will be based on the engagement assignments. |  | 16-Mar: Moved due date from end of Feb to 2-Apr per Al to accurately reflect the target. 5-Mar: Alan and Guy to provide input on the approach based on the options provided Al to request feedback from Pearl Cash to understand the frequency from change. 20-Feb JC - Siggi will discuss UK with Robin Tye. Brett developed an approach but this needs to be fine tuned - if we are talking about only a small number of users who need to stay On-Prem then the rest should move : Pending decision from Pearl Cash |  | FALSE
D80 | unknown | Steve Jelf | Steve Jelf | Technology Foundation |  | Pending | 2012-04-04 |  | Q&RM & FSG | Email Archive Decision making group to follow-up with global Q&RM to determine which countries need e-mail archiving. Validated that there is no Q&RM legal or regulatory requirement to implementing a global archiving solution, however do believe that IT Services should prepare for some kind of archiving solution due to likely political pressure applied by Service Lines / Business Units or particular countries. For those countries that do have a archiving system in place today, due diligence is taking time to analyse the detail of legal / regulatory statements. It is thought that this would run into a number of weeks / months. Initial indications show that countries believe a legal position exists in retaining an email archive, however no strict evidence is being found confirming this is the case. Decision required asap on (a) If a archiving solution(s) are required and (b) exactly what is required for "day 1". Target date reflects the fact that a recomendation should be put to the FSG for 28/29h Feb. |  | 17-Mar - Still awaiting decision on Swedenk, Switzerland and DE. Likely date to get recomendation Friday 24th March. 08-Mar - We don't need any email archiving in the Americas or A-P In EMEIA, we have a potential need for email archiving in Sweden, Switzerland and maybe Germany. However, we're pushing hard on these as the requirements don't appear to be based on any legal or regulatory criteria. Will keep you posted on progress here. One thing to flag is the broker-dealer entity in Canada - Brett is aware of this but it currently uses a specific email archiving system which will need to be replaced. (Note: dep. on decision, refer back to R3 (deferred). May need to open a corresponding issue; do so through R3). 5-Mar: JC to follow-up with Gillian H. 20-Feb JC - We had always talked about archiving being a separate project and we have time because the user will have plenty of space in their 5GB mail file on day one. We need the answer from Q&RM about whether any country needs and why. Further Q&RM due diligence is required to confirm if legal position exist in countries. It is however thought that regardless of this, further thought should be given by IT Services to accommodate these requests. 1-Feb: meeting scheduled with Q&RM tomorrow; update thereafter. Decision required asap on (a) If a archiving solution(s) is required overall and (b) exactly what is required for "day 1". 10-Feb SJ - This is significant. Q&RM due diligence will take weeks / months to complete. A. Mickelson was to attempt at opening up a RFP activity around general electronic archiving , however it is not known if this has come to fruition. Impact of not having a decision on what is required for day 1. If it is decided that an email archiving solution is required in 1 or more countries for day 1 then significant additional cost would be incurred from both a H/W and resourcing view point. P/ Neave to confirm when drop dead date is for a decision to be made. |  | FALSE
D83 | unknown | Steve Jelf | Al Grljevic | Technology Foundation |  | Closed | 2012-03-13 | 2012-03-16 | John Costello and Siggi Hauer | 5gb Mail file limit. Users will have a 5gb mail file however no personal archiving will be available. Q&RM have aligned with IT Services strategy on this factor. The user population will all get a 5GB mail file. This means the user will not be able to exceed this limit. Once the user reaches the limit, they will need to delete unneeded e-mails. (16-Mar) Decision makers: John Costello and Siggi Hauer | 2012-03-16 | 6- March - J. Meiser To confirm to A. Grljevic 5-Mar: A 25Gb plan on O365 is an additional $5.00 per user per month. Note that as we approach scope lock on O365 this decision needs to be final in the next 2 weeks. Any increase in mail file size allocations will also increase the cost of the On-Prem solution. Assumption is to continue with 5GB and also verify that ithe storage can be increase this on an individual basis. Paul Neave to confirm whether we can increase the limit on an individual user basis 20-Feb JC - 5GB it is - there is a question about partners getting 25GB; JC requested Al send him and Siggi the costs for this vs. 5GB. Q&RM have express no concern, other than the fact the business reps need to buy into the plan we are no proposing 1-Feb: moved date out 3 weeks; Al and Adrian to raise with FSG. 10-Feb: SJ - IT recommendation validated by Q&RM. Decision making authority now required to rubber stamp this . (Don’t believe this is a “Business decision”) |  | TRUE
D84 | unknown | Steve Jelf | Steve Jelf | Technology Foundation |  | Closed | 2012-03-22 | 2012-03-07 | Q&RM | 7-Mar: Steve Jelf: Q&RM confirmed that this request / requirement no longer exists. No saving of external chats are required. Due to a previous Q&RM recommendation, the current Instant Messaging client (Sametime) saving facility is disabled. Q&RM have re-validated this previous recommendation and concluded that the risk profile has not changed. It is however now assumed that chats with external parties will be enabled in the future state (from the server end). This presents additional challenge | 2012-03-07 | 7-mar: Steve Jelf: Q&RM confirmed that this request / requirement no longer exists. No saving of external chats are required. Also closed corresponding risk, R93. 29th Feb :- Q&RM Chair reaching out to key participants of the Legal Exec Committee to recommend that this requirement is no longer worth pursuing given the impact. Awaiting feedback. 22nd Feb - Email highlighting high level impact sent to Q&RM. SC to brief Legal Exec Comittee. It is thought that this requirement may be dropped when impact is fully understood. 2nd Feb - Recomendation made by Q&RM. A) Saving of chats (internal or external) should be disabled from the users (Lync Client) perspective. B) "Archiving" of External client chats should be configured / scoped into the design at the server (Tech Foundation) side. However a key risk is outstanding in that if this is the case, does additional H/W need to be put on premise for countries that have a restricted in moving data outside of country borders. Furthermore, Legal discliamers should not be configured for Internal chat, but should be enabled for External Chats. (Q&RM to confirm wording of disclaimer). 10-Feb SJ - This is significant .It affects the Lync functional spec, and overall Infrastructure build of Lync. We may need Infrastructure build out for On Prem locations as well as amendments to any cloud offering chosen. . Still awaiting formal decision from Q&RM. Escalated again 9th Feb. Once formal recommendation made by Q&RM, Architecture team will require to investigate likely costs. Costs vs Risk decision then needs to be taken. |  | FALSE
D85A | unknown | Steve Jelf | Steve Jelf | Technology Foundation |  | Pending | 2012-03-22 |  | Q&RM | Lync Voicemails. 6-Mar: Accepted that no technical solution exists. Outstanding decision required by Americas area as to if voicemail forrwarding and speech translation to text should be disabled. All other areas have accepted the risk. Enabling either voicemail forwarding or translation of speech to text presents a risks in that messages cannot be tracked and automatically deleted after a defined period of time. Requirements Q&RM direction |  | 6th March - Accepted that no technical solution exists. Outstanding decision required by Americas area as to if voicemail forrwarding and speech translation to text should be disabled. All other areas have accepted the risk. 22nd Feb - It is confirmed that no technical solution exists out of the box or via RMS 3rd party tools to meet the business requirement. Further request made to confirm if a product does exist on the market to cater for our "auto delete" requirements. Q&RM have been asked to make a decision assuming no further tools are available to meet the requirement. Further info expected 9th March. (SJ) to set up a further meeting with IIT Services engineering architects to review what exact configurations can be made, reporting back to SC on this., The aim will then be to confirm a configuration for the enabling of legal disclaimers for external related chats. 1-Feb: Nick, Juan and Klara working on a deck around this. Need Nick to tell us whether Msft can meet the need or what 3rd party tools are available. Adrian will chase this as a first step and come back to Steve. 9-Feb James H.-Unable to clarify the scope with vendor (if cloud is chosen) until decision is made. 10-Feb SJ - Either the technology will support the requirements, or not. Awaiting technical validation, prior to cycling back to Q&RM. (Don’t believe this will be a business decision at this point). |  | FALSE
D81 | unknown | Steve Jelf | Steve Jelf | Technology Foundation |  | Closed | 2012-02-22 | 2012-02-10 | FSG | No Backups Q&RM have agreed with the working assumption that no backups will be part of the overall messaging & collaboration solution. | 2012-02-10 | Validation required with FSG. Q&RM have no issues with this proposal 1-Feb: moved date out 3 weeks; Al and Adrian to raise with FSG. 10-Feb: SJ - IT recommendation validated by Q&RM. Decision making authority now required to rubber stamp this. (Don’t believe this is a “Business decision”) PIN - Likely that requirements from Senior mgt will require we design and cost a Backup solution for small sites where there is not DR site. Note this will result in a reduced service level for those countries. 10-Feb: closed this item as decision has been agreed; closed on TF decisions call (Paul, Adrian, Al, Ant, James, Steve, Brett) |  | TRUE
D82 | unknown | Steve Jelf | Steve Jelf | Technology Foundation |  | Closed | 2012-02-22 | 2012-02-10 | FSG | Trash retention period. Due to moving to the "cloud" , 30 days is the default setting. | 2012-02-10 | Challenged by Q&RM on behalf of the US firm. Microsoft have confirmed that this cannot be amended and as yet have resisted clients requests. 1-Feb: Adrian will raise with Q&RM again (needs to go back to them); then can proceed. 10-Feb Steve J. - From a Q&RM point of view, there are issues, but the decision fundamentally has been made / that is the service we signed up for , close. |  | TRUE
D85B |  | Steve Jelf |  | Technology Foundation |  | Closed | 2012-02-03 | 2012-02-02 | FSG | "Ethical Walls" aka "ring fencing" QRM to confirm if "Ethical Walls" or "ring fencing" currently exists. (enabling virtual or physical separation of data between certain parts of the business) For example, should EY professionals working on both sides of a deal be separated logically from an IT point of view? | 2012-02-02 | SJ Meeting on Ring Fencing procedures now arranged for 1st Feb 1-Feb: Susan following up with SP; Steve will update this item. 2nd Feb - Meeting held and confirmation obtained that this only affects the SharePoint work stream - specifically engaging / managing clients. This therefore is a Q&RM requirements that will be fed into the appropriate work stream by S. Chakerian. |  | TRUE
D106 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-08 | Participants in the November TF Meeting in Secaucus | Tier A will consist of Firm assets, no external facing, no engagement data, Tier A specific archiving, no streaming meai - Communities, People, Search, Metadata, and Content |  | 9-Mar Travis: Need to re-work Tier A definition based on Office365 decision. Some services and capabilities may shift out of Tier A based on O365 constraints, policies and procedures and technical limitations of on-premises integration points. Arch imp: YES |  | TRUE
D107 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-08 | Participants in the November TF Meeting in Secaucus | A tier A specific archiving solution will be constructed. Note that it may not include all the data in Tier A Tier A: We will build a Tier-A only specific archiving solution for //content and //communities only |  | 11_11_08.1.15 - "Tier A: We will build a Tier-A only specific archiving solution for //content and //communities only" O365 Hosted if aplicable for workloads, therefore need to revalidate Travis 9-Mar: Need to re-validate what "archiving" means to EY. Although "Content" has a large user-base, it should still be considered an Application-Specific workload (i.e. vertical). Assuming verticals do not live in O365, it will require an on-premises archiving solution which is not considered in the "to-be" architecture. Assuming all community types live in O365, EY can take advantage of the O365 "Records Center" site collection which can grow to 400GB (at this threshold, this is a maximum of 300 based on latest service description). Need to re-visit the requirement for archiving and determine if the constraints still meet the requirement. Arch imp: YES |  | TRUE
D109 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-04 | Participants in the November TF Meeting in Secaucus | Client assets in the initial rollout will start in Tier B. Aspiration is to evolve base offering to handle Client Assets. | 2012-03-09 | 9-Mar Travis: Confirmed. Scope - Tier B has yet to be defined. Use of base service offering remains aspirational. |  | TRUE
D110 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | User Experience will be a Farm WSP. -Branding governance -Generic EY -Browser-based -All tiers | 2012-03-09 | 9-Mar Travis: Confirmed. The design for UX is being delivered by Frog, but not sure who is doing the implementation to a WSP. This is guidance to the implementers. |  | TRUE
D111 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | Research Tools: content will be included in Tier A for Phase 1. |  | 16-Mar Al: Paul neave to set up a meeting with Martin Versteeg to understand costs 9-Mar Travis: Need to re-validate decision as research tools may have been shifted to Blueprinting as a vertical/application-specific capability. Is current solution conducive to storing data in Office365? Arch imp: YES |  | TRUE
D112 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | Authoritative content will be in all three Tiers. EY has no restrictions on authoritative content residing in Office365. | 2012-03-09 | 9-Mar Travis: Confirmed. EY has no restrictions on authoritative content residing in Office365. |  | TRUE
D113 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | Criteria for falling outside of Tier A: -Isolation (outside of site collection) -App-specific -Change management -Releases -Data size/scale -Access -Outside GDCs -Client assets -External piece (for both Firm and Client assets) -security requirement -Host name | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D114 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | Summary of Engaging Clients Managing Accounts (ECMA) work stream: -Not a GAMx replacement -extranet experience (from infrastructure perspective) -EY account teams: high level visibility and control around engagements; clients have limited visibility. -Concerns around one infrastructure to include client access controls because risk of human error in selecting site collection. -Engaging clients does not fit in Tier A. (Some scenarios may fit, but when clients accessing content, looking at higher level tier.) | 2012-03-09 | 9-Mar Travis: Confirmed. No change in direction on ECMA as far as I know. |  | TRUE
D115 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | Business Connectivity Services (BCS) will only be used for User Profiles in Tier A for the GHRDB connection. No other uses planned at this time BCS may not even be used for supplemental profile import depending on approach, but is supported by Office365 either way. | 2012-03-09 | 9-Mar Travis: Confirmed. BCS may not even be used for supplemental profile import depending on approach, but is supported by Office365 either way. |  | TRUE
D116 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | Use Web Trends for Web Analytics | 2012-03-09 | 9-Mar Travis: Confirmed. Web Trends is supported in Office365. |  | TRUE
D117 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | Centrally managed services that are cross-farm capable will be based in Frankfurt (this is the position for the initial rollout) (In the future, we can look at exceptions, for example something consuming GHRDB data, which resides in Secaucus). |  | 9-Mar Travis: Revalidate based on Office365 decision. Since cross-farm services design were originally intended to be part tier A, we need to confirm that the O365 environment can still host these as cross-farm services. Arch imp: YES |  | TRUE
D118 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | EY’s view is that we want the CVs shared. Some countries have concern that if your CV is published, someone in another service line in another country will hook you- this needs to be resolved by business management. | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D119 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | All farms will need to consume a single, global MMSA (Managed Metadata Service App). (Implication for regional/in-country deployments that they will consume this service) Ref: 11_11_07.1.21 |  | Travis 9-Mar: Conceptually this decision holds, but technically there are hurdles with the integration scenarios with Office365. If this is the vision, we need to wrap a maturity model around this capability/feature. This is has been impacted by Office365. Arch imp: YES |  | TRUE
D120 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | Based on Office365, User Profile sync will occur in Office365. GHRDB data will be populated in AD via a process outside of user profile sync (IDSync). | 2012-03-09 | 9-Mar Travis: Invalid decision. Based on Office365, User Profile sync will occur in Office365. GHRDB data will be populated in AD via a process outside of user profile sync (IDSync). Initially read: User Profiles and BCS: User profiles sync will live in Secaucus with GHRDB and BCS. UPRE will leverage that to replicate to the other two global data centers (Frankfurt and Singapore). |  | TRUE
D121 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | MySites will only live in Office 365. | 2012-03-09 | 9-Mar Travis: Confirmed. MySites will only live in Office 365. Previous questions: Decide whether My Sites will be in the additional locations (locations in addition to Frankfurt) to keep them close to users for performance reasons. |  | TRUE
D122 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | Would like Service Applications to fit into Tier A; the allowable service request is part of Tier A, along with SLAs. (11_11_07.1.25) -Excel services will probably be in one of base templates -Graphs and charts needed right away -Can include some uses in Tier A; some in another Tier. -Co-authoring piece/all Office services -the ability to take action from search results (preview) |  | 9-Mar Travis: Need to revalidate based on Office365 features and capabilities. |  | TRUE
D123 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-07 | Participants in the November TF Meeting in Secaucus | We will not use Power Pivot (service application) in the initial rollout; requires different version of SQL2008 R2 - which is not curently an EY standard | 2012-03-09 | 9-Mar Travis: Confirmed. This is not supported in Office365 in the current service description. |  | TRUE
D124 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-08 | Participants in the November TF Meeting in Secaucus | We will not include file shares in migration (to SharePoint) of business content - consensus decision | 2012-03-09 | 9-Mar Travis: Confirmed. Long-term file shares may be migrated, but not in scope for initial phases/releases. |  | TRUE
D125 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-08 | Participants in the November TF Meeting in Secaucus | Tier A: We will plan for 50 TBs and may scale to 300 TBs in the next couple years. No archiving workload management. |  | 9-Mar Travis: Revalidate data capacity and sizing requirements based on latest information. Arch imp: YES |  | TRUE
D126 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-08 | Participants in the November TF Meeting in Secaucus | SharePoint will allow media as attachment, but will not support direct streaming. Fusion may extend this further | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D127 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-08 | Participants in the November TF Meeting in Secaucus | We will not migrate ARC (Archive Records Center) to SharePoint | 2012-03-09 | 9-Mar Travis: Confirmed. See D107 for archiving strategy. |  | TRUE
D128 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-08 | Participants in the November TF Meeting in Secaucus | CKRs (Community Knowledge Repository) will be migrated and searchable. This is being cleaned up, retagged with new taxonomy, and then migrated into the Content management system. Fusion will be responsible for automation of this migration - this is outside Foundation scope. |  | 9-Mar Travis:Confirmed. Need to revalidate target source for this migration. If these are going to the "Content" service/application, then that is outside of Office365. If these are going to "Communities", then need to consider implications to CKR migration strategy for Office365. Arch imp: YES |  | TRUE
D129 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-08 | Participants in the November TF Meeting in Secaucus | No conversion of in-flight/active engagements (e-Docs, GAMx, GRC, eRooms) (80 TBs). Idea is to let such engagements finish up in the tools they currently use. If any such items are identified for automatic migration, Fusion will develop apps/customizations to enable such a migration. | 2012-03-09 | 9-Mar Travis: Confirmed. This is an opportunity to align with the co-existence strategy between SharePoint and these systems. |  | TRUE
D130 |  |  |  | Technology Foundation |  | Obsolete |  | 2011-11-08 | Participants in the November TF Meeting in Secaucus | Tier A: We will build a Tier-A only specific archiving solution for //content and //communities only |  | 9-Mar Travis: Revalidate based on archiving requirements. These requirements are being reevaluated as part of D107 as well. (duplicate - marked obsolete.) |  | TRUE
D131 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-08 | Participants in the November TF Meeting in Secaucus | Tier A: Site Taxonomy web apps -My Sites (My Site) -Communities (Team Sites) -Content (doc center) -Archiving (record center) -Search (search portal) |  | 9-Mar Travis: Office 365 does not support this many web apps. These services would either have to move to a different tier, outside of Office 365 or consolidated under the given set of O365 web apps assuming there are no constraints prohibiting these services.Arch imp: YES |  | TRUE
D132 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-08 | Participants in the November TF Meeting in Secaucus | GETD (global Engagement Team Databases) will not be automatically converted/migrated. Fusion will be responsible for automation of this migration - this is outside Foundation scope. | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D133 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-08 | Participants in the November TF Meeting in Secaucus | Tax agrees that archived data from eDocs does not need to move to SharePoint |  | 9-Mar Travis: Confirmed. Check with Prokopios and Blueprinting effort on archiving requirements, but not currently part of scope. |  | TRUE
D134 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-09 | Participants in the November TF Meeting in Secaucus | This project (Fusion/Foundation) will not be building the firm archiving tool | 2012-03-09 | 9-Mar Travis: Confirmed. Even if archiving becomes a requirement in SharePoint and SharePoint becomes the core, archiving repository for this capability, the tool will not be built by EY. |  | TRUE
D135 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-09 | Participants in the November TF Meeting in Secaucus | This project is not delivering a Service Management Framework. This action is being addressed by the PMO team and is captured on the RAID list | 2012-03-09 | 9-Mar Travis: Confirmed. Office365 has a service management framework wrapped around it. EY operations will have to integrate these processes with their ITSM framework and processes. |  | TRUE
D136 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-09 | Participants in the November TF Meeting in Secaucus | Sharepoint/FAST will not search Fileshares |  | 9-Mar Travis: Need to re-confirm content sources being indexed by FAST. Bring Pat Velderman and Steve N. into the fold on this one. I have recently heard rumblings of indexing Lotus Notes databases, so the strategy has shifted. |  | TRUE
D137 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-09 | Participants in the November TF Meeting in Secaucus | Mobile access is limited to out of the box capabilities of SharePoint. Foundation will not be designing the infrastructure to allow mobile devices to access SharePoint | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D138 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-10 | Participants in the November TF Meeting in Secaucus | Monitoring of the existing resources will be an Operational task; they should understand rate of growth to tell us when we should plan for the addition of columns (capacity). Operations will also be responsible for monitoring PEAK queries for additional planning purposes. | 2012-03-05 | Paul Neave & TF team - still valid, marked revalidated. 9-Mar Travis: Confirmed. |  | TRUE
D139 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-10 | Participants in the November TF Meeting in Secaucus | We will plan for 20 Queries Per Second (QPS) for 2013. Meaning we need 2 rows and 10 columns per active farm |  | 9-Mar Travis: Confirmed. This still stands as far as I know. The decision can be revalidated with FAST team, Pat Velderman and Ed Dale if still valid decision. |  | TRUE
D140 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-10 | Participants in the November TF Meeting in Secaucus | There will be one global enterprise search technology (FAST) that can be used by other Tiers. This includes in-country as part of this one search service. |  | 9-Mar Travis: This is the vision, but not necessarily the capability being delivered by the "To-Be" architecture in Phase 1/Release 1. This needs to be re-evaluated with the hybrid, O365 architecture. Arch imp: YES |  | TRUE
D141 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-10 | Participants in the November TF Meeting in Secaucus | Indexing Latency SLA for GAAIT once hosted in SP 2010 CMS:(6 TB of content) ish 15 minute indexing latency | 2012-03-09 | 9-Mar Travis: Confirmed. This is configuration. |  | TRUE
D142 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-10 | Participants in the November TF Meeting in Secaucus | FAST will only search Published content | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D143 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-10 | Participants in the November TF Meeting in Secaucus | Plan for a 12-hour index latency SLA unless a lower SLA is otherwise identified for a particular application. | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D144 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-10 | Participants in the November TF Meeting in Secaucus | Operations should monitor indexing time and content churn rate (to add servers if needed to meet SLAs). | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D145 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-10 | Participants in the November TF Meeting in Secaucus | Page rendering time in SP and query response time (defined as when main search results appear) from end user perspective should appear to be about the same. | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D146 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-10 | Participants in the November TF Meeting in Secaucus | FAST Web Analyzer will not be deployed | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D147 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-10 | Participants in the November TF Meeting in Secaucus | If there is a requirement for a content source to be encrypted, given that this can be reconstituted based on the index, would need to either encrypt the index (which is not a FAST capability, but at hardware level), the firm would have to assume the risk, or exclude this from search. | 2012-03-09 | 9-Mar Travis: Confirmed. No special encryption capability at FAST level. This is at the hardware level and outside the scope of the SharePoint architecture. |  | TRUE
D148 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-10 | Participants in the November TF Meeting in Secaucus | There is an assumption that for in-country ("SP in a box"), search technology will always be FAST, regardless of scale, and governance will be the same around these in-country farms. The boundary is the site collection. Search center will either: display global results with in-country federated in through web part or the in-country piece could become the main results with the global search results federated in through web part. Global search is not indexing in-country content and in-country is not indexing global. |  | 9-Mar Travis: Need to re-validate approach with blueprinting and FAST teams to ensure this meets the requirements and user experience needs.Arch imp: YES |  | TRUE
D149 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-10 | Participants in the November TF Meeting in Secaucus | Plan FAST for 10 Columns, 150 Million docs, 50 TB total indexable content, (implication doc size = 358K) for June 2012, day 1 of SPF Production. ( Ref: 11_11_10.1.03) |  | 9-Mar Travis: Need to re-confirm with Fusion that this is still the case. My understanding is there has been additional analysis done here that may impact the original sizing. Need to re-confirm with Pat Velderman. Arch imp: YES |  | TRUE
D150 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-11 | Participants in the November TF Meeting in Secaucus | My Site will not be the landing page for the initial rollout. | 2012-03-09 | 9-Mar Travis: Confirmed. Assumes this is still the direction and has not been changed by the UX/Frog workstream. Impact would impact farm capacity and load, but is mitigated to some degree now that Mysites are deployed to Office365. |  | TRUE
D151 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-11 | Participants in the November TF Meeting in Secaucus | AD is the primary source of User Profile data and GHRDB will supplement additional information. (Note that there is more information is coming from GHRDB, so this sync will take longer.) |  | Travis 9-Mar: This needs to be re-visited as the proposed solution in the workshops was to use an LDIF import over the WAN to Frankfurt. We need to validate this approach is still the direction and if it fits into the Office365 constraints. Arch impact: YES |  | TRUE
D152 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-11 | Participants in the November TF Meeting in Secaucus | Do not automatically populate peers (people reporting to the same manager) as colleagues; colleague import will be turned off. | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D153 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-11 | Participants in the November TF Meeting in Secaucus | Internally, there is 1 forest, 22 domains and EY does not plan to change this in the near future. | 2012-03-05 | Paul Neave and TF team - still valid; marked revalidated. 9-Mar Travis: Confirmed. |  | TRUE
D154 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-11 | Participants in the November TF Meeting in Secaucus | msDS-SourceObjectDN will be used to join accounts for a single User Profile |  | 9-Mar Travis: Need to re-validate with IAM and O365 folks on the population and use of this attribute. What are the constraints? Is this still valid? Arch imp: YES |  | TRUE
D155 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-11 | Participants in the November TF Meeting in Secaucus | People will provide their own photos into User Profile. The photo will be pushed into AD (this is the only content that will be pushed into AD). |  | 9-Mar Travis: Need to validate approach with IAM and Office365 teams. Arch imp: YES |  | TRUE
D156 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-11 | Participants in the November TF Meeting in Secaucus | EY will allow default behavior of SP for user to write wwwHomePage attribute in AD. Where attribute clashes exist, EY will take action to fix this (e.g., in-country provisioning). | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D157 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-11 | Participants in the November TF Meeting in Secaucus | Content and data from the My Site will not be retained/ archived once the owner leaves the firm beyond a short period of time. In other words, People work stream will determine a de-provisioning approach for mySites (ref 11_11_11.1.20) |  | 9-Mar Travis: Validate that this requirement can be achieved now that MySites are in Office365. Arch imp: YES |  | TRUE
D158 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-11 | Participants in the November TF Meeting in Secaucus | There will not be infrastructure in Secaucus because of need to extract data from GHRDB (Ref 11_11_11.1.05) | 2012-03-09 | 9-Mar-Travis: Confirmed. User Profile import approach should align with this. |  | TRUE
D159 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-14 | Participants in the November TF Meeting in Secaucus | SQL Server 2008 R2 will be the standard database | 2012-03-05 | Paul Neave - still valid; revalidated. 9-Mar Travis: Confirmed. This continues to be the direction and is what is being used to build out the non-production environments. |  | TRUE
D160 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-14 | Participants in the November TF Meeting in Secaucus | GAAIT does not have to be encrypted. It is not encrypted today. | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D161 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-14 | Participants in the November TF Meeting in Secaucus | Office 365 is a one-data center approach. SPF should assume that the benefits of a one-data center approach outweighs the risk of the cost of rework if design is developed to a one-data center approach | 2012-03-09 | 9-Mar Travis: Office 365 is a one-data center approach. |  | TRUE
D162 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-14 | Participants in the November TF Meeting in Secaucus | Design to one-data center approach | 2012-03-09 | 9-Mar Travis: Confirmed. Single datacenter approach for Tier A and is reflected by moving Tier A to Office365. |  | TRUE
D163 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-14 | Participants in the November TF Meeting in Secaucus | Design for expansion beyond one data center | 2012-03-09 | Note: EY Directive not taken by MCS 9-Mar Travis: Confirmed. |  | TRUE
D164 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-15 | Participants in the November TF Meeting in Secaucus | All of Tier A requires DR |  | 9-Mar Travis: Assuming Tier A now wholly exists in Office365, DR capabilities are built into the Service. We need to validate the DR capability meets the requirement. Arch imp: YES |  | TRUE
D165 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-15 | Participants in the November TF Meeting in Secaucus | Validate that replication is done and can be done at the Storage (SAN) Level between GDC (Frankfurt/Telecity) and Eschborn - Yes |  | 9-Mar Travis: This may be invalidated with the Office365 decision because this was a solution for DR when the Tier A services lived in Frankfurt. This DR strategy may still be valid for other on-premises services, but that is TBD. |  | TRUE
D90 | unknown | Paul Neave | Adrian Mickleson | Technology Foundation |  | Obsolete | 2012-02-03 | 2012-02-10 | DA | Does the customer require Lync Online to Outlook Web App (OWA) integration? A delay in the decision will potentially delay scope Lock and impact the O365 service ready delivery date |  | Need to input the required settings as part of the discovery questionnire Need to change the service to be delivered before Scope Lock 10-Feb - Adrian said this doesn't belong here; mark it obsolete; belongs with RFP team. (team agreed on 10-Feb TF decisions call) |  | TRUE
D54 |  |  |  | Technology Foundation |  | Obsolete | ASAP | 2012-02-01 | Business | DEC_001 Final decision on In-Country Locations and corresponding DR sites |  | Need to finalise the list of countries that will require exchange to be deployed (currently 28) in order to finalise design decisions. Also what the corresponding DR sites are if DR is required in all instances (prev. DP1) 1-Feb: This is the same as D92 and D93. Close this item. |  | FALSE
D55 |  |  |  | Technology Foundation |  | Obsolete | ASAP | 2012-02-01 | Business | DEC_002 Agreement to Retention policy (defaults: 14 days trash, 30 days dumpster) |  | Current assumption is we will go with defaults unless directed otherwise (prev DP2) 1-Feb: Same as D80 and D82. Close here. |  | FALSE
D56 |  |  |  | Technology Foundation |  | Obsolete | ASAP | 2012-02-01 | Business | DEC_004 Business Tolerance to data loss (in case of compete corruption of all mbx copies) |  | How many mailboxes can be lost in case of corruption. This decision will drive the backup/non-backup decision (prev DP3) 1-Feb: included in D81 around backups; close here. |  | FALSE
D166 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-15 | Participants in the November TF Meeting in Secaucus | Design In-Country SharePoint Infrastructure for a minimum baseline high-availability farm leveraging standard branch office configuration | 2012-03-09 | 9-Mar Travis: Confirmed. An in-country SP design with local HA is in the current architecture description. |  | TRUE
D57 |  |  |  | Technology Foundation |  | Obsolete | ASAP | 2012-02-01 | Business | DEC_003 Confirmation of decision that there will be no backup requirement for mail on exchange |  | Current assumption is that we are designing with no backup provision for mail in any location (prev DP4) 1-Feb: same as D81 - mark obsolete. |  | FALSE
D167 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-15 | Participants in the November TF Meeting in Secaucus | SPF design will not include an In-country DR solution | 2012-03-09 | 9-Mar Travis: Confirmed. Current design only includes a local HA solution with redundancy at web and app tiers. |  | TRUE
D60 |  |  |  | Technology Foundation |  | Obsolete | ASAP | 2012-02-01 |  | DEC_011 External vendor RFP |  | (prevDP7) 1-Feb: included in other items, D94 and others. Obsolete. |  | FALSE
D168 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-15 | Participants in the November TF Meeting in Secaucus | Lower level environments (non-production) will not have DR | 2012-03-05 | Paul Neave and TF team - still valid; marked revalidated. 9-Mar Travis: Confirmed. Validate how DR testing will be performed. |  | TRUE
D62 | unknown |  | Adrian Mickleson/Nick Wood | Technology Foundation |  | Obsolete | 2012-03-14 |  | Business | DEC_005 Groups; what is required to be migrated, none, identified, all? |  | There are some 400,000 groups in Lotus Notes. Need to understand what the requirement is to migrate these. There is significant effort involved in migrating them and further development needed to implement a mechanism to keep these groups synced during co-existence which is not in the group management scope being delivered by IAM. (prev DP9) 9-Feb: Al closed; this is a duplicate item, D83. |  | TRUE
D63 |  |  |  | Technology Foundation |  | Obsolete | ASAP | 2012-02-01 | Business | DEC_006 Legal Hold; what is required in respect of voicemail? |  | Are there any requirements beyond the Legal hold capabilities of exchange to capture and hold those VMs that have been delivered to the respective mbx, e.g is there anything associated with the user on legal hold leaving VM for others (prev DP10) 1-Feb: included in D85A. Obsolete. |  | FALSE
D169 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-15 | Participants in the November TF Meeting in Secaucus | Capacity at DR site will be less than a 100%. Eschborn Data Center may not have the capability to provide full redundancy. | 2012-03-09 | PN: PN - assumption for Exchange system is will have full redundancy at DR site 9-Mar Travis: Confirmed. DR footprint is TBD for SP Services beyond Tier A. Assumes deployment of DR infrastructure is diminished or not required for Tier A services. |  | TRUE
D170 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-16 | Participants in the November TF Meeting in Secaucus | Requirements for Partnership are not part of this design and will fall in Tier C | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D65 |  | Al Grljevic / Adrian Mickleson |  | Technology Foundation |  | Obsolete | ASAP | 2012-02-01 | Business | DEC_009 Confirmation of Archive requirements |  | (prev DP12) 1-Feb: same as D80; obsolete. |  | FALSE
D171 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-16 | Participants in the November TF Meeting in Secaucus | Partners may need their own infrastructure when they move to SharePoint (Tier C). Ref 11_11_16.1.02 | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D172 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-16 | Participants in the November TF Meeting in Secaucus | Initial SPF Design will be based on the current two AD forest scenario (ey.net and eydmz.net) with two separate identities | 2012-03-09 | 9-Mar Travis: Confirmed. |  | TRUE
D173 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-16 | Participants in the November TF Meeting in Secaucus | Solution to regulatory in-country is “SharePoint in a box” that lives 80% of time in the DMZ. Ref 11_11_16.1.04 | 2012-03-09 | 9-Mar Travis: Confirmed. As far as I know, in-country deployments are meant to live in the DMZ as the requirement exists for collaborating on client data/assets. |  | TRUE
D174 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-17 | Participants in the November TF Meeting in Secaucus | All attributes needed by SharePoint will be available and managed in the Global AD Catalog |  | Travis 9-Mar: My understanding is this still holds. It makes sense to do a quick sync with the IAM work stream and validate. |  | TRUE
D175 |  |  |  | Technology Foundation |  | Closed |  | 2011-11-17 | Participants in the November TF Meeting in Secaucus | SPF design will not leverage RBS (Remote Blob Storage) | 2012-03-09 | 9-Mar Travis: Confirmed. This is still the direction as far as I know. Gerd is keen on the value proposition of RBS, but current thinking suggests it is not the right solution at the moment. This may change if more specialized workloads are deployed on Sharepoint like streaming media. |  | TRUE
D89 | unknown | Paul Neave | Adrian Mickleson | Technology Foundation |  | Closed | 2012-02-03 | 2012-02-09 | M&C programme/ FSG? | Does EY require Mobile Data Service - Connection Service (MDS-CS)? A delay in the decision will potentially delay scope Lock and impact the O365 service ready delivery date | 2012-02-09 | Need to input the required settings as part of the discovery questionnire Need to change the service to be delivered before Scope Lock 9-Feb: Paul - Closed; it will take a week to stand up this CR so will address when required, not for Day 1. |  | TRUE
D59 |  |  |  | Technology Foundation |  | Closed | ASAP |  |  | DEC_010 BPOS/Non-BPOS We are going with O365 | 2012-03-05 | (prev DP6) Paul Neave and TF team - valid! 9-Mar Travis: Confirmed. |  | FALSE
D86 | unknown | Steve Jelf | Steve Jelf | Technology Foundation |  | Pending | 2012-03-23 |  | Q&RM | Email Deprovisioning Implementing a global process to decommission Exchange mailboxes when staff leave the firm. It is believed that there are a number of countries throughout Europe that have requirements indicating that data needs to be removed within 5 days or less of staffing leaving the firm. Need consistent approach that says, when a person leaves, this is what happens to their mail |  | 8th March- General acceptance provided on this (30 day period) . It is thought that this setting could be changed based on a justified / approved Change Request -awaiting on confirmation from Nick Wood. (email sent 8th March) c20th Feb - Discussed with SC 21st Feb. Email being sent to members of the LEC to confirm a standard 30 day policy is likely to exist across all countries. Awaiting feedback from SC on this. 10-Feb: SJ - Q&RM direction required (escalated again 9th Feb). Paul Neave should confirm how critical a decision is, however it is believed that this needs to be fed into the “scope lock” phase- due to finalise early March. PIN – the opposite is also true - there are countries who also expect to retain mailboxes for leavers 10-Feb: Steve to go back to Susan (Q&RM): Our default position is 30 days, but we can move it to 5 if we need to. Our recommendation is not to leave it any longer than 30 days because of the cost implications. |  | FALSE
D100 | unknown | Paul Neave | Adrian Mickleson | Technology Foundation |  | Closed |  | 2012-03-05 | Siggi and John | Confirmed with Russia that the blackberry restriction does not apply. Plan for Exchange servers in Moscow for Russia. Russia has a requirement for mandatory Govt software to run on Blackberry Servers. To ensure the BB service this will require On-prem exchange for Russia. Need to confirm that the requirement still stands and OnPrem is required in Russia | 2012-03-05 | 5-Mar: CIS – BB restriction does not apply We need to plan for exchange servers in Moscow for Russia 20-Feb JC - Siggi? 9-Feb: Paul suggested this go to Siggi and John as per the on-going discussion around on-prem locations. |  | TRUE
D91 | unknown | Paul Neave | Adrian Mickleson | Technology Foundation |  | Closed | 2012-02-03 | 2012-02-10 | UC (Rewa Bouji) | Need to provide Resource Booking Attendant global settings for the O365 service if not the default Confirmed we will go with default value. | 2012-02-10 | Need to input the required settings as part of the discovery questionnaire 9-Feb: Paul - Rewa Bouji - needs to come back to us after meeting with GRE as to whether we need to change from the technical recommendation I have so far. 10-Feb: team on TF decisions call (Al, Adrian, Steve, James, Paul, Brett, Ant) said it has been confirmed that we will go with the default value. |  | TRUE
D58 | unknown | Adrian Mickleson | Adrian Mickleson | Technology Foundation |  | Closed | 2012-02-29 | 2012-02-10 | Design Authority Programme Authority | DEC_012 PR/DR site Replication method - native DAG, WOC or SAN replication? We are using native Exchange Plus wocification. | 2012-02-10 | Currently producing recommendation to be approved by the DA technically and then signed off by the programme authority for cost impact (prev DP5) 10-Feb: closed on TF decisions call (Paul, Ant, Brett, Adrian, Al, Steve, James) |  | TRUE
D180 | unknown | Paul Neave | Adrian Mickleson | Technology Foundation |  | Obsolete |  |  | Program Management | Need confirmation there is no requirement for moving on and off the cloud i.e. Based on Engagements for UK and Aus |  | 9-Feb: This is a duplicate of D96 (which is a more explicit item). Obsolete. |  | TRUE
D184B | 2012-02-09 | Martin Evans | Nick Wood, Brett van Gelder | Technology Foundation |  | Closed | 2012-02-15 | 2012-03-05 | Siggi Hauer / John Costello | Decision: We no longer stick to the two parameters RTO/RPO. Acknowledgement for on-premises RTO (24 hrs)/RPO (2 hrs) for the Exchange on-prem design with DR site. Exchange online agreed: the recovery time objective for Exchange on Premises. O365 is engineered to 2 hour RTO & 45min RPO | 2012-03-05 | 5-Mar: Paul – The numbers for the On-Prem came from the BIA assessment confirmation received from Arlan Singer on 16th Nov 11 (see Here) We no longer stick to the two parameters RTO/RPO 20-Feb JC - Where did these numebrs from from for On Prem? PIN – currently we are designing the On-Prem solution in accordance with the BIA – This will increase the bandwidth required between the locations significantly. It also will not be achieved if we only have one site with a backup (See D81). |  | TRUE
D178 | unknown | Paul Neave | Adrian Mickleson | Technology Foundation |  | Obsolete |  | 2012-02-10 | Program Management | Need confirmation on archiving requirements for exchange, and if they are to be delivered as part of M&C and if for day 1 |  | PIN - Repeat of D80? 10-Feb: obsolete as repeated. |  | TRUE
D68 | unknown |  | Adrian Mickleson / Nick Wood / Klara Neginsky | Technology Foundation |  | Closed | 2012-05-05 |  | Neil Forrester Klara Neginsky Nick Wood | DEC_012 Confirm shared permissions decision for exchange | 2012-03-08 | There are still some concerns from our operations and security colleagues regarding the decision taken at the planning workshops to proceed with shared permissions rather than split permissions for Exchange. Meeting on 14/11/11 in order to more fully understand the choice and its consequences.. (prev DP15) 01-Feb: Laura emailed Klara and Nick to followup/confirm ability to close. 08-Feb: Klara said this is being discussed on this Friday's UC DA call. |  | FALSE
D64 |  | Al Grljevic / Adrian Mickleson |  | Technology Foundation |  | Closed | ASAP | 2012-02-01 | Security | DEC_008 Validation of Exchange data classification; still mixed? | 2012-02-01 | Is the data classification for mail still mixed - i.e... That drive the requirement for the data protection measures that require in-country deployments for exchange (prev DP11) 1-Feb: Al and Adrian said this has been confirmed; can close. |  | FALSE
D67 |  |  |  | Technology Foundation |  | Closed | 2011-11-08 | 2012-03-09 | Guy / Adrian | Approval of CR001 & CR002 for SharePoint Foundation | 2012-03-09 | Both CRs are beyond the dates for acceptance specified by MS (prevDP14) 9-Mar Travis: Confirmed. |  | TRUE
D1 |  |  |  | Technology Foundation |  | Closed |  | 2011-04-01 | Al Grljevic | Source UK based project managers for the resourcing needs of the UC & Tech Foundation work streams. | 2012-03-05 | Paul Neave and TF team - still valid; marked revalidated. |  | TRUE
D66 |  | Al Grljevic / Adrian Mickleson |  | Technology Foundation |  | Closed |  | 2012-02-01 | Guy / Adrian | Confirm MS the authority to proceed with change Request for Lync workstream to optimise dates and reduce PoC to an ITSec lab test (currently being built) | 2012-02-01 | MS have expressed that JT has given them a different steer to the scope of the CR discussed in Secaucus. The plan has been to bring in delivery dates in order to achieve build completion in the 1sr GDC as early as 21/12/11 (prevDP13) 1-Feb: this decision was confirmed; going ahead. Per Al and Adrian on weekly RAID call. |  | TRUE
D61 | unknown | Adrian Mickleson | Adrian Mickleson | Technology Foundation |  | Closed |  | 2012-02-10 | Design Authority Programme Authority | DEC_012 Storage SAN/JBOD/RAID: SAN in large and medium siates and JBOD/RAID in small sites | 2012-02-10 | Currently producing recommendation to be approved by the DA technically and then signed off by the programme authority for cost impact (prev DP8) 10-Feb: closed on TF decisions call (Paul, Ant, Brett, Adrian, Al, Steve, James) |  | TRUE
D179 | unknown | Paul Neave | Adrian Mickleson | Technology Foundation |  | Closed |  | 2012-02-09 | Program Management | Need confirmation of whether ON-prem exchange solution will be on SP2 9-Feb: Confirmed. | 2012-02-09 | 9-Feb: Al confirmed that this decision has been made; will be on SP2. |  | TRUE
D181 | unknown | Paul Neave | Adrian Mickleson | Technology Foundation |  | Closed |  | 2012-02-09 | Program Management | Need confirmation of approach to be taken to building out ON-Prem exchange. By EY, a vendor or with Microsoft 9-Feb: Have a signed contract with Microsoft. | 2012-02-09 | 9-Feb: Al confirmed there is a signed contract with Msft. Close. |  | TRUE
D185 | 2012-02-09 | Martin Evans | Nick Wood, Brett van Gelder | Technology Foundation |  | Closed | 2012-02-15 |  | FSG? | The results of the BIS performed for mail need to be ratified. With imperfect information an RTO of 12 hours was determined but with estimated "losses" of $13.52 per person per hour is this acceptable to the business? The RTO is a design input for on premise solutions & influences hosting / DCC direction. |  | 14-Mar - PIN: The On Premise Exchange design is for 2 hours RPO & 2 Hours RTO where we have the full 3 copies, two site design, which meets the 16th Nov 2011 BIA. Have agreed this is acceptable to Martin Evans. 12-Mar: LM followed up with Paul for decision maker and decision date. Paul thinks it's closed - designing to meet BIA, confirming with Martin Evans. Martin suggested he and Paul talk because designing to the BIA results is what he is concerned about i.e. 24 hour RTO which is why the issue was raised. The Current On Premise Exchange design is for 2 hours RPO & 2 Hours RTO which meets the 16th Nov 2011 BIA. |  | TRUE
D196 | 2012-03-01 | Al Grljevic | Al Grljevic | Technology Foundation |  | Pending | 2012-06-01 |  |  | With the adoption of O365 and the constraints of the current agreement around the migration scheduling i.e. being constrained to weekdays and across 9 months with a specified ramp. In order to finalise the Migration infrastructure sizing for On-Prem we need to know the intended Migration strategy. Are we now going to adopt this approach? How many days in a week we are expecting to be migrating and how many Users per week, month etc. The decision will impact the number of servers/workstations we need to stand up to support migration which could vary between 10s and 100s depending on the decision. |  | 5-Mar: The Programme needs to asses risk of whether it is feasible to run On-prem and Cloud migration in parallel. The migration approach needs to happen throughout the week. The programme needs to define the approach that is least risk to the organisation |  | FALSE
D198 | 2012-03-07 | Mark Reade |  | Technology Foundation |  | Pending | 2012-04-20 |  | Michelle / Norm | Prioritise and stabilise demand for SharePoint environments - demand from SPE has been subject to constant change and additional requests. Need SPE to accept normalised dates for environment hand-off; these are dates that align with Foundation ability to design/build/deploy. Verification of design and configuration will reduce the number of changes requested and can deliver in less time. |  | SharePoint Enablement |  | FALSE
D199 | 2012-03-07 | Mark Reade |  | Technology Foundation | TF - SPF | Pending | 2012-04-20 |  | Michelle / Norm | Projects expecting to consume SharePoint environments need to agree to a 6-12 week rolling revision plan for environment changes to avoid constant reiteration and delay, this to include verification of requirements and designs before environment builds. Normalisation of "required by" dates received from SPE have been proposed to align with a framework of change/release windows for environments once handed off to SPE. |  | SharePoint enablement |  | FALSE
D200 | 2012-03-07 | Mark Reade |  | Technology Foundation |  | Pending | 2012-04-20 |  | Fareed Naeem / Jeremy Brown | An EY SharePoint Governance body needs to be established and empowered to make decisions affecting the consumption and operation of SharePoint following O365 iteration of design. This will require a goverance body to be set up comprising IT/Ops/InfoSec/S&I/M&C representation to own SharePoint specific decisions throughout the build, delivery and beyond to operate SharePoint as a service. |  | Program 7-Mar: Al and Mark had a conversation around this item; will be part of blueprints. Decision will need to come first from Fareed Naeem and then Jeremy Brown. |  | FALSE
D201 | 2012-03-07 | Mark Reade |  | Technology Foundation |  | Pending | 2012-04-20 |  | Ant / Afzaal / Klara | Extranet- Confirm strategy for external authentication and content management. This is required before Extranet design can be re-factored into the existing EY SharePoint Infrastructure and Design document submitted by Msft. |  | IAM/InfoSec |  | FALSE
D202 | 2012-03-07 | Mark Reade |  | Technology Foundation | TF - SPF | Pending | 2012-04-20 |  | Michelle / Norm | SPE need to confirm scope and business requirements for client collaboration (ECMA). Requirements for client collaboration are not confirmed and are needed to allow the effective design for client collaboration in the refactored design. |  | SharePoint enablement (requirements) |  | FALSE
D203 | 2012-03-07 | Paul Neave |  | Technology Foundation |  | Closed | 9th March | 2012-03-09 |  | CR0026 for the re-design approved (to get the re-design underway to get to the final design) CR approved. | 2012-03-09 | 9-Mar: CR0026 closed today. |  | FALSE
D204 | 2012-03-07 | Paul Neave |  | Technology Foundation |  | Closed | 9th March | 2012-03-09 |  | 3-way coexistence design: Microsoft will prime this work and O365 will underwrite that the design will work with O365. Part of CR 26 (9-Mar: CR approved) | 2012-03-09 | 9-Mar: CR0026 closed today; as part of CR26, closed. |  | FALSE
D205 | 2012-03-07 | Paul Neave |  | Technology Foundation |  | Obsolete |  |  |  | Confirmation of lead times for Storage |  | Task |  | TRUE
D206 | 2012-03-07 | Paul Neave |  | Technology Foundation |  | Obsolete |  |  |  | Are IAM dependencies going to be met? |  | Task |  | TRUE
D207 | 2012-03-07 | Paul Neave |  | Technology Foundation |  | Pending | 2012-05-05 |  |  | Are DCC contracted for buildout for Exchange? |  |  |  | FALSE
D208 | 2012-03-07 | Paul Neave |  | Technology Foundation |  | Closed |  |  |  | Is Good EWS going to be delivered? What is the future service model for Exchange - who does what, up to OS, Storage, application | 2012-03-07 | related to I19? |  | TRUE
D210 | 2012-03-07 | Al Grljevic | Al Grljevic | Technology Foundation |  | Closed |  | 2012-03-07 | Al, Adrian and Mark provided the update. | It is confirmed that Frankfurt will be the only data center for the installation of the required infrastructure for the M&C program. | 2012-03-07 | 7-Mar: It has been confirmed that Frankfurt will be the only data center; mark validated per Al, Adrian, and Mark. This came out of A2. |  | TRUE
D211 | 2012-03-12 | Paul Neave | Siggi Hauer | Technology Foundation | TF - Messaging | Pending | 2012-03-20 |  | Siggi Hauer | We require a decision on the funding model for the Cloud as to whether there is to be a per HC/MBX charge, whether it is to be added to the Internal IT Services charges, or some Hybird with a portion such as the Data Centre charges added ot the internal charge and a Per user charge going direct. |  | 16-Mar: Meeting Monday to discuss. |  | TRUE
D213 | 2012-03-14 | Chris Rae | Chris Rae | Technology Foundation |  | Closed |  | 2012-03-15 | The following attended the meeting. Myself Pete Bruinsma Adrian Mickleson, Mark Reade, Gregory Van Valkenburgh, Christopher Arnold Jahanzeb Ahmed, Amit Tak, Oliver Berchtold Jaco Lanza Dan P. Mulligan The following received the email follow up and raised no objection. Brett van Gelder Klara Neginsky Norm Lambert Scott Strange Michelle Edmonds Al Grljevic Afzaal Syed | User profile FIM filter section will be submitted as it is. We are aware the the current filters do not cope with duplicate AD accounts to create a single profile. This item will be continued to be managed, and if the solution needs a change to the filters they will be submitted as CR. The consequences are that unless something is done in the interim, O365 will be stood up and will have duplicate user profiles. | 2012-03-15 | 15-Mar Chris: The rationale was that although the FIM filters in O365 might form part of a possible solution to duplicate profiles, we still have not decided on the final solution, indeed we don't even know if there is one. As the final O365 questionnaire needed to be submitted nothing was included in an attempt to deal with this, and it was decided if a change was required to the FIM filters this could easily be achieved via a standard O365 CR. 14-Mar-12 BvG: Note this means that there are likely going to be duplicate profiles for users with multiple AD accounts which which is likely to cause some end-user confusion. |  | TRUE
D78 | unknown | Rewa Bouji | Rewa Bouji | Unified Communications |  | Closed | 2012-02-16 | 2012-03-06 | FSG | Need to determine how the business wishes UAT to be conducted - whether the business will create use cases and commit business resources to the execution of UAT, or whether the business will "in-source" UAT to the QA team and allow the program to execute UAT on behalf of users, but having signed off the use cases/test scripts etc | 2012-03-06 | 06/03/12: RB: Jeremy Brown confirmed on behalf of FSG that business users will execute UAT 20-Feb JC - Discussion point for FSG 14/02/12: RB: Awaiting update from MK 25/01/12: R Bouji: MK indicated that business users will participate - awaiting confirmation of validation with BR/FSG 18/01/12: R Bouji: Pending discussions with Martin Kremmer on alternative decision making route 11/01 Update from R Bouji: Was scheduled for decision at next FSG meeting, however the meeting has been shortened and it is not yet clear when this will reappear on the agenda. QA need to know by end of Jan to start ramping up resources and planning. Await update on next FSG meeting and agenda 19-Dec update from Nicky that this has been bumped from the FSG agenda 2X; hoping to get it in next meeting. Adrian Mickleson to raise this to the FSG on 15 November for a decision (prev DP25) ADM (MS): We are creating a "UAT pack" with guides and templates for what needs to be created and undertaken along with a schedule of effort and when it needs to take place. For each application, this will be provided to the business immediately after initiation of the project. We will facilitate the UAT process and provide guidance, but do not believe that we should be "in-sourced" to conduct the UAT for the business. We HAVE NOT allowd budget for the in-sourcing of UAT, or have resources lined up to conduct these activities. |  | TRUE
D79 | unknown | Rewa Bouji | Rewa Bouji | Unified Communications |  | Closed | 2012-05-11 | 2012-03-05 | John Costello / Siggi Hauer | Decision needed on exact configuration of Day 1 Exchange feature set and whether this will include any mail-integrated applications. Discovery and analysis currently underway within Unified Comms stream, and impact assessment work to be conducted by Engineering and in consultation with Microsoft where any O365 impact/constraint may be identified. Presentation to FSG for decision targeted for mid March latest to finalise specification and communicate to stakeholders on Day 1 feature set 5-Mar: Decision is for the product owner to ensure that their product works with Exchange | 2012-03-05 | 05-Mar: Decision is for the product owner to ensure that their product works with exchange 22/02/12: RB: 1) Outlook Config settings due to complete 20/04. Recommended Day 1 Plug in list due to complete 20/04. Decision required by 11 May (not clear who decision-making body would be however). 20-Feb JC - Ok - would like to see both the feature and integration list so we can ok. 14/02/12: RB: Engineering & Application Management likely to complete impact assessment by mid-March. RB to prepare presentation to summarise approach to agreeing Day 1 mail-integrated application scope for stakeholders, intention for scope to be agreed by end April 31/01/12: R Bouji - Engineering can no longer meet end Feb deadline - awaiting revised date. Also need to determine whether FSG is appropriate decision-making authority. To be discussed with AG and MK 18/01/12: R Bouji - Awaiting outcome of engineering impact assessment due end February, for presentation to FSG and final decision on Day 1 configuration |  | FALSE
D183 | unknown | Rewa Bouji | Rewa Bouji | Unified Communications |  | Pending | 2012-04-30 | 2012-03-05 | John Costello / Siggi Hauer | Agreement is not to migrate static groups. We should limit which users are allowed to create static groups. The approach used for GLMS should be replicated to avoid duplication of groups. Decision needs to made as to whether existing static email groups (distribution lists) will be migrated to the new Exchange AD or not. If yes, the MMD Self-service portal will continue to be developed, but the process of asking thousands of users to nominate groups for migration is inherently risky and time-consuming. The portal is being built on the assumption that static group migration will be required but this is not IT's preferred option. There also needs to be a decision made as to what will happen to legacy group management tools and whether they will be replaced by IAM's new GroupID tool, or GLMS, or have the option of either. | 2012-03-05 | 12/03/12: RB: Decision re-opened based on lack of business representation in previous approval decision. Proposals now with Bob Reiner and Jeremy Brown for review/approval 5-Mar: Agreement is not to migrate static groups. We should limit which users are allowed to create static groups. The approach used for GLMS should be replicated to avoid duplication of groups. 22/02/12: RB: RB – M&C and IAM teams have developed proposal for managing migration of Domino groups and legacy group management tools. Decisions required ASAP but not clear who decision making authority would be across M&C and IAM 20-Feb JC - Legacy group management tools should be retired and replaced by the tool we acquired. For groups, are you talking about personal mail groups I have setup? 14/02/12: RB: Group Management Proposals being re-drafted following further discussion with N Wood and B van Gelder. Meeting to finalise proposals rescheduled to 20/02/12 due to impact of workshops on SME availability 02/02/12: R Bouji - A set of proposals have been drafted and are currently being finalised with input from the GLMS team, for presentation to the FSG for decision making. Decision is required very soon so as to avoid potentially significant wasted development effort on the Self-service portal, and potential confusion around requirements for GroupID tool, which are being finalised in a workshop week of 6th Feb 10-Feb: PIN – need to know this soon as influences both On-Prem and O365 |  | FALSE
D108 |  |  |  | Unified Communications |  | Closed |  | 2011-11-07 | Bob Reiner | CRM integration is not required for Day 1 of Outlook |  | 11-Nov-11: Added by R Bouji following confirmation by A Mickleson on 7-Nov-11 |  | TRUE
D50 |  |  |  | Unified Communications |  | Closed |  | 2011-09-28 | Participants in September 2011 Functional Stakeholders meeting Washington DC | Agreement that we will not use Super Users. |  | 04-Oct-11: R Bouji: A Mickleson confirmed agreement by FSG in Washington |  | TRUE
D51 |  |  |  | Unified Communications |  | Closed |  | 2011-10-04 | Participants in September 2011 Functional Stakeholders meeting Washington DC | a) Unified Comms will migrate the past thirty (30) days of email from users' Lotus Notes to users' Microsoft Outlook accounts. The 30 days is calculated as the migration start date less 30 days. b) Unified Comms will migrate the folder structure from users' Lotus Notes accounts (all folders), but only the last 30 days of email within those folders. c) Unified Comms will migrate all future calendar entries and the past thirty (30) days of calendar entries from users' Lotus Notes to users' Microsoft Outlook accounts. The 30 days is calculated as the migration start date less 30 days d) Unified Comms will migrate all synchronised contacts stored in local Contacts files from users' Lotus Notes to users' Microsoft Outlook accounts |  | 04-Oct-11: R Bouji: A Mickleson confirmed this decision was made by FSG in Washington 28-Oct-11: R Bouji: N Wood & B van Gelder confirmed this requires further discussion and there is no documented decision on this. This functionality was one of the options discussed. A Mickleson & N Wood to clarify and provide update to Program team at next RAID meeting. |  | TRUE
D52 |  |  |  | Unified Communications |  | Closed |  | 2011-10-04 | Participants in September 2011 Functional Stakeholders meeting Washington DC | Each individual's Sametime groups will not be moved as part of the Lync go live. There will be an xml applet/widget that users can choose to run once Lync is activated that will migrate their Sametime groups across to Lync |  | 04-Oct-11: Added by R Bouji |  | TRUE
D182 | unknown | Rewa Bouji | Rewa Bouji | Unified Communications |  | Closed | 2012-03-16 |  | TBD | Need confirmation on whether business or program will absorb cost of peripherals to be used with Lync (headsets, webcams, etc) | 2012-03-12 | 12/03/12: RB: Confirmation received from R Cansick that process is for IT to make provision in country budgets for the total device spend. Whilst countries will pay for devices when purchased, these will be charged to the country itself, but then cross-charged back to IT via the settlements process. Provision of $10m has been made in M&C budget for FY13. 5-Mar: Confirm who agrees the provisioning rules for Lync devices They will need to work closely with Liz king to ensure she is aware of the approach and agreement is provided Al to reach out to Andrea Cohnen-Mohns 22/02/12: RB: Updated cost model due 28/02/12 for delivery to A Guthrie & J Costello 20-Feb JC - Should be in FY13 budgets for each country - believe we have discussed this before- need to provide these costs to Scott Armbrecht so they can be included in country budgets - we need to see a model vs cost analysis on the headsets before choosing - Brendan Millard has already done work on this. 14/02/12: RB: Cost model for projected device spend per country being developed with Global Procurement and OSS - aim to have early draft of costs by 24/02/12 for delivery to Alan Guthrie who will then take to stakeholders for decision 31/01/12: R Bouji - UC has inherited the working assumption that countries will bear the cost of purchasing peripherals (headsets, webcams etc) to be used with Lync, rather than the program, however it has been found that this assumption has not previously been logged or validated |  | TRUE
D53 |  |  |  | Unified Communications |  | Closed |  | 2011-10-04 | Program Management | Once all users have had Lync activated on their desktops and are "live", Sametime will be globally disabled |  |  |  | TRUE
D214
D215
D216
D217
D218
D219
D220
D221
Note on K134: Binu Alex: Some apps may have a lower indexing latency and this should be identified in the Roadmap
Note on K174: Binu Alex: Effort underway as part of Fusion and IAM program - Afzaal Syed, Ant Harper and Amit Tak are the contacts.

## Actions Report
MM.DD.## | Status | Action | Comments | Owner | Due Date | Date Closed
01.04.01 | Closed | Michelle to talk to Norm and Adrian about status of Risk 48. Either close the issue or turn it into an issue as appropriate by next meeting. |  | Michelle Edmonds | 2012-01-11 | 2012-01-10
01.04.02 | Closed | Laura to invite Rewa onto RAID call. |  | Laura Murphy | 2012-01-04 | 2012-01-04
01.04.03 | Closed | Steven Jelf to add a new risk to the log; it is an overall risk around dependencies. |  | Steven Jelf | 2012-01-11 | 2012-01-11
01.04.04 | Closed | I69: Michelle to talk with Brett, Klara and Adrian about an update; update the item accordingly. |  | Michelle Edmonds | 2012-01-11 | 2012-01-11
01.04.05 | Closed | I62: Michelle said on the call that there is a risk they have opened that is a part of this issue. She took the action to close out that risk and combine it into this issue. | 21-Feb: This is outstanding; Michelle confirmed can close. | Michelle Edmonds | 2012-01-11 | 2012-02-21
01.04.06 | Closed | I40: Jackie to update; mentioned on call that this is linked with I49. Combine? |  | Jackie Knight | 2012-01-11 | 2012-01-10
01.04.07 | Closed | Michelle to populate column data for Issue 86, which came from Assumption 33 as discussed on the call. Update syntax of description and include/update remaining information. (Also, Issue 87, from Assumption 37) | Issue 87 closed; Issue 86 updated. | Michelle Edmonds | 2012-01-11 | 2012-02-08
01.11.01 | Closed | Michelle and Adrian to review Issues I71B and I71A (respectively). Laura split I71 into two items (as requested on Wednesday's call). The impact, due date, etc. columns need to be reviewed. | Columns have been populated; any missing information will be tracked through the Project Summary snapshots. | Michelle Edmonds/Adrian Mickleson | 2012-01-18 | 2012-02-08
01.11.02 | Closed | I75: Brett and Adrian to discuss off-line. 18-Jan: Brett and Adrian provided update on call. |  | Adrian Mickleson / Brett van Gelder | 2012-01-18 | 2012-01-18
01.11.03 | Closed | I33 - As part of the resolution of this issue, Al took an action to get (from Bob Reiner or other) a list of countries we will build in and a list of countries we will not build in. Plans to have this for the beginning of February. | 6-Mar: Issue closed; Al is following up through pending decision D92. | Al Grljevic | 2012-02-01 | 2012-03-06
01.18.01 | Closed | Adrian and Ken to schedule a conversation for next Tuesday (24-Jan) evening; look at the Group Management workshop scheduled for 6-February and discuss whether to reposition. | Have reached the date and decision made. | Ken Sponaugle and Adrian Mickleson | 2012-01-24 | 2012-02-08
01.25.01 | Closed | D86: Determine cost and take forward to the CR meeting. Decision states: M&C will rebuild Good and BES on exchange on the appropriate versions | Being tracked in Issue 19. | Adrian Mickleson / Nick Wood
01.25.02 | Closed | I40: Rewa will split this item back out (used to be two separate items) so that one is a risk that the lack of decisions being made will h hamper progress. The longer these decisions make, the longer until we can move forward. She will include the O365 decision in the description and assign the item to Ian, Guy and Alan to resolve. | I40 and I106 | Rewa Bouji | 2012-02-01 | 2012-01-26
01.25.03 | Closed | R93: Steve to add a risk around the Lync infrastructure and the Q&RM concern of the saving of transcripts | R93 | Steven Jelf | 2012-02-01 | 2012-01-26
01.26.01 | Open | AD RMS deployed in In-country Data Rooms alongside Exchange. (4.1) | Lack of AD resource within EY - AD representation needs to be embedded in all 4 streams. Late agreement of SOWs. Suggest a deep dive into IAM Programme to better understand exact status. Conflicted Msft resources. | IAM - Ken Sponaugle | 2012-05-01
01.26.02 | Open | Domain Controllers/Global Catalog Servers deployed in In-country Data Rooms and secondary sites alongside Exchange. (4.2) | Lack of AD resource within EY - AD representation needs to be embedded in all 4 streams. Late agreement of SOWs. Suggest a deep dive into IAM Programme to better understand exact status. Conflicted Msft resources. | IAM - Ken Sponaugle | 2012-05-01
01.26.03 | Open | AD schema extension deployed for Exchange (4.3) 26-Jan: Ken responded that this will not be available by 30-Jan as members of team are participating in the O365 workshop. Team will be meeting Monday to provide a response based on what is learned during the sessions. | Lack of AD resource within EY - AD representation needs to be embedded in all 4 streams. Late agreement of SOWs. Suggest a deep dive into IAM Programme to better understand exact status. Conflicted Msft resources. | IAM - Ken Sponaugle | 2012-01-30
01.26.04 | Open | Group management tool able to create migrated mail-only groups. (4.4) | Lack of AD resource within EY - AD representation needs to be embedded in all 4 streams. Late agreement of SOWs. Suggest a deep dive into IAM Programme to better understand exact status. Conflicted Msft resources. | IAM - Ken Sponaugle | 2012-04-01
01.26.05 | Open | Root Domain enabled (4.5) 26-Jan: Ken responded that this will not be available by 30-Jan as members of team are participating in the O365 workshop. Team will be meeting Monday to provide a response based on what is learned during the sessions. | Lack of AD resource within EY - AD representation needs to be embedded in all 4 streams. Late agreement of SOWs. Suggest a deep dive into IAM Programme to better understand exact status. Conflicted Msft resources. | IAM - Ken Sponaugle | 2012-01-30
01.26.06 | Open | Group management tool for creating and managing groups in Exchange (4.6) | Lack of AD resource within EY - AD representation needs to be embedded in all 4 streams. Late agreement of SOWs. Suggest a deep dive into IAM Programme to better understand exact status. Conflicted Msft resources. | IAM - Ken Sponaugle | 2012-04-01
01.26.07 | Open | Identity Synchronization/Content Standardization (01Apr2012) (4.7) | Lack of AD resource within EY - AD representation needs to be embedded in all 4 streams. Late agreement of SOWs. Suggest a deep dive into IAM Programme to better understand exact status. Conflicted Msft resources. | IAM - Ken Sponaugle | 2012-04-01
01.26.08 | Open | Operational In-Country Data Rooms ready with Domain Controllers, network connectivity, Network Load Balancers and Exchange and SharePoint infrastructure built to the OS layer in place. (5.1) | DCC preference would be to complete build on primary sites where location and stds are currently known in the timescale, e.g. one or more of Canada, Australia, Japan, China, India | DCC - John Lawler | 2012-04-01
01.26.09 | Open | Operational In-Country Secondary/Disaster recovery sites with Domain Controllers, network connectivity, Network Load Balancers, and Exchange and SharePoint infrastructure built to the OS layer in place. (5.2) | DCC preference would be to build for the secondary/disaster recovery sites at large sites where the lcoation is not currently known, i.e. China, India | DCC - John Lawler | 2012-04-01
01.26.10 | Open | Connectivity between the BPOS solution and the EY network (5-6 mths from order placement) (6.1) | Orders need to be placed subject to 4.1 (01.26.01) | GNP - Brendan Millard (Steve Yeomans) | 2012-05-01
01.26.11 | Open | Adequate bandwidth between primary and secondary sites to support Exchange mailbox replication. (6.2) | In hand with network investigate scale of problem | GNP - Brendan Millard (Steve Yeomans) | 2012-05-01
01.26.12 | Closed | Understanding of full service offering for both SharePoint and Exchange - impacts SharePoint build for GDC and impacts BES & GOOD migration strategy. (7.1) | There is a limited understand within the Delivery team of how the coexistence of BES/GOOD will work on cloud and on-premise. Clarification for TF of the SharePoint service offering in the cloud vs. what is required on-premise. 21-Feb: Al confirmed that this action has been covered as part of the risks/issues (I19) | BPOS - John Costello | 2012-01-13 | 2012-02-21
01.26.13 | Open | Understanding of Global Outlook config baseline and key differences in user experience (Cloud and on-Premise) (8.1) | All dates are depending on acceptance and buy-in from relevant stakeholder at a Subarea and country level. | Business Change & Deployment - Sophie Boiron & Martin Kremmer (Rewa and Martin) | 2012-02-13
01.26.14 | Open | High level impact assessment for Outlook and Lync with key business representatives. (8.1) | All dates are depending on acceptance and buy-in from relevant stakeholder at a Subarea and country level. | Business Change & Deployment - Sophie Boiron & Martin Kremmer (Rewa and Martin) | 2012-03-19
01.26.15 | Open | Completion of early lifecycle support (ELS) (8.2) | Possible major issues around the sufficient number of resources needed to support ELS. | Operations - Siggi Hauer | 2012-04-15
01.26.16 | Closed | Provision of devices to enable use of the functionality (9.1) | Devide strategy is confused and lack of confidence that timelines are going to be met. 21-Feb: Al confirmed this can be closed. | Procurement - Florence Tinsley-Roy | 2012-04-01 | 2012-02-21
01.26.17 | Open | We require a dedicated EY lead, at a minimum, across each of the programme streams to ensure that activities around planning and execution for the on-premise and cloud solution can be executed. (11.1) | Without having a dedicated Service Integrator or the ability to ramp up resources, key milestones around delivery will not be achieved. | Guy Morgan to define needs | 2012-01-23
02.01.01 | Closed | D61 - update with comment on what the decision was and then close. | Updated. | Al Grljevic/Adrian Mickleson | 2012-02-08 | 2012-02-10
02.08.01 | Closed | R92 (Riverbed) - Al to touch base with Alan to ensure he is explicitly aware of this risk and its implications. | This item had been closed due to positive references from current clients. | Al Grljevic | 2012-02-15 | 2012-03-06
02.08.02 | Closed | R93 (archiving of external chats): Steve to go to Q&RM to ensure they understand this risk; then Al, Adrian and Steve to take to engineering to discuss costs. | 6-Mar: Steve - Q&RM - no longer a requirement. | Steve / Adrian / Al | 2012-02-15 | 2012-03-06
02.08.03 | Open | R101: Daren to talk with GCL5 and make sure they what they are building today is what we are expecting. Provide team an update on this call next week. |  | Daren Wicks | 2012-02-15
02.08.04 | Open | I91: Neil to officially socialize within IT Services that the project plan for IT Services assumes Dec 2017 completion, meaning the firm will be dependent on Notes beyond 2013. |  | Neil Sahdev | ASAP
02.09.01 | Open | End state Target Operating Model (TOM) for collaborative platform support Significant challenge to transition workstream | This was D95, but Al clarified that it is not a decision, but rather an action for the transition management team to resolve. Marked obsolete. | Transition management team
02.20.01 | Closed | D83: John Costello confirmed D83 that there will be a 5GB mail file limit; he said there is a question about partners getting 25GB and requested Al send himself (John) and Siggi the cost for this vs the 5 GB. | Being actively managed through D83 and TF subsequent actions. This has been completed 5-Mar. | Al Grljevic |  | 2012-03-05
02.22.01 | Closed | R97: Rewa to reword the risk description to reflect the conversation with Brett on the call around the crux of the matter: EY needs to review the assumptions made around migration in light of the O365 changes. | Add'l info in Comments column of risk tab | Rewa Bouji | 2012-02-29 | 2012-02-27
Note on C16: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C17: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C18: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C19: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C20: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C21: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C22: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C23: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C24: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C25: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C26: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C27: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C28: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C29: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C30: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C31: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.
Note on C32: Laura Murphy: *Actions added 26-Jan are from the Key Decisions and Actions Jan 12 2012.pptx deck.

## RAID Summary
| 2011-12-21 | 2012-01-04 | 2012-01-11 | 2012-01-18 | 2012-01-25 | 2012-02-01 | 2012-02-08 | 2012-02-15 | 2012-02-22 | 2012-02-29 | 2012-03-06 | 2012-03-07 | 2012-03-08 | 2012-03-09 | 2012-03-12 | 2012-03-13 | 2012-03-14 | 2012-03-15 | 2012-03-16 | 2012-03-19 | 2012-03-20 | 2012-03-21 | 2012-03-22 | 2012-03-23 | 2012-03-26 | current
Total Open Risks | 40 | 34 | 33 | 30 | 32 | 32 | 30 | 30 | 32 | 39 | 45 | 38 | 37 | 32 | 30 | 29 | 32 | 32 | 32 | 35 | 35 |  |  |  |  | 35
Total Open High or Critical Risks | 15 | 10 | 13 | 13 | 14 | 14 | 16 | 16 | 21 | 28 | 25 | 19 | 17 | 14 | 14 | 14 | 17 | 16 | 16 | 15 | 15 |  |  |  |  | 15
Risks: Missed Required Resolution Date |  |  | 2 | 3 | 5 | 7 | 8 | 10 | 9 | 13 | 9 | 2 | 2 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 |  |  |  |  | 0
Total Open Issues | 37 | 37 | 42 | 42 | 45 | 48 | 52 | 43 | 49 | 51 | 55 | 51 | 53 | 46 | 47 | 44 | 44 | 42 | 41 | 37 | 37 |  |  |  |  | 37
Total Open High or Critical Issues |  |  | 25 | 25 | 28 | 33 | 39 | 31 | 37 | 40 | 45 | 42 | 45 | 37 | 37 | 36 | 36 | 34 | 33 | 29 | 29 |  |  |  |  | 29
Issues: Missed Required Resolution Date |  |  | 13 | 12 | 7 | 13 | 16 | 14 | 12 | 22 | 20 | 14 | 16 | 13 | 8 | 6 | 4 | 7 | 6 | 3 | 4 |  |  |  |  | 4
Total Assumptions | 78 | 70 | 67 | 67 | 68 | 69 | 69 | 69 | 63 | 63 | 63 | 63 | 63 | 63 | 62 | 62 | 62 | 62 | 62 | 62 | 54 |  |  |  |  | 54
Total Decisions | 153 | 153 | 154 | 154 | 161 | 182 | 183 | 179 | 179 | 179 | 181 | 194 | 192 | 191 | 192 | 193 | 193 | 191 | 191 | 191 | 176 |  |  |  |  | 176
Total Pending Decisions | 24 | 24 | 25 | 24 | 30 | 39 | 40 | 29 | 28 | 27 | 22 | 33 | 28 | 26 | 26 | 26 | 26 | 23 | 22 | 21 | 21 |  |  |  |  | 21
Total Assumptions to be Validated | [16 empty] | 43 | 43 | 43 | 43 | 12 |  |  |  |  | 12
Total Assumptions to be Validated - Past Due | [12 empty] | 41 | 41 | 40 | 39 | 39 | 38 | 38 | 37 | 6 |  |  |  |  | 6
Total Pending Decisions - Past Due | [12 empty] | 11 | 9 | 9 | 9 | 8 | 5 | 2 | 1 | 2 |  |  |  |  | 2
Top Critical Risks
[27 empty] | Item | Description | Proposed Action
1
2
3
Top Critical Issues
[27 empty] | Item | Description | Action
1
2
3
Today's Date: | 2012-03-22

## Project Summary
App & Data Migration | 2012-02-13 | 2012-02-16 | 2012-02-20 | 2012-02-23 | 2012-02-27 | 2012-03-01 | 2012-03-05 | 2012-03-06 | 2012-03-07 | 2012-03-08 | 2012-03-09 | 2012-03-12 | 2012-03-13 | 2012-03-14 | 2012-03-15 | 2012-03-16 | 2012-03-19 | 2012-03-20 | 2012-03-21 | 2012-03-22 | 2012-03-23 | 2012-03-26 | current
Total Open Risks | 7 | 7 | 7 | 6 | 6 | 7 | 7 | 7 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2
Total Open High or Critical Risks | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
Risks: Missed Required Resolution Date | 3 | 5 | 6 | 5 | 5 | 5 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks with no Required Resolution Date | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks open 1-3 months | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
Risks open 3-6 months | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks open longer than 6 months | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Total Open Issues | 5 | 4 | 4 | 5 | 5 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3
Total Open High or Critical Issues | 5 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3
Issues: Missed Required Resolution Date | 4 | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Issues with no Required Resolution Date | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Issues open 1-3 months | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
Issues open 3-6 months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Issues open longer than 6 months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Total Assumptions not yet validated | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2
Total Pending Decisions | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3
Change Management | 2012-02-13 | 2012-02-16 | 2012-02-20 | 2012-02-23 | 2012-02-27 | 2012-03-01 | 2012-03-05 | 2012-03-06 | 2012-03-07 | 2012-03-08 | 2012-03-09 | 2012-03-12 | 2012-03-13 | 2012-03-14 | 2012-03-15 | 2012-03-16 | 2012-03-19 | 2012-03-20 | 2012-03-21 | 2012-03-22 | 2012-03-23 | 2012-03-26 | current
Total Open Risks | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
Total Open High or Critical Risks | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks: Missed Required Resolution Date | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks with no Required Resolution Date | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks open 1-3 months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks open 3-6 months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks open longer than 6 months | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
Total Open Issues | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
Total Open High or Critical Issues | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
Issues: Missed Required Resolution Date | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Issues with no Required Resolution Date | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Issues open 1-3 months | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Issues open 3-6 months | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
Issues open longer than 6 months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Total Assumptions not yet validated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Total Pending Decisions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
M&C Program | 2012-02-13 | 2012-02-16 | 2012-02-20 | 2012-02-23 | 2012-02-27 | 2012-03-01 | 2012-03-05 | 2012-03-06 | 2012-03-07 | 2012-03-08 | 2012-03-09 | 2012-03-12 | 2012-03-13 | 2012-03-14 | 2012-03-15 | 2012-03-16 | 2012-03-19 | 2012-03-20 | 2012-03-21 | 2012-03-22 | 2012-03-23 | 2012-03-26 | current
Total Open Risks | 4 | 4 | 4 | 4 | 4 | 9 | 9 | 8 | 7 | 7 | 7 | 7 | 7 | 6 | 7 | 7 | 7 | 7 |  |  |  |  | 7
Total Open High or Critical Risks | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 |  |  |  |  | 5
Risks: Missed Required Resolution Date | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks with no Required Resolution Date | 3 | 3 | 3 | 2 | 2 | 7 | 7 | 6 | 3 | 1 | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | 0
Risks open 1-3 months | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 2 | 3 |  |  |  |  | 3
Risks open 3-6 months | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 |  |  |  |  | 2
Risks open longer than 6 months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Total Open Issues | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 8 | 14 | 15 | 15 | 15 | 15 | 15 | 14 | 14 |  |  |  |  | 14
Total Open High or Critical Issues | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 9 |  |  |  |  | 9
Issues: Missed Required Resolution Date | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 |  |  |  |  | 1
Issues with no Required Resolution Date | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 4 | 2 | 1 | 1 | 1 | 0 | 0 |  |  |  |  | 0
Issues open 1-3 months | 3 | 3 | 5 | 6 | 7 | 7 | 7 | 5 | 5 | 6 | 6 | 9 | 9 | 9 | 9 | 9 | 9 | 10 |  |  |  |  | 10
Issues open 3-6 months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
Issues open longer than 6 months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Total Assumptions not yet validated | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
Total Pending Decisions | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2
SharePoint | 2012-02-13 | 2012-02-16 | 2012-02-20 | 2012-02-23 | 2012-02-27 | 2012-03-01 | 2012-03-05 | 2012-03-06 | 2012-03-07 | 2012-03-08 | 2012-03-09 | 2012-03-12 | 2012-03-13 | 2012-03-14 | 2012-03-15 | 2012-03-16 | 2012-03-19 | 2012-03-20 | 2012-03-21 | 2012-03-22 | 2012-03-23 | 2012-03-26 | current
Total Open Risks | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 13 | 13 | 12 | 7 | 5 | 4 | 5 | 5 | 5 | 6 | 6 |  |  |  |  | 6
Total Open High or Critical Risks | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks: Missed Required Resolution Date | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks with no Required Resolution Date | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 |  |  |  |  | 2
Risks open 1-3 months | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks open 3-6 months | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks open longer than 6 months | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Total Open Issues | 12 | 13 | 13 | 18 | 18 | 18 | 18 | 26 | 26 | 27 | 14 | 15 | 13 | 11 | 9 | 8 | 6 | 6 |  |  |  |  | 6
Total Open High or Critical Issues | 5 | 6 | 6 | 11 | 11 | 12 | 12 | 18 | 18 | 20 | 9 | 11 | 11 | 9 | 7 | 6 | 4 | 4 |  |  |  |  | 4
Issues: Missed Required Resolution Date | 2 | 3 | 3 | 4 | 4 | 7 | 8 | 8 | 8 | 9 | 6 | 3 | 2 | 1 | 3 | 3 | 0 | 0 |  |  |  |  | 0
Issues with no Required Resolution Date | 6 | 7 | 7 | 6 | 6 | 6 | 6 | 3 | 3 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Issues open 1-3 months | 8 | 9 | 9 | 8 | 8 | 10 | 10 | 7 | 7 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 |  |  |  |  | 1
Issues open 3-6 months | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 1 |  |  |  |  | 1
Issues open longer than 6 months | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Total Assumptions not yet validated | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 36 | 36 | 36 | 36 | 36 | 37 | 37 | 37 | 6 |  |  |  |  | 6
Total Pending Decisions | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 0 | 0 |  |  |  |  | 0
Tech Foundation | 2012-02-13 | 2012-02-16 | 2012-02-20 | 2012-02-23 | 2012-02-27 | 2012-03-01 | 2012-03-05 | 2012-03-06 | 2012-03-07 | 2012-03-08 | 2012-03-09 | 2012-03-12 | 2012-03-13 | 2012-03-14 | 2012-03-15 | 2012-03-16 | 2012-03-19 | 2012-03-20 | 2012-03-21 | 2012-03-22 | 2012-03-23 | 2012-03-26 | current
Total Open Risks | 10 | 9 | 9 | 9 | 9 | 9 | 8 | 5 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 7 | 7 |  |  |  |  | 7
Total Open High or Critical Risks | 7 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 |  |  |  |  | 1
Risks: Missed Required Resolution Date | 2 | 1 | 2 | 2 | 2 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  |  |  |  | 0
Risks with no Required Resolution Date | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 4 |  |  |  |  | 4
Risks open 1-3 months | 3 | 3 | 3 | 3 | 5 | 4 | 5 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3
Risks open 3-6 months | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks open longer than 6 months | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  |  |  |  | 0
Total Open Issues | 20 | 13 | 13 | 13 | 15 | 15 | 15 | 12 | 11 | 12 | 12 | 12 | 11 | 11 | 11 | 11 | 11 | 11 |  |  |  |  | 11
Total Open High or Critical Issues | 16 | 9 | 9 | 9 | 11 | 11 | 11 | 11 | 10 | 8 | 9 | 11 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  |  | 10
Issues: Missed Required Resolution Date | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 3 |  |  |  |  | 3
Issues with no Required Resolution Date | 12 | 2 | 2 | 2 | 4 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Issues open 1-3 months | 9 | 7 | 7 | 8 | 8 | 7 | 7 | 3 | 2 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3
Issues open 3-6 months | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 3 | 4 | 5 | 5 | 5 | 4 | 4 | 4 | 4 |  |  |  |  | 4
Issues open longer than 6 months | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
Total Assumptions not yet validated | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2
Total Pending Decisions | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 22 | 17 | 15 | 16 | 16 | 16 | 16 | 15 | 15 | 15 |  |  |  |  | 15
Unified Communications | 2012-02-13 | 2012-02-16 | 2012-02-20 | 2012-02-23 | 2012-02-27 | 2012-03-01 | 2012-03-05 | 2012-03-06 | 2012-03-07 | 2012-03-08 | 2012-03-09 | 2012-03-12 | 2012-03-13 | 2012-03-14 | 2012-03-15 | 2012-03-16 | 2012-03-19 | 2012-03-20 | 2012-03-21 | 2012-03-22 | 2012-03-23 | 2012-03-26 | current
Total Open Risks | 3 | 3 | 3 | 5 | 5 | 6 | 9 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 |  |  |  |  | 7
Total Open High or Critical Risks | 3 | 3 | 3 | 5 | 5 | 6 | 9 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 3 | 3 |  |  |  |  | 3
Risks: Missed Required Resolution Date | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks with no Required Resolution Date | 1 | 0 | 0 | 2 | 2 | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Risks open 1-3 months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 |  |  |  |  | 3
Risks open 3-6 months | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
Risks open longer than 6 months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Total Open Issues | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Total Open High or Critical Issues | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Issues: Missed Required Resolution Date | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Issues with no Required Resolution Date | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Issues open 1-3 months | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Issues open 3-6 months | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Issues open longer than 6 months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Total Assumptions not yet validated | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 |  |  |  |  | 1
Total Pending Decisions | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1

## Snapshot
| Risks: Past Required Resolution Date | Risks due in the next week | Risks with no required resolution date specified | Risks missing other information | Issues: Past Required Resolution Date | Issues due in the next week | Issues with no required resolution date specified | Issues missing other information | Assumptions not yet validated | Assumptions to be revalidated in light of BPOS decision | Pending Decisions | Decisions to be revalidated in light of BPOS decision
App & Data Migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 3 | 1
Change Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M&C Program | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 1 | 2 | 2 | 1
SharePoint | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 1 | 6 | 10 | 0 | 11
Technology Foundation | 0 | 0 | 4 | 5 | 3 | 1 | 0 | 0 | 2 | 0 | 15 | 23
Unified Communications | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 5

## Snapshot Detail
| Risk # | Missing Data | Owner | Issue # | Missing Data | Owner | Assumption # | Status | Decision # | Status | Missing Data
App and Data Migration | All A&DM risks fully updated. |  |  | I140 | Escalation level | Neil Sahev | All unvalidated A&DM assumptions are fully updated. No items to be revalidated. |  | D75A | To be revalidated in light of the BPOS decision
|  |  |  | I141 | Escalation level | Neil Sahdev
Change Management | All Change Management risks fully updated. |  |  | All Change Management issues fully updated. |  |  | No Change Management assumptions in log. |  | No pending decisions; closed decisions have been revalidated.
M&C Program | R86 | Contingency, Mitigation plans | Ted Balfour | I110 | All columns | Guy / Alan | A21, A27 | To be revalidated in light of the BPOS decision | D11 | To be revalidated in light of the BPOS decision
|  |  |  | I139 | Escalation level | Martin Kremmer
|  |  |  | I97 | Impact: Scope, Quality, Schedule, Cost | Michelle Edmonds
SharePoint | R117 | Contingency plan | Norm Beard | I96 | Planned Resolution, Escalation Level | Michelle Edmonds | See log: 37 items | To be validated; fill in forum/individual, due date and next review date | II items | To be revalidated in light of the BPOS decision
| R118 | Contingency plan, Mitigation plan, Trigger, Required Resolution Date | Michelle Edmonds |  |  |  | A22, A23, A24, A30, A31, A35, A36, A40, A41, A42 | To be revalidated in light of the BPOS decision | D76 | Pending | Due date
| R121 | Contingency plan, Mitigation plan | Mike/Ritesh
| R132 | Contingency Plan, Required Resolution Date, Next Review Date | Michelle Edmonds
| R120 | Contingency Plan | Michelle/Brett
Technology Foundation | R128 | All columns | Al Grljevic | All Tech Foundation issues have been fully updated. |  |  | All unvalidated Tech Foundation assumptions are fully updated. No items to be revalidated. |  | See log: 23 items | To be revalidated in light of the BPOS decision | In progress
| R129 | All columns | Al Grljevic
| R130 | All columns | Al Grljevic
| R131 | All columns | Al Grljevic
| R90 | Proximity, Risk Trigger, Response, Contingency Plan, Mitigation Plan, Escalation level, Req. Risk Resolution Date | Al / Jean-Michel
Unified Communications | R105 | Escalation Level | Rewa/Martin/Paul | All Unified Comms Issues have been fully updated. |  |  | All updated |  | D108, D50, D51, D52, D53 | To be revalidated in light of the BPOS decision
| R112 | Escalation Level | Rewa Bouji

## Cross Org Data
| Wk 31-Oct | 2012-01-25 | 2012-02-03 | 2012-02-10 | 2012-02-17 | 2012-02-24 | 2012-03-02 | 2012-03-09 | 2012-03-16 | 2012-03-23 | current
Decisions | 14 | 161 | 182 | 183 | 174 | 179 | 179 | 194 | 191 | 176 | 176
Critical Assumptions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Critical Risks | 15 | 14 | 14 | 16 | 16 | 21 | 28 | 16 | 16 | 15 | 15
Assumptions (Total) | 71 | 68 | 69 | 69 | 69 | 63 | 63 | 63 | 62 | 54 | 54
Issues (Total) | 30 | 45 | 48 | 52 | 43 | 49 | 51 | 53 | 42 | 37 | 37
Risks (Total) | 36 | 32 | 32 | 30 | 30 | 32 | 39 | 37 | 32 | 35 | 35