## Slide 1: IT Services ABCD Program IT Service Delivery Weekly report
19 March 2012

## Slide 2
2. Overall assessment of Program health
PMO Narrative
Schedule – Overall status AMBER Detailed MS Project schedules now all baselined with the exception of Business Deployment. Low confidence level in all plans has caused a “30 day get to green” plan to be constructed and driven by A. Guthrie. Draft re-baselined plans to be submitted to the PMO by 19th march. Full Re-baselined final plans which Work stream leads will be accountable for delivering against – 2nd April . Enterprise Planning team have taken new baseline plans, but as thought dependency alignment has reduced to 31%. Working with all streams to improve this over the coming weeks with a full review of dependencies being complete as of 2nd April.
Resource. AMBER status for App&Data only resourcing all others RED. Although detailed plans should have been available at start of March this has not been the case and without these it is not possible to clearly define resource requirements. This is what is driving the red statuses below. Awaiting new plan for SharePoint Foundation. Uncertainty around organizational structure and plans is limiting activity. Initial meeting held with Experimentus around environment management. We should have a clearer role description and framework for this area in a few weeks but need agreement between I&O and Cross Org about where these resources will come out of.
RAIDs. RAG status reflects the workstream’s progress with regards to the completion of cleaning up of their RAIDs (taking into account updated details and overdue items). RAID activity continues to progress with the advancement of the M&C Get to Green 30 day plan. Overdue items are steadily declining. Assumptions to be validated remain in need of review, as do both pending decisions and decisions to be revalidated. Weekly M&C Program RAID meetings are on hold for four weeks, as attention will be dedicated to the daily reviews instead.
Change Control. Lync Planning – Approved as a legacy change by CCB. ADM Ramp Down – Approved by CCB, Approved by Alan Guthrie and Bob Reiner Tech Foundation - Messaging Design O365D Impact – approved by Alan Guthrie and Bob Reiner Unified Comms - MMD – descope – CR rejected pending action from PM.
General . Program generally rated as RED budgeting has declined for 4 programs this week. MS Project schedules now all baselined except business deployment, new AMBER status for schedule. Program Planning still ongoing and POAP expected 5th of March. Resourcing RED due to Planning and changes in scope. M&C 30 day Get to Green exercise in progress and significant progress is being made. Weekly report review process now in place. (PMO)
 |  | RAG Trend |  |  |  |  | 
Program | This week | Last week | Week -2 | Week -3 | Week -4 | Week -5 | Week -6
SharePoint | RED | RED | RED | RED | RED | RED | RED
App & Data | RED | RED | RED | RED | RED | RED | RED
Change Management | RED | RED | AMBER | AMBER | AMBER | AMBER | AMBER
Tech Foundation | RED | RED | RED | RED | NO REPORT | AMBER | AMBER
Unified Communications | RED | AMBER | RED | RED | RED | RED | RED
IT Transition Management | AMBER | AMBER | AMBER | AMBER | AMBER | AMBER | AMBER
Business Deployment | TBC | TBC | TBC | TBC | TBC | TBC | TBC
Release Management | TBC | TBC | TBC | TBC | TBC | TBC | TBC
Weekly Ratings |  |  |  |  |  |  |  |  | 
 | Program Assessment (Per PM Tool) |  |  |  | PMO Assessment |  |  |  | 
Program | Overall | Scope | Time | Cost | RAID | Resource | Financial | Schedule | Vendor
SharePoint | RED | RED | RED | RED | RED | RED | RED | AMBER | TBC
App & Data | RED | AMBER | AMBER | AMBER | GREEN | AMBER | RED | AMBER | TBC
Change Management | RED | AMBER | AMBER | AMBER | GREEN | RED | RED | AMBER | TBC
Unified Communications | RED | AMBER | AMBER | AMBER | AMBER | RED | GREEN | AMBER | TBC
Tech Foundation | RED | AMBER | AMBER | AMBER | AMBER | RED | RED | AMBER | TBC
IT Transition Management | AMBER | AMBER | AMBER | AMBER | AMBER | GREEN | GREEN | AMBER | TBC
Business Deployment | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
TOM | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
Release Management | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
Overall | RED | RED | RED | RED | RED | RED | RED | TBC | TBC
Notes: Cost
GREEN - Estimate at Completion (EAC) = + 0 - 5% of approved spend (cost baseline + approved change requests)
AMBER - Estimate at Completion (EAC) = + 6 - 10% of approved spend (cost baseline + approved changes) and/or pending spend
RED – Estimate at Completion (EAC) exceeds + 10% or $100,000 of approved spend (cost baseline + approved changes) and/or pending spend or no project budget defined
Schedule
GREEN - The project schedule supports the end date of the project (with some elapsed time contingency).
AMBER - The project schedule supports the end date, but issues, risks and/or changes exist that may put the date in jeopardy.
RED – The project schedule does not exist and/or the project schedule does not support the end of the project.
Scope
GREEN - Scope defined and approved (scope baseline) with no pending change requests.
AMBER - Scope defined and approved (scope baseline) with pending change requests – known and not raised and raised but not agreed.
RED – Scope undefined or unapproved (no scope baseline) and/or multiple pending change requests.
Risk
GREEN – Low amount of risks with negligible impact
AMBER – Medium amount of risks. High or medium impact but with mitigation actions in place. Time left to put in place mitigation plans.
RED – High number of risks. High score risks which impact in the near term. No mitigation in place for High risks.
Issue
GREEN – No or low impact issues. Medium impact issues with resolution plans agreed and in place.
AMBER – Large amount of issues and/or Medium impact issues with no resolution plans.
RED – High impact issues present. No resolution plans in place for Medium of High level issues
Commercial
GREEN - TBD
AMBER - TBD
RED – TBD
Resource
GREEN – No resource issue or constraints
AMBER – Resource issues exist but plans are in place to resolve.
RED – Resource issues exist with no plans in place to resolve.

## Slide 3: Appendix A – ABCD Reports.

## Slide 4
B. KEY ACCOMPLISHMENTS THIS PERIOD
Benefits: (1) Continued development of the refreshed M&C Business Case, (2) Developed high level summary of potential Lync Benefits Comms: (1) First review of M&C refreshed comms strategy, (2) Decision on Epipheo voiceover artist, (3)
C. ACTIVITIES BEHIND SCHEDULE
Comms: (1) Progress visual design themes, (2) revised comms strategy and plan
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Comms: (1) Develop communications plan and strategy following 1st drafts, (2) Develop Epipheo animation story based on Comms feedback, (3) Start work on one-pager for stakeholders Outlook and Lync: (1) Complete Impact Assessment update, (2) Set up and run sessions with ‘approvers’ within L&O governance proposal to run through governance and confirm the right people have been identified
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
Comms: continuing to work on the creation and implementation of the comms strategy and to support the change management team. Learning : Learning lead for Lync & Outlook and Sharepoint not recruited, so limited activity beyond initial preparation, planning and learning inventory creation.
OVERALL INITIATIVE STATUS | 
Last Period | This Period
RED
AMBER
GREEN
COMPLETE
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
Messaging and Collaboration Business Change
MILESTONES |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Last Period | This Period
CHS/intranet site | 30 April | 30 April |  | 
Epipheo video/animation graphic | TBC | TBC |  | 
Identify Lync/Outlook Change network | 20/07/12 | 20/07/12 |  | 
Identify 'Lync & Outlook Community' volunteers/EAs | 12/10/12 | 12/10/12 |  | 
Sign-off Lync High Level Business Change Readiness Plan | 06/08/12 | 06/08/12 |  | 
Sign-off HL Impact assessment for Lync | 09/07/12 | 09/07/12 |  | 
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative | 
Risks to be addressed | Mitigating Action
Potential for rumours and mis-information on M&C based on not having communicated to wider audiences since initial announcement | Still considering ‘holding statement’ comms to global leadership teams, and Daily News Alert story
Recruitment of comms support on-hold | Marianela Venables supporting on intranet work. Potential for using GSS comms/design services.
Recruitment of required resources | Recruitment underway but decisions on which function these people will be recruited into are unanswered.
Alignment of M&C with GCL5.0 and DECC | Meetings established with Catherine Graham’s team (Learning) and investigation of enterprise plans (CM).
Any agreement to go to Cloud may have implications on the Change interventions if we have a different solutions for Cloud and on prem | Align with Technical teams to understand and close gap between the two solutions or identify different interventions required to address differences.
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes | 
Issues to be resolved | Recommended Action
Engagement with the Areas is well behind schedule which prevents direct preparation of a Change/ Deployment network and understanding of local impacts. | Initial calls taken place with AsiaPac and Americas Sophie and Martin have had discussions with Margaret Walsh for ITSD. And now we are working on a joint governance approach with DCC. EMEAIA rep identified.
Decision making in business for Lync and Outlook is unclear. FSG not engaged over L&O. L&O Governance required | Drafted L&O governance and reviewed with Jeremy Brown. A matrix of reviewers, approvers and escalation point has been prepared for functional areas and Areas.
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
All areas are now green due to re-planning exercise

## Slide 5
B. KEY ACCOMPLISHMENTS THIS PERIOD
Team workshop in Secaucus to focus on detailed plans and service design approach. Established weekly checkpoint call with Operational stakeholders. Began discussion with Microsoft with approach to design and O365 service integration Redefined the transition management planning approach and aligned with CLEAR.
C. ACTIVITIES BEHIND SCHEDULE
Recruitment of TM resources.
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Preparation for Microsoft meeting w/c 26 March Baseline service design plan Baseline service transition plan. Schedule Service Transition and Service Design workshop. Review RACI for Engaging formally with Operations leadership regarding formal engagement of I&O resources.
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes | 
Issues to be resolved | Recommended Action
The common SP infrastructure for the firm does not have clear business ownership therefore we need new governance that will be responsible long term for communication of emergency outages and planning for regular maintenance System will not meet expectations post go live as it may not be available (due to an emergency, without prior communication) and patches may not occur per the schedule causing instability | To be determined via new Support model needed to support Sharepoint
Scope Change requests to be approved | Recommended Action
None | 
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
Developing transition plans with each workstream based on current Transition methodology. Deployment of the dormant Lync client has reached full saturation. Deployment of the dormant Outlook client has started M&C Transition team developing the future Service Design and resulting program transition plan. Recruitment activities ongoing. Candidate identified, due to move on offer. Defining approach to ensure all transition and service design activity is aligned to CLEAR.
E. MILESTONES |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Last Period | This Period
IT Transition Plan for SharePoint | 1 Feb | 16 Mar | AMBER | AMBER
IT Transition Plan for Lync & Messaging | 1 Feb | 16 Mar | AMBER | AMBER
IT Transition Plan for Exchange | 1 Feb | 16 Mar | AMBER | AMBER
IT Transition Plan for A&DM | TBD | TBD | RED | RED
Overall M&C Transition Plan | 17 Feb | 16 Mar | AMBER | AMBER
OVERALL INITIATIVE STATUS | 
Last Period | This Period
AMBER | AMBER
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative | 
Risks to be addressed | Mitigating Action
There is a risk that revised project timelines may impact the timeline of TOM design. If we do this too early we may not get buy in and could potentially create rework later in the process. | Will need to revisit once all plans are baselined and following 30 day 'get to green' approach to assess if our current plan timeline remains valid.
The deployment approach for Outlook and SharePoint could significantly increased the cost associated with both internal and external support. | Will be validated via Service Design approach and better understanding of external support costs from external vendors for Cloud and On Premise.
Lack of Enterprise Standards for Disaster Recovery (DR) may affect quality of design deliverables | Review current DR strategy wth Ops and define next steps.
RED
AMBER
GREEN
COMPLETE
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
IT Transition Management – 16 March
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
The overall Amber assessment is due to current status of workstream delivery dates to baseline a transition plan. Red A&DM status due to the overall status of A&DM

## Slide 6
B. KEY ACCOMPLISHMENTS THIS PERIOD
Lync Submitted CR to refine MCS SOW down scope and ongoing resource requirements Messaging Functional Specification Change Request Impact Assessment now completed Sharepoint O365 Draft Discovery Documentation completed and uploaded and currently being reviewed by O365 Engineering team
C. ACTIVITIES BEHIND SCHEDULE
Lync Vendor RFP down selection, interim SOW and Cloud Topology decision remains outstanding and the work stream is still engaged with both vendors further refining the pricing and progressing the independence issue . Messaging Approval of re scoping CR026 is not complete and impacting resource allocation Decision on On Premise locations remains outstanding Network connectivity to O365 activity is being impacted by lack of dedicated resource and delivery dates are at risk Final Architecture for On Premise design not agreed and RTO RPO not aligned Sharepoint Change Request for current On Prem Functional Specification and methodolgy remains outstanding from MCS Replanning of SP environments is requested to improve on the iteration lifecycle Extranet requirement roadmap (EYD & Enablement phase 2) remains undefined but some progress is being made in line with the Blue Print activity stream
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Further refine GWAN engagement and deliverables Refine resource requests
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes | 
Issues to be resolved | Recommended Action
Critical resource issues in engineering, Architecture and Program | Requests in place but not being progressed
O365 Team are being impacted by EY lack of dedicated resource | 
CR generation and approval is slow and impacting SP and messaging | MCS are being advised daily
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
The team has made progress on a number of open items: O365 Messaging discovery documentation is being iterated by MCS engineering team
E. MILESTONES |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Last Period | This Period
Finalize In Country Locations | 17 Nov 2011 | 30 Mar 2012 | RED | RED
O365 Messaging Scope Lock | 2nd March | 9th March | Complete | Complete
O365 Sharepoint Scope Lock | 16th March | 26th March | RED | RED
Lync Vendor Selection | Jan 30th | April 6th | RED | RED
OVERALL INITIATIVE STATUS | 
Last Period | This Period
Amber | Red
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative | 
Risks to be addressed | Mitigating Action
Absence of any BA resource is impacting SP and Lync workstream | Resource requests in place
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
Project is RED due to work stream issues and O365 implications,
RED
AMBER
GREEN
COMPLETE
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
Technology Foundation March

## Slide 7
B. KEY ACCOMPLISHMENTS THIS PERIOD
Lync Devices: Evaluations are currently under review - Once the S&I approval has been granted Global Procurement will finalise the device list with Dell and Lenovo and arrange global resell channels.
C. ACTIVITIES BEHIND SCHEDULE
Deployment plan contingent on Business Deployment Strategy, DCC schedule and bandwidth analysis
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Publish Lync and Outlook governance model
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes | 
Issues to be resolved | Recommended Action
No forum for business validation and sign off of Lync and Outlook business requirements and configuration settings | Deadline for completion and sign-off for business requirements now at risk due to lack of identified SMEs who can provide/sign off reqs. Status is RED
Scope Change requests to be approved | Recommended Action
CR to be raised pending clarity on UC scope in relation to TF, Transition, Business Deployment | Await publication of Org Chart and Roles and Responsibilities, and publication of Bus. Deployment Strategy
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
Work is underway with Joe Grey and Black Knight to develop a governance model for review and approval of Unified Communications deliverables, including business requirements/configuration for Lync and Outlook, and Day 1 Plug in list. RB and JK will begin engaging proposed members of review/approval groups to determine whether they can act in this capacity. JB will publish proposed governance model for Lync and Outlook to FSG and Leadership as part of overall M&C Governance structure
E. MILESTONES |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Last Period | This Period
Migration Master DB Live | 11-MAY-12 | 01-JUN-12 | GREEN | AMBER
Migration Self-service Portal Live | 11-MAY-12 | 01-JUN-12 | N/A | AMBER
Lync Device Provisioning in place | 29-JUN-12 | 29-JUN-12 | AMBER | AMBER
Outlook & Lync Config reqs. | 20-APR-12 | 20-APR-12 | GREEN | RED
OVERALL INITIATIVE STATUS | 
Last Period | This Period
AMBER | RED
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative | 
Risks to be addressed | Mitigating Action
Network bandwidth impact on migration velocity and likely Lync performance will result in significant impact to current migration planning assumptions and end user experience | Meeting scheduled for 21/03 between UC, TF, Business Deployment, Transition and Operations Intake to agree migration approach
Risk that IAM will not deliver AD to UAT environments in time for UAT to start | Working with TF and QA on environment provisioning strategy and aligning with IAM to ensure AD delivery to the necessary timelines
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
Deployment strategy still unknown, and new M&C Transition Approach to be understood before further TM planning is possible. Engagement of business owners impacted by proposal to work through IT SDLs who have limited capacity to support the program
RED
AMBER
GREEN
COMPLETE
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
R19913 – Unified Communications – Ray Wilkinson

## Slide 8: AB&C TF Program Update by Workstream
19th March 2015

## Slide 9
B. KEY ACCOMPLISHMENTS THIS PERIOD
O365: Online Services Messaging discovery review complete Messaging: CR026 approved Identity: CR025 Approved Lync: SharePoint Enablement: POC assessment continues (DTU), Development continues (Search), People, Communities bug fixes SharePoint Foundations: CR for O365 retro fit being developed SharePoint ADM: Stalled
C. ACTIVITIES BEHIND SCHEDULE
O365 Scope lock after engineering review Signature on Deliverables
D. KEY ACTIVITIES PLANNED NEXT PERIOD
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes | 
Issues to be resolved | Recommended Action
Signature for DESIGN Deliverables for Lync, SPF and Messaging | Obtain executive signatures
Confirm approach for ADM | 
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
O365 Services All information has been submitted to engineering to drive towards scope lock. Roles & responsibilities were clarified and project is now moving forward at a good pace. Messaging: Change Request (CR0026) for O365 retrofit approved to the EY PjM and EY PMO on March 4. Still requires commercial execution Lync: CR to close out the project needs to be finalized Identity Management: Deliverable approval process running slow Budget Over Run SharePoint ADM Project postponed by EY ADM team until further notice. As per EY ADM, a new SOW is required. Estimated restart: August, 2012. SharePoint Foundation CR being developed to retrofit for O365, draft being delivered Monday 3/19 SharePoint Enablement
E. MILESTONES |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Last Period | This Period
O365 | 3/23/12 | 3/30/12 | RED | RED
Messaging Plan | 3/9/12 | TBD | AMBER | GREEN
Lync Plan | 3/18/12 | On Hold | AMBER | RED
SharePoint Foundation |  |  | AMBER | AMBER
Application Transformation | Feb 6th 2012 | On Hold | AMBER | 
SharePoint Enablement | 6/29/12 | TBD | RED | RED
Identity Management | 5/9/12 | 5/4/12 | AMBER | RED
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative | 
Risks to be addressed | Mitigating Action
Office 365 impacts across program | Jointly work to execute the appropriate changes to each work stream affected by this agreement.
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
EY Senior management has a strong desire to progress quickly but numerous activities are late, postponed, canceled or not started.
RED
AMBER
GREEN
COMPLETE
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
EY Messaging & Collaboration Program –March PMO
OVERALL INITIATIVE STATUS | 
Last Period | This Period
RED | RED