## Slide 1: M&C Weekly Reporting Template
May 2012

## Slide 2
C. ACTIVITIES BEHIND SCHEDULE
Late activity 1 : corrective action – DD Mmm YY Late activity 2 : corrective action– DD Mmm YY Activities/Tasks on the critical path which are delayed Include corrective actions and target date Link to challenges area.
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Planned activity 1 – DD Mmm YY Planned activity 2– DD Mmm YY Planned to complete Key Milestones Focus on what the sponsor would benefit from knowing Ensure that these are actual accomplishments and not ongoing activities
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes |  |  | 
Issues to be resolved | Recommended Action | Target Date | Completed By
Challenge / issue 1 (I# from RAID log) | Recommendation 1 | DD-MMM-YY | Named person
Challenge / issue 2 (I# from RAID log) | Recommendation 2 | DD-MMM-YY | Named person
Challenge / issue 3 (I# from RAID log) | Recommendation 3 | DD-MMM-YY | Named person
OVERALL INITIATIVE STATUS | 
Last Period | This Period
RED | RED
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative |  |  | 
Risks to be addressed | Mitigating Action | Target Date | Completed By
Key Risk 1 (R# from RAID log) | Relating Action 1 | DD-MMM-YY | Named person
Key Risk 2 (R# from RAID log) | Relating Action 2 | DD-MMM-YY | Named person
RED
AMBER
GREEN
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
INITATIVE NAME – Weekly status report – DD MMM YYYY
Project Sponsor name / Project Manager name
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
Workstream RAG status – plus comments is RED/AMBER FY12 Budget $ Current Budget (Baseline + Approved CRs) $ Spend to Date $ ETC $ Variances $
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
Executive Summary This is: High level and concise summary Ability to cover key successes and challenges High level Risks and Issues What does the Exec/sponsor need to know? What is of prime importance to them? 3-5 lines only, use bullet point to make reading easier Don’t use acronyms/abbreviations (if specific to project) Consistency with previous week – an issue raised in previous week must be commented on this week This is not: Summary of project/program scope
B. KEY ACCOMPLISHMENTS THIS PERIOD
Accomplishment 1 – DD Mmm YY Accomplishment 2– DD Mmm YY Accomplishment 3– DD Mmm YY Accomplishment 4– DD Mmm YY Completed Key Milestones. Resolved Risks, Issues and challenges Successes Focus on what the sponsor would benefit from knowing Ensure that these are actual accomplishments and not ongoing activities
E. MILESTONES |  |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Conf | Last Period | This Period
Milestone 1 | DD MMM YY | DD-MMM-YY | Estimate/Target/Committed | RED | RED
Milestone 2 | DD MMM YY | DD-MMM-YY | Estimate/Target/Committed | AMBER | AMBER
Milestone 3 | DD MMM YY | DD-MMM-YY | Estimate/Target/Committed | GREEN | GREEN
 |  |  |  | RED | RED
 |  |  |  | RED | RED
 |  |  |  | AMBER | AMBER

## Slide 3
Confidence rating guidelines
 | Rating | Description | Probability of occurrence* | 
1 | Estimate | Low confidence that milestone date will be met | Less than 50% | Very likely not to occur
2 | Target | Moderate confidence that milestone date will be met | Somewhere in the middle - between 51% and 79% | Good chance, but some doubt exists
3 | Committed | High confidence that milestone date will be met | 80% or higher | Very likely to occur

## Slide 4
M&C Milestones – Workstream Name – DD MMM YYYY
Project/Program Managers name
Cost RAG | 
RED | Estimate at Completion (EAC) exceeds + 10% or $100,000 of approved spend (budget + approved change requests) and/or pending spend or no project budget defined
AMBER | Estimate at Completion (EAC) = + 6 - 10% of approved spend (budget + approved change request) and/or pending spend
GREEN | Estimate at Completion (EAC) = + 0 - 5% of approved spend (budget + approved change requests)
I. BUDGET – ($) |  |  |  |  |  |  | GREEN
Business Case Budget | Project Charter Budget | PMP Budget (baseline) | Current Budget (Baseline + Approve CR’s) (1) | Spend to Date (2) | Estimate to Complete (ETC) (3) | Estimate at Complete (EAC) (2+3) | Variance (2+3) – (1)
J. IT SERVICES TRACKING MILESTONES |  |  |  |  |  |  |  | 
# | Individual Milestone Name | Planned Date | Projected Date | Actual Date | Last Period | This Period | Comments - must include reasoning for a Red or Amber indicator | Confidence rating (projected date)
M1a | Project launch date (START) |  |  |  | GREEN | GREEN |  | 
M1b | Project launch date (FINSH) |  |  |  | AMBER | AMBER |  | 
M2a | Project planning (START) |  |  |  | RED | RED |  | 
M2b | Project planning (FINSH) |  |  |  | AMBER | AMBER |  | 
M3a | Requirements (START) |  |  |  | AMBER | AMBER |  | 
M3b | Requirements (FINISH) |  |  |  | AMBER | AMBER |  | 
M4a | Architecture & Design (START) |  |  |  | AMBER | AMBER |  | 
M4b | Architecture & Design (FINISH) |  |  |  | AMBER | AMBER |  | 
M5a | Build (START) |  |  |  | AMBER | AMBER |  | 
M5b | Build (FINISH) |  |  |  | AMBER | AMBER |  | 
M6a | IT Testing (START) |  |  |  | AMBER | AMBER |  | 
M6b | IT Testing (FINISH) |  |  |  | AMBER | AMBER |  | 
M7a | UAT Testing (START) |  |  |  | AMBER | AMBER |  | 
M7b | UAT Testing (FINISH) |  |  |  | AMBER | AMBER |  | 
M8a | Deploy to production (START) |  |  |  | AMBER | AMBER |  | 
M8b | Deploy to production (FINISH) |  |  |  | AMBER | AMBER |  | 
M9a | Deploy to end-users (START) |  |  |  | AMBER | AMBER |  | 
M9b | Deploy to end-users (FINISH) |  |  |  | AMBER | AMBER |  | 
M10a | Project closure (START) |  |  |  | AMBER | AMBER |  | 
M10b | Project closure (FINISH) |  |  |  | AMBER | AMBER |  | 
Estimate = Rough date target based on high level plan, vision & scope document or charter. Assumed to only be accurate within a month , Planned = Date target based on a detailed planning activity involving all IT Services stakeholders.
Committed = Date target based on the verification of resource allocation and/or availability. Additionally, this level should be used when the PM is confident enough to share committed target dates with the sponsor., Actual = Date the milestone has been met