## Slide 1: Collaboration Beta Pilot Go / No Go (GNG)
28 November 2012
Notes: For information on applying this template onto existing presentations, refer to the notes on slide 2 of this presentation.
The Input area of the Beam can be customized to reflect the content of the presentation. The Input area is an AutoShape with a picture fill. To change this, ensure you have the image you wish to use (ideally a .jpg or a .png file) in an accessible folder. The image should have a ratio of 1:1 to ensure it does not appear distorted.
Acceptable images for importing into the Input area of the Beam are the three approved graphics (lines), and black and white photography or illustrations which follow the principles laid out on The Branding Zone. Color images should never be imported into this area.
To create a thank you slide with a picture in the Input area of the Beam, duplicate this master slide and create a new master slide. If using the graphic on the title slide the same should be used on the thank you slide. If using a picture in the Input area of the Beam in the title slide, the same or different but related picture can be used on the thank you slide.
Customize the Input area of the Beam as described below.
  Click on the View tab from the menu bar and select Master>Slide Master
  Right-click on the Input graphic and select Format AutoShape
  From the Fill menu, under the Color and Lines tab, click on the drop-down arrow next to Color and select the Fill Effects menu
  From the Picture tab, click on Select Picture. Navigate to the folder containing the image you wish to insert in the Input area. Highlight the image and tick the Lock picture aspect ratio box. Click on OK.
  You can now preview the image before continuing. If you are happy with how it looks, click Ok to continue. Otherwise, repeat the process until you are happy with your selected image
  To exit from Master View, click on View>Normal. The change you made to the Input graphic should now be visible on the title slide

## Slide 2: Timeline : Beta Pilot GNG Gate Process When does the material with supporting sign-offs need to be ready for review by governance bodies?
1.1 UAT Readiness
1.2 Solution Quality reports
1.3 Performance Testing dispensation
3.1 Deployment Readiness
6.1 Q&RM Solution Validation
6.2 Info Sec Solution Validation
1.1 UAT Completion Report/Sign Off
1.2 Solution Quality reports
2.1 Business Readiness assessment
2.2 ITS Support Org Readiness
3.1 Deployment Readiness
4.1 ELS Process/Tools Readiness
4.2 Technical Env Prod-readiness
5.1 Residual Program Risks
6.1 Q&RM Solution Validation
6.2 Info Sec Solution Validation
-Full GNG checklist review
-Outcome of Deployment Execution

## Slide 3: Beta Pilot Go / No Go Governance Timeline : We should be ready to take the completed material with recommendation to the Executive Sponsors Group scheduled Dec 4th
November
December
M&C GNG Forum
14th
FSG
1.1.1 UAT Readiness
1.2.1 Defect Reports
1.2.2 Test Reports
1.2.3 Workaround Log
1.3.1 Performance Test
Exception
Solution is Ready
Organisation is Ready
Ready to Deploy
Ready to Support
Operational Risk and Compliance
Exec Sponsors Group
Go / No Go Key Deliverables
Steering Group ‘Go/No Go’ Decision
Nov 12th
6.1 .1/6.2.1 Req Docs
6.2.2 DA Approval
6.2.3 Security Cert. Testing
3.1.1 Deployment Plans
3.1.2 Resources Ready
3.1.3 Hand-over to Service
Criteria
3.1.4 CVS Completion
28th
Nov 26th
18th
Dec 17th
1.1.1
1.2.1
1.2.2
1.2.3
2.1.1
2.1.2
2.2.1
2.2.2
3.1.1
3.1.2
3.1.3
3.1.4
4.1.1
4.2.1
5.1.1
5.1.1
3.1.1
3.1.2
3.1.3
3.1.4
4.1.1
4.2.1
2.1.1
2.1.2
2.2.1
2.2.2
Will also include outcome of deployment execution
29th
4th
6th
Alan G and Bob R make ‘GNG’ decision

## Slide 4: GNG Criteria: 1. The solution (system, process and data) is ready
Level 1 | Level 2 Criteria | External Quality Review & Approval before M&C GNG Program Forum and FSG Review | Decision Support Material (supplied by program leads) | RAG | Action Plan
1. The Solution (system, process and data) is ready | 1.1 The users have proven that the solution (system & data) meets the business requirements for Beta Pilot | Sign off of UAT to confirm business requirements have been met (Sherry Martin) | 1.1.1 UAT Completion Report, including execution and defect metrics, showing: Execution rates Number of defects found, fixed, open by criticality, root cause and workstream | Complete | - UAT Testing successfully conducted. Please see exit criteria and business recommendation of the next slides.

## Slide 5: GNG Criteria: 1.1 The users have proven that the solution (system & data) meets the business requirements for Beta Pilot
Exit Criteria: | Status
All UAT test cases successfully executed unless agreed by relevant stakeholders as not required | GREEN
No Critical (Severity 1) or High (Severity 2) severity defects or a significant concentration of medium issues outstanding unless agreed with relevant stakeholders | GRENN
Resolution/workaround of any outstanding defects agreed with all relevant parties along with clear plan of action and ownership | AMBER*
UAT test cases & test results uploaded to the ALM tool for future reference | GREEN
The approved UAT Test Summary Report is in place. | GREEN
*Details on Amber status:
  There is not yet an action plan in place or agreed for remediation of the defects raised during EAX UAT, therefore the status remains amber until this has been resolved.
UAT Exit status

## Slide 6: UAT closure Business recommendation
Based on the fact that 676 test cases have been completed with a pass rate of 95% it is recommended that we sign off UAT as successful.
The business has agreed to defer all open defects or has agreed to accept identified workarounds for the beta pilot. However, the expectation is that many of these will be resolved or may need to be reassessed as part of the R1 work.
The Beta Pilot teams will be informed about all open defects to ensure expectations are properly set as a part of their Beta Pilot orientation.
Link to closure issue log
Link to UAT closure report

## Slide 7: GNG Criteria: 1. The Solution (system, process and data) is ready
Level 1 | Level 2 Criteria | External Quality Review & Approval before M&C GNG Program Forum and FSG Review | Decision Support Material (supplied by program leads) | RAG | Action Plan
1. The Solution (system, process and data) is ready | 1.2.The solution quality level is agreed to be fit for purpose | Sign off of open defects and agreed business/operational workarounds (Sherry Martin/Shaun Bradley) Test coverage and test completion approval by Project Test Lead (Nigel Rawson) and Lead Application Architect (Oleksiy Volkov) | 1.2.1 Final Defect Report from All testing activities – number of defects found, resolved, open by criticality, root cause and workstream. 1.2.2 Test Reports: Evidence of test coverage achieved (traceability to requirements) and test completion 1.2.3 Agreed Workaround log showing impact on business and support process of residual system and process issues | Complete | 

## Slide 8: GNG Criteria: 1.2 The solution quality level is agreed to be fit for purpose
1.2.3: Open Issue List: 29 Defects
Status | Defect Id’s | No. of Defects
Deferral approved by business | 327, 356, 415, 416, 426, 432, 436, 443, 447, 448, 453, 452, 456, 463, 464, 467, 458, 469, 475, 478, 480, 481, 477, 471 | 24
Requirement change agreed by business | 449 | 1
Not in Scope for BP | 347 | 1
With IT | 454, 476, 479 | 3

## Slide 9: GNG Criteria: 1.2 The solution quality level is agreed to be fit for purpose
1.2.3: Open Issue List: 29 Defects
Defect Id | Summary | Workaround
415 | Search: Content Search_Field Search is not working on the some of the content properties 1. Created By | Rather than searching using Created By use Author
426 | Search: People Search is not showing any result while deselecting the selected refiner (Subs-service Line). | Execute the search again by clicking on the magnifying glass search button.
452 | Search: Last Modified Date (for Field and Full text) search is not retuning any result. | Use advanced search to search by date.
464 | Team Sites: Uploading media files without filling all the mandatory fields does not leave the file in a checked out status. | Correct the configuration setting during manual site provisioning process to ensure files are checked out.
463 | Team Site: Clicking on 'Calendar' heading, errors out to 404 - Page not found. | Specify the correct calendar URL during manual site provisioning process.
471 | People: Skills, School, Assistant, Manager and Office are shown on the View and Edit Profile pages when they should not be. | Implement post deployment steps to hide the fields via the O365 Customer portal.

## Slide 10: GNG Criteria: 1.2 The solution quality level is agreed to be fit for purpose
1.2.3: Open Issue List:
Defect Id | Summary | Business Exception or Workaround (where available)
449 | People: Global Personnel Number (GPN)’ field is not present on Edit Profile page. | Conflicting requirements were in place regarding the GPN field for People and Search. The following requirements which are in place for Beta Pilot have been agreed with the business (Greg Nemeth and Tammy Heck) : - People Profile View/Edit will not show the GPN - GPN will be set at access level ' Everyone' - GPN will be searchable.
347 | People: Profile photo is not synching from SharePoint to AD. | Confirmed by Delivery Lead (Nicola Cooper) that this functionality is not in scope for Beta Pilot.
454 | Search: PDF files shown incorrectly in search results and shows the webpage which contains the file instead of actual file. | This functionality which was working correctly in the System Test environment is currently not working correctly. However it is working successfully in the UAT environment an as such will be investigated with a low priority to establish the issue in the System Test environment.

## Slide 11: GNG Criteria: 1. The Solution (system, process and data) is ready
Level 1 | Level 2 Criteria | External Quality Review & Approval before M&C GNG Program Forum and FSG Review | Decision Support Material (supplied by program leads) | RAG | Action Plan
1. The Solution (system, process and data) is ready | 1.3. System Performance and resilience is sufficient for Beta Pilot target user groups | NFRs approved by business Enterprise Architecture sign off of technical test outputs | For Beta Pilot no Performance Testing planned 1.3.1 Approved Performance Testing dispensation confirmed | Complete | 

## Slide 12: GNG Criteria: 2. The Organisation (Business and ITS) is ready
Level 1 Criteria | Level 2 Criteria | External Quality Review & Approval before FSG and M&C IT Program Forum Review | Decision Support Material | RAG | Action Plan
2. The Organisation (Business and ITS) is ready | 2.1 Is the business ready to operate the solution | Business readiness assessment completed (Martin Kremmer) Validated learning content and channels (Martin Kremmer) | 2.1.1 Business readiness assessment outcome (or rationale for exclusion) 2.1.2 Learning content complete and eLearning portal operational | Amber (2.1.2) | Escalated to EYK learning lead to ensure focus on delivery. On target for final delivery on Dec 17. Review of draft Nov 28th

## Slide 13: GNG Criteria: 2.1 Is the business ready to operate the solution
2.1.1 Business readiness assessment outcome
Rationale for exclusion
  The learning enablers and the support readiness is considered the main part of declaring the business is ready. Furthermore each team site will be provisioned alongside an interview/preparation process that will ensure that each individual team is ready to adopt the new capabilities. This process will run in waves throughout January and early February and is independent of the overall GNG check for the Beta Pilot deployment.
2.1.2 Learning content complete and eLearning portal operational AMBER
  The learning enablers are planned to be ready as draft for review on November 26th
  The material is still under development and a review is scheduled for November 28th.
  The Learning team within EYK is still on target for finalizing the material for publishing on the product CHS when the Beta Pilot is launched on December 17th

## Slide 14: GNG Criteria: 2. The Organisation (Business and ITS) is ready
Level 1 Criteria | Level 2 Criteria | External Quality Review & Approval before FSG and M&C IT Program Forum Review | Decision Support Material | RAG | Action Plan
2. The Organisation (Business and ITS) is ready | 2.2 ITS Support staff are ready to operationally accept the solution and to provide appropriate operational support for the new system | Validated training completion records (Nick Coburn) | 2.2.1 Training Records to demonstrate trained Support user base | Green | Training completed for Service Desk team to enable incidents to be routed to Microsoft. No further SharePoint specific training needed for Beta Pilot as support will be via the program team with EAM as applicable (existing SharePoint team)
 |  | Operation Acceptance Test (OAT) completed (Nick Coburn) | 2.2.2 OAT Support Readiness checklist results | Amber | A number of OAT activities still need to be completed. Working to clarify those which are truly relevant to Beta Pilot. Also preparing a briefing pack to ensure all support stakeholders are aware of what is required during the pilot phase.

## Slide 15: GNG Criteria: 2.2 ITS Support staff are ready to operationally accept the solution and to provide appropriate operational support for the new system
Training of the various functions in I/O is not required for Beta Pilot as the program will be providing L4 support in conjunction with the L3 support provided by EAM and Digital Enablement providing the primary L1 support to the user community
As a number of support stakeholders need to be aware of our approach to support for Beta Pilot we are running a briefing session on 28th November with I/O leadership to set an expectation that we will not be completing a full handover to support until R1 go live
All support documentation needs to be completed 7 days prior to the CAB so this will be 6th December at the latest with CAB scheduled for 13th December.

## Slide 16: GNG Criteria: 3. We are ready to Deploy the solution (and revert if necessary)
Level 1 Criteria | Level 2 Criteria | External Quality Review & Approval before FSG and M&C IT Program Forum Review | Decision Support Material | RAG | Action Plan
3. We are ready to Deploy the solution (and revert if necessary) | 3.1. Deployment plan is in place, has been adequately rehearsed, communicated and tested; all parties are aware of their roles and responsibilities through the deployment process | Deployment Entry Criteria met Deployment plans in place (Cynthia Markland) Resources secured (Cynthia Markland) ‘Hand-over to Service’ Criteria agreed (Cynthia Markland and Nick Coburn) Service Ready declared by O365 Cloud team (Ann Roberts) CVS Completed (Cynthia Markland) | 3.1.1 Documented and participant-reviewed deployment plans 3.1.2 Deployment resources confirmed for participation in deployment process by team leads 3.1.3 Documented ‘Hand-over to Service’ criteria 3.1.4 Completion reports from CVS | Green | Review O365 deployment plan with team as scheduled 28 November. Update as indicated.

## Slide 17: GNG Criteria: 3.1. Deployment plan is in place, has been adequately rehearsed, communicated and tested; all parties are aware of their roles and responsibilities through the deployment process
Decision Support Material | Status | RAG | Action Plan
3.1.1 Documented and participant-reviewed deployment plans | Deployment schedule received from O365; deployment plan updated; meeting scheduled to review with team on 28 November. | Green | Review with team as scheduled on 28 November, update as appropriate, and socialize/post.
3.1.2 Deployment resources confirmed for participation in deployment process by team leads | O365 beta pilot deployment checklist has been reviewed and confirmed with all participating parties. Deployment resources are confirmed. | Green | Engineering and Operations have confirmed they will team for the deployment process and the Engineering and Operations leads have formulated their resources to be assigned
3.1.3 Documented ‘Hand-over to Service’ criteria | Handover to I&O for beta pilot is documented and being reviewed with cross-functional team. | Green | This action is still in process and being progressed with Operations, Engineering and Transition
3.1.4 Completion reports from CVS | CVS has been rescheduled to begin 27 November, following Service Ready, currently scheduled for completion 26 November midnight PST. | Green | CVS test plan is documented and agreed with CVS test team Kick off session held 26 November Test team is scheduled to begin testing immediately following SR CVS test is scheduled to complete by COB 28 November.

## Slide 18: GNG Criteria: 4. We are ready to Support the solution in Early Life
Level 1 Criteria | Level 2 Criteria | External Quality Review & Approval before FSG and M&C IT Program Forum Review | Decision Support Material | RAG | Action Plan
4. We are ready to Support the solution in Early Life | 4.1. ELS People, Processes and Tools in Place | Beta Pilot Support model & ELS approach signed off by I&O teams (Nick Coburn) | 4.1.1 Documented Beta Pilot Support Model | Amber | Need to complete final documentation suite as part of OAT requirements
Support model defined and agreed but some documentation remains outstanding and final sign off required
Need to confirm who will manage the defect and change process on behalf of the program

## Slide 19: GNG Criteria: 4. We are ready to Support the solution in Early Life
Level 1 Criteria | Level 2 Criteria | External Quality Review & Approval before FSG and M&C IT Program Forum Review | Decision Support Material | RAG | Action Plan
4. We are ready to Support the solution in Early Life | 4.2. Technical Environments are Production-Ready | For O365 Beta Pilot, there are no EY hosted on-premise Production environments to transition to I&O. The O365 hosted service support provides its own support. Nick Coburn is developing internal EY support model as part of 4.1 | 4.2.1 O365 ServiceReady is met by O365 team 4.2.1 Successful exit CVS testing with Cynthia’s team | Amber | O365 confirmed Service Ready complete CVS is in process, expected to complete COB 28 Nov Confirm with Nick that 4.1 is complete

## Slide 20: GNG Criteria: 5. Operational Risks are understood and mitigating actions taken
Level 1 Criteria | Level 2 Criteria | External Quality Review & Approval before FSG and M&C IT Program Forum Review | Decision Support Material | RAG | Action Plan
5. Operational Risks are understood and mitigating actions taken | 5.1 Residual Risks Understood and Accepted by business | Open risks reviewed have mitigating actions in place and approved by business (Bob Reiner/Sherry Martin) | 5.1.1 Key risks from programme risk log not closed prior to Beta Pilot deployment | - | - <Any remedial actions and due date>

## Slide 21: GNG Criteria: Deliverable Owners on Program
GNG Criteria (Level 1) | Decision Support Material (Deliverables) | Owner | Deliverable Link
Solution is Ready | 1.1.1 UAT Completion Report | Martin Kremmer | Closure report
 | 1.2.1 Final Defect Report | Nigel Rawson | Test Report
 | 1.2.2 Test Reports | Nigel Rawson | Test Report
 | 1.2.3 Agreed Workaround log | Martin Kremmer | Closure report
 | 1.3.1 Approved Performance Testing dispensation | Nigel Rawson | Request and Approval
Organisation is Ready | 2.1.1 Business readiness assessment outcome/exception | Martin Kremmer | N/A – see slide
 | 2.1.2 Learning content complete and eLearning portal operational | Maritn Kremmer | Content folder
 | 2.2.1 Training Records to demonstrate trained Support user base | Nick Coburn | N/A
 | 2.2.2 OAT Support Readiness checklist results | Nick Coburn | Operational Acceptance Criteria
Ready to Deploy | 3.1.1 Documented and participant-reviewed deployment plans 3.1.2 Deployment resources confirmed for participation in deployment process by team leads 3.1.3 Documented ‘Hand-over to Service’ criteria 3.1.4 Completion reports from CVS | Cynthia Markland | Deployment L3 Plan
Ready to Support | 4.1.1 Documented Beta Pilot Support Model | Nick Coburn | Support Model
 | 4.2.1 Confirmation from I&O production support environments handed over | Joshua Jackson | 
Operational Risks | 5.1.1 Key risks from programme risk log not closed prior to Beta Pilot deployment | Andy Ioannou | Risk 336, Risk 369, Issue 209
Compliance Requirements | 6.1.1/6.2.1 Requirements documentation | Nicola Cooper | Requirements
 | 6.2.2 DA Approval | Nicola Cooper | Design
 | 6.2.3 Security Certification Testing Exception | Nicola Cooper | Security Testing

## Slide 22: Questions

## Slide 23: GNG Criteria: 1.2 The solution quality level is agreed to be fit for purpose
1.2.1: Final Defect Report: All defects (excluding rejected (20)) by Severity & Workstream

## Slide 24: GNG Criteria: 1.2 The solution quality level is agreed to be fit for purpose
1.2.1: Final Defect Report: All defects (excluding rejected) by Root Cause.

## Slide 25: GNG Criteria: 1.2 The solution quality level is agreed to be fit for purpose
1.2.1: Final Defect Report: Total No. of defects found across System Test & UAT = 159

## Slide 26: GNG Criteria: 1.2 The solution quality level is agreed to be fit for purpose
1.2.2: Test Report: Beta Pilot System Test Completion Summary
The following system test pass rates were achieved during system test execution:
Test Cycle 1: Full Test Execution.
Test Cycle 2: Defect retest and high risk functionality tested.
Item | By Number | By Percentage
Total Tests Run | 394 | 100%
Tests Passed | 298 | 76%
Tests Failed | 95 | 24%
Item | By Number | By Percentage
Total Tests Run | 253 | 100%
Tests Passed | 240 | 95%
Tests Failed | 13 | 5%

## Slide 27: GNG Criteria: 6. We meet the necessary Info Sec and Q&RM Compliance requirements
Level 1 Criteria | Level 2 Criteria | External Quality Review & Approval before FSG and M&C IT Program Forum Review | Decision Support Material | RAG | Action Plan
6. We meet the necessary Info Sec and Q&RM Compliance requirements | 6.1 Q&RM policies and procedures have been adhered to in the solution design | Approval from Susan Chakerian | 6.1.1 Requirements documentation | Complete | - CR 106 Source Country retroactive application to BP TS content

## Slide 28: GNG Criteria: 6. We meet the necessary Info Sec and Q&RM Compliance requirements
Level 1 Criteria | Level 2 Criteria | External Quality Review & Approval before FSG and M&C IT Program Forum Review | Decision Support Material | RAG | Action Plan
6. We meet the necessary Info Sec and Q&RM Compliance requirements | 6.2. Information Security protocols have been adhered to in the solution design | Approval from Klara Neginsky | 6.2.1 Requirements documentation 6.2.2 DA Approval 6.2.3 Security Certification Test Exception | Complete | - Certification Test Exception confirmed, however minor security checks i.e. HTTPS Enabled