## Sheet2 (hidden)
Team Progress Report - Testing SIT/ UAT | Team Progress Report - Business Implementation : Training | Team Progress Report - Solution : People | Team Progress Report - Solution : S&A | Team Progress Report - Solution : HDC | Team Progress Report - Testing : PPR | Team Progress Report - Solution : MI | Team Progress Report - Solution : Payroll Functional | Team Progress Report - Data : Data | Team Progress Report - Solution : Integration | Team Progress Report - Business Implementation: Communications |  | Team Progress Report - Solution : Development
Gurminder Sahota/Mike Kettle | John McGann/Kevin Light | Adam Walden | John Morgan/James Venables | Ryan Fawcett | Mike Ritter/Paul Boocock | Olivier Acar/Stephen Hadley | Jim Chadwick & Andy McLauchlan | Malcolm Bunting/Kevin Middleton/ Peter McNiff | Martin Barrow/Simon Evans | Debbie Benson | Graham O'Neill, Chris Jaques | Surya Dagempude | Bill Robertson, Richard Cowtan
RED | GREEN | GREEN | RED | GREEN | GREEN | AMBER | AMBER | AMBER | RED | GREEN | GREEN | GREEN | GREEN
GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | AMBER
GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
RED | GREEN | GREEN | AMBER | GREEN | GREEN | AMBER | AMBER | AMBER | RED | GREEN | GREEN | GREEN | GREEN
RED | AMBER | GREEN | AMBER | GREEN | GREEN | AMBER | GREEN | RED | AMBER | AMBER | GREEN | GREEN | AMBER
GREEN | GREEN | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
GREEN | AMBER | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | AMBER

## Workstream Status Report
Team Progress Report - Environments
Team Lead: | Joshua Jackson
Period Ending: | 2012-09-07
Workstream Status | [8 empty] | This Period | Last Period
Overall Status | Good News O365 Simulated Cloud buildout has 2 of 3 major sub-milestones complete. 3rd sub-milestone is IAM/AD DC and domain buildout and is in progress. Staging#1 SP2010 Faux Cloud is in progress and SQL cluster buildout is in process Bad News Project is currently Amber due to O365 Simulated Cloud remaining with unknown delivery timeline for remaining 3rd milestone. | [7 empty] | AMBER | AMBER
Stakeholders | [8 empty] | GREEN | GREEN
Schedule | Architecture Per our meeting with Brett we will only be creating a SP2013 Extranet design for the architecture track. Environments Delays in trouble gaining traction (Risk 43) with all necessary steps to build out the prerequisite O365 Simulated Cloud infrastructure. Escalation meeting scheduled with Andy Greinar about DC VM delivery. Additional meeting setup with Afzaal about AD buildout and temporary support for new domains. | [7 empty] | AMBER | AMBER
Team | Team members out of the office for vacation or training Mitch is on vacation Aug 27-Sept 4 Len is on vacation Aug 29-Sept 4 Oleg is on vacation Aug 24-Sept 4 Joshua out for training Oct 9-11 | [7 empty] | GREEN | GREEN
Scope | Plan Updates L3 Engineering and Operations plans are pending additional detail from Scott and Dan. | [7 empty] | GREEN | GREEN
Key Achievements This Week | Architecture Architecture is on vacation and will return mid next week. Environments For O365 Simulated Cloud Prerequisite Infrastructure, submitted 7 of 10 known tickets. 6 are complete and 1 is in progress. Multiple meetings in progress to continue build out. Staging#1 SP2010. 8 of 8 CHG tickets submitted. 8 are complete and SharePoint server installs will begin next week. | [9 empty] | `
Key Activities next week | Architecture Version 3 - SP2013 Version 3 draft table of contents finalized and work in progress. Environments Staging#1 SP2010 CHG tickets submitted and infrastructure build out in progress O365 Simulated Cloud Prerequisite Infrastructure Additional meeting setup with Afzaal about AD buildout and temporary support for new domains. Follow-up on VMs for DC build out. Began custom configuration deployment for Falgun and Greg in preparation for UAT testing.
Progress Against Plan (those in progress / due to start in the next 6-8 weeks). Note: Activities should be derived from L2 while Deliverables from L3
Project Plan Ref. (Unique ID) | Milestone or Deliverable Name | Progress (%) | Baseline Start | Baseline Finish | Actual Start | Actual Finish | Activity/ Deliverable | RAG | Comments
696 | CIDE#3 SP2013 Preview Faux Cloud | 100% | 2012-07-10 08:00 | 2012-08-08 17:00 | 2012-07-06 | 2012-08-08 17:00 | Deliverable | COMPLETE | 3 of 3 CHG tickets complete
829 | LookSee#3 UA SP2013 Preview Faux Cloud | 100% | 2012-07-10 08:00 | 2012-08-08 17:00 | 2012-07-06 | 2012-08-08 17:00 | Deliverable | COMPLETE | 5 of 5 CHG tickets complete
90 | SP2010 Manual Installation Instructions | 100% | 2012-08-13 08:00 | 2012-08-31 17:00 | 2012-08-01 | 2012-08-15 | Activity | COMPLETE
9695 | Staging#1 SP2010 Faux Cloud | 70% | 2012-08-03 | 2012-09-03 | 2012-08-03 |  | Deliverable |  | Because of reprioritizing to complete the code deploymentfor Falgun, we will need to move this environment to Sep 24. First schedule move was because staff went to Ignite training we are pushing out to Sep 14. I have confirmed with Greg that EAX UAT needs this environment on Nov 1 .
1015 | Simulated Cloud Infrastructure DMZ in Frankfurt | 66% | 2012-06-11 08:00 | 2012-09-28 17:00 | 2012-06-11 08:00 |  |  | AMBER | See above and Risk 43 Milestones 1st - Network buildout (complete) 2nd - ESX Host Server buildout (complete) 3rd - IAM/AD DC and domain buildout (in progress)
683 | Engineering SP2013 Preview | 0% | 2012-07-10 08:00 | 2012-09-28 |  |  |  |  | This will be an ongoing effort to build out a few servers as needed by Dan's team. We used several of these servers to mitigate the more important CIDE#3 issue.
36 | SP2013 Architecture Updates | 0% | 2012-07-02 08:00 | 2012-10-17 | 2012-07-31 |  |  | GREEN | Started late due to extra reviews and work on finalizing Version2 for Brett. The scope of these architecture documents is being changed per Brett's request. We believe we are still ok from a timing perspective but will need to asses the impact based on the item below.
28 | Extranet Design | 0% | 2012-08-01 | 2012-10-26 |  |  |  | GREEN | Brett had provided direction that we should only create a SP2013 "reference architecture" to hold up as a model for external groups. We are incorporating this into our plans and will reprioritize accordingly.
89 | SP2013 Scripted Installation | 0% | 2012-07-02 08:00 | 2012-12-28 17:00 |  |  |  |  | Preliminary work is in progress
External Dependencies
Task UID (in MSP) | Dependency Name |  | RAG Status | Entity | Owner |  | Due Date | Actions
Issues
RAID ID | Issue Title |  | Involved | Next Review | Assigned To | Impact | Affected | Actions
Risks
RAID ID | Risk Title |  | Probability | Priority | Assigned To | Impact | Affected | Actions
43 | Have potential impact to CIDE, DIDE, QA, etc. timelines due to environment availability |  | 3) High | 9 | Joshua Jackson | 3) High | Schedule Quality | Andy has escalated to Nick Wood. Nick has identified several individuals that I can meet with to review the infrastructure proposals and review known plans to date. Escalating with Shaun Bradley & Gil Levit for additional EY Infrastructure provisioning process and coordination.
161 | No Disaster Recovery solution for On-prem SharePoint. |  | 0) Under review | 0 | Joshua Jackson | 0) Under review