## Sheet2 (hidden)
Team Progress Report - Testing SIT/ UAT | Team Progress Report - Business Implementation : Training | Team Progress Report - Solution : People | Team Progress Report - Solution : S&A | Team Progress Report - Solution : HDC | Team Progress Report - Testing : PPR | Team Progress Report - Solution : MI | Team Progress Report - Solution : Payroll Functional | Team Progress Report - Data : Data | Team Progress Report - Solution : Integration | Team Progress Report - Business Implementation: Communications |  | Team Progress Report - Solution : Development
Gurminder Sahota/Mike Kettle | John McGann/Kevin Light | Adam Walden | John Morgan/James Venables | Ryan Fawcett | Mike Ritter/Paul Boocock | Olivier Acar/Stephen Hadley | Jim Chadwick & Andy McLauchlan | Malcolm Bunting/Kevin Middleton/ Peter McNiff | Martin Barrow/Simon Evans | Debbie Benson | Graham O'Neill, Chris Jaques | Surya Dagempude | Bill Robertson, Richard Cowtan
RED | GREEN | GREEN | RED | GREEN | GREEN | AMBER | AMBER | AMBER | RED | GREEN | GREEN | GREEN | GREEN
GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | AMBER
GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
RED | GREEN | GREEN | AMBER | GREEN | GREEN | AMBER | AMBER | AMBER | RED | GREEN | GREEN | GREEN | GREEN
RED | AMBER | GREEN | AMBER | GREEN | GREEN | AMBER | GREEN | RED | AMBER | AMBER | GREEN | GREEN | AMBER
GREEN | GREEN | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
GREEN | AMBER | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | AMBER

## Sheet1
ID | Title | Assigned To | Impact | Affected | Update Log | Item Type | Path
37 | Need for new governance responsible for communications (maintenance, outages) | Nick Coburn | 1) Low | Scope;#Schedule;#Quality;#Cost | 27-Jun:Reassigned to Nick Coburn | Item | msibm/Lists/RAID Issues TEST
41 | Unclear on specifications provided for site decomissioning in O365 | Oleksiy Volkov | 2) Medium |  | 27-Jun: (OV) BAs and architects reviewed site deprovisioning options available in Office 365/Sharpeoint 2010. Several concerns were raised : 1) The default out of the box tracking (based on number of days since site creation) is insufficient as it does not reflect is anybody has used the site 2) The default out of the box notification mechanism (emailing site owner group) was deemed insufficient to handle cases when both owners leave the company 3) The default decomissioning actions (outright site deletion) did not have any provisions for "soft-delete", archival, etc. It appears that the full implementations of the concerns above will require a substantial custom development and/or hydbrid decomissioning approach with portions handled by human workflow (operations staff). We may be able to leverage OOB functionality for EAX/OOB to provide "skeleton" implementation; BAs to take back the discussion items and come back with a suggested blueprint of requirements. Will revisit in two weeks (7/11). Follow up session in two weeks | Item | msibm/Lists/RAID Issues TEST
43 | Data/content retention policy for people who leave the firm has not been defined | Steven Jelf | 2) Medium | Scope;#Schedule;#Quality;#Cost | 20-Jun - Please see Decision D141. 30 days after a user leaves the firm has been decided, with the exception of litigation hold cases. Please see D141 for further details. Key answer outstanding from Q&RM is that should this data remain visibile during this time - Response expected by 26th June. 19-Jun : After update in the weekly Collaboration Meeting this item was associated with Steven Jelf, Nicola Cooper to follow up with Steve and ensure this has been assigned correctly 12-Jun (LM) Per Michelle, updated Assigned to to Nicola Cooper. 03-May: M&C Q&RM decision request form sent to Steve Jelf, for disposition. 26-Apr: Logged issue​ | Item | msibm/Lists/RAID Issues TEST
45 | Search filtering will not work as specified due to GHRDB terms not being aligned and other SharePoint solutions will also not work | Nicola Cooper | 3) High | Scope;#Schedule;#Quality;#Cost | 26 Jun: NC First Draft of Data to populate TermStore will be provided to IT from Business Team Friday 27th June, they have confirmed they are working with GHRDB and AD to ensure alignment. After assessment of this dataset Collaboration will confirm if there is an issue in this space. 17 Jun: Reassigned to Nicola Cooper as the Requrements and Design Lead progressing both MetaData Management and People. Latest Status alignment with Ann scheduled for 19th Jun, update will follow... 14-Jun: Greg V met with Ann Wagner, Greg Nemeth, MaryGael Timberlake. Indication is that they would like GHRDB descriptions to be translated to "SharePoint metadata" descriptions at the time they are pulled and stored into AD. (This solution would require several fairly significant things to happen -- e.g., 1. EA endorsement of approach, 2. technical work on GHRDB view [e.g., Oliver Berchtold et al], 3. possible change to ID Sync view access [IF SO THIS WOULD REQUIRE A CHANGE REQUEST TO THE ID SYNC PROJECT, AND THEY ARE ALREADY WELL ON THEIR WAY TO COMPLETING THEIR PORTION OF THE AD UPDATE SO TIME IS OF THE ESSENCE SHOULD IDSYNC IS AFFECTED], 4. On-going management and maintenance of a "GHRDB to SharePoint metadata" translation table to be used. The "best" solution for SharePoint project would be to use the same terms; therefore no translation would be required, but there may be valid reasons outside of SharePoint why this would not work. 4-Jun: Provided Ann Wagner (at MaryGael Timberlake's request) terms in GHRDB that have a corresponding term set within the SharePoint term store. Ann can then compare these terms with the ones she and Cindy Hope have developed and sort out any differences with the People team. Once this comparison is completed, they can schedule a follow up meeting with the People team (target week of 8-Jun) on any term reconciliation. (Updated workstream to "SharePoint" as it's not clear yet that IAM involvement will be required to do translations, and changed resolution definition due date to 29-Jun.) 16-May: The option(s) outlined require transforming data coming from current definitive source (GHRDB/GHRS). Is this transformation in line with our strategic direction? This question needs answered -- question was addressed to Adam Hintz, Cindy Hope, Ed Dale, Greg Nemeth, MaryGael Timberlake, Oliver Berchtold, Rob Taub, Sandra Dillon with confirmation requested by 21-May. The solutions outlined affect scope and approach in IAM / ID Sync project, which obviously is already well underway. Greg to set up call with Oliver Berchtold on approach/feasibility for option B. 07-May: Meeting conducted, participants to address issue identified, follow-up meeting scheduled to review attributes involved in the issue, discuss potential solutions/feasibility and potential downstream impacts. 03-May: Meeting scheduled for 7-May to ensure awareness on the topic, then agree on direction, and next steps to address; added 5th option into resolution column on this log 27-Apr: item logged. Greg to organize meeting of stakeholders to set direction.​ | Item | msibm/Lists/RAID Issues TEST
47 | UAT approach/environment need rework given SP dependency on AD and IAM/ID Sync | Norman Beard | 3) High | Scope;#Schedule;#Quality;#Cost | 27-Jun: Reassigned to Norm Beard. If ID Sync project completed on schedule, this is not an issue for Collaboration. IAM Team believes schedule at risk. 1-Jun: (GJV) updated to a new more appropriate date (29-Jun), agreed in Ted Balfour's 30-May weekly call M&C - IAM Sync call. 9-May: Norm - need IAM changes populated (fields). This is part of dependency alignment. Required by date of 30-May still accurate. 3-May; item logged​ | Item | msibm/Lists/RAID Issues TEST
48 | O365 should have test machines | Binoy Raj | 3) High | Schedule | 19-Jun: resource and technical constraints limiting ability to close issue 11-May : Manesh mani (Infra PM) had a discussion with Serevr Ops, Server Eng and InfoSec teams to identify the person responsible for the N/W designs. No resolution yet 15-May : Contacted Steve Yoemans for resolution. meetings planned for the day​ | Item | msibm/Lists/RAID Issues TEST
51 | Need formalized process for people interested in assessing, requesting, demo'ing SP | Andy Ioannou | 2) Medium | Schedule;#Quality | 20-Jun: Working with Program Execution Services team (Rachel Phillips) to build consistent mechanism for sharing information on Collaboration project, including requests for demos. 19-Jun: The first steps to providing the E&Y business teams with the opportunity to review the SharePoint offering for Release 1 have been taken, by providing demo sites. This Issue needs to be reviewed by Andy Ioannou for its validity now. ​16-May: Kerri requested Laura add this issue to the log. Laura sent her item # for further update. 16-May: Kerri updated status, affected, impact | Item | msibm/Lists/RAID Issues TEST
57 | Have not determined SharePoint 15 direction & plan | Andy Ioannou | 3) High | Scope;#Schedule;#Quality;#Cost | 27-Jun (LM): On RAID call, update provided that this is close to being resolved as the first version of the scope has been shared out. 21-Jun: CR reviewed and decision taken to defer approval to 28-Jun, allowing more time for impact assessment with Messaging stream (Lync/AD integration points). 20-Jun: Change request submitted; ready for CCB on 21-Jun.​ 19-Jun:Change request to be written by Andy 21-May: Andy Ioannou met with Jeremy Brown on 17-May and presented an overview of the SP15 re-plan as it currently stands. Jeremy has suggested it'll take at least 2-3 weeks to 'socialise' proposal and iterate with BPOs before we can expect a decision. Andy will be alerting Alan of our impending intentions and the need to execute from next week on our proposed resource/activity recommendations. | Item | msibm/Lists/RAID Issues TEST
58 | Currently no Metadata Model is agreed to inform requirements | Nicola Cooper | 0) Under review | Scope;#Schedule;#Quality;#Cost | 29 Jun (NC) Metadata fields agreed by audience of the MetaData/Content Types call today, formal confirmation by email now sought and expected to be validate after US Vacation period 9th July. (Audience : Ann Wagner, MaryGael Timberlake, Stephanie Lakser, Hasan nazir, Lee eichleberger, Yi Wen Lui) 25 Jun: NC The Taxonomy first draft will be submitted by the business on Friday 29th June, content types are also being discussed on Friday 29th. 17 Jun: Reassigned to Nicola Cooper as the Requrements and Design Lead. Latest Status : Alignment with Key Business Stakeholder (Ann Wagner) scheduled for 19th Jun, update will follow... ​21 May: issue logged | Item | msibm/Lists/RAID Issues TEST
71 | Tier 4 level support is not defined | Michael Laci | 0) Under review |  | 19-Jun: ​Mike to follow up with Nick. | Item | msibm/Lists/RAID Issues TEST
81 | External Environment may not be ready for go-live of GAAIT | Michelle Edmonds | 1) Low | Scope;#Schedule;#Quality;#Cost | 27-Jun: GAAIT has requested to purchase Ovitas, 3 month delay in purchase to have our Content Management team look at Ovitas to see if it can be used for everything 08-Jun: Created this issue from closed risk 40 | Item | msibm/Lists/RAID Issues TEST
87 | SP15 Dependency on GCL5 Program | Andy Ioannou | 3) High | Scope;#Schedule;#Quality;#Cost |  | Item | msibm/Lists/RAID Issues TEST
90 | The business wants more functionality than what was in plan for R1 | Nicola Cooper | 0) Under review |  | 21-Jun: this is not an issue as we are baselining our plans for Release 1. What we need to provide Bob is a view of business impact of the reduced functionality - the 'so what?'. To enable, the prototyping approach to scope lock will drive our the use cases that model the 'day in the life' user scenario, assets that will quickly highlight solution gaps against business process.​ This gap analysis will inform the business impact of reduced functionality. This has already been communicated to Bob. Nicola, suggest you close once this action plan is embedded in the Requirements and Design L3 plans. 20-Jun: Andy speaking to Bob on how to carry forward. 12-Jun: Andy is working with IT Leadership and Business. | Item | msibm/Lists/RAID Issues TEST
92 | We don't know how to get the photo into AD. We need to understand the official source of the Photo Upload | Norm Lambert | 0) Under review |  | 18-Jun: Upload to SharePoint supported, not supported back to AD 12-Jun: still WIP | Item | msibm/Lists/RAID Issues TEST

## Sheet3
ID | Title | Probability | Priority | Assigned To | Impact | Affected | Update Log | Item Type | Path
43 | Have potential impact to CIDE, DIDE, QA, etc. timelines due to environment availability | 3) High | 9 | Norman Beard | 3) High | Schedule;#Quality | 27-June: In IE review. Passed DA review 19-Jun:IE review tomorrow. 12-Jun: Still gathering details required by InfoSec in order to complete infrastrcture proposal. Determining effort / timeline for creating the simulated cloud env is dependent upon completing this design.25-May: An underutilized firewall has been identified in Frankfurt which could be used till staging DMZ is ready. Infosec and Protection Services Group has no objection in using it. A detailed plan is being developed [Updated by Manesh] 16-May: Working to get workaround vetted through Information Security (needed before approvals can begin). 9-May: Separate project initiated to create appl DMZ infrastructure at Frankfurt GDC. Target completion of that project is Jan 2013. This may be a dependency before creating QA & UAT simulated cloud envs​ 04-Apr-2012: Risk logged | Item | msibm/Lists/Program Risks TEST
44 | Potentially not enough budget in FY13 to cover license costs if estimates are above what is expected. | 2) Medium | 4 | Norman Beard | 2) Medium | Quality;#Cost | 27-Jun: Norm, am not clear on what is being escalated here. From the minimal info in this risk I infer that we need more licenses than planned because of greater than expected infra reuirements? If so, how many licenses purchased so far and what is shortfall in cost? What action do you need me to take? 19-Jun: Reassigned to Andy 19 Mar - Risk will be reassessed as content is entered 7 Feb: Created this Risk. 17 April: Current license count appears to be sufficient for go live; including additional licenses in FY13 budget​ | Item | msibm/Lists/Program Risks TEST
132 | A person may have multiple Sharepoint profiles assigned to them | 3) High | 6 | Brett van Gelder | 2) Medium | Quality | 27-Jun: Need statement from Brett van Gelder on whether this risk is acceptable to Collaboration | Item | msibm/Lists/Program Risks TEST
138 | External Program Demands on M&C Resources | 3) High | 9 | Andy Ioannou | 3) High | Schedule | 27-Jun: Escalated to Andy and David Bingham last week. ​ | Item | msibm/Lists/Program Risks TEST
139 | SP15 Key Delivery Dates | 2) Medium | 6 | Dave Fraser | 3) High | Schedule;#Cost |  | Item | msibm/Lists/Program Risks TEST
146 | Full Search capabilities may not be realized, also may not be able to search from on-prem to cloud (hybrid). | 0) Under review | 0 | Norm Lambert | 0) Under review |  | 15-Jun: The Team will assess Search capabilities with SP15 once we receive the SP15 beta version.​ | Item | msibm/Lists/Program Risks TEST
147 | With change in direction the potential to lose good FAST Search resources could impact delivery | 0) Under review | 0 | Michael Cliffel | 0) Under review |  |  | Item | msibm/Lists/Program Risks TEST
149 | By starting SP15 production environment before the new RTM installation bits are verified in QA/UA poses the risk that some configuration issues may be identified first in Production. | 0) Under review | 0 | Norman Beard | 0) Under review |  | 27-Jun: Norm, can you look into this and clarify what the risk is (not clear to me), impact and proposed mitigating action plan? If you need me to intervene/escalate, I need to know ​what action you expect me to take. | Item | msibm/Lists/Program Risks TEST
150 | With the SDET project running in parallel, key EY engineer and architecture resources being overallocated. | 0) Under review | 0 | Dan Mulligan | 0) Under review |  |  | Item | msibm/Lists/Program Risks TEST
152 | O365 piloting EY ONLY hybrid features, risk of delay | 0) Under review | 0 | Norm Lambert | 0) Under review |  |  | Item | msibm/Lists/Program Risks TEST
153 | No manual process in place to support manual site provisioning (SP2010). | 3) High | 6 | Gregory Van Valkenburgh | 2) Medium | Scope;#Schedule;#Quality;#Cost | ​27-Jun:Only applicable to EAX, not yet approved. 27-Jun: Activites added to L2 plan for defining and establishing manual process. Initial meeting with Scott Strange conducted as to the who/and how for doing this -- e.g., a portion of it may be logging a request into Service Now with an attached pre-defined form that provides the necessary details to execute on the request. | Item | msibm/Lists/Program Risks TEST
154 | Each developer may have a slightly different flavor of DEV VM | 0) Under review | 0 | Falgun Shah | 0) Under review |  | 18-Jun: will make sure devs have consistent VM's​ | Item | msibm/Lists/Program Risks TEST
155 | EY will not be able to performance test the cloud | 0) Under review | 0 | Norm Lambert | 0) Under review |  | 19-Jun: Site provisioning in hybrid environment all that could be done, recommendation to go to MS labs with limited scope​ | Item | msibm/Lists/Program Risks TEST
157 | GAAIT project running in parallel, key EY engineer and architecture resources being overallocated | 0) Under review | 0 | Dan Mulligan | 0) Under review | Schedule;#Cost |  | Item | msibm/Lists/Program Risks TEST
158 | FAS&T project running in parallel, key EY engineer and architecture resources being overallocated | 0) Under review | 0 | Dan Mulligan | 0) Under review | Schedule;#Cost |  | Item | msibm/Lists/Program Risks TEST
159 | Due to lack of governance in the Cloud SP 10 space there are upgrade implications | 0) Under review | 0 | Norman Beard | 0) Under review |  | AI 27-Jun: Norm, can you shed light on source of this risk and provide more detail - impact, mitigation and any escalation, if any?​ | Item | msibm/Lists/Program Risks TEST
160 | Infosec may not accept our connectivity requirements for synchronising MMS from On Prem to the Cloud | 0) Under review | 0 | Oleksiy Volkov | 0) Under review |  | 27-Jun: Had discussion with Klara yesterday.​ Scheduling another meeting with Klara/Norm L to discuss options | Item | msibm/Lists/Program Risks TEST
161 | No Disaster Recovery solution for On-prem SharePoint. | 0) Under review | 0 | Norman Beard | 0) Under review |  | 27-Jun:Re-assigned to Norm Beard. Known issue, no easy obvious solution. 25-Jun: Michael Fry PM for DR portion of the DCC Project ​ | Item | msibm/Lists/Program Risks TEST
164 | Currently unknown whether the Search Service is supported on Premises | 0) Under review | 0 | Norm Lambert | 0) Under review |  |  | Item | msibm/Lists/Program Risks TEST

## Workstream Status Report
Team Progress Report - O365
Team Lead: | Manesh Mani
Period Ending: | 2012-09-14
Workstream Status | [8 empty] | This Period | Last Period
Overall Status | Decided to build GCL5 in the EY.net root domain. | [7 empty] | AMBER | AMBER
Stakeholders | With reference to Issue # 71, owners of the proposed environment have to be finalized. Test Accounts are not ready. | [7 empty] | AMBER | AMBER
Schedule | Trying to meet the schedule for GCL5. | [7 empty] | AMBER | RED
Team | [8 empty] | GREEN | AMBER
Scope | [8 empty] | GREEN | GREEN
Key Achievements This Week | 1.2.6.2 : SP Test Machines Provisioning Met different stakeholders and made decision to host GCL VMs in EY.net domain instead of DE.EURW.EY.net domain. | [9 empty] | `
Key Activities next week | 1.2.6.2 : SP Test Machines Provisioning Complete the deployment of GCL5 VM's Complete the SEP configuration.
Progress Against Plan (those in progress / due to start in the next 6-8 weeks). Note: Activities should be derived from L2 while Deliverables from L3
Project Plan Ref. | Milestone or Deliverable Name | Progress (%) | Baseline Start | Baseline Finish | Actual Start | Actual Finish | Activity/ Deliverable | RAG | Comments
1.2.6.1 . | SP Test Accts Provisioning | 50% | 2012-05-07 | 2012-10-01 | 2012-05-01 |  |  | AMBER | Test accounts is not yet ready. Being handled by David Shapiro and Anthony Harper.
1.2.6.2 | SP Test Machines Provisioning | 50% | 2012-05-07 | 2012-10-01 | 2012-05-01 |  |  | AMBER
| Make GCL5 template | 100% | 2012-08-07 | 2012-08-09 | 2012-08-07 | 2012-08-08 |  | COMPLETE | GCL5 template is made by Stephane Maarek
| Make GCL4 template | 100% | 2012-08-07 | 2012-08-09 | 2012-08-07 | 2012-08-09 |  | COMPLETE | GCL4 template is made in GSS Kerala
| Transfer GCL4 template to Frankfurt | 100% | 2012-08-09 | 2012-08-10 | 2012-08-09 | 2012-08-10 |  | COMPLETE
| Transfer GCL5 template to Frankfurt | 100% | 2012-08-09 | 2012-08-10 | 2012-08-08 | 2012-08-09 |  | COMPLETE
| Test Deployment of GCL 4 & 5 VMs | 100% | 2012-08-10 | 2012-08-17 | 2012-08-09 |  |  | COMPLETE | Test deployment had errors so desktop engineering team suggested to make individual machines in Inida, get it verified, and transfer to Frankfurt.
| Build GCL4 | 25% | 2012-08-22 | 2012-09-08 | 2012-08-21 | 2012-09-11 |  | COMPLETE | All GCL4 VMs were made and transferred to Frankfurt.
| Build GCL5 | 0% | 2012-08-20 | 2012-09-14 | 2012-09-14 |  |  | GREEN | Decided to have GCL5 in the EY.net root domain. Started the build process.
| Apply SEP configuration | 0% | 2012-08-27 | 2012-09-19 | 2012-08-27 |  |  | GREEN | Initiated planning. Kevin Topps is assigned to the activity.
| Internal Testing of the environment | 0% | 2012-09-17 | 2012-09-21 |  |  |  | GREEN
| External testing of the environment | 0% | 2012-09-24 | 2012-09-28 |  |  |  | GREEN | Temporary VPN is getting ready.
1.2.6.4.32 | Internal DNS for the SP URLs. | 100% | 2012-04-09 | 2012-08-01 | 2012-05-01 | 2012-07-24 |  | COMPLETE | Arun C has executed the activity
1.2.6.4.33 | End User browser local intranet sites. | 100% | 2012-04-09 | 2012-10-01 | 2012-05-01 |  |  | COMPLETE | The system is already updated with the specified intranet sites.
1.2.6.4.35 | Entrust certificate authority root SSL certificate on desktops. | 100% | 2012-04-09 | 2012-10-01 | 2012-05-01 |  |  | COMPLETE
1.2.6.4.41 | Security groups | 60% | 2012-06-04 | 2012-10-01 | 2012-06-04 |  |  | GREEN | Executed by Anthony Harper .
1.2.6.4.44 | Access control list. | 50% | 2012-04-09 | 2012-10-01 | 2012-05-01 |  |  | GREEN | Being handled by David Kozinn.
1.2.6.4.45 | Client software requirments. | 90% | 2012-03-23 | 2012-10-01 | 2012-05-01 |  |  | GREEN | All normal requirements have been applied. Could be marked complete only after the extermal testing of the environment is complete
External Dependencies | 5
Task UID (in MSP) | Dependency Name |  | RAG Status | Entity | Owner |  | Due Date | Actions
Issues
RAID ID | Issue Title |  | Involved | Next Review | Assigned To | Impact | Affected | Actions
48 | O365 should have test machines |  |  | 2012-03-07 | Andy Ioannou | High | Schedule | Andy to align with Rewa and discuss any. collaboration team have escalated already to Paul Naeve and the O365 team without success.
71 | Tier 4 level support is not defined, O365 VM Build and Test Blocked |  | Paul Neave | 2012-10-06 | Paul Neave | High | Schedule
Risks
RAID ID | Risk Title |  | Probablilty | Priority | Assigned To | Impact | Affected | Actions
282 | GCL5 Policies are available only in EY.net and EYUA J47 No immediate plans for other Infosec team confirmed there is no technical issue • The issue is purely operational • Decision has to be taken by Desktop operations team -- |  | High | High | Joshua Jackson | High | Schedule | Decided to host GCL5 VM's in the root Ey.net domain where policies are available. RISK has been withdrawn.
Note on B6: Headlines only - should speak to key, upcoming milestones, blockers, decisions
Note on B7: This is an opportunity to RAG our project stakeholders - should focus on any gaps we have in coverage or decision-making delays
Note on B8: Should align with overall status; this is next level down and should highlight any impacts/risks to schedule
Note on B9: Opportunity to comment on team from a resourcing perspective - e.g. Highlight where we have shortage of resources, difficulty sourcing people against budget or unforeseen constraints
Note on B10: Any changes/risks to scope should be highlighted here. Key CRs need to be referenced