## Sheet2 (hidden)
Team Progress Report - Testing SIT/ UAT | Team Progress Report - Business Implementation : Training | Team Progress Report - Solution : People | Team Progress Report - Solution : S&A | Team Progress Report - Solution : HDC | Team Progress Report - Testing : PPR | Team Progress Report - Solution : MI | Team Progress Report - Solution : Payroll Functional | Team Progress Report - Data : Data | Team Progress Report - Solution : Integration | Team Progress Report - Business Implementation: Communications |  | Team Progress Report - Solution : Development
Gurminder Sahota/Mike Kettle | John McGann/Kevin Light | Adam Walden | John Morgan/James Venables | Ryan Fawcett | Mike Ritter/Paul Boocock | Olivier Acar/Stephen Hadley | Jim Chadwick & Andy McLauchlan | Malcolm Bunting/Kevin Middleton/ Peter McNiff | Martin Barrow/Simon Evans | Debbie Benson | Graham O'Neill, Chris Jaques | Surya Dagempude | Bill Robertson, Richard Cowtan
RED | GREEN | GREEN | RED | GREEN | GREEN | AMBER | AMBER | AMBER | RED | GREEN | GREEN | GREEN | GREEN
GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | AMBER
GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
RED | GREEN | GREEN | AMBER | GREEN | GREEN | AMBER | AMBER | AMBER | RED | GREEN | GREEN | GREEN | GREEN
RED | AMBER | GREEN | AMBER | GREEN | GREEN | AMBER | GREEN | RED | AMBER | AMBER | GREEN | GREEN | AMBER
GREEN | GREEN | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
GREEN | AMBER | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | AMBER

## Workstream Status Report
Progress Report - Release
Team Lead: | Falgun Shah
Period Ending: | 15th February 2013
Workstream Status | [8 empty] | This Period | Last Period
Overall Status | Release R1.7.0 to QA#3 Environment and deployed using MSOCAF Manifest Deployment method. Deployment to UA#5b is delayed | [7 empty] | RED | AMBER
Stakeholders | [8 empty] | GREEN | GREEN
Schedule | Deployment to UA#5b is delayed. Beta Pilot code is not MSOCAF compliant. | [7 empty] | AMBER | AMBER
Team | [8 empty] | GREEN | GREEN
Scope | [8 empty] | GREEN | GREEN
Key Achievements This Week | Released R1.7.0 build to QA#3 Environment and deployed using MSOCAF Manifest Deployment method. Prepared R1.7.0C release to go to UA#5b. Completed and reviewed SharePoint interim Release Mgmt deck. | [9 empty] | `
Key Activities next week | Issue R1.8.0 release for QA#3 and UA#5b Complete and Review Action Plan for Lesson Learned assigned to me
Progress Against Plan (those in progress / due to start in the next 6-8 weeks). Note: Activities should be derived from L2 while Deliverables from L3
Project Plan Ref. | Milestone or Deliverable Name | Actual Start | Actual Finish | Baseline Start | Baseline Finish | RAG | Activity/ Deliverable | Progress (%) | Comments |  | Resource
| Generic SDA Milestone | [9 empty] | -
| Deploy Solution to QA#3 SP2013 Preview Simulated cloud | 2012-12-20 | 2013-01-15 | 2012-12-20 | 2013-01-15 | COMPLETE | Generic SDA based Milestone | 100% |  |  | Oleksiy
| Deploy Solution to UA#5b SP2013 RTM Simulated cloud |  |  | 2013-01-22 | 2013-01-22 | RED | Generic SDA based Milestone
| Deploy Solution to QA#5 SP2013 RTM Simulated cloud |  |  | 2013-02-12 | 2013-02-18 | AMBER | Generic SDA based Milestone
| Deploy Solution to UA#5 SP2013 RTM Simulated cloud |  |  | 2013-03-05 | 2013-03-05 | GREEN | Generic SDA based Milestone |  |  |  | Hasan
| Generic SDA deliverable | [9 empty] | Hasan
Deploy Solution to QA#3 SP2013 Preview Simulated cloud
| Deploy Metadata.WSP (BP) | 2012-12-20 | 2012-12-20 | 2012-12-20 | 2012-12-20 | COMPLETE
| Deploy Branding, Team Site Template WSPs (BP) | 2012-12-20 | 2012-12-20 | 2012-12-20 | 2012-12-20 | COMPLETE
| Deploy Profile (BP) + Changes | 2012-12-20 | 2012-12-20 | 2012-12-20 | 2012-12-20 | COMPLETE
| Landing Site (BP) | 2012-12-20 | 2012-12-20 | 2012-12-20 | 2012-12-20 | COMPLETE
| Branding - CR101 WSP (R1) | 2013-01-02 | 2013-01-02 | 2013-01-02 | 2013-01-02 | COMPLETE
| Search R1 (without Admin) | 2013-01-02 | 2013-01-02 | 2013-01-02 | 2013-01-02 | COMPLETE
| Load Search Test Data | 2012-12-20 | 2012-12-20 | 2012-12-20 | 2012-12-20 | COMPLETE
| Site Provisioning - On Prem WSP (R1) | 2013-01-02 | 2013-01-02 | 2013-01-02 | 2013-01-02 | COMPLETE
| Site Provisioning - O365 WSP (R1) | 2013-01-02 | 2013-01-02 | 2013-01-02 | 2013-01-02 | COMPLETE
| Search Admin R1 | 2013-01-15 | 2013-01-15 | 2013-01-15 | 2013-01-15 | COMPLETE
| Team Site Template Upgrade WSP (R1) | 2013-01-15 | 2013-01-15 | 2013-01-15 | 2013-01-15 | COMPLETE
Deploy Solution to UA#5b SP2013 RTM Simulated cloud
| Deploy Metadata.WSP (BP) |  |  | 2013-01-22 | 2013-01-22 | RED |  |  | RAID - Issue 254 - UA5 InfoSec Testing environment will be delayed due to reduced I/O staffing limiting their ability to provision new physical servers. Deployment to UA#5b is plan to completed Feb-21.
| Deploy Branding, Team Site Template WSPs (BP) |  |  | 2013-01-22 | 2013-01-22 | RED
| Deploy Profile (BP) + Changes |  |  | 2013-01-22 | 2013-01-22 | RED
| Landing Site (BP) |  |  | 2013-01-22 | 2013-01-22 | RED
| Branding - CR101 WSP (R1) |  |  | 2013-01-22 | 2013-01-22 | RED
| Search R1 (without Admin) |  |  | 2013-01-22 | 2013-01-22 | RED
| Load Search Test Data |  |  | 2013-01-22 | 2013-01-22 | RED
| Site Provisioning - On Prem WSP (R1) |  |  | 2013-01-22 | 2013-01-22 | RED
| Site Provisioning - O365 WSP (R1) |  |  | 2013-01-22 | 2013-01-22 | RED
| Search Admin R1 |  |  | 2013-01-22 | 2013-01-22 | RED
| Team Site Template Upgrade WSP (R1) |  |  | 2013-01-22 | 2013-01-22 | RED
Deploy Solution to QA#5 SP2013 RTM Simulated cloud
| Deploy Metadata.WSP (BP) |  |  | 2013-02-12 | 2013-02-12 | RED |  |  | RAID - Risk 428 - EY hosted O365 simulated cloud 1-way trust will not fully simulate the Production O365 cloud. Deployment to QA#5 is plan to be completed by Feb-27.
| Deploy Branding, Team Site Template WSPs (BP) |  |  | 2013-02-12 | 2013-02-12 | RED
| Deploy Profile (BP) + Changes |  |  | 2013-02-12 | 2013-02-12 | RED
| Landing Site (BP) |  |  | 2013-02-12 | 2013-02-12 | RED
| Branding - CR101 WSP (R1) |  |  | 2013-02-12 | 2013-02-12 | RED
| Search R1 (without Admin) |  |  | 2013-02-12 | 2013-02-12 | RED
| Load Search Test Data |  |  | 2013-02-12 | 2013-02-12 | RED
| Site Provisioning - On Prem WSP (R1) |  |  | 2013-02-12 | 2013-02-12 | RED
| Site Provisioning - O365 WSP (R1) |  |  | 2013-02-12 | 2013-02-12 | RED
| Search Admin R1 |  |  | 2013-02-12 | 2013-02-12 | RED
| Team Site Template Upgrade WSP (R1) |  |  | 2013-02-12 | 2013-02-12 | RED
Deploy Solution to UA#5 SP2013 RTM Simulated cloud
| Deploy Metadata.WSP (BP) |  |  | 2013-03-05 | 2013-03-05 | GREEN
| Deploy Branding, Team Site Template WSPs (BP) |  |  | 2013-03-05 | 2013-03-05 | GREEN
| Deploy Profile (BP) + Changes |  |  | 2013-03-05 | 2013-03-05 | GREEN
| Landing Site (BP) |  |  | 2013-03-05 | 2013-03-05 | GREEN
| Branding - CR101 WSP (R1) |  |  | 2013-03-05 | 2013-03-05 | GREEN
| Search R1 (without Admin) |  |  | 2013-03-05 | 2013-03-05 | GREEN
| Load Search Test Data |  |  | 2013-03-05 | 2013-03-05 | GREEN
| Site Provisioning - On Prem WSP (R1) |  |  | 2013-03-05 | 2013-03-05 | GREEN
| Site Provisioning - O365 WSP (R1) |  |  | 2013-03-05 | 2013-03-05 | GREEN
| Search Admin R1 |  |  | 2013-03-05 | 2013-03-05 | GREEN
| Team Site Template Upgrade WSP (R1) |  |  | 2013-03-05 | 2013-03-05 | GREEN
Hasan/Lee
Hasan
External Dependencies
Task UID (in MSP) | Dependency Name |  | RAG Status | Entity | Owner |  | Due Date | Actions
Issues
RAID ID | Issue Title |  | Involved | Next Review | Assigned To | Impact | Affected | Actions
254 | UA5 InfoSec Testing environment will be delayed due to reduced I/O staffing limiting their ability to provision new physical servers |  |  | Jan-28 | Josh Jackson | Medium | Schedule | 11 Feb (JJ): Split into two seperate issues for UAT5bIS from CIDE5 9 Feb (NR): With regard to UA#5b an updated R1 Security Testing schedule has been agreed with the Security Team based on the new forecast test ready date of 22 Feb. The security team will now run a first cycle of testing from Mar 4 to 22 Mar. The final week of March will then be available to retest any fixes for issues raised during the first cycle of testing. Currently the end date for Security testing has not been impacted. If fixes are not available by the end of March and retesting is required early in April then the security team have agreed to make resource available (within one ot two days) to retest the fixes. Any further slippage which would potentially impact schedules
272 | Beta Pilot code is not compliant against MSOCAF 2013 |  | Rich Partridge | Mar-08 | Rich Partridge | Medium | Schedule | 15 Feb (NR): Meeting scheduled for 19 Feb with Norm, Sampath and Sachin to review: - Changes required and test impact - Environment where we can test - Timelines for testing 13 Feb (RP): Following up on this discussion this week, below is the proposed action plan: 1) Follow up with the O365 team to determine if the BP code will need to be updated when BP is upgraded to O365. Target date is Feb 27th (owner Yi Wen/Norm) 2) If we don’t hear from O365 by Feb 27th, or if we learn from O365 that the changes are required, then the following activities need to be completed by March 6th. a. Build team will make the BP code changes necessary b. Build team to provide test team with feature/capabilities affected c. Changes will be regression tested in the QA#1 environment (BP test environment) 10 Feb (RP): This issue needs to stay on hold until we understand the SP2013 upgrade plans for O365. If O365 requires the code to be recompiled and verified with the 2013 MSOCAF tool, then two code changes are required. They are minimal, but would require a regression test. Jan 21 (RP) 2013 MSOCAF tool delivered on Jan 18. ​14 Jan (RP): The tool will be available on Jan 18 per Scott Kaldenburg.
RAID ID | Risk Title |  | Probablilty | Priority | Assigned To | Impact | Affected | Actions
428 | EY hosted O365 simulated cloud 1-way trust will not fully simulate the Production O365 cloud |  | Low | 2 | Vel Stoyanchev | Medium | Scope, Schedule

## Sheet4
Deploy Solution to QA#3 SP2013 Preview Simulated cloud
Deploy Metadata.WSP (BP) | 2012-12-20 | 2012-12-20
Deploy Branding, Team Site Template WSPs (BP) | 2012-12-20 | 2012-12-20
Deploy Profile (BP) + Changes | 2012-12-20 | 2012-12-20
Landing Site (BP) | 2012-12-20 | 2012-12-20
Branding - CR101 WSP (R1) | 2013-01-02 | 2013-01-02
Search R1 (without Admin) | 2013-01-02 | 2013-01-02
Load Search Test Data | 2012-12-20 | 2012-12-20
Site Provisioning - On Prem WSP (R1) | 2013-01-02 | 2013-01-02
Site Provisioning - O365 WSP (R1) | 2013-01-02 | 2013-01-02
Search Admin R1 | 2013-01-15 | 2013-01-15
Team Site Template Upgrade WSP (R1) | 2013-01-15 | 2013-01-15
Deploy Solution to QA#5 SP2013 RTM Simulated cloud | 2013-02-11 08:00 | 2013-02-13 17:00
QA#5 Base Build | 2013-02-11 08:00 | 2013-02-11 08:00
QA#5 System Test Cycle 2 Build | 2013-02-13 17:00 | 2013-02-13 17:00
Deploy Solution to UA#5 SP2013 RTM Simulated cloud | 2013-02-11 08:00 | 2013-03-22 08:00
UA#5 Base Build | 2013-02-11 08:00 | 2013-02-11 08:00
UA#5 UAT Test Cycle 1 Build | 2013-03-08 08:00 | 2013-03-08 08:00
UA#5 UAT Test Cycle 2 Build | 2013-03-22 08:00 | 2013-03-22 08:00
Deploy Solution to UA#5b SP2013 RTM Simulated cloud | 2013-01-18 17:00 | 2013-03-15 08:00
UA#5b Base Build | 2013-01-18 17:00 | 2013-01-18 17:00
UA#5b Security Test Cycle 1 Build | 2013-01-25 17:00 | 2013-01-25 17:00
UA#5b Security Test Cycle 2 Build | 2013-03-15 08:00 | 2013-03-15 08:00

## Sheet1
Deploy Solution to QA#3 SP2013 Preview Simulated cloud
Deploy Metadata.WSP (BP) | 2012-12-20 | 2012-12-20
Deploy Branding, Team Site Template WSPs (BP) | 2012-12-20 | 2012-12-20
Deploy Profile (BP) + Changes | 2012-12-20 | 2012-12-20
Landing Site (BP) | 2012-12-20 | 2012-12-20
Branding - CR101 WSP (R1) | 2013-01-02 | 2013-01-02
Search R1 (without Admin) | 2013-01-02 | 2013-01-02
Load Search Test Data | 2012-12-20 | 2012-12-20
Site Provisioning - On Prem WSP (R1) | 2013-01-02 | 2013-01-02
Site Provisioning - O365 WSP (R1) | 2013-01-02 | 2013-01-02
Search Admin R1 | 2013-01-15 | 2013-01-15
Team Site Template Upgrade WSP (R1) | 2013-01-15 | 2013-01-15
Bug Fixing
Deploy Solution to UA#5b SP2013 RTM Simulated cloud
Deploy Metadata.WSP (BP) | 2013-01-22 | 2013-01-22
Deploy Branding, Team Site Template WSPs (BP) | 2013-01-22 | 2013-01-22
Deploy Profile (BP) + Changes | 2013-01-22 | 2013-01-22
Landing Site (BP) | 2013-01-22 | 2013-01-22
Branding - CR101 WSP (R1) | 2013-01-22 | 2013-01-22
Search R1 (without Admin) | 2013-01-22 | 2013-01-22
Load Search Test Data | 2013-01-22 | 2013-01-22
Site Provisioning - On Prem WSP (R1) | 2013-01-22 | 2013-01-22
Site Provisioning - O365 WSP (R1) | 2013-01-22 | 2013-01-22
Search Admin R1 | 2013-01-22 | 2013-01-22
Team Site Template Upgrade WSP (R1) | 2013-01-22 | 2013-01-22
Deploy Solution to QA#5 SP2013 RTM Simulated cloud
Deploy Metadata.WSP (BP) | 2013-02-12 | 2013-02-12
Deploy Branding, Team Site Template WSPs (BP) | 2013-02-12 | 2013-02-12
Deploy Profile (BP) + Changes | 2013-02-12 | 2013-02-12
Landing Site (BP) | 2013-02-12 | 2013-02-12
Branding - CR101 WSP (R1) | 2013-02-12 | 2013-02-12
Search R1 (without Admin) | 2013-02-12 | 2013-02-12
Load Search Test Data | 2013-02-12 | 2013-02-12
Site Provisioning - On Prem WSP (R1) | 2013-02-12 | 2013-02-12
Site Provisioning - O365 WSP (R1) | 2013-02-12 | 2013-02-12
Search Admin R1 | 2013-02-12 | 2013-02-12
Team Site Template Upgrade WSP (R1) | 2013-02-12 | 2013-02-12
Deploy Solution to UA#5 SP2013 RTM Simulated cloud
Deploy Metadata.WSP (BP) | 2013-03-05 | 2013-03-05
Deploy Branding, Team Site Template WSPs (BP) | 2013-03-05 | 2013-03-05
Deploy Profile (BP) + Changes | 2013-03-05 | 2013-03-05
Landing Site (BP) | 2013-03-05 | 2013-03-05
Branding - CR101 WSP (R1) | 2013-03-05 | 2013-03-05
Search R1 (without Admin) | 2013-03-05 | 2013-03-05
Load Search Test Data | 2013-03-05 | 2013-03-05
Site Provisioning - On Prem WSP (R1) | 2013-03-05 | 2013-03-05
Site Provisioning - O365 WSP (R1) | 2013-03-05 | 2013-03-05
Search Admin R1 | 2013-03-05 | 2013-03-05
Team Site Template Upgrade WSP (R1) | 2013-03-05 | 2013-03-05