## Sheet2 (hidden)
Team Progress Report - Testing SIT/ UAT | Team Progress Report - Business Implementation : Training | Team Progress Report - Solution : People | Team Progress Report - Solution : S&A | Team Progress Report - Solution : HDC | Team Progress Report - Testing : PPR | Team Progress Report - Solution : MI | Team Progress Report - Solution : Payroll Functional | Team Progress Report - Data : Data | Team Progress Report - Solution : Integration | Team Progress Report - Business Implementation: Communications |  | Team Progress Report - Solution : Development
Gurminder Sahota/Mike Kettle | John McGann/Kevin Light | Adam Walden | John Morgan/James Venables | Ryan Fawcett | Mike Ritter/Paul Boocock | Olivier Acar/Stephen Hadley | Jim Chadwick & Andy McLauchlan | Malcolm Bunting/Kevin Middleton/ Peter McNiff | Martin Barrow/Simon Evans | Debbie Benson | Graham O'Neill, Chris Jaques | Surya Dagempude | Bill Robertson, Richard Cowtan
RED | GREEN | GREEN | RED | GREEN | GREEN | AMBER | AMBER | AMBER | RED | GREEN | GREEN | GREEN | GREEN
GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | AMBER
GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
RED | GREEN | GREEN | AMBER | GREEN | GREEN | AMBER | AMBER | AMBER | RED | GREEN | GREEN | GREEN | GREEN
RED | AMBER | GREEN | AMBER | GREEN | GREEN | AMBER | GREEN | RED | AMBER | AMBER | GREEN | GREEN | AMBER
GREEN | GREEN | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
GREEN | AMBER | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | AMBER

## Workstream Status Report
Team Progress Report - Requirements and Design
Team Lead: | Nicola Cooper
Period Ending: | 7th September 2012
Workstream Status | [8 empty] | This Period | Last Period
Overall Status | Moved to Red due to the following Issue/Risks EAX Requirements closure delayed, Metadata and Landing Page remain Open Concept Searching agreed Out of Scope for EAX and Release 1 : Confirmation and conditions received from Cindy Hope | [7 empty] | RED | RED
Stakeholders | Metadata remains blocked for closure, 3 key areas have been identified by BPO and Q&RM, IT facilitating requirements elicitation and related closure | [7 empty] | AMBER | GREEN
Schedule | EAX Requirements delayed due to issues/concerns/queries raised during review exceeding the planned contingency for this kind of discussion R1 Requirements impacted due to delay in closing EAX Requirements, Search Discovery after delayed start will now finish | [7 empty] | RED | AMBER
Team | Melissa now working against newly agreed schedule | [7 empty] | AMBER | GREEN
Scope | Volume of potential change to scope for Release 1 continues to increase, placing demand on entire team to perform impact assessments Number of Open Items in the Requirements Documents that have not blocked entrance into Design but will block Design/Build Closure | [7 empty] | AMBER | AMBER
Key Achievements This Week | Team Site Provisioning and Decommissioning Requirements Acknowlegdment from the BPO Community | [9 empty] | `
Key Activities next week | Metadata Outstanding queries raised by Q&RM to resolve Landing Page Configuration Requirements Acknowledgment from Business
Progress Against Plan (those in progress / due to start in the next 6-8 weeks). Note: Activities should be derived from L2 while Deliverables from L3
Project Plan Ref. | Milestone or Deliverable Name | Progress (%) | Baseline Start | Baseline Finish | Actual Start | Actual Finish | Activity/ Deliverable | RAG | Comments |  | Resource
| Enterprise Plan milestone (Start / End of SDA phase only) | [9 empty] | -
| EAX Requirements and Design Phase Complete | 0% | NA | NA | 2012-09-17 17:00 | 2012-09-17 17:00 | Enterprise Plan Milestone | AMBER |  |  | -
| Generic SDA Milestone | [9 empty] | -
| EAX Requirements Complete | 75% | 2012-08-21 17:00 | 2012-08-21 17:00 | 2012-08-27 08:00 | 2012-08-31 17:00 | Generic SDA based Milestone | RED | Landing Page and Metadata remain open |  | Oleksiy
| EAX SAD Complete | 80% | 2012-08-27 17:00 | 2012-08-27 17:00 | 2012-08-28 08:00 | 2012-09-04 17:00 | Generic SDA based Milestone | GREEN |  |  | Hasan
| EY approves EAX Design | 80% | 2012-09-14 08:00 | 2012-09-14 17:00 | 2012-09-17 08:00 | 2012-09-17 17:00 | Generic SDA based Milestone | AMBER |  |  | Pat
| O365 approves EAX HLD | 40% | 2012-09-26 17:00 | 2012-09-26 17:00 | 2012-09-26 17:00 | 2012-09-26 17:00 | Generic SDA based Milestone | AMBER |  |  | Melissa/Mike/Pat
| SP Rel 1.0 Requirements Complete | 0% | 2012-09-17 17:00 | 2012-09-17 17:00 | 2012-09-17 17:00 | 2012-09-17 17:00 | Generic SDA based Milestone | RED | Knock on impact due to EAX Requirements
| SP Rel 1.0 SAD Complete | 0% | 2012-10-01 17:00 | 2012-10-01 17:00 | 2012-10-01 17:00 | 2012-10-01 17:00 | Generic SDA based Milestone | AMBER
| EY approves SP Rel 1.0 Design | 0% | 2012-10-12 | 2012-10-12 | 2012-10-12 | 2012-10-12 | Generic SDA based Milestone | AMBER
| O365 approves SP Rel 1.0 HLD | 0% | 2012-10-16 | 2012-10-16 | 2012-10-16 | 2012-10-16 | Generic SDA based Milestone | GREEN
| Generic SDA deliverable | [9 empty] | Hasan
| Work Product: EAX UI Requirements/Definition Document | 100% | 2012-07-03 17:00 | 2012-07-03 17:00 | 2012-07-03 17:00 | 2012-07-03 17:00 | Generic SDA based Deliverable | COMPLETE | CR being considered for additional UI Requirements |  | Melissa/Mike
| Work Product: EAX Profile Requirements/Definition Document | 100% | 2012-08-21 17:00 | 2012-08-21 17:00 | 2012-08-21 17:00 | 2012-08-21 17:00 | Generic SDA based Deliverable | COMPLETE | Title and Department discovered to be an issue in Technical Response to Requirements |  | -
| Work Product: EAX Team Site Requirements/Definition Document | 100% | 2012-08-10 17:00 | 2012-08-10 17:00 | 2012-08-10 17:00 | 2012-08-10 17:00 | Generic SDA based Deliverable | COMPLETE | InfoSec have now raised item with permissions |  | Yi Wen
| Work Product : EAX Team Site Landing Page Requirement/Definition Document | 35% | NA | NA | 2012-09-06 17:00 | 2012-09-06 17:00 | Generic SDA based Deliverable | RED | Configuration of the Team Site not landed, therefore details of the specific wording, link titles, site verbage not started |  | Bijal
| Work Product: SP Rel 1.0 Team Site Requirement Document | 0% | 2012-08-28 17:00 | 2012-08-28 17:00 | 2012-09-17 17:00 | 2012-09-17 17:00 | Generic SDA based Deliverable | RED |  |  | Dev/YiWen/Bijal
| Work Product: EAX Profile and Team Site SAD Section Draft | 100% | 2012-08-14 17:00 | 2012-08-14 17:00 | 2012-08-14 17:00 | 2012-08-14 17:00 | Generic SDA based Deliverable | COMPLETE | Title and Department discovered to be an issue in Technical Response to Requirements |  | -
| Work Product: EAX Site Provisioning Requirements Document | 35% | 2012-08-17 17:00 | 2012-08-17 17:00 | 2012-08-22 08:00 | 2012-08-22 08:00 | Generic SDA based Deliverable | COMPLETE |  |  | Melissa/Mike
| Work Product: EAX Site Decom Requirements Document | 35% | 2012-08-20 17:00 | 2012-08-20 17:00 | 2012-08-24 17:00 | 2012-08-24 17:00 | Generic SDA based Deliverable | COMPLETE |  |  | Melissa/Mike
| Work Product: Updated SP R1.0 Site Provisioning Requirements Document | 0% | 2012-09-06 17:00 | 2012-09-06 17:00 | 2012-09-06 17:00 | 2012-09-06 17:00 | Generic SDA based Deliverable | RED | EAX Work currently taking priority |  | Melissa/Mike
| Work Product: EAX Site Provisioning and Decom SAD Sections Complete | 85% | 2012-08-27 17:00 | 2012-08-27 17:00 | 2012-08-27 17:00 | 2012-08-27 17:00 | Generic SDA based Deliverable | COMPLETE |  |  | -
| Work Product: SP Rel 1.0 Site Prov/Decom SAD Section Draft | 0% | NA | NA | 2012-09-07 17:00 | 2012-09-07 17:00 | Generic SDA based Deliverable | RED | EAX Work currently taking priority |  | Bijal
| Work Product: EAX Search Requirements/Definition Document | 100% | 2012-08-15 17:00 | 2012-08-15 17:00 | 2012-08-16 08:00 | 2012-08-22 17:00 | Generic SDA based Deliverable | COMPLETE | Item open related to the NFRs |  | -
| Work Product: SP Rel 1.0 Search Requirements/Definition Document | 0% | 2012-09-04 08:00 | 2012-09-06 17:00 | 2012-09-04 08:00 | 2012-09-06 17:00 | Generic SDA based Deliverable | RED | Search Discovery Investigation delayed |  | Pat
| Work Product: EAX Search SAD Draft Complete | 100% | 2012-08-22 17:00 | 2012-08-22 17:00 | 2012-08-22 17:00 | 2012-08-22 17:00 | Generic SDA based Deliverable | COMPLETE |  |  | -
| Work Product: SP Rel 1.0 Search SAD Draft Complete | 0% | NA | NA | 2012-09-12 08:00 | 2012-09-18 17:00 | Generic SDA based Deliverable | RED | Search Discovery Investigation delayed |  | Dev/Shane Delaney
| Work Product: EAX Metadata Requirements/Definition Document | 100% | 2012-08-09 08:00 | 2012-08-09 08:00 | 2012-08-24 17:00 | 2012-08-24 17:00 | Generic SDA based Deliverable | COMPLETE | Q&RM Open Items |  | Hasan/Lee
| Work Product: EAX Metadata SAD Sections Complete | 100% | 2012-08-10 17:00 | 2012-08-10 17:00 | 2012-08-17 08:00 | 2012-08-17 08:00 | Generic SDA based Deliverable | COMPLETE |  |  | Hasan
Specific Program deliverable
| MS Deliverable: EAX Team Sites HLD | 100% | 2012-08-21 17:00 | 2012-08-21 17:00 | 2012-08-21 17:00 | 2012-08-21 17:00 | Key Specific Program Deliverable | COMPLETE
| MS Deliverable: SP Rel 1.0 Site Prov/Decom HLD Draft | 0% | NA | NA | 2012-09-07 17:00 | 2012-09-07 17:00 | Key Specific Program Deliverable | RED | EAX Work currently taking priority
| MS Deliverable: EAX Metadata HLD Section Draft Complete | 100% | 2012-07-30 17:00 | 2012-07-30 17:00 | 2012-07-30 17:00 | 2012-07-30 17:00 | Key Specific Program Deliverable | COMPLETE
External Dependencies
Task UID (in MSP) | Dependency Name |  | RAG Status | Entity | Owner |  | Due Date | Actions
Issues
RAID ID | Issue Title |  | Involved | Next Review | Assigned To | Impact | Affected | Actions
43 | People Profile Data retention policy for people who leave the firm has not been defined |  | Steve Jelf | 13-Aug-12 | Hasan Nazir | 2) Medium | Scope;#Schedule;#Quality;#Cost | 9-Aug (NC) The retention policy and related response from design has been noted in the planned resolution section. Hasan the next steps are as follows please: 1. Raise with the business team that for EAX/R1 we suggest a manual approach to this. 2. Agree the manual process with the business 9-Aug - Updated required resolution date, next prj review date and reassigned to Hasan Nazir. - BP 7-Aug - Updated planned resolution with retention policy and technical approach. As there is no auto deletion of a user's profile in Office 365, MySites will need to be manually deleted. Profile and Social data can be deleted by submitting a monthly spreadsheet. (BP) 20-Jun - Please see Decision D141. 30 days after a user leaves the firm has been decided, with the exception of litigation hold cases. Please see D141 for further details. Key answer outstanding from Q&RM is that should this data remain visibile during this time - Response expected by 26th June. 19-Jun : After update in the weekly Collaboration Meeting this item was associated with Steven Jelf, Nicola Cooper to follow up with Steve and ensure this has been assigned correctly 12-Jun (LM) Per Michelle, updated Assigned to to Nicola Cooper. 03-May: M&C Q&RM decision request form sent to Steve Jelf, for disposition. 26-Apr: Logged issue​
149 | Termset roll-back/restore is not possible in the scope of EAX/Release 1 |  |  | 11-Sep-12 | MaryGael Timberlake | 3) High | Scope;#Schedule;#Quality;#Cost | 9-Aug (NC) The retention policy and related response from design has been noted in the planned resolution section. Hasan the next steps are as follows please: 1. Raise with the business team that for EAX/R1 we suggest a manual approach to this. 2. Agree the manual process with the business 9-Aug - Updated required resolution date, next prj review date and reassigned to Hasan Nazir. - BP 7-Aug - Updated planned resolution with retention policy and technical approach. As there is no auto deletion of a user's profile in Office 365, MySites will need to be manually deleted. Profile and Social data can be deleted by submitting a monthly spreadsheet. (BP) 20-Jun - Please see Decision D141. 30 days after a user leaves the firm has been decided, with the exception of litigation hold cases. Please see D141 for further details. Key answer outstanding from Q&RM is that should this data remain visibile during this time - Response expected by 26th June. 19-Jun : After update in the weekly Collaboration Meeting this item was associated with Steven Jelf, Nicola Cooper to follow up with Steve and ensure this has been assigned correctly 12-Jun (LM) Per Michelle, updated Assigned to to Nicola Cooper. 03-May: M&C Q&RM decision request form sent to Steve Jelf, for disposition. 26-Apr: Logged issue​
Risks
RAID ID | Risk Title |  | Probablilty | Priority | Assigned To | Impact | Affected | Actions
232 | Managed Metadata Service (MMS) is not supported as a cross-farm service in O365 SP2013 release as expected |  | 1) Low | 2 | Nicola Cooper | 2) Medium | Scope;#Schedule;#Quality;#Cost | ​2 Aug (BvG): Nicola, please could you review this risk and enter details around potential cost etc and then mark as Accepted (if you agree).
227 | Schedule and cost risk if project is not able to get sign off for requirements & designs on a timely basis. |  | 3) High | 9 | Jeremy Brown | 3) High | Scope;#Schedule;#Quality;#Cost | 31 Aug (AI): have re-opened as this is our verhicle for monitoring the risk of schedule delay owing to ongoing business challenges to scope thorugh the requirements acknowledgment process.