## Sheet2 (hidden)
Team Progress Report - Testing SIT/ UAT | Team Progress Report - Business Implementation : Training | Team Progress Report - Solution : People | Team Progress Report - Solution : S&A | Team Progress Report - Solution : HDC | Team Progress Report - Testing : PPR | Team Progress Report - Solution : MI | Team Progress Report - Solution : Payroll Functional | Team Progress Report - Data : Data | Team Progress Report - Solution : Integration | Team Progress Report - Business Implementation: Communications |  | Team Progress Report - Solution : Development
Gurminder Sahota/Mike Kettle | John McGann/Kevin Light | Adam Walden | John Morgan/James Venables | Ryan Fawcett | Mike Ritter/Paul Boocock | Olivier Acar/Stephen Hadley | Jim Chadwick & Andy McLauchlan | Malcolm Bunting/Kevin Middleton/ Peter McNiff | Martin Barrow/Simon Evans | Debbie Benson | Graham O'Neill, Chris Jaques | Surya Dagempude | Bill Robertson, Richard Cowtan
RED | GREEN | GREEN | RED | GREEN | GREEN | AMBER | AMBER | AMBER | RED | GREEN | GREEN | GREEN | GREEN
GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | AMBER
GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
RED | GREEN | GREEN | AMBER | GREEN | GREEN | AMBER | AMBER | AMBER | RED | GREEN | GREEN | GREEN | GREEN
RED | AMBER | GREEN | AMBER | GREEN | GREEN | AMBER | GREEN | RED | AMBER | AMBER | GREEN | GREEN | AMBER
GREEN | GREEN | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
GREEN | AMBER | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | AMBER

## Workstream Status Report
Team Progress Report - Service Design and Transition
Team Lead: | Richard Brown
Period Ending: | 18th February 2013
Workstream Status | [8 empty] | This Period | Last Period
Overall Status | Overall status is red due to the Service Strategy requirements overdue, Nick Coburn is working on the deliverables in Richard's absence. O365 security model defined, escalated to Gil Levit as goal post shifting now appears to be taking place. I consider my involvement closed. RAID 245 refers. L3 plan created on PMO template and will be moved onto PMO location ready for w/c 18th Feb Proposal with Gil Levit to move OAT for Collaboration to 15-19 Apr as there is now no environment dependency for the test. Gil to confirm back that these dates are acceptable. John Hutton to advise stakeholders if agreed. | [7 empty] | RED | RED
Stakeholders | [8 empty] | GREEN | GREEN
Schedule | Schedule is currently amber due to awaiting confirmation over OAT dates and it is awaiting optimisation review between Scott Strange and Dan Mulligan The schedule will require review again for R1 once final definition of the deployment plan for SP2013 cloud upgrade and bringing hybrid on-premise architecture online. | [7 empty] | AMBER | RED
Team | Richard Brown is on annual leave from Feb 15th returning 3rd March. Nick Coburn will work on transition activities with Scott Strange in his absence. Status moved to Amber to reflect this. Handover performed to Nick and Scott, it was agreed with Andy that Scott only need report to Andy any risks around deliverables. | [7 empty] | AMBER | GREEN
Scope | [8 empty] | GREEN | GREEN
Key Achievements This Week | Security Incident Model process complete and sent to Gil Levit, refer item in overall status. Service Transition L3 plan defined and moved onto the PMO template, agreed with Steve Jelf that this could remain outside of the overarching project plan due to small number of dependencies and where we are in the project timeline. Release Management deck updated and proposal approved in principle by Andy Iaonnou. Handover performed to Nick Coburn and Scott Strange. | [9 empty] | `
Key Activities next week | L3 plan to be optimised by Scott Strange and Engineering with specific reference to documentation deliverables from Engineering and the timing of their delivery. Nick to take Scott through the Target Operating Model Scott to draft Business Impact Assessment Nick to work on close out of outstanding deliverables
Progress Against Plan (those in progress / due to start in the next 6-8 weeks). Note: Activities should be derived from L2 while Deliverables from L3
Project Plan Ref. | Milestone or Deliverable Name | Progress (%) | Baseline Start | Baseline Finish | Actual Start | Actual Finish | Activity/ Deliverable | RAG | Comments |  | Resource
SP Beta Pilot operational acceptance closure
| SP Beta Pilot operational acceptance closure | 100% | 2013-02-15 | 2013-02-15 | TBC | TBC | Key Specific Program Deliverable | COMPLETE | O365 Security Incident Model approval given. GSIRP will be updated by F&I to include in appendices.
Service Transition Strategy confirmed
| Service Strategy confirmed | 60% | 2013-02-08 | 2013-02-08 | NA | NA | Specific Program Milestone | RED | Nick Coburn is working on completion, Andy aware |  | -
| Documented Service Strategy | 60% | 2013-02-08 | 2013-02-08 | NA | NA | Key Specific Program Deliverable | RED | Nick Coburn is working on completion, Andy aware |  | -
| Service Design principles documented | 60% | 2013-02-08 | 2013-02-08 | NA | NA | Key Specific Program Deliverable | RED | Nick Coburn is working on completion, Andy aware |  | -
Service Transition Design confirmed
| Service Transition Design confirmed | 70% | 2013-02-18 | 2013-02-18 | NA | NA | Specific Program Milestone | RED | Nick Coburn is working on completion, Andy aware |  | Oleksiy
| Interim Target Operating Model designed | 50% | 2013-02-18 | 2013-02-18 | NA | NA | Key Specific Program Deliverable | RED | Nick Coburn is working on completion, Andy aware |  | Hasan
| Transition Impact Assessment | 100% | 2013-02-18 | 2013-02-18 | 2013-02-11 | NA | Key Specific Program Deliverable | GREEN | Submitted by Richard Brown on 15/02 for gETD submission |  | Yi Wen
Service Transition Plan Locked
| Service Transition Plan Locked | 80% | 2013-03-08 | 2013-03-11 | NA | NA | Specific Program Milestone | AMBER | At risk due to uncertainty on the deployment plan for R1
| Detailed transition plan with separate elements for People, Processes, Products, Partners with key activities to move from current state to agreed service design. | 80% | 2013-02-05 | 2013-03-11 | 2013-02-05 | NA | Key Specific Program Deliverable | AMBER | At risk due to uncertainty on the deployment plan for R1 |  | Dev/YiWen/Bijal
CAB1 Preparation
| OAT completed | 20% | 2013-03-29 | 2013-03-29 | NA | NA | Key Specific Program Deliverable | AMBER | OAT plan, date confirmation and resource availability all outstanding
| Operational Acceptance Phase 1 completed | 10% | 2013-04-24 | 2013-04-24 | NA | NA | Specific Program Milestone | AMBER |  |  | -
| Staffing plan executed to support interim TOM | 0% | 2013-05-15 | 2013-05-15 | NA | NA | Key Specific Program Deliverable | AMBER |  |  | Melissa/Mike
| Learning and education plan executed | 0% | 2013-05-15 | 2013-05-15 | NA | NA | Key Specific Program Deliverable | AMBER |  |  | Melissa/Mike
| Organisational Change Assessment completed | 0% | 2013-05-15 | 2013-05-15 | NA | NA | Key Specific Program Deliverable | AMBER
| R1 Governance List items closed | 50% | 2013-05-15 | 2013-05-15 | NA | NA | Key Specific Program Deliverable | AMBER
| Knowledge plans executed | 0% | 2013-05-15 | 2013-05-15 | NA | NA | Key Specific Program Deliverable | AMBER |  |  | Melissa/Mike
| Updated process documentation | 0% | 2013-05-01 | 2013-05-01 | NA | NA | Key Specific Program Deliverable | AMBER
| Service Now tool updates completed for R1 requirements | 0% | 2013-05-15 | 2013-05-15 | NA | NA | Key Specific Program Deliverable | AMBER
R1 Transition Preliminary CAB review
| Preliminary CAB approval received | 0% | 2013-04-24 | 2013-04-24 | NA | NA | Specific Program Milestone | AMBER |  |  | Shane Delaney
R1 Transition CAB
| Go / No-Go decision and CAB | 0% | 2013-05-15 | 2013-05-15 | NA | NA | Specific Program Milestone | AMBER |  |  | Shane Delaney
Stabilisation begins
| Stabilisation begins | 0% | 2013-05-20 | 2013-05-20 | NA | NA | Specific Program Milestone | AMBER
Stabilisation Completed
| Stabilisation Completed | 0% | 2013-06-17 | 2013-06-17 | NA | NA | Specific Program Milestone | AMBER
| Operational Acceptance Stabilisation R1 Criteria Met | 0% | 2013-06-17 | 2013-06-17 | NA | NA | Key Specific Program Deliverable | AMBER
Transition Closure
| BAU achieved | 0% | 2013-07-01 | 2013-07-01 | NA | NA | Specific Program Milestone | AMBER |  |  | Lee
| Operational Acceptance completed | 0% | 2013-07-01 | 2013-07-01 | NA | NA | Key Specific Program Deliverable | AMBER
| CAB Approval for closure of transition | 0% | 2013-07-01 | 2013-07-01 | NA | NA | Key Specific Program Deliverable | AMBER |  |  | Lee
External Dependencies
Task UID (in MSP) | Dependency Name |  | RAG Status | Entity | Owner |  | Due Date | Actions
Issues
RAID ID | Issue Title |  | Involved | Next Review | Assigned To | Impact | Affected | Actions
245 | No defined, agreed and signed off Security Incident process model for Sharepoint Beta Pilot |  | Gil Levit, Jeroen Schoemaker, Scott Strange, Richard Brown, Matt Calloway | 18-Feb | Gil Levit | Low |  | v0.71 issued to Gil Levit, escalation to Gil to the effect that the scope of the requirement appears to have shifted and I believe I have delivered what was reasonably expected of me. I have asked him to send out the v0.71 and then find an owner within I&O to drive forward any further changes that are not part of the EY O365 engagement steps within the process.
269 | O365 SharePoint Cloud production fixes have been applied by O365 support without alignment to EY change management process requirements |  | Dez Nagy, Scott Strange, Scott Kaldenberg, Mark Laverick | 10-Mar | Richard Brown | Low |  | Scott Kaldenberg to submit new one page graphical representation of O365 Change process covering where detail of changes made will be surfaced to EY.
284 | Team site quota request management process is currently not defined |  | Scott Strange, Richard Brown | 10-Mar | Richard Brown | Low |  | 1. Document process 2. Process reviewed and approved 3. Process socialised​ Release 1 Service Transition L3 Plan includes this as part of the Operational Acceptance milestone planning line item activities.
Risks
RAID ID | Risk Title |  | Probablilty | Priority | Assigned To | Impact | Affected | Actions

## Sheet1
Start Architecture and Design | 0% | 2012-09-03 08:00 | 2012-09-03 08:00 | Enterprise Plan Milestone
PRIMARY DELIVERABLE: TOM single page graphical representation | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | Key Specific Program Deliverable
PRIMARY DELIVERABLE: Detailed Word document (structure, roles, capacity, capability etc) | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | Key Specific Program Deliverable
PRIMARY DELIVERABLE: IT change plan | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | Key Specific Program Deliverable
PRIMARY DELIVERABLE: IT comms plan | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | Key Specific Program Deliverable
PRIMARY DELIVERABLE: Scope of service matrix | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | Key Specific Program Deliverable
End Architecture and Design | 0% | 2012-10-05 08:00 | 2012-10-05 08:00 | Enterprise Plan Milestone
Start Build | 0% | 2012-10-01 08:00 | 2012-10-01 08:00 | Enterprise Plan Milestone
PRIMARY DELIVERABLE: Detailed Service Transition plan | 0% | 2012-10-12 17:00 | 2012-10-12 17:00 | Key Specific Program Deliverable
Detailed Service Transition plan for EAX confirmed | 0% | 2012-10-12 17:00 | 2012-10-12 17:00 | Specific Program Milestone
PRIMARY DELIVERABLE: Staffing plan based on R&R definition from service design | 0% | 2012-10-29 17:00 | 2012-10-29 17:00 | Key Specific Program Deliverable
Detailed staffing plan confirmed | 0% | 2012-10-29 17:00 | 2012-10-29 17:00 | Specific Program Milestone
PRIMARY DELIVERABLE: Knowledge proliferation plans | 0% | 2012-11-02 17:00 | 2012-11-02 17:00 | Key Specific Program Deliverable
Confirm knowledge proliferation has been completed successfully | 0% | 2012-12-21 17:00 | 2012-12-21 17:00 | Specific Program Milestone
PRIMARY DELIVERABLE: Updated process documentation | 0% | 2012-11-20 17:00 | 2012-11-20 17:00 | Key Specific Program Deliverable
Process training completed | 0% | 2012-12-20 17:00 | 2012-12-20 17:00 | Specific Program Milestone
PRIMARY DELIVERABLE: Update Operations Manual v0.3.0 - Deployment Test | 0% | 2012-11-15 17:00 | 2012-11-15 17:00 | Key Specific Program Deliverable
PRIMARY DELIVERABLE: ServiceNow documentation | 0% | 2012-11-15 17:00 | 2012-11-15 17:00 | Key Specific Program Deliverable
Product training completed | 0% | 2012-11-29 17:00 | 2012-11-29 17:00 | Specific Program Milestone
End Build | 0% | 2013-06-03 08:00 | 2013-06-03 08:00 | Enterprise Plan Milestone
Start Test | 0% | 2012-08-06 08:00 | 2012-08-06 08:00 | Enterprise Plan Milestone
PRIMARY DELIVERABLE: Service Readiness Test approach | 0% | 2012-09-28 17:00 | 2012-09-28 17:00 | Key Specific Program Deliverable
PRIMARY DELIVERABLE: Operational Acceptance Test approach | 0% | 2012-09-28 17:00 | 2012-09-28 17:00 | Key Specific Program Deliverable
End Test | 0% | 2012-12-14 08:00 | 2012-12-14 08:00 | Enterprise Plan Milestone
Start Deploy | 0% | 2012-08-27 08:00 | 2012-08-27 08:00 | Enterprise Plan Milestone
End Deploy | 0% | 2013-06-28 08:00 | 2013-06-28 08:00 | Enterprise Plan Milestone
Start Run | 0% | 2013-02-15 08:00 | 2013-02-15 08:00 | Enterprise Plan Milestone
Go / No-Go decision | 0% | 2013-01-11 08:00 | 2013-01-11 08:00 | Specific Program Milestone
Early Life Support Completed | 0% | 2013-02-15 17:00 | 2013-02-15 17:00 | Specific Program Milestone
Go / no-go decision | 0% | 2013-02-15 08:00 | 2013-02-15 08:00 | Specific Program Milestone
Stabilisation completed | 0% | 2013-03-15 08:00 | 2013-03-15 08:00 | Specific Program Milestone
PRIMARY DELIVERABLE: Confirm Operations Manual Documentation Complete | 0% | 2013-05-08 08:00 | 2013-05-08 08:00 | Generic SDA based Deliverable
BAU achieved | 0% | 2013-03-15 17:00 | 2013-03-15 17:00 | Specific Program Milestone
End Run | 0% | 2013-03-15 08:00 | 2013-03-15 08:00 | Enterprise Plan Milestone
Transition completed | 0% | 2013-03-15 08:00 | 2013-03-15 08:00 | Specific Program Milestone