## Sheet2 (hidden)
Team Progress Report - Testing SIT/ UAT | Team Progress Report - Business Implementation : Training | Team Progress Report - Solution : People | Team Progress Report - Solution : S&A | Team Progress Report - Solution : HDC | Team Progress Report - Testing : PPR | Team Progress Report - Solution : MI | Team Progress Report - Solution : Payroll Functional | Team Progress Report - Data : Data | Team Progress Report - Solution : Integration | Team Progress Report - Business Implementation: Communications |  | Team Progress Report - Solution : Development
Gurminder Sahota/Mike Kettle | John McGann/Kevin Light | Adam Walden | John Morgan/James Venables | Ryan Fawcett | Mike Ritter/Paul Boocock | Olivier Acar/Stephen Hadley | Jim Chadwick & Andy McLauchlan | Malcolm Bunting/Kevin Middleton/ Peter McNiff | Martin Barrow/Simon Evans | Debbie Benson | Graham O'Neill, Chris Jaques | Surya Dagempude | Bill Robertson, Richard Cowtan
RED | GREEN | GREEN | RED | GREEN | GREEN | AMBER | AMBER | AMBER | RED | GREEN | GREEN | GREEN | GREEN
GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | AMBER
GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
RED | GREEN | GREEN | AMBER | GREEN | GREEN | AMBER | AMBER | AMBER | RED | GREEN | GREEN | GREEN | GREEN
RED | AMBER | GREEN | AMBER | GREEN | GREEN | AMBER | GREEN | RED | AMBER | AMBER | GREEN | GREEN | AMBER
GREEN | GREEN | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
GREEN | AMBER | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | AMBER | GREEN | GREEN | GREEN | GREEN | AMBER

## Workstream Status Report
Team Progress Report - Service Design and Transition
Team Lead: | Nick Coburn
Period Ending: | 7th September 2012
Workstream Status | [8 empty] | This Period | Last Period
Overall Status | Initial draft of Service Transiiton in place for EAX. Timeline for EAX is achievable but further work to be done to validate support approach. This should be done by 5th October and the status should move to Green. | [7 empty] | AMBER | AMBER
Stakeholders | [8 empty] | GREEN | GREEN
Schedule | See overall status | [7 empty] | AMBER | AMBER
Team | TM will not be available until December. Nick Coburn to remain interim TM | [7 empty] | AMBER | GREEN
Scope | [8 empty] | GREEN | GREEN
Key Achievements This Week | Recruitment of Richard Brown confirmed - start date 1st December | [9 empty] | `
Key Activities next week | Continue to work through SP governance items - follow up on progress made by Susie Eastham and Scott Strange Focus on Service Design - to complete by 5th October
Progress Against Plan (those in progress / due to start in the next 6-8 weeks). Note: Activities should be derived from L2 while Deliverables from L3
Project Plan Ref. | Milestone or Deliverable Name | Progress (%) | Baseline Start | Baseline Finish | Actual Start | Actual Finish | Activity/ Deliverable | RAG | Comments |  | Resource
| Start Architecture and Design | 100% | 2012-09-03 08:00 | 2012-09-03 08:00 | NA | NA | Enterprise Plan Milestone | COMPLETE |  |  | -
| PRIMARY DELIVERABLE: TOM single page graphical representation | 20% | 2012-10-26 08:00 | 2012-10-26 08:00 | NA | NA | Key Specific Program Deliverable | GREEN |  |  | -
| PRIMARY DELIVERABLE: Detailed Word document (structure, roles, capacity, capability etc) | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | NA | NA | Key Specific Program Deliverable | GREEN |  |  | -
| PRIMARY DELIVERABLE: IT change plan | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | NA | NA | Key Specific Program Deliverable | GREEN |  |  | Oleksiy
| PRIMARY DELIVERABLE: IT comms plan | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | NA | NA | Key Specific Program Deliverable | GREEN |  |  | Hasan
| PRIMARY DELIVERABLE: Scope of service matrix | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | NA | NA | Key Specific Program Deliverable | GREEN |  |  | Hasan
| End Architecture and Design | 5% | 2012-10-05 08:00 | 2012-10-05 08:00 | NA | NA | Enterprise Plan Milestone | GREEN |  |  | Pat
| Start Build | 0% | 2012-10-01 08:00 | 2012-10-01 08:00 | NA | NA | Enterprise Plan Milestone | GREEN |  |  | Melissa/Mike/Pat
| PRIMARY DELIVERABLE: Detailed Service Transition plan | 0% | 2012-10-12 17:00 | 2012-10-12 17:00 | NA | NA | Key Specific Program Deliverable | GREEN |  |  | Hasan
| Detailed Service Transition plan for EAX confirmed | 0% | 2012-10-12 17:00 | 2012-10-12 17:00 | NA | NA | Specific Program Milestone | GREEN |  |  | Melissa/Mike
| PRIMARY DELIVERABLE: Staffing plan based on R&R definition from service design | 0% | 2012-10-29 17:00 | 2012-10-29 17:00 | NA | NA | Key Specific Program Deliverable | GREEN |  |  | -
| Detailed staffing plan confirmed | 0% | 2012-10-29 17:00 | 2012-10-29 17:00 | NA | NA | Specific Program Milestone | GREEN |  |  | Yi Wen
| PRIMARY DELIVERABLE: Knowledge proliferation plans | 0% | 2012-11-02 17:00 | 2012-11-02 17:00 | NA | NA | Key Specific Program Deliverable | GREEN |  |  | Bijal
| Confirm knowledge proliferation has been completed successfully | 0% | 2012-12-21 17:00 | 2012-12-21 17:00 | NA | NA | Specific Program Milestone | GREEN |  |  | Dev/YiWen/Bijal
| PRIMARY DELIVERABLE: Updated process documentation | 0% | 2012-11-20 17:00 | 2012-11-20 17:00 | NA | NA | Key Specific Program Deliverable | GREEN |  |  | -
| Process training completed | 0% | 2012-12-20 17:00 | 2012-12-20 17:00 | NA | NA | Specific Program Milestone | GREEN |  |  | Melissa/Mike
| PRIMARY DELIVERABLE: Update Operations Manual v0.3.0 - Deployment Test | 0% | 2012-11-15 17:00 | 2012-11-15 17:00 | NA | NA | Key Specific Program Deliverable | GREEN |  |  | Melissa/Mike
| PRIMARY DELIVERABLE: ServiceNow documentation | 0% | 2012-11-15 17:00 | 2012-11-15 17:00 | NA | NA | Key Specific Program Deliverable | GREEN |  |  | Melissa/Mike
| Product training completed | 0% | 2012-11-29 17:00 | 2012-11-29 17:00 | NA | NA | Specific Program Milestone | GREEN |  |  | Melissa/Mike
| End Build | 0% | 2013-06-03 08:00 | 2013-06-03 08:00 | NA | NA | Enterprise Plan Milestone | GREEN |  |  | Melissa/Mike
| Start Test | 0% | 2012-08-06 08:00 | 2012-08-06 08:00 | NA | NA | Enterprise Plan Milestone | GREEN |  |  | -
| PRIMARY DELIVERABLE: Service Readiness Test approach | 0% | 2012-09-28 17:00 | 2012-09-28 17:00 | NA | NA | Key Specific Program Deliverable | GREEN |  |  | Yi Wen
| PRIMARY DELIVERABLE: Operational Acceptance Test approach | 0% | 2012-09-28 17:00 | 2012-09-28 17:00 | NA | NA | Key Specific Program Deliverable | GREEN |  |  | Bijal
| End Test | 0% | 2012-12-14 08:00 | 2012-12-14 08:00 | NA | NA | Enterprise Plan Milestone | GREEN |  |  | Dev/YiWen/Venu
| Start Deploy | 0% | 2012-08-27 08:00 | 2012-08-27 08:00 | NA | NA | Enterprise Plan Milestone | GREEN |  |  | -
| End Deploy | 0% | 2013-06-28 08:00 | 2013-06-28 08:00 | NA | NA | Enterprise Plan Milestone | GREEN |  |  | Pat
| Start Run | 0% | 2013-02-15 08:00 | 2013-02-15 08:00 | NA | NA | Enterprise Plan Milestone | GREEN |  |  | -
| Go / No-Go decision | 0% | 2013-01-11 08:00 | 2013-01-11 08:00 | NA | NA | Specific Program Milestone | GREEN |  |  | Shane Delaney
| Early Life Support Completed | 0% | 2013-02-15 17:00 | 2013-02-15 17:00 | NA | NA | Specific Program Milestone | GREEN |  |  | Dev/Shane Delaney
| Go / no-go decision | 0% | 2013-02-15 08:00 | 2013-02-15 08:00 | NA | NA | Specific Program Milestone | GREEN |  |  | Hasan/Lee
| Stabilisation completed | 0% | 2013-03-15 08:00 | 2013-03-15 08:00 | NA | NA | Specific Program Milestone | GREEN |  |  | Hasan
| PRIMARY DELIVERABLE: Confirm Operations Manual Documentation Complete | 0% | 2013-05-08 08:00 | 2013-05-08 08:00 | NA | NA | Generic SDA based Deliverable | GREEN |  |  | Hasan
| BAU achieved | 0% | 2013-03-15 17:00 | 2013-03-15 17:00 | NA | NA | Specific Program Milestone | GREEN |  |  | Lee
| End Run | 0% | 2013-03-15 08:00 | 2013-03-15 08:00 | NA | NA | Enterprise Plan Milestone | GREEN |  |  | Lee
| Transition completed | 0% | 2013-03-15 08:00 | 2013-03-15 08:00 | NA | NA | Specific Program Milestone | GREEN
External Dependencies
Task UID (in MSP) | Dependency Name |  | RAG Status | Entity | Owner |  | Due Date | Actions
Issues
RAID ID | Issue Title |  | Involved | Next Review | Assigned To | Impact | Affected | Actions
123 | Governance Queries/Issues currently have no owner to answer them | [6 empty] | RESOLVED
Risks
RAID ID | Risk Title |  | Probablilty | Priority | Assigned To | Impact | Affected | Actions

## Sheet1
Start Architecture and Design | 0% | 2012-09-03 08:00 | 2012-09-03 08:00 | Enterprise Plan Milestone
PRIMARY DELIVERABLE: TOM single page graphical representation | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | Key Specific Program Deliverable
PRIMARY DELIVERABLE: Detailed Word document (structure, roles, capacity, capability etc) | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | Key Specific Program Deliverable
PRIMARY DELIVERABLE: IT change plan | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | Key Specific Program Deliverable
PRIMARY DELIVERABLE: IT comms plan | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | Key Specific Program Deliverable
PRIMARY DELIVERABLE: Scope of service matrix | 0% | 2012-10-26 08:00 | 2012-10-26 08:00 | Key Specific Program Deliverable
End Architecture and Design | 0% | 2012-10-05 08:00 | 2012-10-05 08:00 | Enterprise Plan Milestone
Start Build | 0% | 2012-10-01 08:00 | 2012-10-01 08:00 | Enterprise Plan Milestone
PRIMARY DELIVERABLE: Detailed Service Transition plan | 0% | 2012-10-12 17:00 | 2012-10-12 17:00 | Key Specific Program Deliverable
Detailed Service Transition plan for EAX confirmed | 0% | 2012-10-12 17:00 | 2012-10-12 17:00 | Specific Program Milestone
PRIMARY DELIVERABLE: Staffing plan based on R&R definition from service design | 0% | 2012-10-29 17:00 | 2012-10-29 17:00 | Key Specific Program Deliverable
Detailed staffing plan confirmed | 0% | 2012-10-29 17:00 | 2012-10-29 17:00 | Specific Program Milestone
PRIMARY DELIVERABLE: Knowledge proliferation plans | 0% | 2012-11-02 17:00 | 2012-11-02 17:00 | Key Specific Program Deliverable
Confirm knowledge proliferation has been completed successfully | 0% | 2012-12-21 17:00 | 2012-12-21 17:00 | Specific Program Milestone
PRIMARY DELIVERABLE: Updated process documentation | 0% | 2012-11-20 17:00 | 2012-11-20 17:00 | Key Specific Program Deliverable
Process training completed | 0% | 2012-12-20 17:00 | 2012-12-20 17:00 | Specific Program Milestone
PRIMARY DELIVERABLE: Update Operations Manual v0.3.0 - Deployment Test | 0% | 2012-11-15 17:00 | 2012-11-15 17:00 | Key Specific Program Deliverable
PRIMARY DELIVERABLE: ServiceNow documentation | 0% | 2012-11-15 17:00 | 2012-11-15 17:00 | Key Specific Program Deliverable
Product training completed | 0% | 2012-11-29 17:00 | 2012-11-29 17:00 | Specific Program Milestone
End Build | 0% | 2013-06-03 08:00 | 2013-06-03 08:00 | Enterprise Plan Milestone
Start Test | 0% | 2012-08-06 08:00 | 2012-08-06 08:00 | Enterprise Plan Milestone
PRIMARY DELIVERABLE: Service Readiness Test approach | 0% | 2012-09-28 17:00 | 2012-09-28 17:00 | Key Specific Program Deliverable
PRIMARY DELIVERABLE: Operational Acceptance Test approach | 0% | 2012-09-28 17:00 | 2012-09-28 17:00 | Key Specific Program Deliverable
End Test | 0% | 2012-12-14 08:00 | 2012-12-14 08:00 | Enterprise Plan Milestone
Start Deploy | 0% | 2012-08-27 08:00 | 2012-08-27 08:00 | Enterprise Plan Milestone
End Deploy | 0% | 2013-06-28 08:00 | 2013-06-28 08:00 | Enterprise Plan Milestone
Start Run | 0% | 2013-02-15 08:00 | 2013-02-15 08:00 | Enterprise Plan Milestone
Go / No-Go decision | 0% | 2013-01-11 08:00 | 2013-01-11 08:00 | Specific Program Milestone
Early Life Support Completed | 0% | 2013-02-15 17:00 | 2013-02-15 17:00 | Specific Program Milestone
Go / no-go decision | 0% | 2013-02-15 08:00 | 2013-02-15 08:00 | Specific Program Milestone
Stabilisation completed | 0% | 2013-03-15 08:00 | 2013-03-15 08:00 | Specific Program Milestone
PRIMARY DELIVERABLE: Confirm Operations Manual Documentation Complete | 0% | 2013-05-08 08:00 | 2013-05-08 08:00 | Generic SDA based Deliverable
BAU achieved | 0% | 2013-03-15 17:00 | 2013-03-15 17:00 | Specific Program Milestone
End Run | 0% | 2013-03-15 08:00 | 2013-03-15 08:00 | Enterprise Plan Milestone
Transition completed | 0% | 2013-03-15 08:00 | 2013-03-15 08:00 | Specific Program Milestone