## Workstream Status Report
Team Progress Report - System Test (QA)
Team Lead: | Greg Van Valkenburgh
Period Ending: | 2012-09-07
Workstream Status | [8 empty] | This Period | Last Period
Overall Status | • Test Plan in place, GHRDB/AD testing assistance provided, SharePoint 2013 testing begun, test case preparation underway • Detail Scope is not yet baselined for EAX and R1; additional work related to TAP testing and delays to upstream activities impacting downstream work | [7 empty] | AMBER | AMBER
Stakeholders | [8 empty] | GREEN | GREEN
Schedule | • Additional work related to TAP testing and delays to upstream activities impacting other work (I146); R1 Provisioning thread will likely need to be replanned/scheduled • "TAP" SP2013 testing remains On Hold due to EAX delivery schedule priorities (I152); SP2013 configuration and therfore testing could be picked up in a couple weeks, or will need to reprioritize over EAX schedule | [7 empty] | AMBER | GREEN
Team | [8 empty] | GREEN | GREEN
Scope | • Detailed scope for EAX & R1 is not yet baselined -- the prevailing philosophy and principle of OOB with no customization other than simple UI and the (more extensive) R1 site provisioning needs to be confirmed. | [7 empty] | AMBER | AMBER
Key Achievements This Week | • TAP Testing ON HOLD -- first due to environment rebuild required (caused by language pack uninstall), then by competing priority with EAX actvities • Test case preparation on Manual Provisioning (including BA review), Search Center / Admin, Team Site | [9 empty] | `
Key Activities next week | • TAP Testing -- TBD • Continue working on Integration Testing, GCL 5, & O365 Validation planning. {If time allows} • Test case preparation on Search Center / Admin, Team Site, OOB Decommissioning • System Test Readiness Review confirmation, and begin System Test for Manual Provisioning
Progress Against Plan (those in progress / due to start in the next 6-8 weeks). Note: Activities should be derived from L2 while Deliverables from L3
Project Plan Ref. | Milestone or Deliverable Name | Progress (%) | Baseline Start | Baseline Finish | Actual Start | Actual Finish | Activity/ Deliverable | RAG | Comments
| Test Preparation & Planning |  | 2012-07-02 | 2012-09-17 | 2012-07-02 |  |  | GREEN
VT-1.1 | Test Plan Draft | 100% | 2012-07-09 | 2012-07-13 | 2012-07-09 | 2012-07-13 | Test Plan | COMPLETE
VT-1.1 | Test Plan Draft 2 | 100% | 2012-07-16 | 2012-07-23 | 2012-07-16 | 2012-07-23 | Test Plan | COMPLETE
VT-1.1 | Test Plan Approval | 100% | 2012-07-24 | 2012-08-17 | 2012-07-24 | 2012-08-17 | Test Plan Approval | COMPLETE
VT-1.2 | Perform static testing | 35% | 2012-07-02 | 2012-09-25 | 2012-08-14 |  | Static Testing Results | GREEN
VT-1.3 | Prepare for system testing | [5 empty] | Test Cases | AMBER
| GHRDB / AD Testing | 100% | 2012-07-02 | 2012-07-02 | 2012-06-18 | 2012-07-02 | Test Cases | COMPLETE
| Profiles (Sync & data contents, View, Edit) - EAX / R1 | 100% | 2012-08-27 | 2012-08-31 | 2012-08-27 | 2012-08-31 | Test Cases | AMBER | Requirements and design not yet complete/approved. |  | *
| Team Sites - EAX/R1 | 75% | 2012-08-31 | 2012-09-10 | 2012-08-31 |  | Test Cases | AMBER | Requirements and design not yet complete/approved.
| Manual Provisioning - EAX | 100% | 2012-09-04 | 2012-09-07 | 2012-09-04 | 2012-09-07 | Test Cases | AMBER | Requirements and design not yet complete/approved.
| OOB Decommissioning - EAX / R1 | 0% | 2012-09-04 | 2012-09-28 |  |  | Test Cases | GREEN
| Search - Search Center Admin - EAX / R1 | 20% | 2012-08-27 | 2012-09-14 |  |  | Test Cases | AMBER | Requirements and design not yet complete/approved. |  | *
| Search - People Search - EAX / R1 | 0% | 2012-09-17 | 2012-09-21 |  |  | Test Cases | GREEN
| Search - Team Sites - EAX / R1 | 0% | 2012-09-24 | 2012-09-28 |  |  | Test Cases | GREEN
| Integration/Regression Test - EAX/R1 | 10% | 2012-07-30 | 2012-09-28 | 2012-08-06 |  | Test Cases | GREEN
| Site Provisioning - R1 | 0% | 2012-09-04 | 2012-09-28 |  |  | Test Cases | RED | Impacted by TAP Testing effort. Requirements and design not yet complete/approved. Will need to be rescheduled.
| Landing Page - EAX / R1 | 0% | 2012-09-17 | 2012-09-21 |  |  | Test Cases | GREEN |  |  | *
| O365 Service Validation - EAX | 95% | 2012-07-30 | 2012-09-28 | 2012-08-06 |  | Test Cases | GREEN | Need to verify/add e-mail integration.
| GCL 4/5 Testing | 5% | 2012-07-30 | 2012-09-28 | 2012-08-06 |  | Test Cases | GREEN
| Non-Functional Requirements Testing | 0% | 2012-08-10 | 2012-09-28 |  |  | Test Cases | AMBER | Not yet started. Dependent upon collection of NFRs. Will need to be rescheduled.
| UI Testing - EAX/R1 | 100% | 2012-07-30 | 2012-08-15 | 2012-07-30 | 2012-08-13 | Test Cases | COMPLETE
| TAP Program Testing | [6 empty] | RED | see lines 27, 29, 30, and Issue 152 on priority vs. EAX
| Initiation | 100% | 2012-07-20 | 2012-08-10 | 2012-07-20 | 2012-08-10 | Activity | COMPLETE
| Environment | 100% | 2012-07-20 | 2012-08-10 | 2012-07-20 | 2012-08-10 | Activity | COMPLETE
| Update Scenarios if/as needed | 100% | 2012-08-06 | 2012-08-08 | 2012-08-06 | 2012-08-16 | Test Cases | COMPLETE
| Configure TAP Testing environment for Test | 80% | 2012-08-09 | 2012-08-13 | 2012-08-09 | TBD | Activity | RED | Environment had to be reconfigured due to technical issues caused by Language Pack problem
| Prepare for testing | 100% | 2012-08-07 | 2012-08-15 | 2012-08-07 | 2012-08-14 | Activity | GREEN
| Execute Testing | 60% | 2012-08-15 | 2012-08-30 | 2012-08-14 | TBD | Test Execution | RED | Blockers (e.g., Search, Multi-language, MMS) identified in TAP defect list, and need analyzed/addressed
| Report Results | 50% | 2012-08-15 | 2012-08-30 | 2012-08-15 | TBD | Test Results | RED | Blockers (e.g., Search, Multi-language, MMS) identified in TAP defect list, and need analyzed/addressed
| Pilot Test | 100% | 2012-08-21 | 2012-08-30 | 2012-08-15 | 2012-08-27 | Pilot Test | GREEN | Participation level is not significant; so ended this
GHRDB / AD Testing
VT-1.4 | Conduct test readiness review | 100% | 2012-07-02 | 2012-07-02 | 2012-06-18 | 2012-07-02 | Test Readiness | COMPLETE
VT-2.1 | Perform application testing | 75% | 2012-07-02 | 2012-09-18 | 2012-07-02 |  | Test Results | GREEN
EAX Test
VT-1.4 | Conduct test readiness review | 0% | 2012-09-10 | 2012-09-10 |  |  | Test Readiness | GREEN | Scheduled for 9/11
V2.1 | Perform system testing
| Profiles (Sync & data contents, View, Edit) - EAX / R1 | 0% | 2012-09-14 | 2012-11-01 |  |  | Test Execution | GREEN
| Team Sites - EAX/R1 | 0% | 2012-10-05 | 2012-11-02 |  |  | Test Execution | GREEN
| Manual Provisioning - EAX | 0% | 2012-09-10 | 2012-10-05 |  |  | Test Execution | GREEN
| OOB Decommissioning - EAX / R1 | 0% | 2012-10-01 | 2012-10-26 |  |  | Test Execution | GREEN
| Search - Search Center - EAX / R1 | 0% | 2012-09-17 | 2012-09-21 |  |  | Test Execution | GREEN
| Search - People Search - EAX / R1 | 0% | 2012-09-24 | 2012-09-28 |  |  | Test Execution | GREEN
| Search - Team Sites - EAX / R1 | 0% | 2012-10-01 | 2012-11-02 |  |  | Test Execution | GREEN
| Landing Page - EAX / R1 | 0% | 2012-10-05 | 2012-10-25 |  |  | Test Execution | GREEN
External Dependencies
Task UID (in MSP) | Dependency Name |  | RAG Status | Entity | Owner |  | Due Date | Actions
External Program Dependencies | IAM - Updated Active Directory in eydev.net environment (new attributes, synchronization, authentication) |  | GREEN | IAM | Ted Balfour |  | 2012-07-18 08:00
| IAM - Updated Active Directory in eyqa.net environment (new attributes, synchronization, authentication) |  | GREEN | IAM | Ted Balfour |  | 2012-07-18 08:00
| IAM - Updated Active Directory in eyua.net environment (new attributes, synchronization, authentication) |  | GREEN | IAM | Ted Balfour |  | 2012-11-19 08:00
| IAM - Define Strategy & Design Concept for Special Considerations on environments in UA domain |  | RED | IAM | Ted Balfour |  | 2012-08-10 | See I153 on synching from production AD
| IAM - Apply Strategy & Design Concept for Special Considerations on environments in UA domain |  | AMBER | IAM | Ted Balfour |  | 2012-01-11 | See above
| GCL 5 - Test workstations for onshore and offshore staff |  | GREEN | GCL-5 | GCL-5 Lead |  | 28/9/2012 | Request is in the queue
Internal Work Stream(s) | SharePoint Environments - CIDE#2 SP2010 faux cloud env ready |  | GREEN | SharePoint Environments | Joshua Jackson |  | 2012-08-09 08:00
| SharePoint Environments - QA#1 SP2010 faux cloud env ready |  | GREEN | SharePoint Environments | Joshua Jackson |  | 2012-07-30 08:00
| SharePoint Environments - CIDE#3 SP2013 Preview faux cloud env ready |  | GREEN | SharePoint Environments | Joshua Jackson |  | 2012-08-08 08:00
| SharePoint Environments - CIDE#4 SP2013 Preview Simulated cloud env ready |  | GREEN | SharePoint Environments | Joshua Jackson |  | 2012-11-20 08:00
| SharePoint Environments - CIDE#5 SP2013 RTM Rebuild Simulated cloud env ready |  | GREEN | SharePoint Environments | Joshua Jackson |  | 2013-02-04 08:00
| SharePoint Environments - QA#3 SP2013 Preview Simulated cloud env ready |  | GREEN | SharePoint Environments | Joshua Jackson |  | 2012-11-13 08:00
| SharePoint Environments - QA#5 SP2013 Preview Simulated cloud env ready |  | GREEN | SharePoint Environments | Joshua Jackson |  | 2013-02-11 08:00
| SharePoint Environments - UA#1 SP2010 faux cloud env ready |  | GREEN | SharePoint Environments | Joshua Jackson |  | 2012-09-14 08:00
| SharePoint Environments - UA#5 SP2013 RTM Simulated cloud env ready |  | GREEN | SharePoint Environments | Joshua Jackson |  | 2013-02-11 08:00
| SharePoint Environments - Managed Metadata and content types loaded into Test environment (EAX) |  | GREEN | SharePoint Environments | Joshua Jackson |  | 2012-09-10 08:00
| SharePoint Environments - O365 Readiness on SharePoint 2010 |  | GREEN | SharePoint Environments | Joshua Jackson |  | 2012-11-12 08:00
| SharePoint Environments - O365 Readiness on SharePoint 2013 |  | GREEN | SharePoint Environments | Joshua Jackson |  | 2013-04-01 08:00
| Lync - Providing real time presence and communication - testl environment |  | RED | Lync | Neil Sahdev |  | 2012-11-05 08:00 | Dependency needs to be confirmed with other project. Lync schedule not yet baselined, Lync integration testing needs to be rescheduled to a later time.
| Outlook - email integration - test environment |  | AMBER | Outlook | Rewa Bowji |  | 2012-11-05 08:00 | Dependency needs to be confirmed with other project.
Issues
RAID ID | Issue Title |  | Involved | Next Review | Assigned To | Impact | Affected | Actions
153 | SP UAT approach will need to change due to InfoSec policy on Prod data |  |  | 2012-09-20 | Greg Van Valkenburgh | 2) Medium | Scope; Schedule; Quality; Cost | 06-Nov: (GJV) logged
152 | TAP SP2013 testing remains On Hold due to EAX delivery schedule priorities |  | Greg Van Valkenburgh | 2012-09-20 | Andy Ioannou | 0) Under review | Schedule, Quality | 06-Nov: (GJV) logged
146 | Additional work related to TAP testing and delays to upstream activities impacting other work |  | Greg Van Valkenburgh | 2012-09-17 | Andy Ioannou | 0) Under review | Scope; Schedule; Cost | 24-Aug (GJV): TAP testing has been good learning exercise, and has helped test some items earlier than we would have otherwise. Impacts (in combination with the requirements/designs not yet being complete): - Test preparation - have rescheduled People test preparation to begin 8/27, Landing Page to 9/21, Search to 8/27, R1 Provisioning still needs to be fit in & rescheduled (I still need to work this) - Test Execution - reduced ability to perform testing on the 2013 platform prior to EAX deployment, as we essentially only have partial September and October for EAX SIT now, and this is agressive just to test on 2010. (This is mitigated somewhat by the work done in TAP testing.) I expect this to be workable. 22-Aug (AI): Greg, please provide detail of what is impacted and the 'so what' of this to overall testing schedule? I.e is the critical path impacted by the effort invested in TAP testing? Also, if you assign something to someone to me please ensure you are clear about what it is you expect me to do. Logging the risk/issue and assigning to someone else doesn't necessarily mean you no longer own it. 17-Aug: (GJV) logged​
145 | Need confirmation on expected go-live date for EAX |  |  |  | Andy Ioannou |  | Schedule | 30-Aug: (GJV) Closing per AI discussion in 27-Aug weekly status call. Andy indicated this issue will be addressed: - temporary VPN can be used during Customer Validation of Service (CVS), so we don't have hard dependency on the ultimate connectivity solution - the CVS duration can be compressed to better align the dates 22-Aug Update 2 (AI): discussed with Klara - no technical reason why biz could not access SP services, more a question of limiting number of concurrent users on platform to mitigate risk of impact to production services (as temp VPN will be hosted in prod domain). Action with Klara to confirm recommended user threshold w/c 3-Sep. Andy indicated this issue will be addressed: - temporary VPN can be used during Customer Validation of Service (CVS), so we don't have hard dependency on the ultimate connectivity solution - the CVS duration can be compressed to better align the dates 22-Aug Update 1 (AI): this issue is linked to Issue 107 (O365 SR date in Nov and proposal to implement temporary VPN in order to preserve OE project schedule). This has clear implications on the EAX go live date in that the temporary VPN 'solution' for OE means that Collaboration's business users will not be able to access the EAX Cloud Services.​ EAX is therefore impacted until such time that the permanent MPLS (link) is available (forecasted early/mid Jan). Need to understand why users unable to access services on temp VPN. In addition, if EAX is indeed dependent upon perm link, need to determine lead time from this point in introducing live service to business. 17-Aug: (GJV) logged​
122 | A person may have multiple Sharepoint profiles assigned to them |  | Bernd Hessbruegge | 2012-07-23 | Nicola Cooper | 2) Medium | Scope; Schedule; Cost | 3 Aug (NC) : As this affects so few staff in the organisation it is our request that the business recognise this is not an issue that should be fixed by numerous disparate solutions in target applications. Rather it shoud be resolved at source in the GHRDB/AD by a Strategic Solution in Global HR Provisioning. Stats : Approx 160,000 GHRDB Records of those 8900 have non-unique GUI, assuming that each represents a duplication of 2 (which we know is not true but gives us the worst case result) there are 4,450 staff which will have this issue. 23 July: (NC) This affects 2.5% of the organisation, and results also in duplicate Outlook and Lync accounts. NC to setup a discussion with internal Collaboration to produce a single slide to concisely describe the issue and reason we move to accept this issue, but ask the business to take the action on their side to rectify it. 23 July: (NC) Converted Risk into Issue 6-July: BvG has asked Norm L and Mitch P to povide definitive input from MSFT that there is no viable means to work around this. Also have escalated to IAM Program (Ted Balfour and Ant Harper).
92 | We don't know how to get the photo into AD. We need to understand the official source of the Photo Upload |  | Mitchel Prince; Brett van Gelder; | 2012-07-23 | Norm Lambert | 2) Medium | Scope; Schedule; Quality | 23 July: (BvG) Updated with full details of this issue. Re-assigning back to Norm to continue to work this with Mitch and the O365 team. 3 July : (NC) Official update provided by O365 via Norm L "This is outlined as a known issue for the upgrade of O365" For Collaboration EAX this will not impact as we will not have upgraded for this release. For Release 1 if the issue has not been fixed by O365 or a work around/mitigation provided we will be impacted. NL to continue to provide any updates as they come and consider or mitigation /workaround
41 | Unclear on specifications provided for site decommissioning in O365 |  | Norm Lambert | 2012-06-29 | Mike Nicholas | 2) Medium |  | 23 Jul:(NC) After engagement with the BPO for the Site Decom Kick Off the SharePoint OOB is deemed unacceptable due to the following reasons: 1. Contacts Site Collection Administrator only OOB, therefore if this role is not someone in the business then notification to this group would not be possible. 2. Usage based reporting was preferreable over duration based reporting. Next Steps are to investigate what MS does .. 1) Reporting 2) Customised Solution
Risks
RAID ID | Risk Title |  | Probability | Priority | Assigned To | Impact | Affected | Actions
227 | Schedule and cost risk if project is not able to get "official approvals" for detail baselines (e.g., requirements & designs) on a timely basis |  | 3) High | 9 | Jeremy Brown | 3) High | Scope; Schedule, Quality, Cost | 31 Aug (AI): have re-opened as this is our verhicle for monitoring the risk of schedule delay owing to ongoing business challenges to scope thorugh the requirements acknowledgment process. 29 Aug (NC) : Bob Reiner has formally confirmed agreement to the Business Acknowldgement of SharePoint EAX Scope Process, I am therefore going to defer this risk until Release 1 Requirements Scope requires discussion and agreement 16 Aug (NC): As this has not been landed, I have given instruction to request Review in a structure way but stopped short of implementing a defined process for return receipt of the review, until Jeremy has completed the actions outline below as next steps. PLEASE NOTE : As this is only Review not agreement/sign off/confirmation we require formal dispensation from the Program Sponsors that this deploy should indeed go ahead. 14 Aug (NC) : We are about to start publising the EAX Requirements Specifications, and in anticipation a process for capturing the review status by both Key Stakeholders and Collaboration Programme Team Members is required. I have drafted a deck (attached) that has been reviewed by both Andy I and Jeremy B and at this point is agreed as a draft for circulation now with the wider community. There is still the outstanding action around R1 as outlined below, however to remain against schedule for EAX we look to progress review of EAX, to ensure the details (fields, config, business rules, process etc) are reviewed by those BPO's that submitted them prior to them entering design and build. Collaboration Review Process v0.2.pptx Next Action with Jeremy 1) Define the BPO Key Stakeholer Reviewers 2) Confirm communication of this process 9 Aug (AI): Risk is associated with business perception of loss of value in current R1 scope against previous plan's scope (pre GTG) with far higher budget. Consequently we are at risk of business not buying into requirements as its own and rather those imposed upon it by IT through its budget constraints. 8 Aug (JB): Given that no requirements have been officially signed off since the start of the Collaboration program and that the scope of R1 is at variance to the original "expected" scope it will now be challenging to consider "sign off" as endorsement of the new baseline requirements. We now need to establish a go forward position based upon the R1 scope that re-engages the BPOs on the basis of what can be achieved within the fixed limitations of the Collaboration program. Proposed actions: Create a clear concise document outlining the specification of R1 (Nicola Cooper) Socialize this document (set up review sessions) with all the BPOs to gather feedback (NC) Continue to develop against this "baseline" (NC) All suggested changes/unfufilled requirements are prioritized into a 2nd release after R1 (AI)
226 | Scope & Schedule risk if program does not adhere to principle of OOB with no customization (other than baseline scope of simple UI and the R1 site provisioning) |  | 0) Under review | 0 | Andy Ioannou | 0) Under review | Scope, Schedule, Cost | 20 Aug (NC): As this risk is a validated in Assumption 233 we will manage any potential Scope and Scheduled change through CR. I am therefore closing this risk. 4 Aug (NC) : This risk may realise, SharePoint Site Decom requested by business for R1 to be reviewed and consider non-OOB offering. This will require CR​ as will impact scope and may impact schedule and cost. 30-Jul: (GJV) logged​
178 | UAT approach/environment need rework given SP dependency on AD and IAM/ID Sync |  | 2) Medium | 0 | Gregory Van Valkenburgh | 2) Medium | Scope; Schedule; Quality; Cost | 09-Aug: (GJV) Met with IAM team, and agreed overall approach, essentially as per 06-Jul log entry below, therefore marking as mitigated and closed. Potential performance and infosec considerations to be followed up as details are worked through. 27-Jul: (GJV) Discussed on IAM dependency call to revisit notes below with IAM team w/e 10-Aug 6-Jul: logged as risk per NC from Issue 47​ (now withdrawn). Need to more fully understand the ID Sync project timing on AD data population (currently being worked by ID Sync team), but here's potential approach/plan and is current assumption: - SP UAT environment syncs against production AD for People Profiles (this may need EA and InfoSec approval) - SP UAT relies on the trust to the production domain, e.g., so that any user could participate in UAT, using their normal login credentials and AD data. - SP UAT relies on whatever production AD data is in place at that time. There are few hard dependenies on specific data attributes given the scope of EAX/R1. - Since SP is to be updating the AD (e.g., photos) for EAX, the UAT process and environment design will need to make sure the best possible test is executed, but that production AD is not updated. (This likely may require the picture update test be executed outside of UAT, and the results verified and accepted in another environment -- e.g., qa)
161 | No Disaster Recovery solution for on-prem SharePoint. |  | 0) Under review | 0 | Andy Ioannou | 0) Under review |  | 20-Aug (AI): Confirm wiht Brett with whom we need to validate this approach. 13-Aug (AI): Reviewed DR approach for EAX and R1 with Brian and Brett and documented Collaboration team's proposals including mitigating repsonse in event of DR scenario: http://sp.ey.net/msibm/MC%20Program/SharePoint/03%20-%20Quality%20Assurance/DR%20Testing/Collaboration%20EAX%20and%20R1%20Disaster%20Recovery%20Approach%20V1.0.pptx Confirm with Brett on return from holiday whether any formal dispensation/further review required in order for proposal to be formally accepted. 30-Jul: (GV) Assigning to PM for disposition 27-Jul: (GJV) added note below into Test Plan document 20-July: "Collaboration EAX and R1 Disaster Recovery Approach V1.0.pptx" deck prepared by Andy I after meeting with Brett vG, Brian R on 19 Jul. Conclusions listed in that deck: ►No On-Prem DR requirement for EAX since all services hosted in O365 and High Availability and Disaster Recovery managed via SLAs with MSFT ►For Release 1, M&C will plan a HA test against failure scenarios limited to On-Prem server outages within the Frankfurt data centre ►M&C is not planning a DR test against a data centre outage scenario given: ►No DR site to plan failover test against ►Cost of implementing a DR site in Release 1 timeframe ►Low level of business impact associated with loss of On-Prem services in Release 1 Greg V V to incorporate into Test Strategy; reassigned to him\
155 | EY will not be able to performance test the cloud |  | 0) Under review | 0 | Dave Fraser | 0) Under review |  | 25 July : Microsoft has a capability to build a simulated environment to do performance testing, but does not feel this will provide much value. Recommendation is to evaluate the network connectivity versus performance test of the O-365 environment. 11 July : Unfortunately performance testing is not within the guidelines of our current contract. Our contract is focused on financially backed SLA's. MS recommendation is not to do performance test, the higher risk is throughput to the data centers. I have asked Howard Jones to get the cost of doing a test. I should have status by the next RAID review.
149 | By starting SP15 production environment before the new RTM installation bits are verified in QA/UA poses the risk that some configuration issues may be identified first in Production. |  | 0) Under review | 0 | Gregory Van Valkenburgh | 0) Under review | Schedule, Quality, Cost | 30-Aug: (GJV) Marked as accepted/deferred per below 13-Aug update log. To restate/summarize -- L2 plan shows production env build begins in Jan -- L2 plan shows earliest QA testing on RTM to be 18-Feb, @6 weeks after production env build begins. 13-Aug:Risk to the schedule is accepted due to contingency currently added in latest plans. Norm B, Norm L and Josh to align on mitigation for infrastructure 3rd July : (NC) Andy to update the mitigation description after discussion at Collaboration weekly RAID Call, Andy to then align with Norm L on way forward. 27-Jun: Norm, can you look into this and clarify what the risk is (not clear to me), impact and proposed mitigating action plan? If you need me to intervene/escalate, I need to know ​what action you expect me to take.
43 | Unknowns for building out the Simulated Cloud in Frankfurt could cause a delay to the CIDE, QA, and UA environment availability |  | 3) High | 9 | Joshua Jackson | 3) High | Schedule; Quality | 8-Aug: Joshua and Norm meet with Andy to review the tasks needed for building out the Simulated Cloud in Frankfurt and ServiceNow process. Joshua requested additional help from Andy. 1-Aug: Follow-up meeting with Gil Levit. Gil has infromed us that we are "having similar issues as the O365 Exchange project" and that he is escalating. 18-Jul: Josh met with Shaun Bradley and Gil Levit; follow-up meeting to be scheduled for next week. Change request tickets being submitted, but delivery dates not available yet. Required date aligned with project PoaP 09-Jul: Josh has meeting tomorrow with Shaun Bradley 3 July : (NC) Norm B took action to update to articulate when Josh expects to have an outcome and update the relevant. 27-June: In IE review. Passed DA review