## Slide 1
2. Overall assessment of Program health
PMO Summary
Budget.
Schedule – Overall status AMBER Detailed MS Project schedules now all baselined with the exception of Business Deployment. Low confidence level in all plans has caused a “30 day get to green” plan to be constructed and driven by A. Guthrie.
Resource. AMBER status for App&Data only resourcing all others RED. Although detailed plans should have been available at start of March this has not been the case and without these it is not possible to clearly define resource requirements. This is what is driving the red statuses below.
RAIDs. RAG status reflects the workstream’s progress with regards to the completion of cleaning up of their RAIDs (taking into account updated details and overdue items). RAID activity continues to progress with the advancement of the M&C Get to Green 30 day plan. Overdue items are steadily declining. Assumptions to be validated remain in need of review, as do both pending decisions and decisions to be revalidated. Weekly M&C Program RAID meetings are on hold for four weeks, as attention will be dedicated to the daily reviews instead.
Change Control. Lync Planning – Approved as a legacy change by CCB. ADM Ramp Down – Approved by CCB, Approved by Alan Guthrie and Bob Reiner Tech Foundation - Messaging Design O365D Impact – approved Unified Comms - MMD – descope – CR rejected pending action from PM.
General . Program generally rated as RED budgeting has declined for 4 programs this week. MS Project schedules now all baselined except business deployment, new AMBER status for schedule. Program Planning still ongoing and POAP expected 5th of March. Resourcing RED due to Planning and changes in scope. M&C 30 day Get to Green exercise in progress and significant progress is being made. Weekly report review process now in place. (PMO)
 |  | RAG Trend Weekly |  |  |  |  | 
Program | This week | Last week | Week -2 | Week -3 | Week -4 | Week -5 | Week -6
Communications | AMBER | GREEN | GREEN | AMBER | AMBER | RED | RED
Transitions | GREEN | RED | AMBER | RED | RED | GREEN | GREEN
Email | AMBER | AMBER | AMBER | AMBER | AMBER | RED | RED
Oyster Card | GREEN | GREEN | NO REPORT | NO REPORT | NO REPORT | AMBER | AMBER
Weekly Ratings |  |  |  |  |  |  |  | 
 | Program Assessment (Per PM ) |  |  |  | PMO Assessment |  |  | 
Program | Overall | Scope | Time | Cost | RAID | Resource | Financial | Schedule
Communications Management | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
Transitions Management | RED | AMBER | AMBER | AMBER | GREEN | AMBER | RED | AMBER
Email Deployment | AMBER | AMBER | AMBER | AMBER | GREEN | RED | RED | AMBER
Oyster Card | GREEN | AMBER | AMBER | AMBER | AMBER | RED | GREEN | AMBER
Overall | RED | AMBER | AMBER | AMBER | AMBER | RED | RED | AMBER
Notes: Cost
GREEN - Estimate at Completion (EAC) = + 0 - 5% of approved spend (cost baseline + approved change requests)
AMBER - Estimate at Completion (EAC) = + 6 - 10% of approved spend (cost baseline + approved changes) and/or pending spend
RED – Estimate at Completion (EAC) exceeds + 10% or $100,000 of approved spend (cost baseline + approved changes) and/or pending spend or no project budget defined
Schedule
GREEN - The project schedule supports the end date of the project (with some elapsed time contingency).
AMBER - The project schedule supports the end date, but issues, risks and/or changes exist that may put the date in jeopardy.
RED – The project schedule does not exist and/or the project schedule does not support the end of the project.
Scope
GREEN - Scope defined and approved (scope baseline) with no pending change requests.
AMBER - Scope defined and approved (scope baseline) with pending change requests – known and not raised and raised but not agreed.
RED – Scope undefined or unapproved (no scope baseline) and/or multiple pending change requests.
Risk
GREEN – Low amount of risks with negligible impact
AMBER – Medium amount of risks. High or medium impact but with mitigation actions in place. Time left to put in place mitigation plans.
RED – High number of risks. High score risks which impact in the near term. No mitigation in place for High risks.
Issue
GREEN – No or low impact issues. Medium impact issues with resolution plans agreed and in place.
AMBER – Large amount of issues and/or Medium impact issues with no resolution plans.
RED – High impact issues present. No resolution plans in place for Medium of High level issues
Commercial
GREEN - TBD
AMBER - TBD
RED – TBD
Resource
GREEN – No resource issue or constraints
AMBER – Resource issues exist but plans are in place to resolve.
RED – Resource issues exist with no plans in place to resolve.

## Slide 2
B. KEY ACCOMPLISHMENTS THIS PERIOD
ATT have completed their Security tasks for all three Data Centres The EYQA AD Trust was established successfully The GAP team have successfully completed the build phase of ‘new’ FIM The CR to SOW2 to extend ATT Consulting Resources has been approved by both EY and ATT Support models for both pre-pilot and pilot defined
C. ACTIVITIES BEHIND SCHEDULE
Completing remaining CoLo build work for Amsterdam Finalising contract change for SBA orders Building the eBond solution – way-forward agreed with ATT, dependant on EY resource availability Completing the GAP testing required for Lync testing to commence and establishing the Production Trust (I522)
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Establish the Production trust with ATT then commence Infrastructure Readiness Tests. Agree contracts for procuring future SBAs and implementing additional security controls (services). Progress remaining activities to finalise Amsterdam colo spaces. Commence functional testing Rollout Lync to ~400 IT Staff (pre-pilot)
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes |  |  | 
Issues to be resolved | Recommended Action | Target Date | Owner
I216 - There is no complete test environment for the M&C Solution so once users are 'live' there is no integrated way of testing enhancements / fixes | Look at options for developing the right environment for post go live | 01-Nov-13 | Tom Cruise
I489 - There is currently no plan for the delivery of the eBonding Solution for Lync | Meet with ATT to agree technical way-fwd and raise request internally for resource | 15-Nov-13 | Will Smith
Scope Change requests to be approved | Recommended Action |  | 
CR161 - Additional Security Controls | Approved subject to confirmation from InfoSec and Ops |  | 
CR TBC - Delays due to two external factors | Quantify impacts of changes from dependant teams (GAP and AD) then update Lync plan accordingly |  | 
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
The team have successfully established the trust connection between EYQA and ATT. Two external factors have impacted the Lync Program Milestones by an estimated 1 week (I522) : The GAP team were requested to complete some changes on the UVT solution, therefore diverting efforts from their Lync deliverables Issues with Production AD prevented the Lync team from establishing the trust connection between Production and ATT Implementing additional controls to address a Security requirement for SBAs (“Isolation and Separation of the SBAs within the office locations”) is likely to impact the delivery of Enterprise Voice by months – will most likely need snr management decision Work progresses to define solution for VPN-less access (i.e. EDGE) to mitigate potential call quality issues (R458).
E. MILESTONES |  |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Conf. Rating | Last Period | This Period
Plan Updated | 20-Sep-13 | 20-Sep-13 | Target | COMPLETE | COMPLETE
Testing Starts | 31-Oct-13 | 05-Nov-13 | Target | AMBER | GREEN
Testing Completes | 07-Mar-14 | 14-Mar-14 | Target | AMBER | RED
Pilot Starts | 04-Dec-13 | 11-Dec-13 | Target | AMBER | RED
Pilot Completes | 24-Jan-14 | 31-Jan-14 | Target | AMBER | RED
Deployment Starts | 10-Mar-14 | 17-Mar-14 | Target | AMBER | RED
Deployment Completes | TBC | TBC | Target |  | 
OVERALL INITIATIVE STATUS | 
Last Period | This Period
GREEN | AMBER
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative |  |  | 
Risks to be addressed | Mitigating Action | Target Date | Owner
R458 - EYRC or other non factored infrastructure constraints may limit deployment | Expedite implementation of EDGE for remote access | 10-Mar-14 | Tom Cruise
R680 - Change freeze may impact Lync timelines | Raise changes in advance, escalate issue | 01-Nov-13 | Will Smith
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
Moved to “Red” status reflects delay to Pilot and Full Deploy milestones due to late delivery of two critical path inbound dependencies.
RED
AMBER
GREEN
COMPLETE
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
Project: Communications Management 27-May-2022
PM: Femi

## Slide 3
B. KEY ACCOMPLISHMENTS THIS PERIOD
ATT have completed their Security tasks for all three Data Centres The EYQA AD Trust was established successfully The GAP team have successfully completed the build phase of ‘new’ FIM The CR to SOW2 to extend ATT Consulting Resources has been approved by both EY and ATT Support models for both pre-pilot and pilot defined
C. ACTIVITIES BEHIND SCHEDULE
Completing remaining CoLo build work for Amsterdam Finalising contract change for SBA orders Building the eBond solution – way-forward agreed with ATT, dependant on EY resource availability Completing the GAP testing required for Lync testing to commence and establishing the Production Trust (I522)
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Establish the Production trust with ATT then commence Infrastructure Readiness Tests. Agree contracts for procuring future SBAs and implementing additional security controls (services). Progress remaining activities to finalise Amsterdam colo spaces. Commence functional testing Rollout Lync to ~400 IT Staff (pre-pilot)
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes |  |  | 
Issues to be resolved | Recommended Action | Target Date | Owner
I216 - There is no complete test environment for the M&C Solution so once users are 'live' there is no integrated way of testing enhancements / fixes | Look at options for developing the right environment for post go live | 01-Nov-13 | Tom Cruise
I489 - There is currently no plan for the delivery of the eBonding Solution for Lync | Meet with ATT to agree technical way-fwd and raise request internally for resource | 15-Nov-13 | Will Smith
Scope Change requests to be approved | Recommended Action |  | 
CR161 - Additional Security Controls | Approved subject to confirmation from InfoSec and Ops |  | 
CR TBC - Delays due to two external factors | Quantify impacts of changes from dependant teams (GAP and AD) then update Lync plan accordingly |  | 
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
The team have successfully established the trust connection between EYQA and ATT. Two external factors have impacted the Lync Program Milestones by an estimated 1 week (I522) : The GAP team were requested to complete some changes on the UVT solution, therefore diverting efforts from their Lync deliverables Issues with Production AD prevented the Lync team from establishing the trust connection between Production and ATT Implementing additional controls to address a Security requirement for SBAs (“Isolation and Separation of the SBAs within the office locations”) is likely to impact the delivery of Enterprise Voice by months – will most likely need snr management decision Work progresses to define solution for VPN-less access (i.e. EDGE) to mitigate potential call quality issues (R458).
E. MILESTONES |  |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Conf. Rating | Last Period | This Period
Plan Updated | 20-Sep-13 | 20-Sep-13 | Target | COMPLETE | COMPLETE
Testing Starts | 31-Oct-13 | 05-Nov-13 | Target | AMBER | RED
Testing Completes | 07-Mar-14 | 14-Mar-14 | Target | AMBER | RED
Pilot Starts | 04-Dec-13 | 11-Dec-13 | Target | AMBER | RED
Pilot Completes | 24-Jan-14 | 31-Jan-14 | Target | AMBER | RED
Deployment Starts | 10-Mar-14 | 17-Mar-14 | Target | AMBER | RED
Deployment Completes | TBC | TBC | Target |  | 
OVERALL INITIATIVE STATUS | 
Last Period | This Period
AMBER | RED
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative |  |  | 
Risks to be addressed | Mitigating Action | Target Date | Owner
R458 - EYRC or other non factored infrastructure constraints may limit deployment | Expedite implementation of EDGE for remote access | 10-Mar-14 | Tom Cruise
R680 - Change freeze may impact Lync timelines | Raise changes in advance, escalate issue | 01-Nov-13 | Will Smith
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
Moved to “Red” status reflects delay to Pilot and Full Deploy milestones due to late delivery of two critical path inbound dependencies.
RED
AMBER
GREEN
COMPLETE
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
Project: Transition Management 27-May-2022
PM: Gladys & TJ

## Slide 4
B. KEY ACCOMPLISHMENTS THIS PERIOD
ATT have completed their Security tasks for all three Data Centres The EYQA AD Trust was established successfully The GAP team have successfully completed the build phase of ‘new’ FIM The CR to SOW2 to extend ATT Consulting Resources has been approved by both EY and ATT Support models for both pre-pilot and pilot defined
C. ACTIVITIES BEHIND SCHEDULE
Completing remaining CoLo build work for Amsterdam Finalising contract change for SBA orders Building the eBond solution – way-forward agreed with ATT, dependant on EY resource availability Completing the GAP testing required for Lync testing to commence and establishing the Production Trust (I522)
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Establish the Production trust with ATT then commence Infrastructure Readiness Tests. Agree contracts for procuring future SBAs and implementing additional security controls (services). Progress remaining activities to finalise Amsterdam colo spaces. Commence functional testing Rollout Lync to ~400 IT Staff (pre-pilot)
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes |  |  | 
Issues to be resolved | Recommended Action | Target Date | Owner
I216 - There is no complete test environment for the M&C Solution so once users are 'live' there is no integrated way of testing enhancements / fixes | Look at options for developing the right environment for post go live | 01-Nov-13 | Tom Cruise
I489 - There is currently no plan for the delivery of the eBonding Solution for Lync | Meet with ATT to agree technical way-fwd and raise request internally for resource | 15-Nov-13 | Will Smith
Scope Change requests to be approved | Recommended Action |  | 
CR161 - Additional Security Controls | Approved subject to confirmation from InfoSec and Ops |  | 
CR TBC - Delays due to two external factors | Quantify impacts of changes from dependant teams (GAP and AD) then update Lync plan accordingly |  | 
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
The team have successfully established the trust connection between EYQA and ATT. Two external factors have impacted the Lync Program Milestones by an estimated 1 week (I522) : The GAP team were requested to complete some changes on the UVT solution, therefore diverting efforts from their Lync deliverables Issues with Production AD prevented the Lync team from establishing the trust connection between Production and ATT Implementing additional controls to address a Security requirement for SBAs (“Isolation and Separation of the SBAs within the office locations”) is likely to impact the delivery of Enterprise Voice by months – will most likely need snr management decision Work progresses to define solution for VPN-less access (i.e. EDGE) to mitigate potential call quality issues (R458).
E. MILESTONES |  |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Conf. Rating | Last Period | This Period
Plan Updated | 20-Sep-13 | 20-Sep-13 | Target | COMPLETE | COMPLETE
Testing Starts | 31-Oct-13 | 05-Nov-13 | Target | AMBER | AMBER
Testing Completes | 07-Mar-14 | 14-Mar-14 | Target | AMBER | RED
Pilot Starts | 04-Dec-13 | 11-Dec-13 | Target | AMBER | RED
Pilot Completes | 24-Jan-14 | 31-Jan-14 | Target | AMBER | RED
Deployment Starts | 10-Mar-14 | 17-Mar-14 | Target | AMBER | RED
Deployment Completes | TBC | TBC | Target |  | 
OVERALL INITIATIVE STATUS | 
Last Period | This Period
AMBER | AMBER
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative |  |  | 
Risks to be addressed | Mitigating Action | Target Date | Owner
R458 - EYRC or other non factored infrastructure constraints may limit deployment | Expedite implementation of EDGE for remote access | 10-Mar-14 | Tom Cruise
R680 - Change freeze may impact Lync timelines | Raise changes in advance, escalate issue | 01-Nov-13 | Will Smith
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
Moved to “Red” status reflects delay to Pilot and Full Deploy milestones due to late delivery of two critical path inbound dependencies.
RED
AMBER
GREEN
COMPLETE
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
Project: Outlook Email Deployment 27-May-2022
PM: Roy & Chudi

## Slide 5
B. KEY ACCOMPLISHMENTS THIS PERIOD
ATT have completed their Security tasks for all three Data Centres The EYQA AD Trust was established successfully The GAP team have successfully completed the build phase of ‘new’ FIM The CR to SOW2 to extend ATT Consulting Resources has been approved by both EY and ATT Support models for both pre-pilot and pilot defined
C. ACTIVITIES BEHIND SCHEDULE
Completing remaining CoLo build work for Amsterdam Finalising contract change for SBA orders Building the eBond solution – way-forward agreed with ATT, dependant on EY resource availability Completing the GAP testing required for Lync testing to commence and establishing the Production Trust (I522)
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Establish the Production trust with ATT then commence Infrastructure Readiness Tests. Agree contracts for procuring future SBAs and implementing additional security controls (services). Progress remaining activities to finalise Amsterdam colo spaces. Commence functional testing Rollout Lync to ~400 IT Staff (pre-pilot)
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes |  |  | 
Issues to be resolved | Recommended Action | Target Date | Owner
I216 - There is no complete test environment for the M&C Solution so once users are 'live' there is no integrated way of testing enhancements / fixes | Look at options for developing the right environment for post go live | 01-Nov-13 | Tom Cruise
I489 - There is currently no plan for the delivery of the eBonding Solution for Lync | Meet with ATT to agree technical way-fwd and raise request internally for resource | 15-Nov-13 | Will Smith
Scope Change requests to be approved | Recommended Action |  | 
CR161 - Additional Security Controls | Approved subject to confirmation from InfoSec and Ops |  | 
CR TBC - Delays due to two external factors | Quantify impacts of changes from dependant teams (GAP and AD) then update Lync plan accordingly |  | 
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
The team have successfully established the trust connection between EYQA and ATT. Two external factors have impacted the Lync Program Milestones by an estimated 1 week (I522) : The GAP team were requested to complete some changes on the UVT solution, therefore diverting efforts from their Lync deliverables Issues with Production AD prevented the Lync team from establishing the trust connection between Production and ATT Implementing additional controls to address a Security requirement for SBAs (“Isolation and Separation of the SBAs within the office locations”) is likely to impact the delivery of Enterprise Voice by months – will most likely need snr management decision Work progresses to define solution for VPN-less access (i.e. EDGE) to mitigate potential call quality issues (R458).
E. MILESTONES |  |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Conf. Rating | Last Period | This Period
Plan Updated | 20-Sep-13 | 20-Sep-13 | Target | COMPLETE | COMPLETE
Testing Starts | 31-Oct-13 | 05-Nov-13 | Target | AMBER | GREEN
Testing Completes | 07-Mar-14 | 14-Mar-14 | Target | AMBER | GREEN
Pilot Starts | 04-Dec-13 | 11-Dec-13 | Target | AMBER | RED
Pilot Completes | 24-Jan-14 | 31-Jan-14 | Target | AMBER | RED
Deployment Starts | 10-Mar-14 | 17-Mar-14 | Target | AMBER | RED
Deployment Completes | TBC | TBC | Target |  | 
OVERALL INITIATIVE STATUS | 
Last Period | This Period
GREEN | GREEN
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative |  |  | 
Risks to be addressed | Mitigating Action | Target Date | Owner
R458 - EYRC or other non factored infrastructure constraints may limit deployment | Expedite implementation of EDGE for remote access | 10-Mar-14 | Tom Cruise
R680 - Change freeze may impact Lync timelines | Raise changes in advance, escalate issue | 01-Nov-13 | Will Smith
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
Moved to “Red” status reflects delay to Pilot and Full Deploy milestones due to late delivery of two critical path inbound dependencies.
RED
AMBER
GREEN
COMPLETE
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
Project: Oyster Card Deployment 27-May-2022
PM: Busayo M