## Management Summary
[9 empty] | Last Period | This Period
[7 empty] | Project Status |  | Amber | Amber
[7 empty] | Test Status |  | Green | Green
A. PROJECT DETAILS |  |  |  |  | B. EXECUTIVE SUMMARY
ACT Reference | R27436
Baseline Start Date | 2013-01-14 | Baseline Estimate (hours) | TBC
Actual Start Date | 2013-01-14 | Target Hours to Date | TBC
Target Resource No. | 7 | Actual Hours to Date
Actual Resource No. | 2 | Target Hours to Completion | TBC
C. KEY ACCOMPLISHMENTS THIS PERIOD |  |  |  | D. KEY MILESTONES
|  |  |  | Test Analysis/Lync & OIM Research |  | 2012-12-17 |  | 2013-02-01 | Completed
|  |  |  | Revised ROM |  | 2013-02-11 |  | 2013-02-12 | Completed
|  |  |  | ALM Request Submitted |  | 2013-02-11 |  | 2013-02-11 | Completed
|  |  |  | Considered ROM |  | 2013-02-25 |  | 2013-03-01 | Completed
|  |  |  | Test Plan 1st Draft |  | 2013-03-04 |  | 2013-03-15 | Green
|  |  |  | Test Conditions 1st Draft |  | 2013-03-04 |  | 2013-03-21 | Green
|  |  |  | Signed off Test Plan |  | TBC |  | TBC
|  |  |  | Detailed Test Estimate & Schedule |  | TBC |  | TBC
|  |  |  | Signed off Test Conditions |  | TBC |  | TBC
|  |  |  | Test Cases |  | TBC |  | TBC
E. KEY REQUIREMENTS |  |  |  | Test Readiness Review |  | TBC |  | TBC
|  |  |  | Test Execution |  | TBC |  | TBC
|  |  |  | Test Summary Report |  | TBC |  | TBC
|  |  |  | Test Exit/Post Implementation Review |  | TBC |  | TBC
F. KEY ACTIVITIES PLANNED NEXT PERIOD |  |  |  | G. TESTING RISKS
Global Account Provisioning (R27436): - w/e 12 March 2013
James Marsh
Interviews - Paul Ross & James Marsh conducted 7 interviews for the test team (06/03, 07/03 & 11/03)
Performance Testing - Trevor Shaw attended meeting with David Cecil and Raj Penchala 11/03 to provide information for his ROM. Also suggested Trevor email the Aptec team as they could not attend the meeting to ask about Performance Testing on previous projects.
GAP ALM Request - Lisa Bailey has created the ALM project request and given me a walkthrough 06/03 and we have another meeting planned 13/03. ALM Training for engineers (Aptec, MS, EY) scheduled 26/03.
Test Plan - the delivery of the 1st draft has become delayed due to time spent preparing and conducting interviews, so the revised date will be 15/03 instead of planned date 11/03. This will be peer reviewed by Raghu and Paul Ross, then sent to Ant Harper for an initial review and feedback. The test plan will then be updated and circulated to the team to review.
Test Conditions - Raghu has been working on these and meeting regularly with Ally Ward to discuss any issues or gaps that have arisen during the test condition process. The revised date for delivery of the 1st draft will be 21/03 instead of the planned date 18/03
Test Schedule - no further progress from the Considered ROM is possible as no development time lines from Aptec or EY/MS have been provided for component iterations delivered into EYQA.
Completed majority of job interviews
Continue work on draft test plan document (JM)
Continue work draft test conditions (RA) - 4th March
Complete interviews for test team (PR & JM)
Meet with Simon Barkley for deep dive on scope
Meet with Environment Management Team
Environments: No EYQA O365 or EYQA AT&T environment in EYQA. Clarification that EYQA supports GCL5.0 workstation GPOs, how we connect clients to EYQA/ EY X Staging, Limited to two concurrent connections via Remote Connection issue.
Test Team Resource
No clarification of component time lines for EYQA from Aptec or EY/MS
Uncertainty over limitations of EYQA & EY Staging in relation to end to end test (HR-OIM/FIM - AT&T scripts - Lync client)
Time lines when each development component will be available in EYQA from both Aptec and EY/MS
Clarification on EYQA and EY Staging relating to AT&T scripts and Lync client
Use Cases for FIM components
SDD for Aptec components
SDD for FIM components
OIM "training"& demos

## Assigned Defects for Dev
Defect ID | Date Raised | Defect Type | Summary | Status | Sub-Status | Assigned To | Severity | Priority | Application | Detected in Build | Test Case ID | Req ID

## Open Defects for Re-test
Defect ID | Date Raised | Defect Type | Summary | Status | Sub-Status | Assigned To | Severity | Priority | Application | Detected in Build | Test Case ID | Req ID | ALM Allocated To

## Defects Closed this week
Defect ID | Date Raised | Defect Type | Summary | Status | Sub-Status | Assigned To | Severity | Priority | Application | Detected in Build | Closed in Build | Defect Class | Detected in Test Phase | Raised By | Workstream

## Test Metrics
Test Metrics
|  |  | Severity | [5 empty] | Status
Status |  |  | 1 | 2 | 3 | 4 |  |  | Raised | Open | Closed
New | [7 empty] | Week Ending
In Triage | [6 empty] | 2012-05-11
Rejected | [6 empty] | 2012-05-18
Assigned | [6 empty] | 2012-05-25
Deferred | [6 empty] | 2012-06-01
Ready for Retest | [6 empty] | 2012-06-08
Passed Retest | [6 empty] | 2012-06-15
Failed Retest | [6 empty] | 2012-06-22
Closed | [6 empty] | 2012-06-29
|  | Planned | Started | Reviewed | Complete |  |  |  | Planned | Exposed | Passed
| Week Ending | [6 empty] | Week Ending
2011-05-11 | [6 empty] | 2011-05-11
2011-05-18 | [6 empty] | 2011-05-18
2011-05-25 | [6 empty] | 2011-05-25
2011-06-01 | [6 empty] | 2011-06-01
2011-06-08 | [6 empty] | 2011-06-08
2011-06-15 | [6 empty] | 2011-06-15
2011-06-22 | [6 empty] | 2011-06-22
2011-06-29 | [6 empty] | 2011-06-29
Enter Data
Data will autopopulate
Outstanding Defects by Severity vs Defect Status
All Functional Defects - Total Raised vs Closed
Functional Test Preparation Summary
Functional Test Execution Summary

## Sheet1
Green
Amber
Red
Completed
| 1 | 2 | 2 | 3
| 4 | 4 | 4 | 4
| 7 | 7 | 7 | 7
| 2 | 2 | 2 | 2
| 5 | 5 | 5 | 5
| 8 | 8 | 8 | 8
| 4 | 4 | 4 | 4
| 3 | 3 | 3 | 3
| 5 | 5 | 5 | 5