## Preliminary Assessment
Transition Impact Assessment
Project Name |  | Global Account provisioning (GAP)
Portfolio |  | IT / IAM
ACT ID |  | R27436
Service Delivery Leader |  | Alan Guthrie
Project Manager |  | Alexa Briggs
Transition Manager |  | Colette Bond
Deployment Test date range (estimated)
Deployment date range (estimated) |  | Phase 1 - Lync Provisioning & OIM Infratsructure - May - July 2013 Phase 2 - User Validation - TBD Phase 3 - Account Provisioning for AD & SecurID - TBD |  | production Environment needs to be ready for Lync End to End testing in May an transition/handover needsot be completed by July 1, 2013
Operational Acceptance date (estimated) |  | Phase 1 - July 2013 Phase 2 & 3 - TBD
1. Transition Profile |  |  | Assessment | Additional Comments
1.1 | Service summary | Provide a few sentences that describes the product/service (can leverage information from the Product Vision & Scope document) | Enabling a global provisioning tool for Phase 1 Lync Phase 2 - User Validation (Security challenge questions for users and service desks) Phase 3 - Active Directory and SecurID account provisioning
1.2 | Related technology | (Web, Notes db, Desktop, etc…) | Lync, AD, Exchange 0365, Oracle identity manager
1.3 | Transition approach | Describe Transition approach (SMS, Notes db, Email comm, CHS, Silent, User intervention, etc….) and (phased, all at once, by BU, etc….) | Web tool for Admins, backend Oracle Database that connects to the related technologies. Phases described above. Technical - tool available globally upon deployment - How or if countries migrate to tool and timing is TBD
1.4 | Transition scope | Describe the Transition scope (Global, BU, Geography Based, etc...), provide details for BU and/or Geography | Global
1.5 | Target audience | Provide estimate of target audience size | 1-1000 | Tool is to be used by IT Admins in IAM -possibly othr support groups will have access to view reports or make changes re: Lync especially - however it affects provisioning globally for Lync accounts first, then user validation, and finally Active Direcory Accounts and SecurID accounts.
1.6 | Project classification | Enter project classification (per PM toolkit or other project related documents) | Enterprise
1.7 | Top 10 Project? | Is the project on the Top 10 list? | No
2. Expected Support Impacts |  |  | Assessment | Additional Comments
2.1 | L0-L1 Support Impact | GSH, Remote Services Service Desks | Low
2.2. | L2 Support Impact | IAM, OSS, Infra/App Service Desks | Medium | IAM, UAM,
2.3. | L3 Support Impact | How many groups are expected to be effected? (Remotes Services -Sec Ops, Telecomm Services, App Mgmt, Hosting Services, Vendor) | High | Enterprise Directories - AD, telephony support teams, Lync support teams
3. Estimated Requirements and Dependencies |  |  | Assessment | Additional Comments
3.0 | Transition impacts or is impacted by other transition efforts | Identify if the transition of this product/service/application is a requirement for the transition of another product/service/application | Requirement for Lync
3.1 | Requirements - Global Core Loadset | List any estimated requirements from the Global Core Loadset to support the transition of this product/service/application. This includes specific versions of products or configuration settings that must be running on a computer in order for this product/service/application to function correctly. | N/A
3.2 | Requirements - software | List any other anticipated software requirements that are mandatory for the transition of this product/service/application. For example, this might include a specific version of the network operating system, a specific version of Domino server, etc. | Operating System: Windows Server 2008 R2 (all SP levels included) 64-bit, WebLogic 10.3.6, JRockit 6 Update 29 R28.2.0+ 64-bit, Oracle 11.2.0.3+ database
3.3 | Requirements - dependencies | List any anticipated software/hardware dependencies or interfaces with other services | Active Directory, Lync, Exchange 0365
3.4 | Requirements - infrastructure | List any anticipated infrastructure requirements such as Integrated Global Directory Service, Internet Mail Service, etc. | Standard
3.5 | Requirements - PC hardware | List the estimated minimum and recommended hardware requirements to support the transition of this product/service/application. | N/A
3.6 | Requirements - hosting | List any estimated hosting requirements (estimated number of servers at each tier by location) | TBD - arch being reviewed
3.7 | Requirements - network | List any estimated connectivity requirements to support the transition of this product/service such as firewall ports, bandwidth capacity, remote access, etc. | Standard - firewall changes
3.8 | Requirements - licensing/vendor | List any estimated vendor requirements, including licenses that will need be maintained after the transition is complete
3.9 | Requirements - information governance | List any estimated information governance areas that need to be addressed to support the transition of this product/service/application such as data storage and retention, archive/backup requirements, data access, etc. | Account Governance should align with existing policies
3.10 | Requirements - decommissioning | If a decommissioning effort is required, list any estimated information that needs to be addressed to support the decommissioning of a server/application/service, such as operational aspects, legal/data and Information Security aspects, Project related activities, Processes & Procedures | AMPs will eventually be decomissioned and other similar apps in local countries -out of scope for this project at this time

## Additional Planning Information
For Transition Manager Use Only:
4. Functional Profile |  |  | Assessment | Additional Comments
4.1 | Sponsorship | Is this an IT Services initiative or a business/other CBS sponsored project? | IT
4.2 | Business sponsor identified? | Has a business/functional sponsor been identified? | Yes
4.3 | Business involvement confirmed? | If there is a sponsor from outside of IT Services, are they either engaged personally or through a project team? It is important that all teams understand the transition process. | Yes
4.4 | Area business contacts available? | If the service is being sponsored from outside of IT Services, are there area business/functional contacts for the Transition Managers to work with? (Enablement Center, GATIN, et al.) | Yes
4.5 | Which component(s) of Transition support should be involved? | Indicate which components of Transition support will be involved (e.g. Communications, Learning, Change Management) | Communications Change Management requirement to be assessed Training possibly required | *potential trianing required for local countires for when they decide to migrate
4.6 | Contact Names | Provide a contact for each project team member, if known | Alexa Briggs - PM Alexander Kotkov - Info Sec Ally Ward- Lync BA Anthony Harper -Architect Bharat Sambyal/ -OIM BA Chris Rae - Lync Engineer Colette Bond - TM David A. Cecil - OIM Engineer David Esposito - Siteminder Engineer James Marsh - Test manager Raghu Aggarwal - Test lead Raj Penchala - OIM Engineer Sharanjit Singh - Architect Waqar Ali - OIM BA William Phillips -Infosec Kathleen Anderson - IT Change Mangamenet Charlotte Jeffries - Comms and Business Change Management | Learning resource will be requested.
5. Addional Project Considerations |  |  |  | Additional Comments
5.1 | Global Shared Services (GSS) profile | Establish if this service will be transitioned to GSS (India and/or China). If it will, follow the Transition Model for GSS | N/A | GSS Service Transition Model
5.2 | T-Minus approach required? | Establish if there is a need for a t-minus style approach to the plan. A T-minus approach is a backward countdown of time remaining before a transition (typically, an hourly schedule). Use this approach for precisely coordinated transitions such as code migrations | No
5.3 | Desktop impact? | Will there be an impact to the desktop (i.e. application added to the loadset)? | No
5.4 | Transition Complexity | Use the following guidance to help determine the complexity factor of the transition: Complex: Global deployment, Change Management impact high, There is a regulatory impact, Learning Plan Required, Communication planned required, Deployment Test required, Support Model required Standard: Global/Area/Country deployment, Change Management impact Med/Low, There is an existing support model (some changes required), Communication plan (minimum requirements), Regulatory impact low. All desktop transitions are minimally categorized as standard, but could also be complex. Simple: No Deployment Test required, Deployment to 1 or 2 Area(s), Communication plan (minimum requirements), No updates needed to existing support model, No decommissioning of existing application. | Complex
5.5 | Transition Hours estimate | Provide a high level estimate of the number of hours for this transition. Includes Transition, Communications and Learning managers. |  | Service Transition Hours Estimate Worksheet
5.6 | Deployment Test plan | What form will the Deployment Test take (SMS package test, website test plan) | TBD
6. IT Communications & Training |  |  | Assessment | Additional Comments
6.1 | Technical training materials | Identify if training materials will be provided by the project team or will need to be produced by the business unit/locally | TBD - however admin teams will nee dto be completely trained in order to support and use tool
6.2 | Awareness | Identify the general level of awareness of the project within IT Services (and at user level) | no end user knowledge required - High level of awareness in IT
6.3 | IT Communications plan | Identify if a communications plan for transition will be provided by the project team or by the business unit/locally | TBD - but required
6.4 | Language | Are there any unique country/language considerations that need to be taken into account? Documentation/support material et al. |  | unkown at this time
7. Network Impact |  |  | Assessment | Additional Comments
7.1 | Impact of transition to GWAN/LAN | Will the transition of the product/service/application have an impact to the GWAN/LAN? | No
7.2 | Impact of transition to local Internet connection | Will the transition of the product/service/application have an impact to the local internet connection | Unknown at this time
7.3 | Impact of transition to client site connections (e.g. direct T1 connections between client site & EY) | Will the transition of the product/service/application have an impact to client site connections? | No
7.4 | Impact of transition on EY Remote Connect (EYRC) | Will the service or application need to be accessible through EYRC? | Yes
8. Overall Transition Risk Assessment |  |  | Assessment | Additional Comments
8.1 | Transition Risk Assessement (overall) | Quality, timeline, quality concerns, et al. | Medium | Add comments here

## Definitions Tab
Field #/Assessment Question | Definition
Project Name
Portfolio
ACT ID
Change Request ID | Enter the RFC Remedy ID number
Customer Service and Portfolio Contact | Enter the name of the Portfolio contact.
Project Manager | Enter the name of the PM
Transition Manager | Enter the name ofTransition Manager (your name)
Release Package Ready Date | Enter the date when the package is ready for testing. A target month can be entered if no further detail is available.
Deployment Test Date Range (estimated) | Enter the date span for the Deployment Test. A target month can be entered if no further detail is available.
Deployment Date Range (estimated) | Enter the date or date range of production delivery. A target month can be entered if no further detail is available.
Operational Acceptance Date (estimated) | Enter the date in which the product/service transitioned will be handed over to Operations. A target month can be entered if no further detail is available.
Transition Profile
1.1 | Enter a summary of what is being transitioned, why and for who.
1.2 | Enter the technology that is impacted with this transtion - LN Dbase?, Web based tool?, Desktop app?
1.3 | Enter the transition approach - SMS, LN App Registry, .net/sql code migration. Also include if it will be a phased approach or a big bang all in one approach.
1.4 | Describe the Transition scope (Global, BU, Geography Based, etc...), provide details for BU and/or Geography
1.5 | Select from the drop down menu the estimate of target audience size.
1.6 | Enter Project Classification (per PM toolkit or other project related documents).
1.7 | Select Yes if project is on the top ten list.
Expected Support Impacts
2.1 | Select the impact to L0 and L1 support - Will a change be required in an existing support model? Will completely new knowledge be available for user and L1 to review? What will be the impact to GSH users and Remote Services Desk staf?
2.2 | Select the impact to L2 - Will a change be required in an existing support model? Will completely new knowledge be available for L2 to review? What will be the impact to IAM, OSS and Infra/App Services Desk staff?
2.3 | Select the impact to L3 support - Will a change be required in an existing support model? Will completely new knowledge be available for L3 to review? What will be the impact to Remotes Services -Sec Ops, Telecomm Services, App Mgmt, Hosting Services, Vendor support?
Estimated Requirements and Dependencies
3 | Identify if the transition of this product/service/application is a requirement for the transition of another product/service/application.
3.1 | List any estimated requirements from the Global Core Loadset to support the transition of this product/service/application. This includes specific versions of products or configuration settings that must be running on a computer in order for this product/service/application to function correctly.
3.2 | List any other anticipated software requirements that are mandatory for the transition of this product/service/application. For example, this might include a specific version of the network operating system, a specific version of Domino server, etc.
3.3 | List any anticipated software/hardware dependencies or interfaces with other services
3.4 | List any anticipated infrastructure requirements such as Integrated Global Directory Service, Internet Mail Service, etc.
3.5 | List the estimated minimum and recommended PC hardware requirements to support the transition of this product/service/application. This should include PC and server configurations where applicable.
3.6 | List any estimated hosting requirements (estimated number of servers at each tier by location)
3.7 | List any estimated network connectivity requirements to support the transition of this product/service such as firewall ports, bandwidth capacity, remote access, etc.
3.8 | List any estimated vendor requirements, including licensnes that will need be maintained after the transition is complete - including new user licenses etc.
3.9 | List any estimated information governance areas that need to be addressed to support the transition of this product/service/application such as data storage and retention, archive/backup requirements, data access, etc.
3.1 | If a decommissioning effort is required, list any estimated information that needs to be addressed to support the decommissioning of a server/application/service, such as operational aspects, legal/data and Information Security aspects, Project related activities, Processes & Procedures
Functional Profile
4.1 | Please select the appropriate group - either IT, CBS or one of the business groups as the sponsor of this transition.
4.2 | Select Yes if a business sponsor has been identified. Please include the name / email of the sponsor in the comments field.
4.3 | Select Yes if the sponsor outside of IT is involved personally in the project, and attending project meetings.
4.4 | Select Yes if there are business area/functional contacts for the Transition manager to work with. Provide details in the comments section.
4.5 | Enter the specific Transition groups that will work on this project - eg. Communications, OCM etc.
4.6 | Enter the contact names and email addresses for the groups listed in 4.5
Additional Project Considerations
5.1 | Enter Yes if this product/application will be transitioned to GSS - refer to the link for the GSS Model.
5.2 | Select Yes if a Tminus approach will be required. Usually used for code migrations. Note - the PM may have already created one.
5.3 | Select Yes if there will be an impact to the Desktop - eg.. SMS distribution of .exe application or program.
5.4 | Taking into account the criteria listed, as well as research done on project materials available please select the complexity of the project.
5.5 | Using the Transition Hours Estimate worksheet (link has been provided), enter the number of hours estimated for this project.
5.6 | Enter the form of Deployment Test that will take place for this project. Enter NA if none will be scheduled - In the comments section ensure to note why there is not Deployment Test.
IT Communications and Training
6.1 | If needed, state whether technical training materials will need to be produced, or will be provided by the project team or business.
6.2 | Enter general level of awareness of the project for both IT and end users - specify any details in the comments section.
6.3 | Enter the communication channels that were used to provide awareness - eg., business comms, IT Newsflashes, etc.
6.4 | Select Yes if special language requirements are needed for the transition. Provide details in the comments section.
Network Impact
7.1 | Select Yes if the transition will have any impact to the GWAN or LAN. Provide details in the comments section.
7.2 | Select Yes if the transition will have any impact to the local area internet connection. Provide details in the comments section.
7.3 | Select Yes if the transition will have any impact to client site connections. Provide details in the comments section.
7.4 | Select Yes if the service or application will need to also be transitioned via EY Remote Connect.
Overall Transition Risk Assessment
8.1 | Provide a general overall assessment of any risks associated to the transition - provide details in the comments section.