## Slide 1
B. KEY ACCOMPLISHMENTS THIS PERIOD
ATT have completed their Security tasks for all three Data Centres The EYQA AD Trust was established successfully The GAP team have successfully completed the build phase of ‘new’ FIM The CR to SOW2 to extend ATT Consulting Resources has been approved by both EY and ATT Support models for both pre-pilot and pilot defined
C. ACTIVITIES BEHIND SCHEDULE
Completing remaining CoLo build work for Amsterdam Finalising contract change for SBA orders Building the eBond solution – way-forward agreed with ATT, dependant on EY resource availability Completing the GAP testing required for Lync testing to commence and establishing the Production Trust (I522)
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Establish the Production trust with ATT then commence Infrastructure Readiness Tests. Agree contracts for procuring future SBAs and implementing additional security controls (services). Progress remaining activities to finalise Amsterdam colo spaces. Commence functional testing Rollout Lync to ~400 IT Staff (pre-pilot)
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes |  |  | 
Issues to be resolved | Recommended Action | Target Date | Owner
I216 - There is no complete test environment for the M&C Solution so once users are 'live' there is no integrated way of testing enhancements / fixes | Look at options for developing the right environment for post go live | 01-Nov-13 | Geoff Thomson
I329 - GWAN upgrade decision will arrive too late for Canadian sites | Work with GNP team to understand plan for upgrade to Canada sites | 15-Nov-13 | Neil Sahdev
I522 - Lync Pilot and Full Deploy milestones impacted by 2 x external factors | Quantify impacts of changes from dependant teams (GAP and AD) then update Lync plan accordingly | 06-Nov-13 | Neil Sahdev
I489 - There is currently no plan for the delivery of the eBonding Solution for Lync | Meet with ATT to agree technical way-fwd and raise request internally for resource | 15-Nov-13 | Neil Sahdev
Scope Change requests to be approved | Recommended Action |  | 
CR161 - Additional Security Controls | Approved subject to confirmation from InfoSec and Ops |  | 
CR TBC - Delays due to two external factors | Quantify impacts of changes from dependant teams (GAP and AD) then update Lync plan accordingly |  | 
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
The team have successfully established the trust connection between EYQA and ATT. Two external factors have impacted the Lync Program Milestones by an estimated 1 week (I522) : The GAP team were requested to complete some changes on the UVT solution, therefore diverting efforts from their Lync deliverables Issues with Production AD prevented the Lync team from establishing the trust connection between Production and ATT Implementing additional controls to address a Security requirement for SBAs (“Isolation and Separation of the SBAs within the office locations”) is likely to impact the delivery of Enterprise Voice by months – will most likely need snr management decision Work progresses to define solution for VPN-less access (i.e. EDGE) to mitigate potential call quality issues (R458). According to available data points approx. half of the countries do not have suitable bandwidth for the deployment of Lync’s voice and/or video capabilities, severely limiting the ability to realise associated benefits.
E. MILESTONES |  |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Conf. Rating | Last Period | This Period
Plan Updated | 20-Sep-13 | 20-Sep-13 | Target | COMPLETE | COMPLETE
Testing Starts | 31-Oct-13 | 05-Nov-13 | Target | AMBER | RED
Testing Completes | 07-Mar-14 | 14-Mar-14 | Target | AMBER | RED
Pilot Starts | 04-Dec-13 | 11-Dec-13 | Target | AMBER | RED
Pilot Completes | 24-Jan-14 | 31-Jan-14 | Target | AMBER | RED
Deployment Starts | 10-Mar-14 | 17-Mar-14 | Target | AMBER | RED
Deployment Completes | TBC | TBC | Target |  | 
OVERALL INITIATIVE STATUS | 
Last Period | This Period
AMBER | RED
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative |  |  | 
Risks to be addressed | Mitigating Action | Target Date | Owner
R458 - EYRC or other non factored infrastructure constraints may limit deployment | Expedite implementation of EDGE for remote access | 10-Mar-14 | Neil Sahdev
R680 - Change freeze may impact Lync timelines | Raise changes in advance, escalate issue | 01-Nov-13 | Neil Sahdev
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
Moved to “Red” status reflects delay to Pilot and Full Deploy milestones due to late delivery of two critical path inbound dependencies.
RED
AMBER
GREEN
COMPLETE
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
M&C – Lync – October 2013
David Bingham/Neil Sahdev

## Slide 2
M&C – Lync – October 2013
David Bingham/Neil Sahdev
Budget RAG Status | 
RED | Variance is =+ 10% or $100,000 of current budget (baseline + approved change requests) and/or pending spend - or - no project budget is defined/approved
AMBER | Variance is =+ 6% - 9% of current budget (baseline + approved change requests) and/or pending spend
GREEN | Variance is = + 5% of current budget (baseline + approved change requests) and/or pending spend
VARIANCE FACTORS
NEG: Unplanned capital expenses
NEG: Unplanned resource expenses
NEG: Unplanned project (misc) expenses
SIG POS: Unused planned capital
SIG POS: Unused planned resources
SIG POS: Project not progressing as planned
OTHER (Please explain in section below)
Page 2
J. Key Inbound Dependency View |  |  |  |  |  | 
Criticality | Supplying Program | Dependency | Delivery Date | Required by Date | RAG Status | Current State
High | GAP | GAP build and test complete (EYQA) | 05-Dec-13 | 28-Nov-13 | RED | 
High | GAP | GAP build and test complete (Production) | 15-Jan-14 | 10-Jan-14 | RED | 
I. BUD - ($) |  |  |  |  |  |  |  |  |  | STATUS
 |  |  | PLANNED |  | ACTUAL |  |  |  |  | GREEN
 |  |  |  | Current Bud (Baseline + Approved CRs) | Spend to Date | Estimate to Completion (ETC) | Capital Spend ETC | Revenue Spend ETC | Estimate at Completion (EAC) | Variance
Fiscal year | Business Case Bud | Project Charter Bud | PMP Bud (baseline) | -1 | -2 | -3 |  |  | (2+3) | (1) - (2+3)
FY11 |  |  |  | 352,844 | 352,844 |  |  |  | 352,844 | 0
FY12 |  |  |  | 5,707,907 | 6,657,078 |  |  |  | 6,657,078 | -949,171
FY13 |  |  |  | 5,266,663 | 5,266,663 |  |  |  | 5,266,663 | 0
FY14 |  |  |  | 5,603,976 | 987,836 | 4,616,139 |  |  | 5,603,976 | 0
FY15 |  |  |  | 2,333,305 |  | 2,333,305 |  |  | 2,333,305 | 0
TOTALS | 0 | 0 | 0 | 19,264,694 | 13,264,421 | 6,949,444 | 0 | 0 | 20,213,865 | -949,171
Brief explanation for RED or AMBER variance |  |  |  |  |  |  |  | Variance Factor: | OTHER (please explain in section below) | 
ATD may be greater than reported through the Portfolio Report Actuals for vendor spend due to the effect of pending Invoices that may not have yet been Accrued. |  |  |  |  |  |  |  |  |  |