## Slide 1
C. ACTIVITIES BEHIND SCHEDULE
Application & Data: Wave 1 PVS & Requirements Spec signoff delayed due to stakeholder availability. SharePoint: Research tools – GAAIT and Credential replacements, Subscribe and Deliver – Overall Vision/Scope. Finalizing Project Replanning. Unified Communications: Completion of MMD due to change in scope to add group and shared mail file migration, and to SSP. Completion of Lync/Outlook requirements and identification of Day 1 integration suite. Technology Foundation: Lync - Installation for Japan is underway for 6913 installations. Completion of last 500 installations is due by w/c 1st April. Outlook - Due to SCCM Operational issues, deployment has been delayed. Change Management: Progress visual design themes, revised comms strategy and plan. Recruitment of key positions, finalization of M&C CHS initial awareness & learning materials, IT Transition Management: Recruitment of TM resources. Detailed transition plans based on workstream delivery dates. Detailed planning sessions with I&O teams, specifically RSS / OSS.
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Application Data Migration: Rebaseline both Phase 1 and Rediscovery project plans once delivery dates of key inbound dependencies have been defined, confirmed and communicated. SharePoint : Revise FY12 plan, Ovitas Workshops will continue. Technology Foundation: Outlook - Start Full deployment of Outlook. Unified Communications: Determine UC decision-making forum Change Management: Complete initial refresh of M&C financial Benefit Case, Hold further benefit identification calls with SharePoint stakeholders, Develop high level summary of Lync and Outlook benefits. IT Transition Management: Transition team workshop week of 12 March in Secaucus. Requesting two telephone interviews for London based TM candidates.
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes | 
Issues to be resolved | Recommended Action
Need to recruit a significant number of additional resources into the program. Recruitment of skilled staff proving very difficult and will impact schedules. | To be reviewed as part of 30 Day Plan exercise.
Engagement with Areas has not moved at the pace required to establish a Change Network and start to develop Deployment plans. | Jackie Knight working with Sophie Boiron and Martin Kremmer on planning engagement to engage with areas from Feb (work in progress).
Team is investigate the impact of the Office 365 contract and will replan accordingly. | Investigate timescale, resource and cost implications.
SharePoint - Not able to test due to no test environments. | Providing MS admin & DB rights to fix the issue, Joint SPF / SPE team working to resolve.
On going challenges around a number of inbound technical dependencies on IAM continue to constrain early delivery of infrastructure. | IAM team have added 3 more resources and we are working through the additional activity caused by Office 365.
OVERALL INITIATIVE STATUS | 
Last Period | This Period
RED | RED
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative | 
Risks to be addressed | Mitigating Action
Final selection arising from the hosting services RFP may become delayed by the selection of options and services. | Once the outcomes of the various RFP decisions are known, will asses the impact upon the current plans.
Project will require a significant amount of time from SMRs from both the business & IT. | Provide detailed plans so early visibility of the need for such expertise is identified as early as possible.
RED
AMBER
GREEN
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
13 - Messaging & Collaboration – 9 March 2012
Guy Morgan
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
Overall Program status is Red due to re-planning which is the key current focus. Need to investigate Office 365 impact. FY12 Budget $38,500,000 Current Budget (Baseline + Approved CRs) TBD Spend to Date $ 19.5M ETC TBD Variances TBD
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
Application & Data Migration: Both the Phase 1 and Rediscovery are awaiting dates for identified inbound dependencies from other work streams (namely SharePoint not expected until 15th Mar) to finalize their plans. Unified Communications: Significant challenges experienced with business engagement on mail-integrated applications. Discovery effort being challenged by lack of clarity on engagement via IT Service Delivery leads and business confusion over multiple discovery efforts across several transformational programs. Technology Foundation: M&C have agreed not to role out to the 6078 workstations which already have Outlook installed. Approval received from key stakeholders to proceed to Full Outlook Deployment for remaining users. SharePoint: Project replanning in progress. Testing has started on Communities. Issues are still holding up the People testing. ECMA is RED as the current Blueprint work has not been integrated with the existing plan. Change Management: Continuing to work on the creation/implementation of the comms strategy. Learning lead for Lync & Outlook and SharePoint not recruited, so limited activity beyond initial preparation, planning and learning inventory creation. IT Transition Management: Developing transition plans with each workstream based on Transition methodology. Deployment of the dormant Lync client has reached full saturation. Outlook client to start by mid March 2012.
B. KEY ACCOMPLISHMENTS THIS PERIOD
Application & Data Migration: Requirements replan completed based on CR65. First engagement with SharePoint leads held to define scope of their Program vs. A&DM. Unified Communications: Lync Configuration - Confirmation that Q&RM request to store external chats and archiving no longer required. Lync Devices - Device evaluations are complete. Technology Foundation: Lync saturation of 97% and a EY Operational Standard of 90% for completion, Outlook Transition test 2 was successful and has gained approval from key stakeholders to proceed to full deployment. SharePoint: POC Development continues (DTU), Development continues (Search), People, Communities bug fixes. Communities, Working O365 major issues (i.e. Meta Data Management & People Profile replication). Change Management: Calls held to review People and Lync benefits, Call held to review potential benefits from social collaboration tools, Commenced refresh of M&C financial benefit case ahead of meeting w/c 12/03/12 IT Transition Management: Continuing to refocus and reprioritize Transition structure for M&C while working with Nick Coburn.
E. MILESTONES |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Last Period | This Period
Sign off Messaging Design | Replanning | Replanning | RED | RED
IT Transition Plan for SharePoint, Lync & Messaging | 1 Feb 2012 | 16 Mar 2012 | AMBER | AMBER
ADM - Rediscovery Wave 1 and Wave 2 Report complete | 3 Feb 2012 | 2 Mar 2012 (awaiting input from IT SD) | RED | RED
Overall M&C Transition Plan | 17 Feb 2012 | 16 Mar 2012 | AMBER | AMBER
SP - O365 Replan | 20 February | 23 March | AMBER | AMBER
SharePoint QA testing (any iteration) | 16 Dec 2012 | TBD | RED | RED