## Slide 1
C. ACTIVITIES BEHIND SCHEDULE
Application & Data: Finalizing Phase 1 and Rediscovery re-planning activities given the need for dependant Programs (namely SharePoint and Tech Foundation) to complete their re-planning activities. SharePoint: Research tools – GAAIT and Credential replacements. Subscribe and Deliver – Overall Vision and Scope. DTU – BA and SA activity are behind. Outlook/Exchange: Deployment plan contingent on Business Deployment Strategy, DCC schedule and bandwidth analysis. Completion of Outlook Mail Integrated Apps impact assessment/validation with the business. Publish Lync and Outlook governance model. Lync - Technology Foundation: Lync - Vendor RFP down selection, interim SOW and Cloud Topology decision remains outstanding and the work stream is still engaged with both vendors further refining the pricing and progressing the independence issue. Messaging - Approval of re scoping CR026 is not complete and impacting resource allocation. Change Management: Progress visual design themes, revised comms strategy and plan. IT Transition Management: Recruitment of TM resources.
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Application Data Migration: Rebaseline both Phase 1 and Rediscovery project plans once delivery dates of key inbound dependencies have been defined, confirmed and communicated. SharePoint: Revising Release 1 plan. Ovitas Workshops will continue. Updating detailed project plan. Technology Foundation: Move to Scope Lock for both O365 SP and Messaging with MCS. Unified Communications: Re-alignment of programs from UC/TF structure to new end-to-end delivery model. Update plans for checkpoint on 29 March focusing on critical path items and potential options for bringing in deployment timelines. Change Management: Walk through with Neil Sahdev current plans for A&DM to update A&DM Change plans. Discuss potential SharePoint benefits with Kerri Keller, Further develop refreshed M&C Business Case, Engage with SharePoint stakeholder around benefits. IT Transition Management: Attending Microsoft O365 workshop w/c 26 March. Baseline service design plan. Baseline service transition plan.
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes | 
Issues to be resolved | Recommended Action
Need to recruit a significant number of additional resources into the program. Recruitment of skilled staff proving very difficult and will impact schedules | To be reviewed as part of 30 Day Plan exercise.
Engagement with Areas has not moved at the pace required to establish a Change Network and start to develop Deployment plans. | Jackie Knight working with Sophie Boiron and Martin Kremmer on planning engagement to engage with areas from Feb (work in progress).
Team is investigate the impact of the Office 365 contract and will replan accordingly. | Investigate timescale, resource and cost implications
Lack of clarity on the SharePoint 15 adoption/features | Update on daily stand up call that a meeting is occurring later this week to resolve
Agreement needs to be reached between Cross-Org and IT Service Delivery teams on the common operating model and resourcing strategy for the Portfolio Teams | Alan now progressing with Mo, Margaret and Chris to finalise the Operating Model (incl. reaching agreement on the resourcing strategy) – decision was expected during Interlock meeting held 24/02/12 however mixed messages on the outcome. Neil to set-up meeting with Cross-Org, Strategy and Architecture and IT SD to reach agreement (in progress)
OVERALL INITIATIVE STATUS | 
Last Period | This Period
RED | RED
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative | 
Risks to be addressed | Mitigating Action
Final selection arising from the hosting services RFP may become delayed by the selection of options and services. | Once the outcomes of the various RFP decisions are known, will asses the impact upon the current plans.
Project will require a significant amount of time from SMRs from both the business & IT. | Provide detailed plans so early visibility of the need for such expertise is identified as early as possible.
RED
AMBER
GREEN
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
Messaging & Collaboration – March 2012
Alan Guthrie
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
Overall Program status is Red due to re-planning which is the key current focus. Need to investigate Office 365 impact. FY12 Budget $36,700,000 Current Budget (Baseline + Approved CRs) TBD Spend to Date $ 23.5M ETC TBD Variances TBD
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
Application & Data Migration: The A&DM Operating Model is yet to be agreed and communicated to all IT Service Delivery Leads – session being planned with Margaret Walsh, Chris Hall, Bob Reiner, Alan Guthrie and John Costello to review the Operating Model. Outlook/Exchange: The TF and UC programs have now been re-aligned as end-to-end program delivery teams for Outlook/Exchange and Lync. Work is now underway to transition to the new delivery model. Lync - Technology Foundation: O365 Messaging discovery documentation is being iterated by MCS engineering team. O365 SharePoint discovery documentation is submitted for MCS peer review. SharePoint: Project replanning continues. Focused on the “30 day Get to Green” plan. Change Management: Continuing to work on the creation/implementation of the comms strategy. Learning lead for Lync & Outlook and SharePoint not recruited, so limited activity beyond initial preparation, planning and learning inventory creation. IT Transition Management: Developing transition plans with each workstream based on Transition methodology. Deployment of the dormant Lync client has reached full saturation. Deployment of Outlook client has started.
B. KEY ACCOMPLISHMENTS THIS PERIOD
Application & Data Migration: Completed Transition Planning. Engaged Operations Leadership regarding formal engagement of I&O resources. Outlook/Exchange: MMD: Migration RACI under development. Outlook configuration: Requirements submitted to DA for review, further requirements continue to be identified from business contacts. Lync - Technology Foundation: Lync - Submitted CR to refine MCS SOW down scope and ongoing resource requirements. SharePoint - O365 Draft Discovery Documentation completed, uploaded and currently being reviewed by O365 Engineering team. SharePoint: Development continues Search, People, Communities and DTU bug fixes. Communities, DTU Requirements in progress. Design begun on subscription management requirements (DTU) Change Management: Continued development of the refreshed M&C Business Case, Developed high level summary of potential Lync Benefits. First review of M&C refreshed comms strategy, IT Transition Management: Continuing to refocus and reprioritize Transition structure for M&C.
MILESTONES |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Last Period | This Period
Migration Master DB Live | 11 May 2012 | 01 Jun 2012 | GREEN | AMBER
Outlook Deployment Start | 27 May 2013 | 27 May 2013 | AMBER | AMBER
ADM - Rediscovery Wave 1 and Wave 2 Report complete | 3 Feb 2012 | 2 Mar 2012 (awaiting input from IT SD) | RED | RED
SP - O365 Replan | 20 Feb 2012 | 23 Mar 2012 | AMBER | AMBER