## Slide 1
B. KEY ACCOMPLISHMENTS THIS PERIOD
Performed two Pilot deployments with South Africa – a total of 151 migrations completed through 3 July Issue with activation on GCL4 machines (XP) that are leading to high call volume; assessing fix and determining impact on full velocity. FAX solution testing for South Africa and Germany in progress and both are in User Acceptance Testing Completed assessment of business requirements, operational architecture and system integrated testing and all ready for sign off. Recoding of Are You Prepared Shared Mailbox portal is 50% complete and target date to send out global communications is week of 15 July Kickoff meeting with United Kingdom/Ireland migration planning
C. ACTIVITIES BEHIND SCHEDULE
Germany full schedule deployment is being worked and first draft will be completed by 8 Jul. See I310.
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Complete testing of fax solution for Germany and South Africa Conduct weekly planning meetings with all engaged countries to move forward on the scheduling Canada United States Argentina United Kingdom/Ireland Pre-planning for Malaysia/Indonesia/Singapore
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes |  |  | 
Issues to be resolved | Recommended Action | Target Date | Owner
I310 – Microland management of Germany servers per contract | Contract modification in process, Germany has provided feedback that is being assessed | 05-Jul-13 | Nick Coburn
Scope Change requests to be approved | Recommended Action |  | 
CR to be raised to formally baseline the Plan | CR’s are being drafted to change dates for South Africa and Germany |  | 
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
OVERALL: Full Velocity – based on adjusting scheduled due to recent delays Germany – Red South Africa – Red (based on requirement to submit CR to formally change program dates); this will be submitted since CAB has approved for Pilot RED Germany continues to be red due based on: Resolving Microland support issue. Progress made but not signed. Archiving solution has not been resolved. Meeting held on 3 July and open questions to Germany to respond. Expect feedback on 5 July.
E. MILESTONES |  |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Conf. Rating | Last Period | This Period
Pilot end South Africa (CLOUD) | 05-Jul-13 | 02-Aug-13 | COM | RED | RED
Velocity start South Africa (CLOUD) | 29-Apr-13 | 15-Jul-13 | COM | RED | RED
Velocity complete South Africa (CLOUD) | 02-Aug-13 | 02-Aug-13 | COM | RED | RED
Pilot go-live Germany (ON PREM) | 27-May-13 | 18-Jul-13 | COM | RED | RED
Pilot end Germany (ON PREM) | 20-Jun-13 | 26-Jul-13 | COM | RED | RED
Velocity start Germany (ON PREM) | 29-APR-13 | 05-Aug-13 | COM | RED | RED
Velocity complete Germany (ON PREM) | 05-AUG-13 | 12-Sep-13 | COM | RED | RED
OVERALL INITIATIVE STATUS | 
Last Period | This Period
RED | RED
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative |  |  | 
Risks to be addressed | Mitigating Action | Target Date | Owner
R214- Additional BT licenses will be required to migrate all required mailboxes | Will need to submit CR but not urgent as there are plenty of licenses in the short term | 15-Jul-13 | Dez Nagy
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
RED – Now that CAB has approved Pilot phase CR will be submitted to support new dates. Have agreement with Germany on new dates and with the CAB approval, will submit CR. The integrated schedule continues to be a challenge as GCL5 slips and GAMx rollout. There are also network implementation issues globally and waiting on schedule impact.
RED
AMBER
GREEN
COMPLETE
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
R19913 – M&C Outlook Exchange – June 2013
David Bingham/Mike Caudill

## Slide 2
R19913 – M&C Outlook Exchange – June 2013
David Bingham/Mike Caudill
Budget RAG Status | 
RED | Variance is =+ 10% or $100,000 of current budget (baseline + approved change requests) and/or pending spend - or - no project budget is defined/approved
AMBER | Variance is =+ 6% - 9% of current budget (baseline + approved change requests) and/or pending spend
GREEN | Variance is = + 5% of current budget (baseline + approved change requests) and/or pending spend
VARIANCE FACTORS
NEG: Unplanned capital expenses
NEG: Unplanned resource expenses
NEG: Unplanned project (misc) expenses
SIG POS: Unused planned capital
SIG POS: Unused planned resources
SIG POS: Project not progressing as planned
OTHER (Please explain in section below)
Page 2
J. Key Inbound Dependency View |  |  |  |  |  | 
Criticality | Supplying Program | Dependency | Delivery Date | Required by Date | RAG Status | Current State
I. BUD - ($) |  |  |  |  |  |  |  |  |  | STATUS
 |  |  | PLANNED |  | ACTUAL |  |  |  |  | AMBER
 |  |  |  | Current Bud (Baseline + Approved CRs) | Spend to Date | Estimate to Completion (ETC) | Capital Spend ETC | Revenue Spend ETC | Estimate at Completion (EAC) | Variance
Fiscal year | Business Case Bud | Project Charter Bud | PMP Bud (baseline) | -1 | -2 | -3 |  |  | (2+3) | (1) - (2+3)
FY11 |  |  |  | 196,610 | 196,610 |  |  |  | 196,610 | 0
FY12 |  |  |  | 8,526,958 | 8,167,868 |  |  |  | 8,167,868 | 359,090
FY13 |  |  |  | 11,680,707 | 12,708,896 | 1,421,364 |  |  | 14,130,259 | -2,449,553
FY14 |  |  |  | 10,084,648 |  | 10,084,648 |  |  | 10,084,648 | 
FY15 |  |  |  |  |  |  |  |  |  | 
TOTALS | 0 | 0 | 0 | 30,488,922 | 21,073,373 | 11,506,012 | 0 | 0 | 32,579,385 | -2,090,463
Brief explanation for RED or AMBER variance |  |  |  |  |  |  |  | Variance Factor: | OTHER (please explain in section below) | 
ATD may be greater than reported through the Portfolio Report Actuals for vendor spend due to the effect of pending Invoices that may not have yet been Accrued. |  |  |  |  |  |  |  |  |  |