## Slide 1
G. MATTERS FOR IMMEDIATE ATTENTION – typically specific current issues or scope changes |  |  | 
Issues to be resolved | Recommended Action | Target Date | Completed By
Revised target dates set for AD Hardening however plans to support are yet to be baselined | Escalated to CLT | 01-Dec-13 | The Rock
OVERALL INITIATIVE STATUS | 
Last Period | This Period
AMBER | AMBER
F. KEY RISKS – typically future challenges or external circumstances that may affect the initiative |  |  | 
Risks to be addressed | Mitigating Action | Target Date | Completed By
Time needed to clarify scope impacts from security audit, impacts time to deliver planned scope in FY14. | Confirm priority actions as a result of security audit findings and which pipeline concepts should be commenced Escalated to Business Sponsor with follow-up actions agreed | 01-Dec-13 | The Rock
RED
AMBER
GREEN
Project is not on track and has significant challenges and/or issues that materially impact the overall successful achievement of the expected outcomes.
Fully achieved
The overall initiative status is governed by the RAG Status Guidance, summarized below. This guidance also applies to the individual Milestones Stats.
Project is on track and has no significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes, now or in the future.
Project is on track but has some significant challenges and/or issues that may materially impact the overall successful achievement of the expected outcomes.
<Project Name> <Date> <Project Manager>
H. GENERAL COMMENTS – must include reasoning for an overall Red or Amber Status
Amber as 1) initiatives are behind due to resource diversion to Audit impacting delivery to plan b) no agreed new initiatives yet, from ESP pipeline / Security Controls Roadmap for November onwards which risks under delivery and delayed resourcing.
A. EXECUTIVE SUMMARY – a summary of the progress for this period (not of the initiative)
Four new initiatives approved by FPG to start, will provide anti-virus for SharePoint, enhancements to group management, a standard tool to sanitise media and ServiceNow integration with HP configuration management database providing better incident impact identification and management. Key delivery for M&C’s Lync program is tracking a week behind plan due to resource diversion to the security audit, however is otherwise making good progress through testing.
B. KEY ACCOMPLISHMENTS THIS PERIOD
Four new concepts approved by FPG QA and Prod engineering builds in progress for GAP Comms sent to the I&O team informing them about the upcoming AD Hardening production changes related to NTLMV2 in December
C. ACTIVITIES BEHIND SCHEDULE
Re-platform engineering build tasks (due to change freeze issues as well as prioritization on UVT lite) Completion of RFP document prior to issue for SecurID replacement – final requirements being included Guest Wi-Fi server configuration (delayed due to Security Operations resource prioritization to Audit)
D. KEY ACTIVITIES PLANNED NEXT PERIOD
Resolve Matters For Immediate Attention Complete re-platform Microsoft Forefront Identity Manager build and start testing Upgrade outstanding M&C users to 25Gb mail box Identify resource from Security Operation to move forward with guest Wi-Fi
Scope Change requests | Recommended Action
R25192 Secure hard drive wipe tool R31222 Antivirus for SharePoint R32254 Group ID Enhancements Release R32988 ServiceNow - Integration with HP uCMDB | New Initiatives Approved in Oct FPG
E. MILESTONES |  |  |  |  | 
Individual Milestone Name | Planned Date | Projected Date | Confidence | Last Period | This Period
AD Hardening remed’n plans set down | 30-Apr-13 | 14-Nov-13 | ESTIMATE | RED | RED
Security awareness training in Australia | 31-Jul-13 | 14-Oct-13 | N/A | RED | Complete
Security awareness training rolls out | 14-Oct-13 | 02-Dec-13 | ESTIMATE | RED | RED
Comp. PoC for Public Key Infrastructure | 30-Oct-13 | 30-Oct-13 | COMMIT | AMBER | Complete