## Slide 1
Messaging & Collaboration Program Reporting Process
July 2013

## Slide 2: Governance Schedule
Tuesday
Monday
Thursday
Wednesday
Friday
Weekly
Fortnightly
Monthly
Program
Management
Meeting
Program
Finance
Review
Executive
Steering
Pack
Change Control
Boards
PMO Pack
Workstream
Program
Mgt Team
Director, Sponsor,
Exec and/or PMO
A
A
A
Quality
Review
PM Tool
Program Management Pack
Program Health
Report
Dashboard
CRs with
completed Impact
Assessments
CCB Panel Review
ITS Status
Reports
IT Executive
Steering Group
Report
RAID
RAID

## Slide 3: Reporting Types?
Reports | Objective | Inputs | Review Control | Outputs | Frequency | Audience
ITS Status Report | Provides a summary of Program status to Sponsors and Executives Escalation channel for Program concerns | Mandated ITS standard report template Finance summary (to be completed by PMO) RAID CCB | Fortnightly QA review (includes a Workstream lead or PM) | Consolidated Program status report Uploaded into the IT PM tool by M&C PMO team | Mid-Month Month End (as per the ITS calendar) | Executive GPMO
Program Health Report Dashboard | Provide RAG snapshot of the status of each individual program and associated delivery life cycle stages | Health report template. PMO RAG status for each of the key governance processes | Internal PMO review. | Program Health Report Dashboard Program Management meeting pack | Weekly | Program Management
Executive Steering Pack | Program level summary for presentation at Executive Steering Group meeting Escalation channel for key Program concerns | ITS Status Report M&C Program Lead updates Program Director | M&C Program Lead | Executive Steering Pack | Monthly (as requested) | Program Sponsors and Executives
  Program Finance review is submitted monthly by PMO, no workstream lead input required
3
Messaging & Collaboration Program Reporting Process July 2013

## Slide 4
  Report Repositories
  SharePoint
  Workstream Leads must upload completed reports into SharePoint folder created by PMO
    M&C PMO will email the link to the latest folder repository to the Workstream Leads weekly.
  Workstream Leads should use the following naming convention below when uploading the reports:
  <<Program>> <<Workstream>> <<Period of Reporting>><<Status Report>><<MMMYYYY>>
  i.e. Collaboration Release 1 (Mid-Month or Month End) Status Report Jul 2013
  IT Services PM Tool
  Repository for all IT Services Status Reports
  M&C ITS reports and Program finances are uploaded into the IT PM Tool (The tool is designed to track Program RAID, Program Planning milestones, Program deliverables and Program Stage-gates.
  M&C PMO are responsible for collating Workstream Status Reports and uploading into the IT Services PM Tool
5
Messaging & Collaboration Program Reporting Process July 2013

## Slide 5: Reporting Profile
Transition
Change/Deployment
Lync
Outlook/Exchange
Collaboration
PMO
R1
R2
Executive/Sponsor:
ITS Status Report Review
Executive Steering Pack Review
Programs:
Program Health Dashboard submission
ITS Status Report submission
Horizontal Workstreams:
Program Health Dashboard inputs
ITS Status Report inputs
4
Messaging & Collaboration Program Reporting Process July 2013
Executive/Sponsor
Program Management
Program Management:
Program Health Dashboard Review
ITS Status Report A
Executive Steering Pack submission
Finance Review
Program Health Dashboard
ITS
Finance review
Program Health
Dashboard
Program Finance
Review
ITS
Report

## Slide 6: Useful links
ITS Status Report Template
Program Health Report Dashboard Template
Executive Steering Pack Sample
Program RAG Report Guidance
6
Messaging & Collaboration Program Reporting Process July 2013

## Slide 7: Thank you